## Grid
[8 empty] | System type |  |  |  | Metering |  | APPLICATION REVIEW |  |  |  | PRELIMINARY REVIEW |  |  | CESIR |  |  |  | SIR Costs |  |  |  |  | Construction
[14 empty] | 10 business days |  |  |  | 15 business days |  |  | 60 / 80 business days |  |  |  | CESIR Costs |  | Project Installation / Upgrade Costs |  |  | Payments
Company | Developer | Application / Job # | Division | City/Town | Zip Code | Circuit ID | Substation | Hybrid (Y/N) | PV (kWAC) | ESS (kWAC) | WIND (kWAC) | Metering (NA / NM / RNM / CDG) | Value Stack (Y/N) | Start Date | End Date | Calculated Duration | Application Approved Date (Utility) | Start Date (Must Match Application Approved Date) | End Date | Calculated Duration | Payment Received Date | Start Date | End Date | Calculated Duration | CESIR cost to customer | CESIR cost to utility | Estimated Costs by Utility | Actual Customer Project Costs | Actual Utility Project Costs | Down Payment Date | Full Payment Date | Construction Start Date | Construction Complete Date | Verification Testing or Final Acceptance Date | Final Letter of Acceptance Date | Project Complete (Y/N) | Utility Retention of REC (Y/N)
NIMO | Dynamic Energy | 00102057 | 032 - Schenectady | SCHENECTADY | 12306 | 36_30_28355 | ALTAMONT 283 | N | 1980 |  |  | CDG | N | 2016-03-15 | 2016-03-15 | 0 | 2016-09-29 | 2016-09-29 | 2016-10-12 | 0 | 2017-01-27 | 2017-01-27 | 2017-04-20 | 59 | 19700 |  | 144550 |  |  | 2017-06-16 | 2017-12-06 | 2017-07-24 | 2018-12-12 | 2018-12-20 | 2018-12-20 | Y | N
NIMO | FOREFRONT POWER LLC | 00101370 | 030 - Albany | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | N | 2000 |  |  | RNM | N | 2015-11-17 | 2015-11-17 | 0 | 2016-03-15 | 2016-03-15 | 2016-04-08 | 0 | 2016-08-23 | 2016-08-23 | 2016-11-16 | 60 | 25000 |  | 226100 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-24 | 2017-07-24 | 2018-12-28 | 2018-12-28 | Y | N
NIMO | Jared Alvord (Mad River Solar Holdings, LLC) | 00250558 | 032 - Schenectady | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | N | 5000 |  |  | CDG | N | 2019-12-10 | 2020-01-14 | 34.8882 | 2020-01-15 | 2020-01-15 | 2020-01-31 | 11 | 2020-05-20 | 2020-05-20 | 2020-09-17 | 56 | 9000 |  | 11055087 | [8 empty] | N | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00208409 | 030 - Albany | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | N | 5000 |  |  | CDG | Y | 2019-02-07 | 2019-02-19 | 11.9361 | 2019-02-20 | 2019-02-20 | 2019-03-01 | 7 | 2019-03-15 | 2019-03-15 | 2019-09-23 | 60 | 8600 |  | 532192 |  |  | 2020-03-17 | 2020-09-11 |  |  |  |  | N | Y
NIMO | Michael Whigham (ConEd CEB) | 00267993 | 030 - Albany | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | Y | 5000 | 5000 |  | CDG | N | 2020-02-06 | 2020-02-20 | 11 | 2020-02-20 | 2020-02-20 | 2020-02-20 | 0 | 2020-04-17 | 2020-04-17 | 2020-07-31 | 58 | 9100 |  | 10980784 | [8 empty] | N | N
NIMO | Patrick McGowin (Dynamic Energy) | 00102219 | 032 - Schenectady | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | N | 1980 |  |  | CDG | N | 2016-03-15 | 2016-09-29 | 14 | 2016-09-29 | 2016-09-29 | 2016-10-12 | 0 | 2017-01-27 | 2017-01-27 | 2017-04-20 | 59 | 18700 |  | 292000 |  |  | 2017-06-16 | 2017-12-05 | 2017-07-24 | 2018-12-12 | 2018-12-20 | 2018-12-20 | Y | N
NIMO | Michael Whigham (ConEd CEB) | 00276467 | 030 - Albany | ALTAMONT | 12009 | 36_30_28356 | ALTAMONT 283 | Y | 5000 | 5000 |  | CDG | N | 2020-01-24 | 2020-02-05 | 11.6875 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 0 | 2020-04-08 | 2020-04-08 | 2020-08-31 | 48 | 8600 |  | 11355837 | [8 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100904 | 030 - Albany | ALTAMONT | 12009 | 36_30_28356 | ALTAMONT 283 | N | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-10 | 4 | 2015-06-10 | 2015-06-10 | 2015-06-25 | 0 | 2016-04-11 | 2016-04-11 | 2016-07-06 | 62 | 25000 |  | 225100 |  |  |  |  | 2017-04-05 |  | 2018-06-11 | 2018-06-11 | Y | N
NIMO | Austin Behrmann (Jordan Energy & Food Enterprises, | 00255158 | 038 - Glens Falls | FORT ANN | 12827 | 36_38_33151 | ASHLEY 331 | N | 5000 |  |  | CDG | N | 2019-09-26 | 2019-10-23 | 26.825 | 2019-10-24 | 2019-10-24 | 2019-11-14 | 14 | 2019-12-26 | 2019-12-26 | 2020-08-24 | 55 | 9200 |  | 2215633 | [8 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00269517 | 004 - Batavia | ATTICA | 14011 | 36_04_1262 | ATTICA 12 | N | 5000 |  |  | CDG | N | 2020-01-06 | 2020-01-27 | 21.0278 | 2020-01-28 | 2020-01-28 | 2020-01-28 | 0 | 2020-02-14 | 2020-02-14 | 2020-06-12 | 58 | 10900 |  | 795737 |  |  | 2020-10-20 | [5 empty] | N | N
NIMO | RER Energy Group | 00094520 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 | AVON 43 | N | 1080 |  |  | RNM | N | 2014-07-18 | 2014-12-30 | 118 | 2014-12-30 | 2014-12-30 | 2015-01-15 | 0 | 2015-03-06 | 2015-03-06 | 2015-06-17 | 73 | 14860 |  | 260420 | [6 empty] | 2016-07-12 | 2016-07-12 | Y | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00231708 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_15054 | BAKER ST 150 | N | 1250 |  |  | CDG | Y | 2019-05-31 | 2019-06-12 | 11.9271 | 2019-06-13 | 2019-06-13 | 2019-06-24 | 7 | 2019-07-29 | 2019-07-29 | 2019-12-13 | 59 | 9600 |  | 849958 |  |  | 2020-06-05 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00231537 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_15054 | BAKER ST 150 | N | 2750 |  |  | CDG | Y | 2019-05-31 | 2019-06-12 | 11.9104 | 2019-06-13 | 2019-06-13 | 2019-06-24 | 7 | 2019-10-07 | 2019-10-07 | 2020-01-06 | 56 | 9600 |  | 842316 |  |  | 2020-06-29 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00231545 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_15054 | BAKER ST 150 | N | 5000 |  |  | CDG | Y | 2019-05-31 | 2019-06-24 | 23.884 | 2019-06-25 | 2019-06-25 | 2019-07-03 | 6 | 2019-07-29 | 2019-07-29 | 2019-12-13 | 59 | 10100 |  | 975450 |  |  | 2020-06-05 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00254053 | 009 - Lakewood/Stow | ASHVILLE | 14710 | 36_09_15056 | BAKER ST 150 | N | 3750 |  |  | CDG | N | 2019-09-13 | 2019-09-27 | 13.7944 | 2019-09-30 | 2019-09-30 | 2019-10-16 | 12 | 2020-01-06 | 2020-01-06 | 2020-04-21 | 59 | 11200 |  | 1654643 |  |  | 2020-09-09 | [5 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00254055 | 009 - Lakewood/Stow | ASHVILLE | 14710 | 36_09_15056 | BAKER ST 150 | N | 5000 |  |  | CDG | N | 2019-09-13 | 2019-09-27 | 13.8083 | 2019-09-30 | 2019-09-30 | 2019-10-16 | 12 | 2020-01-06 | 2020-01-06 | 2020-04-22 | 58 | 11200 |  | 1787870 |  |  | 2020-10-06 | [5 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00296545 | 011 - Syracuse | CAZENOVIA | 13035 | 36_11_22151 | BALLINA 221 | N | 5000 |  |  | CDG | N | 2020-07-01 | 2020-07-14 | 10 | 2020-07-14 | 2020-07-14 | 2020-07-14 | 0 | 2020-07-30 | 2020-07-30 |  |  | 9400 | [10 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00296551 | 011 - Syracuse | CAZENOVIA | 13035 | 36_11_22151 | BALLINA 221 | N | 5000 |  |  | CDG | N | 2020-07-08 | 2020-07-14 | 4 | 2020-07-14 | 2020-07-14 | 2020-07-14 | 0 | 2020-07-30 | 2020-07-30 |  |  | 10900 | [10 empty] | N | N
NIMO | Rob Garrity (Finlo, LLC) | 00316561 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_01252 | BALLSTON 12 | Y | 5000 | 0 |  | CDG | N | 2020-10-26 | 2020-11-03 | 6 | 2020-11-04 | 2020-11-04 | 2020-11-19 | 0 |  |  |  |  | 10300 | [10 empty] | N | N
NIMO | Rob Garrity (Finlo, LLC) | 00317963 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_01252 | BALLSTON 12 | Y | 5000 | 0 |  | CDG | N | 2020-10-12 | 2020-10-19 | 5 | 2020-10-20 | 2020-10-20 | 2020-11-03 | 10 |  |  |  |  | 10300 | [10 empty] | N | N
NIMO | Christopher Stroud (Cipriani Energy Group Corp.) | 00287224 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_01254 | BALLSTON 12 | N | 1400 |  |  | CDG | N | 2020-04-13 | 2020-04-24 | 9 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 0 | 2020-05-04 | 2020-05-04 | 2020-07-28 | 55 | 8600 |  | 150473 |  |  | 2020-12-09 | [5 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00283166 | 011 - Syracuse | CENTRAL SQUARE | 13076 | 36_11_32554 | BARTELL RD 325 | N | 5000 |  |  | CDG | N | 2020-03-27 | 2020-04-01 | 3 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-25 | 59 | 8800 |  | 782260 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00283167 | 011 - Syracuse | CENTRAL SQUARE | 13076 | 36_11_32554 | BARTELL RD 325 | N | 5000 |  |  | CDG | N | 2020-03-27 | 2020-04-02 | 4 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-25 | 59 | 9400 |  | 833421 | [8 empty] | N | N
NIMO | David Spotts (SSC Cicero LLC) | 00298227 | 011 - Syracuse | BREWERTON | 13029 | 36_11_32555 | BARTELL RD 325 | N | 5000 |  |  | CDG | N | 2020-06-26 | 2020-07-05 | 5 | 2020-07-05 | 2020-07-05 | 2020-07-05 | 0 | 2020-07-16 | 2020-07-16 | 2020-10-26 | 59 | 10400 |  | 235991.31 |  |  | 2020-12-07 | [5 empty] | N | N
NIMO | Matt Marino (Galehead DG Solutions, LLC) | 00299975 | 011 - Syracuse | BREWERTON | 13029 | 36_11_32555 | BARTELL RD 325 | N | 5000 |  |  | CDG | N | 2020-07-21 | 2020-07-27 | 4 | 2020-07-28 | 2020-07-28 | 2020-07-28 | 0 | 2020-09-18 | 2020-09-18 |  |  | 9400 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00230713 | 011 - Syracuse | CLAY | 13041 | 36_11_32556 | BARTELL RD 325 | N | 2200 |  |  | CDG | Y | 2019-06-13 | 2019-06-25 | 11.8493 | 2019-06-26 | 2019-06-26 | 2019-07-09 | 8 | 2019-07-31 | 2019-07-31 | 2019-10-31 | 58 | 9200 |  | 321059 |  |  | 2020-04-14 | [5 empty] | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00296976 | 011 - Syracuse | BREWERTON | 13029 | 36_11_32556 | BARTELL RD 325 | Y | 5000 | 2500 |  | CDG | N | 2020-07-01 | 2020-07-09 | 5 | 2020-07-17 | 2020-07-17 | 2020-07-17 | 0 | 2020-08-28 | 2020-08-28 |  |  | 9300 | [10 empty] | N | N
NIMO | guo qing Zhou (Advanced Solar Power Holdings INC) | 00254704 |  | BATAVIA | 14020 | 36_04_0152 | BATAVIA 1 | Y | 5040 | 5040 |  | CDG | Y | 2019-10-21 | 2019-10-29 | 6 | 2019-10-29 | 2019-10-29 | 2019-11-18 | 12 | 2020-02-03 | 2020-02-03 | 2020-06-17 | 54 | 9100 |  | 243646.68 |  |  | 2020-10-29 | [5 empty] | N | Y
NIMO | Kevin Rabbitt (Bright Oak Solar LLC) | 00188994 | 004 - Batavia | BATAVIA | 14020 | 36_04_0152 | BATAVIA 1 | N | 4000 |  |  | CDG | Y | 2018-06-28 | 2018-06-28 | 0 | 2018-07-11 | 2018-07-11 | 2018-07-30 | 13 | 2018-08-20 | 2018-08-20 | 2019-01-23 | 59 | 13300 |  | 202776 |  |  | 2019-05-29 | 2019-05-31 | 2019-10-31 | 2020-03-05 |  |  | N | Y
NIMO | Cypress Creek Renewables LLC | 00101629 | 004 - Batavia | BATAVIA | 14020 | 36_04_0153 | BATAVIA 1 | N | 2000 |  |  | CDG | Y | 2016-08-08 | 2016-08-15 | 5 | 2016-08-15 | 2016-08-15 | 2016-08-16 | 1 | 2016-11-29 | 2016-11-29 | 2017-02-27 | 60 | 21200 |  | 212250 |  |  | 2017-05-23 | 2017-12-06 | 2017-05-23 | 2017-12-06 | 2018-12-28 | 2018-12-28 | Y | Y
NIMO | Cypress Creek Renewables LLC | 00102232 | 004 - Batavia | BATAVIA | 14020 | 36_04_0153 | BATAVIA 1 | N | 2000 |  |  | CDG | Y | 2016-07-07 | 2016-07-13 | 4 | 2016-07-13 | 2016-07-13 | 2016-07-16 | 3 | 2016-09-13 | 2016-09-13 | 2017-01-07 | 60 | 21200 |  | 147500 |  |  | 2017-04-07 | 2017-12-06 | 2017-04-07 | 2017-12-06 | 2018-12-28 | 2018-12-28 | Y | Y
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00100862 | 004 - Batavia | BATAVIA | 14020 | 36_04_0154 | BATAVIA 1 | N | 2000 |  |  | RNM | N | 2015-05-13 | 2015-05-28 | 3 | 2015-05-28 | 2015-05-28 | 2015-06-17 | 0 | 2015-10-30 | 2015-10-30 | 2016-06-17 | 165 | 20600 |  | 144500 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-24 | 2018-06-21 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00101327 | 004 - Batavia | BATAVIA | 14020 | 36_04_0154 | BATAVIA 1 | N | 2000 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 8 | 2015-06-11 | 2015-06-11 | 2015-07-02 | 0 | 2015-10-22 | 2015-10-22 | 2016-07-15 | 191 | 30000 |  | 213350 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-14 | 2018-06-21 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00305239 | 004 - Batavia | BATAVIA | 14020 | 36_04_0154 | BATAVIA 1 | N | 5000 |  |  | CDG | N | 2020-09-24 | 2020-10-02 | 5 | 2020-10-02 | 2020-10-02 | 2020-10-02 | 0 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00196061 | 004 - Batavia | BATAVIA | 14020 | 36_04_0155 | BATAVIA 1 | N | 3000 |  |  | CDG | Y | 2018-09-20 | 2018-10-01 | 11.0632 | 2018-10-02 | 2018-10-02 | 2018-10-04 | 2 | 2018-12-17 | 2018-12-17 | 2019-04-22 | 48 | 13300 |  | 216004 |  |  | 2019-05-07 | 2019-05-10 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00196062 | 004 - Batavia | BATAVIA | 14020 | 36_04_0155 | BATAVIA 1 | N | 4000 |  |  | CDG | Y | 2018-09-20 | 2018-10-02 | 12.0194 | 2018-10-03 | 2018-10-03 | 2018-10-04 | 1 | 2018-12-21 | 2018-12-21 | 2019-04-22 | 48 | 13300 |  | 216997 |  |  | 2019-05-07 | 2019-05-10 |  |  |  |  | N | Y
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00315631 | 004 - Batavia | BATAVIA | 14020 | 36_04_0158 | BATAVIA 1 | N | 5000 |  |  | CDG | N | 2020-09-28 | 2020-10-07 | 6 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 0 | 2020-11-09 | 2020-11-09 |  |  | 9400 | [10 empty] | N | N
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00315638 | 004 - Batavia | BATAVIA | 14020 | 36_04_0158 | BATAVIA 1 | N | 5000 |  |  | CDG | N | 2020-10-02 | 2020-10-08 | 4 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00299765 | 039 - Saratoga | SCHUYLERVILLE | 12871 | 36_39_34256 | BATTENKILL 342 | N | 5000 |  |  | CDG | N | 2020-07-07 | 2020-07-17 | 8 | 2020-07-20 | 2020-07-20 | 2020-07-22 | 2 | 2020-09-08 | 2020-09-08 |  |  | 10500 | [10 empty] | N | N
NIMO | Bradley Davis (RENESOLA) | 00311516 | 039 - Saratoga | GREENWICH | 12834 | 36_39_34257 | BATTENKILL 342 | N | 5000 |  |  | CDG | N | 2020-09-24 | 2020-10-11 | 5 | 2020-10-11 | 2020-10-11 | 2020-10-11 | 0 | 2020-12-03 | 2020-12-03 |  |  | 8100 | [10 empty] | N | N
NIMO | Dynamic Energy | 00082328 | 039 - Saratoga | GREENWICH | 12834 | 36_39_34258 | BATTENKILL 342 | N | 1932 |  |  | RNM | N | 2015-02-13 | 2015-03-25 | 2 | 2015-03-25 | 2015-03-25 | 2015-04-09 | 0 | 2015-05-14 | 2015-05-14 | 2015-10-02 | 101 | 40000 | [7 empty] | 2015-12-03 | 2016-03-25 | 2016-03-25 | Y | N
NIMO | Michael Whigham (ConEd CEB) | 00250969 | 039 - Saratoga | GREENWICH | 12834 | 36_39_34258 | BATTENKILL 342 | Y | 5000 | 5000 |  | CDG | N | 2019-09-26 | 2019-10-09 | 13.009 | 2019-10-10 | 2019-10-10 | 2019-10-28 | 12 | 2019-12-16 | 2019-12-16 | 2020-07-31 | 58 | 11400 |  | 2539355 | [8 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00203564 | 039 - Saratoga | GREENWICH | 12834 | 36_39_34258 | BATTENKILL 342 | N | 5000 |  |  | CDG | Y | 2019-01-02 | 2019-01-11 | 8.8681 | 2019-01-14 | 2019-01-14 | 2019-01-24 | 7 | 2019-03-20 | 2019-03-20 | 2019-06-21 | 55 | 9800 |  | 145198 |  |  | 2019-09-13 | 2019-09-17 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00248469 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26051 | BELMONT 260 | N | 5000 |  |  | CDG | Y | 2019-08-27 | 2019-09-06 | 10.1132 | 2019-09-09 | 2019-09-09 | 2019-09-24 | 11 | 2019-11-18 | 2019-11-18 | 2020-02-25 | 59 | 9600 |  | 858424 |  |  | 2020-07-07 | [5 empty] | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00309114 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26051 | BELMONT 260 | N | 5000 |  |  | CDG | N | 2020-09-01 | 2020-09-10 | 5 | 2020-09-10 | 2020-09-10 | 2020-09-10 | 0 | 2020-10-26 | 2020-10-26 |  |  | 10100 | [10 empty] | N | N
NIMO | Zach Drescher (Warner Energy LLC) | 00268401 | 011 - Syracuse | LIVERPOOL | 13090 | 36_11_26054 | BELMONT 260 | N | 4975 |  |  | CDG | Y | 2019-12-05 | 2019-12-18 | 13.0514 | 2019-12-18 | 2019-12-18 | 2019-12-18 | 0 | 2019-12-20 | 2019-12-20 | 2020-04-14 | 57 | 9400 |  | 973056 |  |  | 2020-08-21 | [5 empty] | N | Y
NIMO | Andrew Day (Source Renewables, LLC) | 00108584 | 008 - Dunkirk/Fredoni | SILVER CREEK | 14136 | 36_08_9954 | BENNETT RD 99 | Y | 5000 | 5000 |  | CDG | Y | 2017-09-14 | 2017-09-14 | 0 | 2017-09-20 | 2017-09-20 | 2017-09-28 | 6 | 2019-04-17 | 2019-04-17 | 2019-07-09 | 57 | 20600 |  | 563300.34 |  |  | 2019-11-12 | 2019-11-13 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00249978 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9954 | BENNETT RD 99 | N | 3750 |  |  | CDG | N | 2019-08-21 | 2019-08-28 | 6.8299 | 2019-08-29 | 2019-08-29 | 2019-09-05 | 4 | 2019-11-25 | 2019-11-25 | 2020-04-16 | 58 | 9600 |  | 440978 |  |  | 2020-09-01 | [5 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00279582 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9954 | BENNETT RD 99 | N | 3060 |  |  | CDG | N | 2020-04-08 | 2020-04-16 | 6 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 0 | 2020-06-10 | 2020-06-10 |  |  | 8600 |  | 1277596 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00254020 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9955 | BENNETT RD 99 | N | 5000 |  |  | CDG | Y | 2019-09-13 | 2019-09-26 | 12.966 | 2019-09-27 | 2019-09-27 | 2019-10-04 | 5 | 2019-12-10 | 2019-12-10 | 2020-03-18 | 58 | 9000 |  | 251741 |  |  | 2020-08-12 | [5 empty] | N | Y
NIMO | RIC Development, LLC | 00306421 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9955 | BENNETT RD 99 | N | 3000 |  |  | CDG | N | 2020-08-13 | 2020-08-20 | 5 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 0 | 2020-10-13 | 2020-10-13 |  |  | 9000 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00252184 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_9956 | BENNETT RD 99 | N | 3500 |  |  | CDG | N | 2019-09-05 | 2019-10-18 | 43.3868 | 2019-10-21 | 2019-10-21 | 2019-11-04 | 10 | 2019-12-09 | 2019-12-09 | 2020-10-12 | 59 | 7900 |  | 337673 | [8 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00262694 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_9956 | BENNETT RD 99 | N | 5000 |  |  | CDG | N | 2019-10-29 | 2019-11-25 | 26.9035 | 2019-11-26 | 2019-11-26 | 2019-12-03 | 3 | 2020-01-21 | 2020-01-21 | 2020-10-12 | 59 | 10000 |  | 408438 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00236876 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N | 5000 |  |  | CDG | N | 2019-06-14 | 2019-06-25 | 10.9896 | 2019-06-26 | 2019-06-26 | 2019-07-09 | 8 | 2019-07-29 | 2019-07-29 |  |  | 10100 | [10 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00186138 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  | 2000 | CDG | N | 2018-05-24 | 2018-05-24 | 0 | 2018-11-13 | 2018-11-13 | 2018-11-19 | 3 | 2019-01-14 | 2019-01-14 | 2019-05-01 | 59 | 12000 |  | 633322.53 |  |  | 2019-09-24 | 2019-09-24 |  |  |  |  | N | N
NIMO | Mario Rice (NY DIRECTWIND Portland, LLC) | 00106008 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  | 1000 | CDG | N | 2017-07-07 | 2017-07-07 | 0 | 2017-08-16 | 2017-08-16 | 2017-09-26 | 5 | 2018-05-23 | 2018-05-23 | 2018-10-22 | 59 | 14000 |  | 1675624.12 |  |  | 2019-03-13 | 2019-03-18 |  |  |  |  | N | N
NIMO | Mario Rice (NY DIRECTWIND Portland, LLC) | 00106013 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  | 1000 | CDG | N | 2017-08-08 | 2017-08-08 | 0 | 2017-09-08 | 2017-09-08 | 2017-09-14 | 4 | 2018-05-25 | 2018-05-25 | 2018-10-22 | 56 | 17800 |  | 1080544 |  |  | 2019-03-13 | 2019-03-18 |  |  |  |  | N | N
NIMO | Mario Rice (NY DIRECTWIND Portland, LLC) | 00109592 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  | 1000 | CDG | N | 2017-10-05 | 2017-10-05 | 0 | 2017-10-18 | 2017-10-18 | 2017-11-01 | 10 | 2018-05-23 | 2018-05-23 | 2018-10-22 | 59 | 18700 |  | 841189 |  |  | 2019-03-13 | 2019-03-18 |  |  |  |  | N | N
NIMO | Michael Prinzi (Solar Liberty Energy Systems, Inc. | 00217761 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_15352 | BERRY RD 153 | Y | 1100 | 484 |  | RNM | Y | 2019-04-08 | 2019-05-10 | 32.0569 | 2019-05-13 | 2019-05-13 | 2019-05-16 | 3 | 2019-07-19 | 2019-07-19 | 2019-12-10 | 58 | 11200 |  | 251298 |  |  | 2020-03-09 | 2020-03-10 | 2020-03-10 |  |  |  | N | Y
NIMO | RIC Development | 00296550 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15352 | BERRY RD 153 | N | 3000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 0 | 2020-08-20 | 2020-08-20 |  |  | 9400 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00236961 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15353 | BERRY RD 153 | N | 3875 |  |  | CDG | N | 2019-06-14 | 2019-06-25 | 11.0437 | 2019-06-26 | 2019-06-26 | 2019-07-03 | 5 | 2019-07-29 | 2019-07-29 |  |  | 9800 | [10 empty] | N | N
NIMO | Jared Perram (Saturn Power Corp.) | 00250375 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_15353 | BERRY RD 153 | N | 5000 |  |  | CDG | N | 2019-08-28 | 2019-09-24 | 27.0049 | 2019-09-25 | 2019-09-25 | 2019-10-14 | 13 | 2019-11-07 | 2019-11-07 | 2020-10-06 | 57 | 8700 |  | 14867676 | [8 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00251479 | 008 - Dunkirk/Fredoni | BROCTON | 14716 | 36_08_15353 | BERRY RD 153 | N | 5000 |  |  | CDG | Y | 2019-08-29 | 2019-09-11 | 12.7035 | 2019-09-12 | 2019-09-12 | 2019-09-17 | 3 | 2019-10-29 | 2019-10-29 | 2020-03-11 | 59 | 9800 |  | 579197.01 |  |  | 2020-07-20 | [5 empty] | N | Y
NIMO | Mario Rice (EWT Americas, Inc.) | 00221628 | 008 - Dunkirk/Fredoni | BROCTON | 14716 | 36_08_15353 | BERRY RD 153 | N |  |  | 1000 | CDG | N | 2019-05-10 | 2019-05-29 | 19.0687 | 2019-05-30 | 2019-05-30 | 2019-06-04 | 3 | 2019-07-19 | 2019-07-19 | 2019-12-04 | 59 | 9200 |  | 262020 |  |  | 2020-05-05 | [5 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00221618 | 008 - Dunkirk/Fredoni | BROCTON | 14716 | 36_08_15353 | BERRY RD 153 | N |  |  | 2000 | CDG | N | 2019-05-10 | 2019-05-29 | 19.05 | 2019-05-30 | 2019-05-30 | 2019-06-03 | 2 | 2019-07-19 | 2019-07-19 | 2019-12-04 | 59 | 8700 |  | 65504.99 |  |  | 2020-05-05 | [5 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00221627 | 008 - Dunkirk/Fredoni | BROCTON | 14716 | 36_08_15353 | BERRY RD 153 | N |  |  | 2000 | CDG | N | 2019-05-10 | 2019-05-29 | 18.9806 | 2019-05-30 | 2019-05-30 | 2019-06-03 | 2 | 2019-07-19 | 2019-07-19 | 2019-12-04 | 59 | 9200 |  | 65504.99 |  |  | 2020-05-05 | [5 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00273778 | 030 - Albany | GLENMONT | 12077 | 36_30_02156 | BETHLEHEM 21 | N | 5000 |  |  | CDG | N | 2020-01-17 | 2020-02-01 | 14.7618 | 2020-02-03 | 2020-02-03 | 2020-02-05 | 2 | 2020-04-30 | 2020-04-30 | 2020-10-14 | 58 | 9000 |  | 220189 | [8 empty] | N | N
NIMO | Pat McGowin | 00101326 | 030 - Albany | GLENMONT | 12077 | 36_30_02156 | BETHLEHEM 21 | N | 1990 |  |  | RNM | N | 2015-05-29 | 2015-05-29 | 0 | 2015-07-13 | 2015-07-13 | 2015-08-11 | 0 | 2015-10-14 | 2015-10-14 | 2016-04-21 | 136 | 30000 |  | 620000 |  |  | 2017-05-22 | 2017-07-31 | 2017-05-24 | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00284528 | 030 - Albany | SELKIRK | 12158 | 36_30_02158 | BETHLEHEM 21 | N | 2000 |  |  | CDG | N | 2020-03-23 | 2020-04-01 | 7 | 2020-04-02 | 2020-04-02 | 2020-04-03 | 1 | 2020-04-20 | 2020-04-20 | 2020-07-29 | 58 | 8100 |  | 155384 |  |  | 2020-12-09 | [5 empty] | N | N
NIMO | Wendy DeWolf (East Light Partners) | 00292694 | 033 - Hudson | HUDSON | 12534 | 36_33_30353 | BLUE STORES 303 | N | 5000 |  |  | CDG | N | 2020-06-01 | 2020-06-08 | 5 | 2020-06-08 | 2020-06-08 | 2020-06-08 | 0 | 2020-06-17 | 2020-06-17 | 2020-09-22 | 59 | 9400 |  | 740831 | [8 empty] | N | N
NIMO | David Elliott (NY SOLAR FARMS INC) | 00283374 | 031 - Troy | HOOSICK FALLS | 12090 | 36_31_33351 | BOYNTONVILLE 333 | N | 5000 |  |  | CDG | N | 2020-03-27 | 2020-04-02 | 4 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 |  |  |  |  | 10000 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00195264 | 031 - Troy | JOHNSONVILLE | 12094 | 36_31_33351 | BOYNTONVILLE 333 | N | 5000 |  |  | CDG | Y | 2018-09-11 | 2018-09-18 | 7.1785 | 2018-09-19 | 2018-09-19 | 2018-10-05 | 12 | 2018-12-19 | 2018-12-19 | 2019-03-27 | 28 | 14300 |  | 847878 |  |  | 2019-09-06 | 2019-09-11 |  |  |  |  | N | Y
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00280312 | 028 - Ogdensburg | OGDENSBURG | 13669 | 36_25_95755 | BRADY 957 | Y | 5000 | 5000 |  | CDG | N | 2020-03-12 | 2020-03-18 | 6 | 2020-03-18 | 2020-03-18 | 2020-03-18 | 0 | 2020-03-24 | 2020-03-24 |  |  | 11400 | [10 empty] | N | N
NIMO | Joe Fiori (Nexamp) | 00218932 | 025 - Potsdam | LISBON | 13658 | 36_25_95755 | BRADY 957 | Y | 5000 | 5000 |  | CDG | Y | 2019-04-11 | 2019-05-02 | 21.05 | 2019-05-03 | 2019-05-03 | 2019-05-14 | 7 | 2019-06-05 | 2019-06-05 | 2019-08-30 | 59 | 9900 |  | 313644.91 |  |  | 2020-01-17 | 2020-01-17 | 2020-09-14 |  |  |  | N | Y
NIMO | Samantha Lennon (GSPP County Route 31, LLC) | 00225692 | 025 - Potsdam | LISBON | 13658 | 36_25_95755 | BRADY 957 | N | 5000 |  |  | CDG | Y | 2019-05-08 | 2019-05-22 | 14.1076 | 2019-05-23 | 2019-05-23 | 2019-05-28 | 2 | 2019-10-17 | 2019-10-17 | 2020-01-31 | 59 | 9800 |  | 725320.75 |  |  | 2020-07-14 | [5 empty] | N | Y
NIMO | Michael Frateschi (TJA Clean Energy) | 00318875 | 025 - Potsdam | WADDINGTON | 13694 | 36_25_95756 | BRADY 957 | N | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-20 | 4 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 0 | 2020-12-08 | 2020-12-08 |  |  | 9800 | [10 empty] | N | N
NIMO | Joe Fiori (Nexamp) | 00219099 | 025 - Potsdam | MADRID | 13660 | 36_25_95757 | BRADY 957 | Y | 5000 | 5000 |  | CDG | Y | 2019-04-11 | 2019-04-16 | 5.0542 | 2019-04-17 | 2019-04-17 | 2019-04-22 | 3 | 2019-06-04 | 2019-06-04 | 2019-08-30 | 59 | 9900 |  | 554383.19 |  |  | 2020-01-17 | 2020-01-17 | 2020-09-11 |  |  |  | N | Y
NIMO | Nexamp Interconnections (Nexamp Inc.) | 00218997 | 025 - Potsdam | MADRID | 13660 | 36_25_95757 | BRADY 957 | Y | 2500 | 2500 |  | CDG | Y | 2019-04-19 | 2019-04-30 | 10.8993 | 2019-05-01 | 2019-05-01 | 2019-05-03 | 2 | 2019-07-02 | 2019-07-02 | 2019-09-27 | 57 | 9900 |  | 360714 |  |  | 2020-02-10 | 2020-02-10 | 2020-09-14 |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00317324 | 025 - Potsdam | BRASHER FALLS | 13613 | 36_25_85162 | BRASHER 851 | N | 2000 |  |  | CDG | N | 2020-10-07 | 2020-10-12 | 3 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00320064 | 025 - Potsdam | BOMBAY | 12914 | 36_25_85162 | BRASHER 851 | N | 5000 |  |  | CDG | N | 2020-11-06 | 2020-11-17 | 6 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 | 2020-12-07 | 2020-12-07 |  |  | 12100 | [10 empty] | N | N
NIMO | Greg Hering (ClearPath Energy) | 00265070 | 023 - Lowville | LOWVILLE | 13367 | 36_23_81556 | BREMEN 815 | Y | 4000 | 3000 |  | CDG | Y | 2019-11-21 | 2019-12-28 | 37.2035 | 2019-12-28 | 2019-12-28 | 2019-12-28 | 0 | 2020-02-03 | 2020-02-03 | 2020-05-20 | 59 | 9900 |  | 1389501 |  |  | 2020-10-01 | [5 empty] | N | Y
NIMO | Greg Hering (NB Development LLC) | 00265065 | 023 - Lowville | LOWVILLE | 13367 | 36_23_81556 | BREMEN 815 | Y | 4000 | 3000 |  | CDG | Y | 2019-11-21 | 2019-12-28 | 36.9347 | 2019-12-28 | 2019-12-28 | 2019-12-28 | 0 | 2020-01-30 | 2020-01-30 | 2020-05-20 | 59 | 10900 |  | 782850 |  |  | 2020-09-30 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00278235 | 011 - Syracuse | CICERO | 13039 | 36_11_16852 | BRIDGEPORT 168 | N | 4600 |  |  | CDG | N | 2020-02-21 | 2020-03-04 | 9 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-07 | 59 | 9800 |  | 878447 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00278216 | 011 - Syracuse | CICERO | 13030 | 36_11_16852 | BRIDGEPORT 168 | N | 5000 |  |  | CDG | N | 2020-02-21 | 2020-03-04 | 9 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-07 | 59 | 9800 |  | 837058 | [8 empty] | N | N
NIMO | John J. Watson (CAERO) | 00292138 | 011 - Syracuse | BRIDGEPORT | 13030 | 36_11_16854 | BRIDGEPORT 168 | N | 5000 |  |  | CDG | N | 2020-05-18 | 2020-05-26 | 5 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 0 | 2020-07-13 | 2020-07-13 | 2020-10-27 | 59 | 9400 |  | 759311 | [8 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00252174 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7452 | BROCKPORT 74 | N | 3600 |  |  | CDG | N | 2019-09-05 | 2019-10-18 | 43.3674 | 2019-10-21 | 2019-10-21 | 2019-11-04 | 10 | 2019-11-18 | 2019-11-18 | 2020-10-01 | 57 | 7500 |  | 12977291 | [8 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00250373 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7452 | BROCKPORT 74 | N | 5000 |  |  | CDG | N | 2019-08-28 | 2019-09-23 | 26.1076 | 2019-09-24 | 2019-09-24 | 2019-10-02 | 6 | 2019-11-07 | 2019-11-07 | 2020-09-28 | 57 | 8100 |  | 125018 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248893 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7457 | BROCKPORT 74 | N | 4250 |  |  | CDG | N | 2019-08-15 | 2019-08-27 | 12.0611 | 2019-08-28 | 2019-08-28 | 2019-09-04 | 4 | 2019-11-22 | 2019-11-22 | 2020-04-23 | 58 | 9400 |  | 331849 | [8 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00251021 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7458 | BROCKPORT 74 | N | 4700 |  |  | CDG | N | 2019-09-13 | 2019-09-26 | 13.1479 | 2019-09-27 | 2019-09-27 | 2019-10-15 | 12 | 2019-12-20 | 2019-12-20 | 2020-04-14 | 59 | 8100 |  | 12740689 |  |  | 2020-11-16 | [5 empty] | N | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00173286 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7459 | BROCKPORT 74 | N | 5000 |  |  | CDG | Y | 2018-04-09 | 2018-04-09 | 0 | 2018-06-20 | 2018-06-20 | 2018-07-09 | 12 | 2018-09-13 | 2018-09-13 | 2019-01-24 | 59 | 13300 |  | 188419 |  |  | 2019-06-07 | 2019-06-14 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00173288 |  | BROCKPORT | 14420 | 36_06_7459 | BROCKPORT 74 | N | 5000 |  |  | CDG | Y | 2018-04-09 | 2018-04-09 | 0 | 2018-06-20 | 2018-06-20 | 2018-07-09 | 12 | 2018-09-13 | 2018-09-13 | 2019-01-24 | 59 | 13300 |  | 211615 |  |  | 2019-06-04 | 2019-07-01 |  |  |  |  | N | Y
NIMO | Dynamic Energy | 00102515 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_36951 | BROOK RD 369 | N | 2000 |  |  | RNM | N | 2013-03-22 | 2013-03-22 | 0 | 2013-03-22 | [15 empty] | 2014-07-30 | 2014-07-30 | 2014-07-30 | Y | N
NIMO | Lluis Torrent (CAERO) | 00314693 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_36952 | BROOK RD 369 | N | 3060 |  |  | CDG | N | 2020-09-24 | 2020-11-02 | 6 | 2020-11-09 | 2020-11-09 | 2020-11-09 | 0 | 2020-11-10 | 2020-11-10 |  |  | 8800 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00321454 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_36952 | BROOK RD 369 | N | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-08 | 5 | 2020-12-08 | 2020-12-08 | [6 empty] | 9800 | [10 empty] | N | N
NIMO | Caitlin Majewski (xxx) | 00101073 | 031 - Troy | TROY | 12180 | 36_31_26453 | BRUNSWICK 264 | N | 3960 |  |  | CDG | N | 2015-03-18 | 2016-01-11 | 214 | 2016-01-11 | 2016-01-11 | 2016-03-14 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-27 | 54 | 25000 |  |  |  |  | 2017-06-22 | 2019-09-19 | 2018-12-05 | 2019-09-18 | 2019-09-19 | 2019-09-19 | Y | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00276844 | 031 - Troy | TROY | 12180 | 36_31_26453 | BRUNSWICK 264 | Y | 5000 | 5000 |  | CDG | N | 2020-01-30 | 2020-02-13 | 14.0222 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 0 | 2020-04-30 | 2020-04-30 | 2020-09-21 | 58 | 9100 |  | 810960 | [8 empty] | N | N
NIMO | SunStream Partners | 00094626 | 033 - Hudson | HUDSON | 12208 | 36_33_45451 | BUCKLEY CORNERS 454 | N | 2000 |  |  | RNM | N | 2014-06-23 | 2014-07-10 | 6 | 2014-07-10 | 2014-07-10 | 2014-07-28 | 0 | 2015-03-18 | 2015-03-18 | 2015-07-20 | 88 | 17160 |  | 1018410 | [6 empty] | 2016-11-23 | 2016-11-23 | Y | N
NIMO | SunStream Partners | 00094627 | 033 - Hudson | HUDSON | 12134 | 36_33_45451 | BUCKLEY CORNERS 454 | N | 2000 |  |  | RNM | N | 2014-07-01 | 2014-07-07 | 3 | 2014-07-07 | 2014-07-07 | 2014-07-28 | 4 | 2015-07-19 | 2015-07-19 | 2015-08-04 | 11 | 17160 |  | 218990 | [6 empty] | 2016-11-23 | 2016-11-23 | Y | N
NIMO | Wendy DeWolf (East Light Partners) | 00265520 | 033 - Hudson | HUDSON | 12534 | 36_33_45451 | BUCKLEY CORNERS 454 | N | 3490 |  |  | CDG | Y | 2019-11-21 | 2019-12-04 | 12.8056 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 0 | 2019-12-12 | 2019-12-12 | 2020-06-11 | 59 | 9800 |  | 197807 |  |  | 2020-10-19 | [5 empty] | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00229993 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | BUFFALO STATION | N | 5000 |  |  | CDG | Y | 2019-07-10 | 2019-08-22 | 42.9042 | 2019-08-23 | 2019-08-23 | 2019-09-04 | 7 | 2019-10-31 | 2019-10-31 | 2020-02-04 | 58 | 11800 |  | 726918 |  |  | 2020-04-10 | [5 empty] | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00278951 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | BUFFALO STATION | N | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-16 | 9 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-03-24 | 2020-03-24 | 2020-08-08 | 59 | 9800 |  | 823066 | [8 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00290891 | 004 - Batavia | LEROY | 14482 | 36_04_0457 | BUFFALO STATION | N | 2750 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-29 | 2020-06-29 | 2020-10-12 | 58 | 9400 |  | 780727 | [8 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00278950 | 004 - Batavia | LEROY | 14482 | 36_04_0457 | BUFFALO STATION | N | 3250 |  |  | CDG | N | 2020-03-05 | 2020-03-16 | 9 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-03-24 | 2020-03-24 | 2020-08-08 | 59 | 9800 |  | 809345 | [8 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00271890 | 004 - Batavia | LEROY | 14482 | 36_04_0457 | BUFFALO STATION | N | 4950 |  |  | CDG | N | 2020-02-03 | 2020-02-03 | 0 | 2020-02-04 | 2020-02-04 | 2020-02-04 | 0 | 2020-02-28 | 2020-02-28 | 2020-08-31 | 58 | 9800 |  | 904665 | [8 empty] | N | N
NIMO | Active Solar Development | 00101791 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_20952 | BUFFALO STATION 209 - LONG RD | N | 1992 |  |  | CDG | N | 2016-08-24 | 2016-09-20 | 5 | 2016-09-20 | 2016-09-20 | 2016-10-07 | 0 | 2017-01-27 | 2017-01-27 | 2017-04-21 | 60 | 16200 |  | 120494 |  |  | 2017-07-27 | 2018-04-19 | 2017-07-27 | 2018-04-19 | 2020-04-08 | 2020-04-08 | Y | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00305861 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_20952 | BUFFALO STATION 209 - LONG RD | N | 5000 |  |  | RNM | N | 2020-08-31 | 2020-09-05 | 5 | 2020-09-08 | 2020-09-08 | 2020-09-22 | 10 | 2020-11-02 | 2020-11-02 |  |  | 9400 | [10 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy) | 00230055 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_23251 | BUFFALO STATION 232 - OAKWOOD DR | Y | 5000 | 5000 |  | CDG | Y | 2019-08-22 | 2019-09-13 | 21.9049 | 2019-09-16 | 2019-09-16 | 2019-09-27 | 9 | 2019-12-13 | 2019-12-13 | 2020-04-17 | 57 | 9000 |  | 519354 |  |  | 2020-06-02 | [5 empty] | N | Y
NIMO | Dan Leary (OurGeneration, LLC) | 00272582 | 001 - Buffalo | AMHERST | 14228 | 36_03_23252 | BUFFALO STATION 232 - OAKWOOD DR | Y | 3500 | 1500 |  | CDG | N | 2020-01-09 | 2020-01-24 | 15.2139 | 2020-01-24 | 2020-01-24 | 2020-01-24 | 0 | 2020-04-01 | 2020-04-01 | 2020-07-27 | 58 | 8800 |  | 368400 |  |  | 2020-12-08 | [5 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00236931 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_23253 | BUFFALO STATION 232 - OAKWOOD DR | N | 3750 |  |  | CDG | Y | 2019-06-24 | 2019-07-02 | 7.841 | 2019-07-03 | 2019-07-03 | 2019-07-11 | 5 | 2019-09-20 | 2019-09-20 | 2020-01-24 | 59 | 9000 |  | 114703.54 |  |  | 2020-04-13 | 2020-10-02 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00190121 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_23255 | BUFFALO STATION 232 - OAKWOOD DR | N | 5000 |  |  | CDG | Y | 2018-07-16 | 2018-07-23 | 6.8785 | 2018-07-24 | 2018-07-24 | 2018-08-02 | 7 | 2018-08-30 | 2018-08-30 | 2018-12-19 | 60 | 13300 |  | 190843 |  |  | 2019-03-21 | 2019-04-03 |  |  | 2020-10-01 | 2020-10-01 | Y | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00315183 | 001 - Buffalo | BUFFALO | 14207 | 36_01_4869 | BUFFALO STATION 48 - GELSTON & BRECKENRIDGE | N | 4950 |  |  | RNM | N | 2020-09-25 | 2020-10-05 | 5 | 2020-10-05 | 2020-10-05 | 2020-10-05 | 0 |  |  |  |  | 10100 | [10 empty] | N | N
NIMO | Alicia Scott (BQ Energy Development, LLC.) | 00284584 | 001 - Buffalo | BUFFALO | 14210 | 36_01_5161 | BUFFALO STATION 51 - ELK & DOLE | N | 3500 |  |  | CDG | N | 2020-03-27 | 2020-04-08 | 8 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 0 | 2020-04-21 | 2020-04-21 | 2020-10-01 | 58 | 9100 |  | 121956 | [8 empty] | N | N
NIMO | Dallas Manson (Nexamp) | 00278801 | 032 - Schenectady | SCHENECTADY | 12306 | 36_32_26553 | BURDECK ST 265 | N | 5000 |  |  | CDG | N | 2020-03-10 | 2020-03-17 | 7 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-04-24 | 2020-04-24 | 2020-08-31 | 57 | 9900 |  | 1449377 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00328095 | 032 - Schenectady | SCHENECTADY | 12306 | 36_32_26553 | BURDECK ST 265 | N | 5000 |  |  | CDG | N | 2020-11-25 | 2020-12-03 | 4 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Kelsey Crane (ForeFront Power) | 00101267 | 032 - Schenectady | SCHENECTADY | 12305 | 36_32_26553 | BURDECK ST 265 | N | 2000 |  |  | CDG | N | 2015-09-15 | 2015-09-15 | 0 | 2015-09-15 |  |  |  | 2016-02-09 | 2016-02-09 | 2016-05-17 | 70 | 10000 |  | 328650 |  |  | 2017-02-14 | 2017-07-21 | 2017-07-24 | 2017-07-24 | 2018-12-27 | 2018-12-27 | Y | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00194524 | 038 - Glens Falls | ARGYLE | 12809 | 36_38_33751 | BURGOYNE 337 | Y | 4980 | 5000 |  | CDG | Y | 2018-08-29 | 2018-09-11 | 12.991 | 2018-09-12 | 2018-09-12 | 2018-10-01 | 13 | 2018-12-06 | 2018-12-06 | 2019-03-11 | 58 | 15300 |  | 781786.8 |  |  | 2019-10-08 | 2019-10-10 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00201351 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_33751 | BURGOYNE 337 | Y | 4980 | 5000 |  | CDG | N | 2018-11-16 | 2018-12-10 | 23.9097 | 2018-12-11 | 2018-12-11 | 2018-12-12 | 1 | 2019-08-14 | 2019-08-14 | 2020-08-28 | 83 | 9400 |  | 831850 | [8 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00172236 | 038 - Glens Falls | SOUTH HARTFORD | 12838 | 36_38_33752 | BURGOYNE 337 | N | 2500 |  |  | CDG | Y | 2018-04-05 | 2018-04-05 | 0 | 2018-04-20 | 2018-04-20 | 2018-05-07 | 11 | 2018-12-07 | 2018-12-07 | 2019-06-18 | 59 | 16400 |  | 826877 |  |  | 2019-09-13 | 2019-09-20 |  |  |  |  | N | Y
NIMO | Andrea DeBernardis (AC Power) | 00302351 | 038 - Glens Falls | HUDSON FALLS | 12839 | 36_38_33754 | BURGOYNE 337 | N | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-09 | 5 | 2020-08-09 | 2020-08-09 | 2020-08-09 | 0 | 2020-09-17 | 2020-09-17 |  |  | 9200 | [10 empty] | N | N
NIMO | Dave Byrne (Renua Energy, Inc.) | 00318630 | 038 - Glens Falls | GANSEVOORT | 12831 | 36_38_36251 | BUTLER 362 | N | 5000 |  |  | CDG | N | 2020-11-04 | 2020-11-09 | 3 | 2020-11-09 | 2020-11-09 | 2020-11-16 | 3 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00211371 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_36253 | BUTLER 362 | N | 5000 |  |  | CDG | Y | 2019-02-25 | 2019-03-08 | 10.9646 | 2019-03-11 | 2019-03-11 | 2019-03-13 | 2 | 2019-05-08 | 2019-05-08 | 2019-08-28 | 59 | 9200 |  | 573532 |  |  | 2020-02-21 | 2020-02-25 |  |  |  |  | N | Y
NIMO |  | 00211385 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_36253 | BUTLER 362 | N | 5000 |  |  | CDG | Y | 2019-02-25 | 2019-03-08 | 10.9736 | 2019-03-11 | 2019-03-11 | 2019-03-13 | 2 | 2019-05-08 | 2019-05-08 | 2019-08-28 | 59 | 9800 |  | 241382.66 |  |  | 2020-02-21 | 2020-02-25 |  |  |  |  | N | Y
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00326621 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_25555 | BUTTERNUT 255 | N | 5000 |  |  | CDG | N | 2020-11-18 | 2020-11-30 | 6 | 2020-11-30 | 2020-11-30 | 2020-12-11 | 8 |  |  |  |  | 9900 | [10 empty] | N | N
NIMO | Michael Roach (RER Energy Group LLC) | 00100828 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_25555 | BUTTERNUT 255 | N | 1980 |  |  | RNM | Y | 2015-06-01 | 2015-06-11 | 7 | 2015-06-11 | 2015-06-11 | 2015-07-01 | 0 | 2016-06-06 | 2016-06-06 | 2017-08-15 | 60 | 25000 |  | 144550 |  |  | 2017-11-07 | 2017-11-09 |  |  | 2020-09-17 | 2020-09-17 | Y | Y
NIMO | Solar City (Solar City) | 00100869 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7252 | BUTTS RD 72 | N | 912 |  |  | RNM | N | 2015-05-18 | 2016-09-15 | 3 | 2016-09-15 | 2016-09-15 | 2016-09-29 | 0 | 2016-11-30 | 2016-11-30 | 2017-02-23 | 60 | 16200 |  |  |  |  | 2017-11-02 | 2018-10-31 | 2017-11-02 | 2018-10-31 | 2019-03-29 | 2019-03-29 | Y | N
NIMO | Lluis Torrent (CAERO) | 00298068 | 017 - Utica | MARCY | 13403 | 36_17_61651 | CAVANAUGH 616 | N | 3060 |  |  | CDG | N | 2020-06-25 | 2020-07-02 | 5 | 2020-07-02 | 2020-07-02 | 2020-07-02 | 0 | 2020-08-20 | 2020-08-20 | 2020-12-07 | 59 | 8800 |  | 365404 | [8 empty] | N | N
NIMO | Benjamin Rubin (Ameresco Inc.) | 00218905 | 017 - Utica | MARCY | 13403 | 36_17_61652 | CAVANAUGH 616 | N | 4482 |  |  | RNM | Y | 2019-05-01 | 2019-05-24 | 22.9847 | 2019-05-28 | 2019-05-28 | 2019-06-06 | 7 | 2019-06-17 | 2019-06-17 | 2019-08-30 | 47 | 9400 |  | 174653.46 |  |  | 2020-01-14 | 2020-01-15 |  |  |  |  | N | Y
NIMO | Haley Orvedal (Galehead DG Solutions, LLC) | 00303754 | 017 - Utica | MARCY | 13403 | 36_17_61654 | CAVANAUGH 616 | N | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-10 | 5 | 2020-08-10 | 2020-08-10 | 2020-08-10 | 0 | 2020-09-18 | 2020-09-18 |  |  | 9400 | [10 empty] | N | N
NIMO | Kevin Bailey (High Peaks Solar, LLC) | 00242647 | 038 - Glens Falls | QUEENSBURY | 12804 | 36_38_45351 | CEDAR 453 | N | 4650 |  |  | CDG | Y | 2019-07-31 | 2019-09-23 | 53.8438 | 2019-09-24 | 2019-09-24 | 2019-09-25 | 1 | 2019-10-22 | 2019-10-22 | 2020-03-30 | 59 | 8800 |  | 307051 |  |  | 2020-09-17 | [5 empty] | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00310886 | 038 - Glens Falls | QUEENSBURY | 12804 | 36_38_45352 | CEDAR 453 | Y | 5000 | 5000 |  | CDG | N | 2020-09-14 | 2020-09-24 | 7 | 2020-09-25 | 2020-09-25 | 2020-09-29 | 2 | 2020-11-02 | 2020-11-02 |  |  | 9400 | [10 empty] | N | N
NIMO | BWC Crum Run, LLC (BlueWave Solar) | 00297807 | 035 - Gloversville | FONDA | 12068 | 36_35_37952 | CENTER ST 379 | N | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-21 | 8 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 2020-10-06 | 2020-10-06 |  |  | 11700 | [10 empty] | N | N
NIMO | BWC Indian Rd Pond, LLC (BlueWave Solar) | 00297826 | 035 - Gloversville | FONDA | 12068 | 36_35_37952 | CENTER ST 379 | N | 3620 |  |  | CDG | N | 2020-08-11 | 2020-08-21 | 8 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 2020-10-06 | 2020-10-06 |  |  | 11700 | [10 empty] | N | N
NIMO | Trevor Hardy (BlueWave Solar) | 00297692 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_37952 | CENTER ST 379 | N | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-21 | 8 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 2020-10-06 | 2020-10-06 |  |  | 11700 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00317427 | 035 - Gloversville | FONDA | 12068 | 36_35_37953 | CENTER ST 379 | N | 5000 |  |  | RNM | N | 2020-10-14 | 2020-10-19 | 3 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Ryan Lloyd (DG VEMV, LLC) | 00217483 | 035 - Gloversville | FULTONVILLE | 12072 | 36_35_37954 | CENTER ST 379 | Y | 4980 | 5000 |  | CDG | Y | 2019-04-03 | 2019-04-15 | 11.6417 | 2019-04-16 | 2019-04-16 | 2019-04-23 | 5 | 2019-10-08 | 2019-10-08 | 2020-01-09 | 55 | 9200 |  | 1060500.94 |  |  | 2020-01-22 | 2020-01-22 |  |  |  |  | N | Y
NIMO | Ryan Lloyd (DG VEMV, LLC) | 00217569 | 035 - Gloversville | FULTONVILLE | 12072 | 36_35_37954 | CENTER ST 379 | Y | 4980 | 5000 |  | CDG | Y | 2019-04-04 | 2019-04-15 | 11.009 | 2019-04-16 | 2019-04-16 | 2019-04-23 | 5 | 2019-07-23 | 2019-07-23 | 2020-01-15 | 54 | 11300 |  | 309980.9 |  |  | 2020-01-22 | 2020-01-22 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00273247 | 017 - Utica | FRANKFORT | 13340 | 36_17_66851 | CHADWICKS 668 | N | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-17 | 8 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-05-20 | 2020-05-20 |  |  | 10800 | [10 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00273255 | 017 - Utica | FRANKFORT | 13340 | 36_17_66851 | CHADWICKS 668 | N | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-17 | 8 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-05-20 | 2020-05-20 |  |  | 10800 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00318911 | 017 - Utica | SAUQUOIT | 13456 | 36_17_66851 | CHADWICKS 668 | N | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-03 | 7 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00315418 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_66852 | CHADWICKS 668 | N | 3750 |  |  | CDG | N | 2020-10-21 | 2020-10-21 | 0 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 0 | 2020-11-17 | 2020-11-17 |  |  | 9800 | [10 empty] | N | N
NIMO | William Jordan (Jordan Energy & Food Enterprises, | 00314444 | 017 - Utica | SAUQUOIT | 13456 | 36_17_66852 | CHADWICKS 668 | N | 5000 |  |  | CDG | N | 2020-10-08 | 2020-10-14 | 4 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 0 | 2020-11-20 | 2020-11-20 |  |  | 10100 | [10 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00263262 | 009 - Lakewood/Stow | MAYVILLE | 14757 | 36_09_5762 | CHAUTAUQUA 57 | N | 3500 |  |  | CDG | Y | 2019-11-13 | 2019-12-04 | 20.8403 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 0 | 2020-01-13 | 2020-01-13 | 2020-05-20 | 57 | 11700 |  | 1062859 |  |  | 2020-10-12 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00101016 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_04356 | CHURCH ST 43 | N | 1992 |  |  | RNM | N | 2015-02-13 | 2015-04-14 | 6 | 2015-04-14 | 2015-04-14 | 2015-05-15 | 0 | 2015-07-23 | 2015-07-23 | 2015-10-23 | 66 | 25000 |  | 251383 | [6 empty] | 2016-12-23 | 2016-12-23 | Y | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315545 | 034 - Amsterdam | HAGAMAN | 12086 | 36_35_04356 | CHURCH ST 43 | N | 5000 |  |  | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 10100 | [10 empty] | N | N
NIMO | Josh katz (Onyx Development Grou) | 00100909 | 034 - Amsterdam | AMSTERDAM | 10210 | 36_35_04356 | CHURCH ST 43 | N | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 3 | 2015-06-11 | 2015-06-11 | 2015-08-03 | 0 | 2015-12-15 | 2015-12-15 | 2016-05-18 | 111 | 25000 |  | 144467 |  |  | 2016-12-13 | 2017-11-01 | 2017-11-02 | 2018-01-09 | 2018-03-26 | 2018-03-26 | Y | N
NIMO | Josh Katz (Onyx Development Grou) | 00100910 | 034 - Amsterdam | AMSTERDAM | 10210 | 36_35_04356 | CHURCH ST 43 | N | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 3 | 2015-06-11 | 2015-06-11 | 2015-08-03 | 0 | 2015-12-15 | 2015-12-15 | 2016-05-18 | 111 | 25000 |  | 1195525 | [5 empty] | 2018-03-23 | 2018-03-28 | 2018-03-28 | Y | N
NIMO | Mike Borkowski (Community Power Group) | 00273436 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_04356 | CHURCH ST 43 | N | 5000 |  |  | CDG | N | 2020-01-16 | 2020-01-31 | 15.141 | 2020-01-31 | 2020-01-31 | 2020-01-31 | 0 | 2020-04-15 | 2020-04-15 |  |  | 9400 | [10 empty] | N | N
NIMO | Brendan Mooney (AMP Solar US Holdings Inc.) | 00305541 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_04357 | CHURCH ST 43 | Y | 5000 | 0 |  | CDG | N | 2020-10-14 | 2020-12-03 | 0 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Brendan Mooney (AMP Solar US Holdings Inc.) | 00305634 |  | AMSTERDAM | 12010 | 36_35_04357 | CHURCH ST 43 | Y | 5000 | 0 |  | CDG | N | 2020-10-22 | 2020-10-29 | 5 | 2020-10-30 | 2020-10-30 | 2020-11-04 | 3 |  |  |  |  | 11000 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316701 | 035 - Gloversville | PALATINE BRIDGE | 13428 | 36_35_36652 | CLINTON 366 | N | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-22 | 4 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2020-12-02 | 2020-12-02 |  |  | 10400 | [10 empty] | N | N
NIMO | Nexamp Interconnections (Nexamp) | 00198681 | 035 - Gloversville | PALATINE BRIDGE | 13428 | 36_35_36652 | CLINTON 366 | Y | 5000 | 5000 |  | CDG | Y | 2018-10-16 | 2018-11-14 | 28.9451 | 2018-11-15 | 2018-11-15 | 2018-11-26 | 5 | 2019-01-03 | 2019-01-03 | 2019-04-16 | 59 | 13300 |  | 2130947 |  |  | 2019-09-24 | 2019-10-28 | 2019-09-25 | 2019-10-28 |  |  | N | Y
NIMO | Irby (Cypress Creek Renewables) | 00243855 | 035 - Gloversville | CANAJOHARIE | 13317 | 36_35_36654 | CLINTON 366 | N | 5000 |  |  | CDG | N | 2019-08-29 | 2019-09-13 | 14.8882 | 2019-09-16 | 2019-09-16 | 2019-10-01 | 11 | 2019-12-16 | 2019-12-16 | 2020-09-03 | 54 | 11700 |  | 3074679 | [8 empty] | N | N
NIMO |  | 00243856 | 035 - Gloversville | CANAJOHARIE | 13317 | 36_35_36654 | CLINTON 366 | N | 5000 |  |  | CDG | N | 2019-08-29 | 2019-09-13 | 14.8736 | 2019-09-16 | 2019-09-16 | 2019-10-01 | 11 | 2019-12-16 | 2019-12-16 | 2020-09-03 | 57 | 11700 |  | 3074679 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00270253 | 017 - Utica | CLINTON | 13323 | 36_17_60451 | CLINTON 604 | Y | 5000 | 0 |  | CDG | Y | 2020-01-06 | 2020-01-22 | 16.0604 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 0 | 2020-02-04 | 2020-02-04 | 2020-06-15 | 59 | 9500 |  | 265642.96 |  |  | 2020-06-16 | 2020-12-04 |  |  |  |  | N | Y
NIMO | David Spotts (SSC Kirkland II LLC) | 00280860 | 017 - Utica | CLINTON | 13323 | 36_17_60454 | CLINTON 604 | Y | 5000 | 0 |  | CDG | Y | 2020-03-03 | 2020-03-13 | 8 | 2020-03-13 | 2020-03-13 | 2020-03-13 | 0 | 2020-04-29 | 2020-04-29 | 2020-08-19 | 58 | 9900 |  | 176367 | [8 empty] | N | Y
NIMO | David Spotts (Summit Solar Capital, LLC) | 00267494 | 017 - Utica | CLINTON | 13323 | 36_17_60454 | CLINTON 604 | Y | 5000 | 5000 |  | CDG | Y | 2019-11-27 | 2019-12-11 | 14.1986 | 2019-12-12 | 2019-12-12 | 2019-12-16 | 2 | 2019-12-24 | 2019-12-24 | 2020-04-27 | 59 | 9900 |  | 176367 |  |  | 2020-10-01 | [5 empty] | N | Y
NIMO | Dallas Manson (Nexamp Solar LLC) | 00247815 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76054 | COFFEEN 760 | N | 5000 |  |  | CDG | N | 2019-09-17 | 2019-09-30 | 12.7569 | 2019-10-01 | 2019-10-01 | 2019-10-18 | 13 | 2019-12-02 | 2019-12-02 |  |  | 8300 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar L.P.) | 00268269 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76055 | COFFEEN 760 | Y | 5000 | 5000 |  | CDG | N | 2020-01-07 | 2020-01-14 | 7.2361 | 2020-01-15 | 2020-01-15 | 2020-01-21 | 3 | 2020-03-25 | 2020-03-25 |  |  | 11400 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00244403 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76055 | COFFEEN 760 | N | 5000 |  |  | CDG | Y | 2019-07-26 | 2019-08-21 | 26.4069 | 2019-08-22 | 2019-08-22 | 2019-08-28 | 4 | 2019-09-04 | 2019-09-04 | 2020-01-09 | 59 | 9900 |  | 1325818.85 |  |  | 2020-03-30 | 2020-10-27 |  |  |  |  | N | Y
NIMO | David Wagner (Cypress Creek) | 00100819 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76056 | COFFEEN 760 | N | 1988 |  |  | RNM | N | 2015-05-27 | 2015-05-27 | 0 | 2015-11-19 | 2015-11-19 | 2015-11-24 | 3 | 2016-02-26 | 2016-02-26 | 2016-07-05 | 92 | 20000 |  | 145767 |  |  |  | 2017-12-29 | 2017-06-19 | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Kelsey Crane (ForeFront Power) | 00100863 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76056 | COFFEEN 760 | N | 2000 |  |  | CDG | N | 2015-05-13 | 2015-06-01 | 3 | 2015-06-01 | 2015-06-01 | 2015-06-17 | 0 | 2015-10-21 | 2015-10-21 | 2016-05-06 | 142 | 25000 |  | 213350 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-24 | 2018-12-11 | 2018-12-21 | 2018-12-21 | Y | N
NIMO | Kelsey Crane (Forefront Power) | 00208992 | 013 - Watertown | DEXTER | 13634 | 36_13_76056 | COFFEEN 760 | N | 5000 |  |  | CDG | Y | 2019-02-08 | 2019-02-20 | 11.8667 | 2019-02-21 | 2019-02-21 | 2019-03-01 | 6 | 2019-07-22 | 2019-07-22 | 2019-10-17 | 59 | 9000 |  | 816401.74 |  |  | 2019-12-30 | 2020-01-03 | 2020-09-11 |  |  |  | N | Y
NIMO | Andrew Day (Source Renewables, LLC) | 00250816 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_151156 | COLLAMER CROSSING | Y | 5000 | 5000 |  | CDG | Y | 2019-08-26 | 2019-09-04 | 8.9021 | 2019-09-05 | 2019-09-05 | 2019-09-09 | 2 | 2019-12-26 | 2019-12-26 | 2020-05-05 | 59 | 10300 |  | 973056 |  |  | 2020-09-11 | [5 empty] | N | Y
NIMO | Todd Friedman (RESunance, LLC) | 00319891 | 007 - Angola | COLLINS | 14034 | 36_07_8361 | COLLINS 83 | N | 5000 |  |  | CDG | N | 2020-10-30 | 2020-11-06 | 5 | 2020-11-06 | 2020-11-06 | 2020-11-06 | 0 | 2020-11-16 | 2020-11-16 |  |  | 11700 | [10 empty] | N | N
NIMO | Ryan Mccune (Nexamp) | 00259078 | 016 - Pulaski | PARISH | 13131 | 36_16_32151 | COLOSSE 321 | N | 5000 |  |  | CDG | Y | 2019-11-05 | 2019-11-18 | 13.0722 | 2019-11-18 | 2019-11-18 | 2019-11-18 | 0 | 2019-12-30 | 2019-12-30 | 2020-03-30 | 52 | 8700 |  | 756679 |  |  | 2020-08-21 | [5 empty] | N | Y
NIMO | Kevin O'Neill (Seaboard Solar) | 00319298 | 038 - Glens Falls | COMSTOCK | 12821 | 36_38_04808 | COMSTOCK 48 | N | 4975 |  |  | CDG | N | 2020-10-28 | 2020-11-04 | 5 | 2020-11-05 | 2020-11-05 | 2020-11-13 | 5 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00328584 | 005 - Avon | GROVELAND | 14462 | 36_05_5262 | CONESUS 52 | N | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-08 | 5 | 2020-12-08 | 2020-12-08 | [17 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00283966 | 035 - Gloversville | HADLEY | 12822 | 36_39_28551 | CORINTH 285 | N | 5000 |  |  | CDG | N | 2020-04-23 | 2020-04-30 | 5 | 2020-05-01 | 2020-05-01 | 2020-05-04 | 1 | 2020-08-11 | 2020-08-11 |  |  | 11300 | [10 empty] | N | N
NIMO | BlueWave Project Development, LLC (BlueWave Solar) | 00303657 | 039 - Saratoga | CORINTH | 12822 | 36_39_28552 | CORINTH 285 | N | 5000 |  |  | CDG | N | 2020-08-19 | 2020-08-25 | 4 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 0 | 2020-10-12 | 2020-10-12 |  |  | 11300 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00245119 | 012 - Cortland | CORTLAND | 13045 | 36_12_50203 | CORTLAND 502 | Y | 5000 | 5000 |  | CDG | Y | 2019-07-24 | 2019-08-01 | 7.8278 | 2019-08-02 | 2019-08-02 | 2019-08-13 | 7 | 2019-10-16 | 2019-10-16 | 2020-01-14 | 59 | 11400 |  | 949436 |  |  | 2020-02-19 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Christopher Stroud (Cipriani Energy Group Corp.) | 00289878 | 041 - Ticonderoga | CROWN POINT | 12928 | 36_41_24951 | CROWN POINT 249 | N | 1200 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 2 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-02 | 2020-07-02 | 2020-10-19 | 59 | 9200 |  | 204152 | [8 empty] | N | N
NIMO | Solar City | 00101509 | 032 - Schenectady | SCHENECTADY | 12303 | 36_32_36556 | CURRY RD 365 | N | 1536 |  |  | RNM | N | 2016-01-22 | 2016-03-22 | 9 | 2016-03-22 | 2016-03-22 | 2016-04-11 | 0 | 2016-05-20 | 2016-05-20 | 2016-08-16 | 60 | 17500 |  | 219830 |  |  | 2017-05-17 | 2019-06-13 | 2017-11-02 | 2019-09-18 | 2019-09-20 | 2019-09-20 | Y | N
NIMO | Jordana Jusidman (groSolar) | 00101012 | 028 - Ogdensburg | LISBON | 13669 | DAVID-MCINTYRE #21 | DAVID 979 | N | 1000 |  |  | RNM | N | 2015-02-06 | 2015-03-01 | 16 | 2015-03-01 | 2015-03-01 | 2015-03-10 | 0 | 2015-06-02 | 2015-06-02 | 2015-11-05 | 112 | 28000 |  | 217831 |  |  | 2017-06-02 | 2017-12-06 | 2017-11-20 | 2017-12-06 | 2018-12-19 | 2018-12-19 | Y | N
NIMO | Mike Borkowski (Community Power Group) | 00276811 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_68451 | DEBALSO 684 | N | 5000 |  |  | CDG | N | 2020-03-16 | 2020-03-25 | 9 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 0 | 2020-06-24 | 2020-06-24 | 2020-10-12 | 59 | 10400 |  | 810756 | [8 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00321884 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_68451 | DEBALSO 684 | N | 5000 |  |  | CDG | N | 2020-10-28 | 2020-11-06 | 7 | 2020-11-06 | 2020-11-06 | 2020-11-06 | 0 | 2020-11-30 | 2020-11-30 |  |  | 10400 | [10 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00293901 | 017 - Utica | UTICA | 13502 | 36_17_60656 | DEERFIELD 606 | N | 4000 |  |  | CDG | N | 2020-06-25 | 2020-07-01 | 4 | 2020-07-01 | 2020-07-01 | 2020-07-01 | 0 | 2020-08-18 | 2020-08-18 | 2020-11-24 | 59 | 9400 |  | 2042470 | [8 empty] | N | N
NIMO | Alexander Paul McMenemy (Solar Generation Projects | 00277306 | 017 - Utica | HOLLAND PATENT | 13354 | 36_17_60656 | DEERFIELD 606 | N | 5000 |  |  | CDG | N | 2020-02-21 | 2020-03-04 | 10 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-03-19 | 2020-03-19 | 2020-12-04 | 58 | 10400 |  | 1583225 | [8 empty] | N | N
NIMO | Alexander Paul McMenemy (Solar Generation Projects | 00277347 | 017 - Utica | HOLLAND PATENT | 13354 | 36_17_60656 | DEERFIELD 606 | N | 5000 |  |  | CDG | N | 2020-02-21 | 2020-03-04 | 10 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-04-28 | 2020-04-28 |  |  | 10400 | [10 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00210245 | 017 - Utica | UTICA | 13502 | 36_17_60656 | DEERFIELD 606 | Y | 3200 | 5000 |  | CDG | Y | 2019-04-09 | 2019-04-20 | 10.7312 | 2019-04-22 | 2019-04-22 | 2019-04-29 | 5 | 2019-06-26 | 2019-06-26 | 2020-06-08 | 59 | 10300 |  | 830876 |  |  | 2020-10-14 | [5 empty] | N | Y
NIMO | Lluis Torrent (CAERO) | 00304033 | 017 - Utica | UTICA | 13502 | 36_17_60658 | DEERFIELD 606 | N | 4000 |  |  | CDG | N | 2020-08-04 | 2020-08-14 | 8 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 0 | 2020-09-09 | 2020-09-09 |  |  | 8800 | [10 empty] | N | N
NIMO | John McDonough (National Solar Group LLC) | 00195570 | 029 - Gouvernur | DEKALB JUNCTION | 13630 | 36_29_98455 | DEKALB 984 | N | 3000 |  |  | CDG | Y | 2018-09-17 | 2018-10-18 | 30.9653 | 2018-10-19 | 2018-10-19 | 2018-10-26 | 5 | 2018-12-13 | 2018-12-13 | 2019-04-15 | 56 | 12200 |  | 696561 |  |  | 2019-09-03 | 2019-11-08 | 2019-09-09 | 2019-11-08 |  |  | N | Y
NIMO | John McDonough (National Solar Group LLC) | 00195434 | 029 - Gouvernur | DEKALB JUNCTION | 13630 | 36_29_98455 | DEKALB 984 | N | 5000 |  |  | CDG | Y | 2018-09-17 | 2018-10-18 | 30.9625 | 2018-10-19 | 2018-10-19 | 2018-10-26 | 5 | 2018-12-13 | 2018-12-13 | 2019-04-15 | 56 | 13300 |  | 483676 |  |  | 2019-09-03 | 2019-11-05 | 2019-09-09 | 2019-11-05 |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00286223 | 007 - Angola | ANGOLA | 14006 | 36_07_9351 | DELAMETER RD SUBSTATION | N | 5000 |  |  | RNM | N | 2020-04-03 | 2020-04-10 | 5 | 2020-04-10 | 2020-04-10 | 2020-04-10 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-24 | 59 | 9400 |  | 689651 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00281938 | 007 - Angola | IRVING | 14081 | 36_07_9353 | DELAMETER RD SUBSTATION | N | 5000 |  |  | CDG | N | 2020-03-03 | 2020-03-13 | 9 | 2020-03-16 | 2020-03-16 | 2020-03-19 | 3 | 2020-05-14 | 2020-05-14 | 2020-08-21 | 58 | 10400 |  | 1079502 | [8 empty] | N | N
NIMO | VANGUARD ENERGY PARTNERS LLC | 00102042 | 007 - Angola | ANGOLA | 14006 | 36_07_9353 | DELAMETER RD SUBSTATION | N | 930 |  |  | NA | Y | 2016-02-25 | 2016-03-31 | 7 | 2016-03-31 | 2016-03-31 | 2016-04-13 | 0 | 2016-09-13 | 2016-09-13 | 2016-12-12 | 60 | 21300 |  | 30000 |  |  | 2017-07-18 |  |  |  | 2018-12-13 | 2018-12-13 | Y | Y
NIMO | SUSTAINABLE ENERGY DEVELOPMENTS | 00100891 | 007 - Angola | IRVING | 14081 | 36_07_9354 | DELAMETER RD SUBSTATION | N |  |  | 1500 | RNM | N | 2015-05-20 | 2015-06-02 | 10 | 2015-06-02 | 2015-06-02 | 2015-06-22 | 0 | 2015-10-30 | 2015-10-30 | 2016-02-22 | 81 | 42400 |  | 501989 | [6 empty] | 2017-06-19 | 2017-06-19 | Y | N
NIMO | Nicole LeBlanc (AMP Solar Dev. Inc.) | 00165990 | 037 - Cobleskill | DELANSON | 12053 | 36_37_26951 | DELANSON 269 | Y | 5000 | 4500 |  | CDG | Y | 2017-11-20 | 2017-11-20 | 0 | 2017-12-05 | 2017-12-05 | 2017-12-14 | 7 | 2018-03-12 | 2018-03-12 | 2018-08-16 | 56 | 19300 |  | 173436.44 |  |  | 2019-05-08 | 2019-05-10 |  |  |  |  | N | Y
NIMO | Nicole LeBlanc (AMP Solar Dev. Inc.) | 00166610 | 037 - Cobleskill | DELANSON | 12053 | 36_37_26951 | DELANSON 269 | Y | 5000 | 4500 |  | CDG | Y | 2017-12-05 | 2017-12-05 | 0 | 2017-12-07 | 2017-12-07 | 2017-12-14 | 5 | 2018-03-12 | 2018-03-12 | 2018-08-16 | 56 | 20600 |  | 153177 |  |  | 2019-05-08 | 2019-07-19 |  |  |  |  | N | Y
NIMO | Safari Energy | 00100806 | 037 - Cobleskill | DELANSON | 12817 | 36_37_26951 | DELANSON 269 | N | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-10 | 3 | 2015-06-10 | 2015-06-10 | 2015-06-17 | 0 | 2015-12-15 | 2015-12-15 | 2016-06-28 | 140 | 35000 |  | 862940 |  |  | 2016-12-13 | 2017-11-01 | 2017-11-02 | 2018-03-01 | 2018-04-19 | 2018-04-19 | Y | N
NIMO | Michael Cucchiara (Nexamp) | 00279193 | 037 - Cobleskill | DELANSON | 12053 | 36_37_26952 | DELANSON 269 | N | 5000 |  |  | CDG | N | 2020-03-10 | 2020-03-17 | 7 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-05-20 | 2020-05-20 | 2020-09-21 | 59 | 8600 |  | 3511853 | [8 empty] | N | N
NIMO | Michael Whigham (ConEd CEB) | 00268193 | 037 - Cobleskill | SPRAKERS | 12166 | 36_37_26952 | DELANSON 269 | Y | 2000 | 5000 |  | CDG | N | 2020-01-13 | 2020-02-03 | 20.8903 | 2020-02-04 | 2020-02-04 | 2020-02-04 | 0 | 2020-03-23 | 2020-03-23 | 2020-09-24 | 53 | 10800 |  | 1194703 | [8 empty] | N | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00299301 | 010 - Olean | DELEVAN | 14042 | 36_10_1161 | DELEVAN 11 | N | 5000 |  |  | CDG | N | 2020-07-20 | 2020-07-20 | 0 | 2020-07-21 | 2020-07-21 | 2020-07-23 | 2 | 2020-08-19 | 2020-08-19 |  |  | 10900 | [10 empty] | N | N
NIMO | Todd Friedman (RESunance, LLC) | 00325120 | 010 - Olean | DELEVAN | 14042 | 36_10_1162 | DELEVAN 11 | N | 5000 |  |  | CDG | N | 2020-11-24 | 2020-12-03 | 5 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Johnson (Cypress Creek Renewables) | 00269320 | 012 - Cortland | DE RUYTER | 13052 | 36_11_26252 | DELPHI 262 | N | 5000 |  |  | CDG | N | 2020-02-18 | 2020-03-03 | 11 | 2020-03-03 | 2020-03-03 | 2020-03-04 | 1 | 2020-05-06 | 2020-05-06 | 2020-08-17 | 58 | 9000 |  | 810234 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00286103 | 011 - Syracuse | CAZENOVIA | 13035 | 36_11_26253 | DELPHI 262 | Y |  | 0 | 5000 | CDG | N | 2020-04-13 | 2020-04-24 | 9 | 2020-04-27 | 2020-04-27 | 2020-04-27 | 0 | 2020-07-23 | 2020-07-23 |  |  | 11000 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00270379 | 011 - Syracuse | NEW WOODSTOCK | 13122 | 36_11_26253 | DELPHI 262 | N | 5000 |  |  | CDG | Y | 2020-01-09 | 2020-02-05 | 26.8063 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 0 | 2020-02-13 | 2020-02-13 | 2020-05-29 | 59 | 10900 |  | 952966 |  |  | 2020-10-07 | [5 empty] | N | Y
NIMO | Rob Tompkins (Borrego Solar Systems, Inc) | 00268606 | 011 - Syracuse | NEW WOODSTOCK | 13052 | 36_11_26253 | DELPHI 262 | Y |  | 5000 | 5000 | CDG | N | 2020-04-02 | 2020-04-03 | 2 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 0 | 2020-05-18 | 2020-05-18 | 2020-09-08 | 59 | 15000 |  | 8434775 | [8 empty] | N | N
NIMO | Portville CSG LLC | 00239580 | 010 - Olean | PORTVILLE | 14760 | 36_10_2253 | DUGAN RD 22 | Y | 4550 | 3697.5 |  | CDG | Y | 2019-06-28 | 2019-07-19 | 20.75 | 2019-07-22 | 2019-07-22 | 2019-07-31 | 7 | 2019-08-02 | 2019-08-02 | 2020-02-04 | 54 | 11300 |  | 544419 |  |  | 2020-02-19 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00173382 | 010 - Olean | OLEAN | 14760 | 36_10_2253 | DUGAN RD 22 | N | 5000 |  |  | CDG | Y | 2018-04-16 | 2018-04-16 | 0 | 2018-05-17 | 2018-05-17 | 2018-05-24 | 5 | 2018-09-12 | 2018-09-12 | 2018-12-19 | 55 | 12200 |  | 151694 |  |  | 2019-02-08 | [5 empty] | N | Y
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00269299 | 010 - Olean | OLEAN | 14760 | 36_10_2255 | DUGAN RD 22 | Y | 4550 | 3697.5 |  | CDG | Y | 2019-12-12 | 2019-12-19 | 7.1063 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 0 | 2019-12-27 | 2019-12-27 | 2020-08-06 | 58 | 10100 |  | 514464 |  |  | 2020-08-06 | [5 empty] | N | Y
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00271594 | 010 - Olean | OLEAN | 14760 | 36_10_2255 | DUGAN RD 22 | Y | 4550 | 3697.5 |  | CDG | Y | 2020-01-02 | 2020-01-16 | 13.6354 | 2020-01-17 | 2020-01-17 | 2020-01-27 | 5 | 2020-01-30 | 2020-01-30 | 2020-09-03 | 55 | 9500 |  | 514464 |  |  | 2020-09-08 | [5 empty] | N | Y
NIMO | Lluis Torrent (CAERO) | 00296108 | 010 - Olean | OLEAN | 14760 | 36_10_2256 | DUGAN RD 22 | N | 5000 |  |  | CDG | N | 2020-06-15 | 2020-06-22 | 5 | 2020-06-22 | 2020-06-22 | 2020-06-22 | 0 | 2020-08-12 | 2020-08-12 | 2020-11-30 | 57 | 8800 |  | 181991 | [8 empty] | N | N
NIMO | Margaret Campbell (EDF Renewables) | 00299728 | 010 - Olean | OLEAN | 14760 | 36_10_2256 | DUGAN RD 22 | N | 5000 |  |  | CDG | N | 2020-08-25 | 2020-09-29 | 2 | 2020-09-29 | 2020-09-29 | 2020-09-29 | 0 | 2020-10-19 | 2020-10-19 |  |  | 9400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00317327 | 010 - Olean | OLEAN | 14760 | 36_10_2257 | DUGAN RD 22 | N | 5000 |  |  | CDG | N | 2020-10-07 | 2020-10-12 | 3 | 2020-10-13 | 2020-10-13 | 2020-10-28 | 11 |  |  |  |  | 10400 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00253463 | 011 - Syracuse | FAYETTEVILLE | 13066 | 36_11_26551 | DUGUID 265 | N | 5000 |  |  | CDG | Y | 2019-09-26 | 2019-11-01 | 36.0563 | 2019-11-04 | 2019-11-04 | 2019-11-18 | 9 | 2019-12-05 | 2019-12-05 | 2020-03-13 | 59 | 9800 |  | 736971 |  |  | 2020-04-15 | 2020-10-07 |  |  |  |  | N | Y
NIMO | Andrew Day (SOURCE RENEWABLES LLC) | 00290464 | 011 - Syracuse | MANLIUS | 13041 | 36_11_26552 | DUGUID 265 | Y | 2500 | 2500 |  | CDG | N | 2020-05-21 | 2020-05-29 | 5 | 2020-06-01 | 2020-06-01 | 2020-06-01 | 0 | 2020-08-05 | 2020-08-05 |  |  | 10300 | [10 empty] | N | N
NIMO | Andrew Day (SOURCE RENEWABLES LLC) | 00290463 | 011 - Syracuse | MANLIUS | 13401 | 36_11_26552 | DUGUID 265 | Y | 5000 | 5000 |  | CDG | N | 2020-05-21 | 2020-05-29 | 5 | 2020-06-01 | 2020-06-01 | 2020-06-01 | 0 | 2020-08-05 | 2020-08-05 |  |  | 10300 | [10 empty] | N | N
NIMO | Matt Marino (Galehead DG Solutions, LLC) | 00315012 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26552 | DUGUID 265 | N | 5000 |  |  | CDG | N | 2020-09-25 | 2020-10-05 | 5 | 2020-10-05 | 2020-10-05 | 2020-10-05 | 0 | 2020-11-02 | 2020-11-02 |  |  | 9400 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00250670 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26552 | DUGUID 265 | N | 5000 |  |  | CDG | Y | 2019-08-28 | 2019-09-11 | 13.7153 | 2019-09-12 | 2019-09-12 | 2019-09-23 | 7 | 2019-10-04 | 2019-10-04 | 2020-01-15 | 59 | 8800 |  | 785728 |  |  | 2020-03-02 | 2020-03-03 |  |  |  |  | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00301893 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26553 | DUGUID 265 | Y | 5000 | 5000 |  | CDG | N | 2020-07-31 | 2020-08-10 | 6 | 2020-08-11 | 2020-08-11 | 2020-08-12 | 1 | 2020-08-28 | 2020-08-28 |  |  | 9300 | [10 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00301894 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26553 | DUGUID 265 | Y | 5000 | 2500 |  | CDG | N | 2020-07-31 | 2020-08-10 | 6 | 2020-08-11 | 2020-08-11 | 2020-08-12 | 1 | 2020-08-28 | 2020-08-28 |  |  | 9900 | [10 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00301895 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26553 | DUGUID 265 | Y | 5000 | 2500 |  | CDG | N | 2020-07-31 | 2020-08-10 | 6 | 2020-08-11 | 2020-08-11 | 2020-08-12 | 1 | 2020-08-28 | 2020-08-28 |  |  | 9900 | [10 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables, LLC) | 00262232 | 004 - Batavia | BATAVIA | 14020 | 36_04_2851 | E. BATAVIA 28 | N | 4000 |  |  | CDG | N | 2019-12-20 | 2020-01-23 | 33.8375 | 2020-01-24 | 2020-01-24 | 2020-01-31 | 5 | 2020-03-26 | 2020-03-26 | 2020-07-06 | 60 | 9100 |  | 249314 |  |  | 2020-11-10 | [5 empty] | N | N
NIMO | Harsh Mehta (Cypress Creek Renewables LLC) | 00105725 | 004 - Batavia | BATAVIA | 14020 | 36_04_2851 | E. BATAVIA 28 | N | 5000 |  |  | CDG | Y | 2017-06-16 | 2017-06-16 | 0 | 2018-01-02 | 2018-01-02 | 2018-01-18 | 11 | 2018-04-05 | 2018-04-05 | 2018-09-24 | 58 | 15600 |  | 137937.37 |  |  | 2019-03-14 | 2019-03-15 | 2019-05-07 |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00308463 | 004 - Batavia | STAFFORD | 14143 | 36_04_2855 | E. BATAVIA 28 | N | 5000 |  |  | CDG | N | 2020-08-24 | 2020-09-05 | 4 | 2020-09-05 | 2020-09-05 | 2020-09-05 | 0 | 2020-12-09 | 2020-12-09 |  |  | 10000 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00310125 | 004 - Batavia | STAFFORD | 14143 | 36_04_2855 | E. BATAVIA 28 | N | 5000 |  |  | CDG | N | 2020-09-01 | 2020-09-14 | 7 | 2020-09-14 | 2020-09-14 | 2020-09-14 | 0 | 2020-10-28 | 2020-10-28 |  |  | 11300 | [10 empty] | N | N
NIMO | Sanket Kolte (YSG Solar) | 00265575 | 004 - Batavia | BATAVIA | 14020 | 36_04_2855 | E. BATAVIA 28 | N | 1650 |  |  | CDG | N | 2019-11-25 | 2020-01-08 | 43.6493 | 2020-01-09 | 2020-01-09 | 2020-01-27 | 11 | 2020-03-30 | 2020-03-30 | 2020-09-11 | 60 | 7900 |  | 322030 | [8 empty] | N | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00100794 | 004 - Batavia | BATAVIA | 14020 | 36_04_2856 | E. BATAVIA 28 | N | 2000 |  |  | RNM | N | 2015-04-24 | 2015-04-24 | 0 | 2015-04-24 |  |  |  | 2016-02-05 | 2016-02-05 | 2016-06-17 | 95 |  |  | 213350 |  |  | 2017-01-31 |  |  | 2018-06-21 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Borrego Solar Systems, Inc | 00213630 | 004 - Batavia | BATAVIA | 14020 | 36_04_2856 | E. BATAVIA 28 | N | 5000 |  |  | CDG | Y | 2019-03-20 | 2019-03-27 | 6.7722 | 2019-03-28 | 2019-03-28 | 2019-04-08 | 7 | 2019-06-17 | 2019-06-17 | 2019-11-22 | 56 | 9000 |  | 158311.69 |  |  | 2019-12-06 | 2019-12-13 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00252421 | 004 - Batavia | ELBA | 14422 | 36_04_2856 | E. BATAVIA 28 | Y | 5000 | 5000 |  | CDG | Y | 2019-09-06 | 2019-09-19 | 13.0549 | 2019-09-20 | 2019-09-20 | 2019-10-02 | 8 | 2019-10-21 | 2019-10-21 | 2020-02-07 | 58 | 9500 |  | 990604 |  |  | 2020-06-15 | 2020-12-04 |  |  |  |  | N | Y
NIMO | Haley Orvedal (Galehead DG Solutions) | 00326079 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_6355 | E. DUNKIRK 63 | N | 5000 |  |  | CDG | N | 2020-11-17 | 2020-11-30 | 7 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 9 |  |  |  |  | 10400 | [10 empty] | N | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00273425 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_6355 | E. DUNKIRK 63 | Y | 4550 | 3697.5 |  | CDG | N | 2020-01-15 | 2020-01-30 | 14.9118 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 0 | 2020-03-17 | 2020-03-17 | 2020-08-28 | 59 | 9900 |  | 294414 | [8 empty] | N | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00273428 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_6355 | E. DUNKIRK 63 | Y | 4550 | 3697.5 |  | CDG | N | 2020-01-15 | 2020-01-30 | 14.8757 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 0 | 2020-03-17 | 2020-03-17 | 2020-08-27 | 58 | 9900 |  | 124956 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00229610 | 005 - Avon | CALEDONIA | 14423 | 36_05_5151 | E. GOLAH 51 | N | 1450 |  |  | RNM | Y | 2019-06-05 | 2019-06-18 | 13.1937 | 2019-06-19 | 2019-06-19 | 2019-07-02 | 8 | 2019-07-30 | 2019-07-30 | 2019-12-12 | 59 | 13300 |  | 331719 |  |  | 2020-04-01 | 2020-04-17 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00171666 |  | AVON | 14414 | 36_05_5151 | E. GOLAH 51 | N | 5000 |  |  | CDG | Y | 2018-03-13 | 2018-03-13 | 0 | 2018-03-27 | 2018-03-27 | 2018-04-03 | 5 | 2018-04-25 | 2018-04-25 | 2018-06-28 | 45 | 13400 |  | 323917 |  |  | 2018-11-08 | 2019-02-21 | 2018-08-10 | 2019-02-21 |  |  | N | Y
NIMO | Mike Howell (C2 Energy Capital) | 00102158 | 005 - Avon | CALEDONIA | 14423 | 36_05_5151 | E. GOLAH 51 | N | 2000 |  |  | CDG | N | 2016-03-08 | 2016-06-14 | 10 | 2016-06-14 | 2016-06-14 | 2016-06-17 | 0 | 2017-02-01 | 2017-02-01 | 2017-04-25 | 59 | 24600 |  | 313152 |  |  | 2017-06-13 | 2018-10-11 | 2017-06-19 | 2018-10-11 | 2020-02-28 | 2020-02-28 | Y | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00172238 | 005 - Avon | RUSH | 14543 | 36_05_5155 | E. GOLAH 51 | N | 5000 |  |  | CDG | Y | 2018-04-05 | 2018-04-05 | 0 | 2018-04-18 | 2018-04-18 | 2018-05-01 | 9 | 2018-07-24 | 2018-07-24 | 2018-12-17 | 60 | 9700 |  | 370266.41 |  |  | 2019-04-16 | 2019-05-06 |  |  |  |  | N | Y
NIMO | Joseph Fiori (Nexamp) | 00187820 | 005 - Avon | HONEOYE FALLS | 14472 | 36_05_5156 | E. GOLAH 51 | Y | 5000 | 5000 |  | CDG | Y | 2018-07-05 | 2018-07-05 | 0 | 2018-07-17 | 2018-07-17 | 2018-08-01 | 11 | 2018-09-27 | 2018-09-27 | 2019-05-01 | 60 | 14300 |  | 661928 |  |  | 2019-09-11 | 2019-09-11 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00171907 | 005 - Avon | RUSH | 14543 | 36_05_5157 | E. GOLAH 51 | N | 3000 |  |  | CDG | Y | 2018-03-23 | 2018-03-23 | 0 | 2018-03-27 | 2018-03-27 | 2018-04-03 | 5 | 2018-04-10 | 2018-04-10 | 2018-06-21 | 51 | 9700 |  | 353922 |  |  | 2018-11-08 | 2018-11-08 | 2018-11-15 | 2018-11-15 |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00171687 | 005 - Avon | RUSH | 14543 | 36_05_5157 | E. GOLAH 51 | N | 4500 |  |  | CDG | Y | 2018-03-23 | 2018-03-23 | 0 | 2018-03-27 | 2018-03-27 | 2018-04-03 | 5 | 2018-04-10 | 2018-04-10 | 2018-06-21 | 51 | 9700 |  | 452622 |  |  | 2018-11-08 | 2019-03-14 | 2018-11-15 | 2019-03-14 |  |  | N | Y
NIMO | Andrew Day (Source Renewables, LLC) | 00108583 | 016 - Pulaski | PULASKI | 13142 | 36_16_32451 | E. PULASKI 324 | Y | 2000 | 2000 |  | CDG | Y | 2017-09-06 | 2017-09-06 | 0 | 2017-11-01 | 2017-11-01 | 2017-11-16 | 10 | 2019-04-16 | 2019-04-16 | 2019-04-30 | 10 | 16800 |  | 347451.36 |  |  | 2019-02-07 | [5 empty] | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00214650 | 016 - Pulaski | PULASKI | 13142 | 36_16_32451 | E. PULASKI 324 | Y | 5000 | 5000 |  | CDG | Y | 2019-04-10 | 2019-04-23 | 13.0076 | 2019-04-24 | 2019-04-24 | 2019-05-01 | 5 | 2019-07-12 | 2019-07-12 | 2019-11-26 | 59 | 10600 |  | 243562 |  |  | 2020-03-30 | 2020-10-28 |  |  |  |  | N | Y
NIMO | Chris Matthews (AES Distributed Energy, Inc.) | 00293457 | 016 - Pulaski | PULASKI | 13142 | 36_16_32452 | E. PULASKI 324 | N | 5000 |  |  | CDG | N | 2020-06-03 | 2020-06-10 | 5 | 2020-06-10 | 2020-06-10 | 2020-06-10 | 0 | 2020-08-07 | 2020-08-07 |  |  | 10400 | [10 empty] | N | N
NIMO | Samantha Lennon (GSPP 183 Neilsen Rd, LLC) | 00299797 | 037 - Cobleskill | CHERRY VALLEY | 13320 | 36_37_47751 | E. SPRINGFIELD 477 | N | 5000 |  |  | CDG | N | 2020-07-07 | 2020-07-17 | 8 | 2020-07-20 | 2020-07-20 | 2020-07-22 | 2 | 2020-10-16 | 2020-10-16 |  |  | 9400 | [10 empty] | N | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00100873 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81755 | E. WATERTOWN 817 | N | 2000 |  |  | RNM | N | 2016-01-11 | 2016-01-11 | 0 | 2016-01-11 |  |  |  | 2016-03-03 | 2016-03-03 | 2016-07-20 | 99 | 20000 |  | 727350 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-18 | 2018-06-18 | 2018-06-26 | 2018-06-26 | Y | N
NIMO | Andrew Varrow (NY Solar 1001 LLC) | 00216629 | 013 - Watertown | CARTHAGE | 13619 | 36_13_81756 | E. WATERTOWN 817 | N | 5000 |  |  | CDG | Y | 2019-04-26 | 2019-05-09 | 13.3833 | 2019-05-10 | 2019-05-10 | 2019-05-14 | 2 | 2019-06-26 | 2019-06-26 | 2019-12-05 | 59 | 11700 |  | 430096.61 |  |  | 2020-04-16 | 2020-10-16 |  |  |  |  | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315556 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81756 | E. WATERTOWN 817 | Y |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 13000 | [10 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00170289 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81756 | E. WATERTOWN 817 | N | 4180 |  |  | CDG | Y | 2018-02-09 | 2018-02-09 | 0 | 2018-03-05 | 2018-03-05 | 2018-03-14 | 7 | 2018-12-19 | 2018-12-19 | 2019-04-01 | 55 | 15300 |  | 496572.86 |  |  | 2019-08-07 | 2019-10-29 | 2019-09-04 | 2019-10-29 |  |  | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315558 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 12200 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315563 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 11800 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315565 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 11800 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00259198 | 022 - Carthage | COPENHAGEN | 13626 | 36_13_81757 | E. WATERTOWN 817 | N | 1400 |  |  | CDG | Y | 2019-10-28 | 2019-11-06 | 8.9 | 2019-11-07 | 2019-11-07 | 2019-11-18 | 6 | 2020-01-14 | 2020-01-14 | 2020-04-24 | 59 | 10900 |  | 674527 |  |  | 2020-08-27 | [5 empty] | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00253145 | 022 - Carthage | COPENHAGEN | 13626 | 36_13_81757 | E. WATERTOWN 817 | N | 5000 |  |  | CDG | Y | 2019-09-09 | 2019-09-20 | 10.8139 | 2019-09-23 | 2019-09-23 | 2019-09-25 | 2 | 2019-10-08 | 2019-10-08 | 2020-04-17 | 59 | 11700 |  | 519026 |  |  | 2020-08-20 | [5 empty] | N | Y
NIMO | Tiffany Robicheau (Borrego Solar Systems, Inc) | 00300527 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  | 0 | 5000 | CDG | N | 2020-07-16 | 2020-09-15 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2020-10-26 | 2020-10-26 |  |  | 10900 | [10 empty] | N | N
NIMO | Ryan Storke (Storke, LLC) | 00290485 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_6561 | ELLICOTT 65 | N | 2280 |  |  | CDG | N | 2020-05-07 | 2020-05-14 | 5 | 2020-05-15 | 2020-05-15 | 2020-05-18 | 1 | 2020-08-04 | 2020-08-04 |  |  | 10100 | [10 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00279346 | 032 - Schenectady | CLIFTON PARK | 12019 | 36_32_44256 | ELNORA 442 | Y | 2500 | 2500 |  | CDG | N | 2020-02-14 | 2020-02-28 | 12 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 0 | 2020-05-13 | 2020-05-13 |  |  | 9500 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00170779 | 032 - Schenectady | BALLSTON LAKE | 12019 | 36_32_44256 | ELNORA 442 | N | 4000 |  |  | CDG | Y | 2018-03-01 | 2018-03-01 | 0 | 2018-03-13 | 2018-03-13 | 2018-03-27 | 10 | 2018-06-05 | 2018-06-05 | 2018-07-31 | 39 | 13300 |  | 765245 |  |  | 2018-10-04 |  |  | 2019-12-18 | 2019-12-19 | 2019-12-19 | Y | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00273180 | 032 - Schenectady | BALLSTON LAKE | 12019 | 36_32_44256 | ELNORA 442 | N | 5000 |  |  | CDG | N | 2020-01-28 | 2020-02-07 | 9.875 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 0 | 2020-02-27 | 2020-02-27 | 2020-07-02 | 46 | 8500 |  | 1169705.76 |  |  | 2020-11-12 | [5 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00274601 | 011 - Syracuse | CLAY | 13041 | 36_11_26751 | EUCLID 267 | N | 5000 |  |  | CDG | N | 2020-02-04 | 2020-02-18 | 11 | 2020-02-18 | 2020-02-18 | 2020-02-18 | 0 | 2020-03-16 | 2020-03-16 | 2020-10-01 | 57 | 9600 |  | 2553996 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00257718 | 011 - Syracuse | CLAY | 13041 | 36_11_26751 | EUCLID 267 | Y | 5000 | 6000 |  | CDG | Y | 2019-10-09 | 2019-10-21 | 11.9715 | 2019-10-22 | 2019-10-22 | 2019-11-08 | 13 | 2019-11-26 | 2019-11-26 | 2020-03-31 | 57 | 10300 |  | 1113700 |  |  | 2020-06-18 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00214967 | 011 - Syracuse | CLAY | 13041 | 36_11_26751 | EUCLID 267 | Y | 5000 | 5000 |  | CDG | Y | 2019-03-22 | 2019-04-15 | 23.9479 | 2019-04-16 | 2019-04-16 | 2019-04-24 | 6 | 2019-05-09 | 2019-05-09 | 2019-06-27 | 14 | 9900 |  | 975075.34 |  |  | 2019-10-29 | 2019-10-31 | 2019-11-01 |  |  |  | N | Y
NIMO | SOLARCITY CORP. (Solar City) | 00103026 | 011 - Syracuse | CLAY | 13041 | 36_11_26751 | EUCLID 267 | N | 2000 |  |  | RNM | N | 2014-04-23 | 2014-04-24 | 2 | 2014-04-24 | 2014-04-24 | 2014-05-27 | 0 | 2014-09-16 | 2014-09-16 | 2014-12-12 | 63 | 20000 |  | 387100 | [6 empty] | 2017-11-16 | 2017-11-16 | Y | N
NIMO | Borrego Solar Systems, Inc | 00238767 | 011 - Syracuse | CLAY | 13041 | 36_11_26753 | EUCLID 267 | N | 5000 |  |  | CDG | Y | 2019-06-24 | 2019-07-02 | 7.7903 | 2019-07-03 | 2019-07-03 | 2019-07-16 | 8 | 2019-08-29 | 2019-08-29 | 2020-04-17 | 98 | 8800 |  | 974005 |  |  | 2020-06-15 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00238769 | 011 - Syracuse | CLAY | 13041 | 36_11_26753 | EUCLID 267 | N | 5000 |  |  | CDG | Y | 2019-06-24 | 2019-07-02 | 7.8049 | 2019-07-03 | 2019-07-03 | 2019-07-16 | 8 | 2019-08-29 | 2019-08-29 | 2020-04-17 | 98 | 9400 |  | 730263 |  |  | 2020-06-15 | [5 empty] | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00322367 | 011 - Syracuse | CLAY | 13041 | 36_11_26753 | EUCLID 267 | N | 2000 |  |  | CDG | N | 2020-10-29 | 2020-11-10 | 8 | 2020-11-12 | 2020-11-12 | 2020-11-18 | 4 |  |  |  |  | 9600 | [10 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00327582 | 011 - Syracuse | LAFAYETTE | 13084 | 36_11_5561 | FABIUS 55 | N | 5000 |  |  | CDG | N | 2020-11-23 | 2020-12-01 | 4 | 2020-12-01 | 2020-12-01 | 2020-12-15 | 9 |  |  |  |  | 11700 | [10 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00301997 | 014 - Fulton/Volney | HANNIBAL | 13074 | 36_14_13564 | FAIRDALE 135 | N | 2700 |  |  | CDG | N | 2020-08-26 | 2020-09-03 | 6 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 0 | 2020-10-22 | 2020-10-22 |  |  | 10900 | [10 empty] | N | N
NIMO | Trevor Hardy (BlueWave Solar) | 00301830 | 010 - Olean | FREEDOM | 14065 | 36_10_2762 | FARMERSVILLE 27 | N | 4750 |  |  | CDG | N | 2020-09-09 | 2020-09-17 | 5 | 2020-09-18 | 2020-09-18 | 2020-09-29 | 7 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00294530 | 038 - Glens Falls | SOUTH GLENS FALLS | 12803 | 36_38_47651 | FARNAN RD 476 | N | 2500 |  |  | CDG | N | 2020-07-01 | 2020-07-09 | 5 | 2020-07-09 | 2020-07-09 | 2020-07-09 | 0 | 2020-08-12 | 2020-08-12 |  |  | 8800 | [10 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00304035 | 038 - Glens Falls | SOUTH GLENS FALLS | 12803 | 36_38_47651 | FARNAN RD 476 | N | 2500 |  |  | CDG | N | 2020-08-27 | 2020-09-03 | 5 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 0 | 2020-10-30 | 2020-10-30 |  |  | 9400 | [10 empty] | N | N
NIMO | David Spotts (SSC Cortlandville II LLC) | 00297803 | 012 - Cortland | CORTLAND | 13045 | 36_12_27051 | FISHER 270 | N | 5000 |  |  | CDG | N | 2020-06-24 | 2020-07-01 | 5 | 2020-07-01 | 2020-07-01 | 2020-07-01 | 0 | 2020-07-14 | 2020-07-14 | 2020-10-21 | 59 | 9400 |  | 689652 | [8 empty] | N | N
NIMO | David Spotts (SSC Cortlandville III LLC) | 00297978 | 012 - Cortland | CORTLAND | 13045 | 36_12_27051 | FISHER 270 | N | 5000 |  |  | CDG | N | 2020-07-08 | 2020-07-14 | 4 | 2020-07-14 | 2020-07-14 | 2020-07-14 | 0 | 2020-07-28 | 2020-07-28 | 2020-11-04 | 59 | 9400 |  | 759311 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00294441 | 035 - Gloversville | FULTONVILLE | 12072 | 36_35_50151 | FLORIDA 501 | Y |  | 0 | 5000 | CDG | N | 2020-06-19 | 2020-06-29 | 6 | 2020-06-30 | 2020-06-30 | 2020-07-21 | 14 | 2020-10-12 | 2020-10-12 |  |  | 11800 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316699 | 034 - Amsterdam | FULTONVILLE | 12072 | 36_35_50151 | FLORIDA 501 | N | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-26 | 6 | 2020-10-27 | 2020-10-27 | 2020-11-02 | 4 |  |  |  |  | 10800 | [10 empty] | N | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00103257 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N | 2000 |  |  | RNM | N | 2014-06-21 | 2014-06-21 | 0 | 2014-06-21 | [7 empty] | 17160 |  | 282250 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-24 | 2018-10-24 | 2018-10-25 | 2018-10-25 | Y | N
NIMO | Borrego Solar Systems, Inc | 00100815 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N | 2000 |  |  | RNM | N | 2015-05-29 | 2015-07-20 | 4 | 2015-07-20 | 2015-07-20 | 2015-08-21 | 0 | 2016-06-17 | 2016-06-17 | 2016-09-13 | 60 |  |  | 144500 |  |  | 2017-04-05 |  |  |  | 2018-06-26 | 2018-06-26 | Y | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00303325 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | Y |  | 0 | 5000 | CDG | N | 2020-08-25 | 2020-09-20 | 4 | 2020-09-21 | 2020-09-21 | 2020-09-29 | 6 | 2020-11-13 | 2020-11-13 |  |  | 13000 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100814 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N | 2000 |  |  | RNM | N | 2015-05-29 | 2015-07-20 | 4 | 2015-07-20 | 2015-07-20 | 2015-08-21 | 0 | 2016-06-17 | 2016-06-17 | 2016-09-13 | 60 |  |  | 264156 |  |  | 2017-04-05 |  |  |  | 2018-06-26 | 2018-06-26 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100816 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N | 2000 |  |  | RNM | N | 2015-05-29 | 2015-07-20 | 4 | 2015-07-20 | 2015-07-20 | 2015-08-21 | 0 | 2016-06-17 | 2016-06-17 | 2016-09-13 | 60 |  |  | 286940 |  |  | 2017-04-05 |  |  |  | 2018-06-26 | 2018-06-26 | Y | N
NIMO | John J. Watson (CAERO) | 00290559 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_26151 | FLY RD 261 | N | 5000 |  |  | CDG | N | 2020-05-08 | 2020-05-15 | 5 | 2020-05-15 | 2020-05-15 | 2020-05-15 | 0 | 2020-07-10 | 2020-07-10 | 2020-10-22 | 58 | 9300 |  | 689652 | [8 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00322024 | 011 - Syracuse | KIRKVILLE | 13082 | 36_11_26154 | FLY RD 261 | N | 5000 |  |  | CDG | N | 2020-10-30 | 2020-11-05 | 4 | 2020-11-05 | 2020-11-05 | 2020-11-05 | 0 | 2020-11-17 | 2020-11-17 |  |  | 9800 | [10 empty] | N | N
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00272041 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_26154 | FLY RD 261 | N | 1625 |  |  | CDG | N | 2020-01-13 | 2020-01-27 | 14.1667 | 2020-01-27 | 2020-01-27 | 2020-01-27 | 0 | 2020-03-09 | 2020-03-09 | 2020-07-29 | 58 | 9900 |  | 241581 | [8 empty] | N | N
NIMO | Barton Pitts (Nexamp) | 00292086 | 027 - Malone | FORT COVINGTON | 12937 | 36_27_89642 | FORT COVINGTON 896 | N | 5000 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-16 | 2020-06-16 | 2020-09-23 | 59 | 11700 |  | 765916 | [8 empty] | N | N
NIMO | Joe Fiori (Nexamp) | 00250985 | 027 - Malone | FORT COVINGTON | 12937 | 36_27_89642 | FORT COVINGTON 896 | N | 2000 |  |  | CDG | Y | 2019-09-11 | 2019-10-15 | 34.2236 | 2019-10-16 | 2019-10-16 | 2019-11-04 | 13 | 2019-12-26 | 2019-12-26 | 2020-04-08 | 59 | 9200 |  | 1208292 |  |  | 2020-08-14 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00271526 | 001 - Buffalo | AMHERST | 14228 | 36_01_99551 | FRANKHAUSER 995 | N | 1500 |  |  | RNM | N | 2020-01-03 | 2020-01-21 | 18.2208 | 2020-02-01 | 2020-02-01 | 2020-02-01 | 0 | 2020-03-11 | 2020-03-11 | 2020-08-13 | 52 | 8100 |  | 302175 |  |  | 2020-09-21 | 2020-10-15 |  |  |  |  | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00318629 | 009 - Lakewood/Stow | FREWSBURG | 14738 | 36_09_6961 | FREWSBURG 69 | N | 5000 |  |  | CDG | N | 2020-10-30 | 2020-11-10 | 7 | 2020-11-12 | 2020-11-12 | 2020-11-18 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Gordon Woodcock (Pivot Energy) | 00308812 |  | FREWSBURG | 14738 | 36_09_6962 | FREWSBURG 69 | N | 5000 |  |  | CDG | N | 2020-08-26 | 2020-09-20 | 6 | 2020-09-21 | 2020-09-21 | 2020-09-29 | 6 | 2020-11-05 | 2020-11-05 |  |  | 11300 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00255894 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36051 | FRONT ST 360 | N | 4625 |  |  | CDG | Y | 2019-10-08 | 2019-10-18 | 9.9812 | 2019-10-21 | 2019-10-21 | 2019-11-06 | 12 | 2019-11-12 | 2019-11-12 | 2020-01-28 | 198 | 8500 |  | 227153.72 |  |  | 2020-02-25 | 2020-03-13 |  |  |  |  | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00315742 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36051 | FRONT ST 360 | N | 5000 |  |  | CDG | N | 2020-10-08 | 2020-10-12 | 2 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-10-22 | 2020-10-22 |  |  | 9800 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00315759 | 032 - Schenectady | SCOTIA | 12010 | 36_32_36051 | FRONT ST 360 | N | 5000 |  |  | CDG | N | 2020-10-08 | 2020-10-12 | 2 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-10-22 | 2020-10-22 |  |  | 9800 | [10 empty] | N | N
NIMO |  | 00212139 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36053 | FRONT ST 360 | N | 4125 |  |  | CDG | Y | 2019-03-01 | 2019-03-12 | 10.8042 | 2019-03-13 | 2019-03-13 | 2019-03-19 | 4 | 2019-05-08 | 2019-05-08 | 2019-10-08 | 53 | 9200 |  | 128866 |  |  | 2020-03-09 | 2020-09-03 | 2020-09-04 |  |  |  | N | Y
NIMO | Teddy Epstein (Novis Renewables) | 00272786 | 005 - Avon | GENESEO | 14454 | 36_05_5551 | GENESEO 55 | N | 5000 |  |  | CDG | N | 2020-01-10 | 2020-02-07 | 27.8854 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 0 | 2020-02-18 | 2020-02-18 | 2020-09-10 | 65 | 9400 |  | 744363 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00271877 | 001 - Buffalo | BUFFALO | 14226 | 36_01_6051 | GETZVILLE 60 | N | 965.7 |  |  | NA | Y | 2020-02-27 | 2020-03-12 | 11 | 2020-03-12 |  |  |  | 2020-03-30 | 2020-03-30 | 2020-06-22 | 0 | 10000 | [10 empty] | N | Y
NIMO | Samantha Lennon (GSPP 1616 County Route 12, LLC) | 00242804 | 011 - Syracuse | CENTRAL SQUARE | 13036 | 36_11_24751 | GILBERT MILLS 247 | N | 3100 |  |  | CDG | Y | 2019-07-11 | 2019-07-16 | 5.1562 | 2019-07-17 | 2019-07-17 | 2019-07-26 | 7 | 2019-10-17 | 2019-10-17 | 2020-01-28 | 59 | 9600 |  | 812839.55 |  |  | 2020-04-27 | 2020-10-26 |  |  |  |  | N | Y
NIMO | Haley Orvedal (Galehead DG Solutions, LLC) | 00301143 | 014 - Fulton/Volney | PENNELLVILLE | 13132 | 36_11_24753 | GILBERT MILLS 247 | N | 5000 |  |  | CDG | N | 2020-07-20 | 2020-07-27 | 5 | 2020-07-27 | 2020-07-27 | 2020-07-27 | 0 | 2020-09-18 | 2020-09-18 |  |  | 9900 | [10 empty] | N | N
NIMO | Benjamin Rubin (Ameresco Inc.) | 00197711 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07251 | GLOVERSVILLE 72 | N | 4980 |  |  | CDG | Y | 2018-11-13 | 2018-12-04 | 21.0389 | 2018-12-05 | 2018-12-05 | 2018-12-06 | 1 | 2019-01-17 | 2019-01-17 | 2019-05-13 | 59 | 10100 |  | 413331 |  |  | 2019-08-26 | 2019-09-30 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00172200 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07251 | GLOVERSVILLE 72 | N | 4000 |  |  | CDG | Y | 2018-03-26 | 2018-03-26 | 0 | 2018-04-03 | 2018-04-03 | 2018-04-17 | 10 | 2018-07-31 | 2018-07-31 | 2018-10-16 | 30 | 12200 |  | 128889 |  |  | 2018-11-27 |  |  |  | 2019-12-31 | 2019-12-31 | Y | Y
NIMO | Giovanni Maruca (Eden Devco) | 00197660 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | Y | 4980 | 5000 |  | CDG | Y | 2018-10-03 | 2018-10-17 | 10 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 0 | 2019-01-03 | 2019-01-03 | 2019-04-11 | 58 | 12200 |  | 630605.26 |  |  | 2019-10-04 | 2019-10-10 |  |  |  |  | N | Y
NIMO | Michael McNeley (Kearsarge Solar LLC) | 00100898 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | N | 1452 |  |  | CDG | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-18 | 0 | 2017-01-10 | 2017-01-10 | 2017-06-16 | 60 | 25000 |  | 230933 |  |  | 2017-06-29 |  |  |  | 2018-12-17 | 2018-12-17 | Y | N
NIMO | Michael McNeley (Kearsarge Solar LLC) | 00100899 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | N | 1980 |  |  | CDG | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-18 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-24 | 53 | 25000 |  | 237000 |  |  | 2017-06-29 |  |  |  | 2018-12-17 | 2018-12-17 | Y | N
NIMO | Mike Howell (C2 Energy Capital) | 00101997 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | N | 2000 |  |  | CDG | N | 2016-02-22 | 2016-06-15 | 8 | 2016-06-15 | 2016-06-15 | 2016-06-24 | 0 | 2017-03-24 | 2017-03-24 | 2017-06-16 | 59 | 28400 |  | 379400 |  |  | 2017-07-17 | 2019-11-25 | 2018-07-12 | 2019-11-25 | 2020-03-03 | 2020-03-03 | Y | N
NIMO | Benjamin Broder (Catalyze Energy) | 00290169 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6454 | GRAND ISLAND 64 | N | 5000 |  |  | CDG | N | 2020-05-05 | 2020-05-11 | 4 | 2020-05-12 | 2020-05-12 | 2020-05-12 | 0 | 2020-06-01 | 2020-06-01 | 2020-09-09 | 57 | 10100 |  | 986485 |  |  | 2020-12-04 | [5 empty] | N | N
NIMO | Brian Tran (Baywa-re) | 00169478 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6454 | GRAND ISLAND 64 | Y | 4000 | 4000 |  | CDG | Y | 2018-02-28 | 2018-02-28 | 0 | 2018-03-08 | 2018-03-08 | 2018-03-19 | 7 | 2018-05-14 | 2018-05-14 | 2018-07-31 | 54 | 12200 |  | 223896 |  |  | 2018-08-21 |  | 2018-08-10 |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00103018 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6454 | GRAND ISLAND 64 | N | 5000 |  |  | CDG | Y | 2017-04-27 | 2017-06-02 | 8 | 2017-06-05 | 2017-06-05 | 2017-06-20 | 11 | 2017-08-02 | 2017-08-02 | 2018-01-05 | 57 | 16200 |  | 288636 |  |  | 2018-03-14 |  |  |  | 2020-03-03 | 2020-03-03 | Y | Y
NIMO | Elie Schecter (OurGeneration LLC) | 00305462 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6457 | GRAND ISLAND 64 | N | 5000 |  |  | CDG | N | 2020-08-07 | 2020-08-20 | 9 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 0 | 2020-09-18 | 2020-09-18 |  |  | 8100 | [10 empty] | N | N
NIMO | Elie Schecter (OurGeneration LLC) | 00305463 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6457 | GRAND ISLAND 64 | N | 5000 |  |  | CDG | N | 2020-08-07 | 2020-08-20 | 9 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 0 | 2020-09-18 | 2020-09-18 |  |  | 8600 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171993 | 032 - Schenectady | REXFORD | 12148 | 36_32_34556 | GROOMS RD 345 | N | 2000 |  |  | CDG | Y | 2018-03-29 | 2018-03-29 | 0 | 2018-04-10 | 2018-04-10 | 2018-04-20 | 8 | 2018-07-23 | 2018-07-23 | 2018-10-10 | 56 | 12200 |  | 127366 |  |  | 2018-12-19 |  |  |  | 2020-12-10 | 2020-12-10 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171992 | 032 - Schenectady | REXFORD | 12148 | 36_32_34556 | GROOMS RD 345 | N | 5000 |  |  | CDG | Y | 2018-03-29 | 2018-03-29 | 0 | 2018-04-12 | 2018-04-12 | 2018-04-20 | 6 | 2018-07-23 | 2018-07-23 | 2018-10-10 | 56 | 12200 |  | 212762 |  |  | 2018-12-19 | 2018-12-21 |  |  | 2020-12-10 | 2020-12-10 | Y | Y
NIMO | Borrego Solar Systems, Inc | 00250117 | 032 - Schenectady | REXFORD | 12148 | 36_32_34557 | GROOMS RD 345 | N | 5000 |  |  | CDG | Y | 2019-09-11 | 2019-10-04 | 22.7007 | 2019-10-07 | 2019-10-07 | 2019-10-21 | 10 | 2019-12-24 | 2019-12-24 | 2020-04-06 | 57 | 8800 |  | 251223 |  |  | 2020-04-20 | 2020-10-07 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00198332 | 032 - Schenectady | REXFORD | 12148 | 36_32_34557 | GROOMS RD 345 | N | 5000 |  |  | CDG | Y | 2018-10-19 | 2018-10-30 | 10.9549 | 2018-10-31 | 2018-10-31 | 2018-11-06 | 4 | 2019-02-25 | 2019-02-25 | 2019-06-05 | 59 | 13300 |  | 128866 |  |  | 2019-06-24 | 2019-06-25 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00183842 | 032 - Schenectady | REXFORD | 12065 | 36_32_34558 | GROOMS RD 345 | N | 4750 |  |  | CDG | Y | 2018-06-08 | 2018-06-08 | 0 | 2018-06-22 | 2018-06-22 | 2018-07-11 | 12 | 2018-08-22 | 2018-08-22 | 2018-12-03 | 33 | 12200 |  | 197550 |  |  | 2019-01-22 | 2019-08-13 | 2019-02-01 | 2019-09-26 | 2019-09-26 | 2019-09-26 | Y | Y
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00300053 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41851 | HAGUE RD 418 | N | 2500 |  |  | CDG | N | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-09-17 | 2020-09-17 |  |  | 10100 | [10 empty] | N | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00305249 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41851 | HAGUE RD 418 | N | 5000 |  |  | CDG | N | 2020-08-17 | 2020-08-24 | 5 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 0 | 2020-11-12 | 2020-11-12 |  |  | 9800 | [10 empty] | N | N
NIMO | Margaret Tamm (Standard Solar Inc.) | 00314330 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41851 | HAGUE RD 418 | N | 5000 |  |  | CDG | N | 2020-09-25 | 2020-10-07 | 9 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 0 | 2020-10-30 | 2020-10-30 |  |  | 9400 | [10 empty] | N | N
NIMO | Gordon Woodcock (Pivot Energy) | 00260469 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41852 | HAGUE RD 418 | N | 5000 |  |  | CDG | N | 2019-11-27 | 2019-12-10 | 12.7625 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 0 | 2019-12-12 | 2019-12-12 | 2020-07-16 | 57 | 10800 |  | 1174291 |  |  | 2020-11-23 | [5 empty] | N | N
NIMO | Johnson (Junction Solar, LLC) | 00264683 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41852 | HAGUE RD 418 | N | 5000 |  |  | CDG | N | 2019-12-20 | 2020-02-02 | 44.091 | 2020-02-02 | 2020-02-02 | 2020-02-02 | 0 | 2020-04-06 | 2020-04-06 |  |  | 9400 | [10 empty] | N | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00305256 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41853 | HAGUE RD 418 | N | 5000 |  |  | CDG | N | 2020-08-27 | 2020-09-23 | 20 | 2020-09-24 | 2020-09-24 | 2020-09-29 | 3 | 2020-10-26 | 2020-10-26 |  |  | 8800 | [10 empty] | N | N
NIMO | BQ Energy Inc. | 00100823 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21252 | HARBORFRONT 212 | N | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-03 | 4 | 2015-06-03 | 2015-06-03 | 2015-06-23 | 3 | 2015-10-20 | 2015-10-20 | 2016-05-17 | 150 | 20000 |  | 191000 |  |  | 2016-12-15 |  |  |  | 2019-08-01 | 2019-08-01 | Y | N
NIMO | Kyle Northway (One Sun) | 00284088 |  | LACKAWANNA | 14218 | 36_01_21253 | HARBORFRONT 212 | N | 2000 |  |  | RNM | N | 2020-04-02 | 2020-04-02 | 0 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-21 | 58 | 8500 |  | 235459 | [8 empty] | N | N
NIMO | BQ Energy Inc. | 00100821 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-03 | 4 | 2015-06-03 | 2015-06-03 | 2015-06-23 | 4 | 2015-10-20 | 2015-10-20 | 2016-05-17 | 150 | 45000 |  | 176050 |  |  | 2016-12-15 |  |  | 2018-12-31 | 2019-06-04 | 2019-06-04 | Y | N
NIMO | BQ Energy Inc. | 00100824 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-03 | 4 | 2015-06-03 | 2015-06-03 | 2015-06-23 | 3 | 2015-10-20 | 2015-10-20 | 2016-05-17 | 150 | 15000 |  | 176050 |  |  | 2016-12-15 | 2018-01-09 | 2018-01-10 | 2018-12-31 | 2019-06-04 | 2019-06-04 | Y | N
NIMO | Steel Sun LLC | 00101824 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N | 1488 |  |  | RNM | N | 2016-12-28 | 2016-12-28 | 0 | 2016-12-28 | [16 empty] | 2017-01-25 | 2017-01-25 | Y | N
NIMO | Steel Sun LLC | 00102925 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N | 1488 |  |  | RNM | N | 2017-01-25 | 2017-01-25 | 0 | 2017-01-25 | [16 empty] | 2017-01-25 | 2017-01-25 | Y | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00318995 | 001 - Buffalo | BUFFALO | 14218 | 36_01_21258 | HARBORFRONT 212 | N | 4000 |  |  | RNM | N | 2020-10-26 | 2020-11-03 | 6 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318493 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23550 | HARRIS RD 235 | N | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-08 | 4 | 2020-11-08 | 2020-11-08 | 2020-11-08 | 0 | 2020-12-08 | 2020-12-08 |  |  | 8800 | [10 empty] | N | N
NIMO | Andrew Day (SOURCE RENEWABLES LLC) | 00323777 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23554 | HARRIS RD 235 | N | 2500 |  |  | CDG | N | 2020-11-05 | [21 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00293795 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23554 | HARRIS RD 235 | Y | 5000 | 5000 |  | CDG | N | 2020-06-08 | 2020-06-15 | 5 | 2020-06-15 | 2020-06-15 | 2020-06-15 | 0 | 2020-08-05 | 2020-08-05 |  |  | 9300 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00312212 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23556 | HARRIS RD 235 | N | 5000 |  |  | CDG | N | 2020-09-11 | 2020-09-20 | 5 | 2020-09-21 | 2020-09-21 | 2020-09-29 | 6 | 2020-11-19 | 2020-11-19 |  |  | 10100 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00306783 | 011 - Syracuse | CAMILLUS | 13031 | 36_11_23556 | HARRIS RD 235 | N | 5000 |  |  | CDG | N | 2020-08-17 | 2020-08-25 | 6 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 0 | 2020-10-13 | 2020-10-13 |  |  | 8800 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00325171 | 005 - Avon | LIVONIA | 14487 | 36_05_3851 | HEMLOCK 38 | N | 5000 |  |  | CDG | N | 2020-11-19 | 2020-11-30 | 5 | 2020-11-30 | 2020-11-30 | 2020-11-30 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Dallas Manson (Nexamp) | 00229123 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32851 | HEMSTREET 328 | N | 3500 |  |  | CDG | Y | 2019-05-24 | 2019-06-06 | 13.1486 | 2019-06-07 | 2019-06-07 | 2019-06-26 | 13 | 2019-08-01 | 2019-08-01 | 2019-10-25 | 57 | 9900 |  | 128866 |  |  | 2020-03-25 | 2020-09-22 | 2020-09-24 |  |  |  | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00284812 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32851 | HEMSTREET 328 | N | 2850 |  |  | CDG | N | 2020-04-16 | 2020-04-24 | 6 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 0 | 2020-04-28 | 2020-04-28 | 2020-08-17 | 59 | 9400 |  | 324546 | [8 empty] | N | N
NIMO | Kelsey Crane (ForeFront Power) | 00100795 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32851 | HEMSTREET 328 | N | 2000 |  |  | CDG | N | 2015-04-22 | 2015-05-03 | 3 | 2015-05-03 | 2015-05-03 | 2015-05-29 | 0 | 2015-07-22 | 2015-07-22 | 2016-05-09 | 208 | 35000 |  | 730737 |  |  | 2017-02-14 | 2017-07-21 | 2017-07-24 | 2018-12-20 | 2018-12-20 | 2018-12-20 | Y | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00205940 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32852 | HEMSTREET 328 | Y | 4980 | 4980 |  | CDG | Y | 2019-01-15 | 2019-01-28 | 12.8139 | 2019-01-29 | 2019-01-29 | 2019-02-04 | 4 | 2019-06-06 | 2019-06-06 | 2019-08-28 | 57 | 10100 |  | 187685.07 |  |  | 2020-01-22 | 2020-01-22 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00323467 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32852 | HEMSTREET 328 | N | 5000 |  |  | CDG | N | 2020-11-04 | 2020-11-12 | 5 | 2020-11-12 | 2020-11-12 | 2020-11-23 | 6 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Trevor Davis (Brookfield Power US Asset Management | 00266026 | 025 - Potsdam | COLTON | 13625 | 36_25_92452 | HIGLEY 924 | N | 5000 |  |  | CDG | N | 2019-11-22 | 2019-12-23 | 31.3979 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 0 | 2020-03-03 | 2020-03-03 | 2020-08-19 | 59 | 10100 |  | 2072759 | [8 empty] | N | N
NIMO | David Elliott (NY SOLAR FARMS INC) | 00283380 | 031 - Troy | HOOSICK FALLS | 12090 | 36_31_31451 | HOOSICK 314 | N | 5000 |  |  | CDG | N | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 0 | 2020-08-12 | 2020-08-12 |  |  | 9800 | [10 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00322599 | 031 - Troy | HOOSICK FALLS | 12090 | 36_31_31451 | HOOSICK 314 | N | 4950 |  |  | CDG | N | 2020-11-13 | 2020-11-16 | 1 | 2020-11-16 | 2020-11-16 | 2020-12-01 | 8 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Wendy De Wolf (East Light Partners) | 00173582 | 033 - Hudson | HUDSON | 12534 | 36_33_08751 | HUDSON 87 | Y | 5000 | 0 |  | CDG | Y | 2018-05-20 | 2018-05-20 | 0 | 2018-06-12 | 2018-06-12 | 2018-06-27 | 11 | 2018-08-23 | 2018-08-23 | 2019-01-04 | 56 | 14600 |  | 319451.12 |  |  | 2019-05-03 |  |  |  | 2020-06-01 | 2020-06-01 | Y | Y
NIMO | Wendy DeWolf (East Light Partners) | 00292700 | 033 - Hudson | HUDSON | 12534 | 36_33_08751 | HUDSON 87 | N | 5000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-24 | 2020-06-24 | 2020-06-24 | 0 | 2020-09-11 | 2020-09-11 | 2020-12-08 | 0 | 9800 |  | 531027 | [8 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00190334 | 033 - Hudson | HUDSON | 12534 | 36_33_08752 | HUDSON 87 | Y | 5000 | 4500 |  | CDG | Y | 2018-07-11 | 2018-07-20 | 8.8375 | 2018-07-23 | 2018-07-23 | 2018-08-07 | 11 | 2018-10-30 | 2018-10-30 | 2019-03-08 | 58 | 12200 |  | 862913.71 |  |  | 2019-10-16 | 2019-10-17 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00201083 | 033 - Hudson | HUDSON | 12534 | 36_33_08752 | HUDSON 87 | Y | 5000 | 4500 |  | CDG | Y | 2018-11-14 | 2018-12-05 | 21.2361 | 2018-12-06 | 2018-12-06 | 2018-12-12 | 4 | 2019-02-04 | 2019-02-04 | 2019-03-30 | 28 | 10400 |  | 122285.57 |  |  | 2019-10-15 | 2019-10-16 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00244865 | 033 - Hudson | HUDSON | 12534 | 36_33_08753 | HUDSON 87 | N | 5000 |  |  | RNM | Y | 2019-08-09 | 2019-09-09 | 31.2812 | 2019-09-10 | 2019-09-10 | 2019-09-20 | 8 | 2019-10-22 | 2019-10-22 | 2020-02-28 | 53 | 9000 |  | 247950 |  |  | 2020-07-22 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00233096 | 033 - Hudson | HUDSON | 12534 | 36_33_08755 | HUDSON 87 | N | 5000 |  |  | CDG | Y | 2019-06-14 | 2019-06-26 | 12.1444 | 2019-06-27 | 2019-06-27 | 2019-07-09 | 7 | 2019-09-10 | 2019-09-10 | 2019-12-09 | 58 | 10100 |  | 321098 |  |  | 2020-03-09 | 2020-03-11 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00235092 | 033 - Hudson | HUDSON | 12534 | 36_33_08755 | HUDSON 87 | Y | 5000 | 4500 |  | CDG | N | 2019-06-17 | 2019-06-28 | 10.6813 | 2019-07-01 | 2019-07-01 | 2019-07-12 | 8 | 2020-02-19 | 2020-02-19 | 2020-05-12 | 59 | 9900 |  | 341748 |  |  | 2020-06-26 | [5 empty] | N | N
NIMO | Neil Libidinsky (Solar City) | 00101531 | 033 - Hudson | HUDSON | 12534 | 36_33_08756 | HUDSON 87 | N | 888 |  |  | RNM | N | 2016-02-09 | 2016-03-22 | 7 | 2016-03-22 | 2016-03-22 | 2016-04-11 | 0 | 2016-05-04 | 2016-05-04 | 2016-08-29 | 60 | 23700 |  | 80167 |  |  | 2017-04-26 | 2017-10-22 | 2017-09-19 | 2018-03-16 | 2018-03-21 | 2018-03-21 | Y | N
NIMO | Mike Borkowski (Community Power Group) | 00282762 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_08851 | HUDSON FALLS 88 | N | 5000 |  |  | CDG | N | 2020-05-01 | 2020-05-11 | 6 | 2020-05-11 | 2020-05-11 | 2020-05-11 | 0 | 2020-10-02 | 2020-10-02 |  |  | 10600 | [10 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00280315 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | Y | 5000 | 5000 |  | CDG | N | 2020-07-01 | 2020-07-14 | 10 | 2020-07-15 | 2020-07-15 | 2020-07-15 | 0 | 2020-08-11 | 2020-08-11 |  |  | 10600 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00206376 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | N | 2000 |  |  | RNM | N | 2019-01-30 | 2019-02-11 | 12.2438 | 2019-02-12 | 2019-02-12 | 2019-02-15 | 3 | 2019-04-02 | 2019-04-02 | 2019-09-17 | 72 | 10100 |  | 121624.29 |  |  | 2019-12-02 | 2019-12-05 | 2020-09-11 |  |  |  | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00213825 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | N | 2000 |  |  | RNM | N | 2019-03-20 | 2019-05-01 | 41.8986 | 2019-05-02 | 2019-05-02 | 2019-05-10 | 6 | 2019-07-02 | 2019-07-02 | 2019-10-01 | 59 | 10100 |  | 677253 |  |  | 2019-12-02 | 2019-12-05 | 2020-09-11 |  |  |  | N | N
NIMO | Dallas Manson (Nexamp) | 00237006 | 013 - Watertown | CALCIUM | 13616 | 36_13_32356 | INDIAN RIVER 323 | N | 5000 |  |  | CDG | Y | 2019-06-14 | 2019-06-27 | 12.7215 | 2019-06-28 | 2019-06-28 | 2019-07-05 | 4 | 2019-09-16 | 2019-09-16 | 2019-12-16 | 59 | 13100 |  | 346847.58 |  |  | 2020-04-24 | 2020-10-16 | 2020-10-22 |  |  |  | N | Y
NIMO | Nexamp Interconnections (Nexamp Solar, LLC.) | 00228771 | 013 - Watertown | EVANS MILLS | 13637 | 36_13_32356 | INDIAN RIVER 323 | N | 4000 |  |  | CDG | Y | 2019-05-17 | 2019-05-30 | 13.0188 | 2019-05-31 | 2019-05-31 | 2019-06-10 | 6 | 2019-08-14 | 2019-08-14 | 2019-11-13 | 58 | 8800 |  | 289984 |  |  | 2020-03-26 | 2020-09-15 | 2020-09-17 |  |  |  | N | Y
NIMO | Dallas Interconnections (Nexamp) | 00229020 | 013 - Watertown | EVANS MILLS | 13637 | 36_13_32358 | INDIAN RIVER 323 | N | 5000 |  |  | CDG | Y | 2019-05-17 | 2019-05-30 | 12.941 | 2019-05-31 | 2019-05-31 | 2019-06-10 | 6 | 2019-08-13 | 2019-08-13 | 2019-11-27 | 59 | 11800 |  | 1520854.78 |  |  | 2020-04-09 | 2020-09-29 | 2020-10-23 |  |  |  | N | Y
NIMO | Dallas Manson (Nexamp) | 00313436 | 013 - Watertown | EVANS MILLS | 13637 | 36_13_32358 | INDIAN RIVER 323 | N | 5000 |  |  | CDG | N | 2020-09-22 | 2020-10-08 | 13 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Alex Curlin (Nexamp Solar LLC) | 00254035 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N | 2300 |  |  | CDG | Y | 2019-09-13 | 2019-09-26 | 13.0493 | 2019-09-27 | 2019-09-27 | 2019-10-15 | 12 | 2019-11-13 | 2019-11-13 | 2020-04-20 | 55 | 10500 |  | 196067 |  |  | 2020-08-25 | [5 empty] | N | Y
NIMO | Brendan Mooney (AMP Solar US Holdings Inc.) | 00307516 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | Y | 5000 | 0 |  | CDG | N | 2020-09-30 | 2020-10-08 | 5 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 |  |  |  |  | 9100 | [10 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables) | 00169955 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N | 5000 |  |  | CDG | Y | 2018-02-03 | 2018-02-03 | 0 | 2018-03-08 | 2018-03-08 | 2018-03-19 | 7 | 2018-09-17 | 2018-09-17 | 2018-11-27 | 48 | 12200 |  | 512299.95 |  |  | 2019-04-09 | 2019-04-10 | 2019-05-06 |  |  |  | N | Y
NIMO | Michael McNeley (Kearsarge Solar LLC) | 00101325 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N | 1400 |  |  | CDG | N | 2015-05-29 | 2015-06-28 | 8 | 2015-06-28 | 2015-06-28 | 2015-07-02 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-31 | 58 | 25000 | [7 empty] | 2018-07-16 | 2018-07-23 | 2018-07-23 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100829 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N | 1400 |  |  | RNM | N | 2015-05-29 | 2015-06-28 | 8 | 2015-06-28 | 2015-06-28 | 2015-07-02 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-31 | 58 | 25000 |  | 273750 |  |  |  | 2019-05-13 | 2017-08-28 | 2019-05-13 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Nick Ford (Curtain Solar, LLC) | 00317177 | 011 - Syracuse | SKANEATELES | 13152 | 36_11_29154 | JEWETT RD 291 | N | 5000 |  |  | CDG | N | 2020-10-06 | 2020-12-09 | 0 | 2020-12-09 | 2020-12-09 | 2020-12-09 | 0 |  |  |  |  | 9900 | [10 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00283959 | 011 - Syracuse | SKANEATELES | 13152 | 36_11_29156 | JEWETT RD 291 | N | 5000 |  |  | CDG | N | 2020-04-23 | 2020-04-30 | 5 | 2020-05-01 | 2020-05-01 | 2020-05-04 | 1 | 2020-10-02 | 2020-10-02 |  |  | 11300 | [10 empty] | N | N
NIMO | Noah Siegel (Abundant Solar Power [SK1] LLC) | 00199552 | 011 - Syracuse | SKANEATELES | 13152 | 36_11_29156 | JEWETT RD 291 | N | 1000 |  |  | CDG | Y | 2018-11-28 | 2018-12-05 | 6.8493 | 2018-12-06 | 2018-12-06 | 2018-12-07 | 1 | 2018-12-28 | 2018-12-28 | 2019-04-05 | 51 | 9800 |  | 227956.05 |  |  | 2019-07-08 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG Northeast 1, LLC) | 00211551 | 031 - Troy | COHOES | 12110 | 36_31_35251 | JOHNSON RD 352 | N | 1000 |  |  | NA | Y | 2019-05-15 | 2019-07-19 | 64.8035 | 2019-07-22 | 2019-07-22 | 2019-07-31 | 7 | 2019-10-15 | 2019-10-15 | 2020-01-08 | 55 | 8300 |  | 83672.73 |  |  | 2020-01-15 | 2020-01-17 | 2020-01-21 | 2020-01-21 |  |  | N | Y
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00300060 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_06125 | JOHNSTOWN 61 | N | 3125 |  |  | CDG | N | 2020-07-24 | 2020-07-31 | 5 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 0 | 2020-08-19 | 2020-08-19 |  |  | 11300 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00223799 | 004 - Batavia | AKRON | 14001 | 36_04_22651 | KNAPP RD 226 | N | 5000 |  |  | CDG | Y | 2019-05-24 | 2019-06-21 | 28.0174 | 2019-06-24 | 2019-06-24 | 2019-07-02 | 6 | 2019-08-29 | 2019-08-29 | 2019-12-06 | 57 | 9400 |  | 122018 |  |  | 2019-12-20 | 2019-12-23 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00223801 | 004 - Batavia | AKRON | 14001 | 36_04_22651 | KNAPP RD 226 | N | 5000 |  |  | CDG | Y | 2019-06-06 | 2019-06-19 | 12.9743 | 2019-06-20 | 2019-06-20 | 2019-07-02 | 8 | 2019-08-29 | 2019-08-29 | 2019-12-06 | 57 | 9400 |  | 122018 |  |  | 2019-12-20 | 2019-12-23 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00301884 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | N | 5000 |  |  | CDG | N | 2020-08-26 | 2020-09-23 | 4 | 2020-09-24 | 2020-09-24 | 2020-09-29 | 3 | 2020-11-10 | 2020-11-10 |  |  | 9400 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315537 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | Y |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-16 | 2020-10-16 | 2020-11-02 | 11 |  |  |  |  | 10300 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315567 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | N | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-26 | 2020-10-26 | 2020-11-03 | 6 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315569 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | N | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-26 | 2020-10-26 | 2020-11-03 | 6 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248818 | 004 - Batavia | AKRON | 14001 | 36_04_22652 | KNAPP RD 226 | N | 4000 |  |  | CDG | N | 2019-08-14 | 2019-08-26 | 11.8958 | 2019-08-27 | 2019-08-27 | 2019-09-04 | 5 | 2019-11-22 | 2019-11-22 | 2020-04-20 | 58 | 8800 |  | 1349153 |  |  | 2020-10-19 | [5 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248821 | 004 - Batavia | AKRON | 14001 | 36_04_22652 | KNAPP RD 226 | N | 5000 |  |  | CDG | N | 2019-08-14 | 2019-09-25 | 41.6736 | 2019-09-26 | 2019-09-26 | 2019-10-15 | 13 | 2019-12-18 | 2019-12-18 | 2020-04-02 | 59 | 9400 |  | 1363924 |  |  | 2020-10-21 | [5 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00252425 | 004 - Batavia | AKRON | 14001 | 36_04_22652 | KNAPP RD 226 | Y | 5000 | 5000 |  | CDG | Y | 2019-09-13 | 2019-09-26 | 13.0271 | 2019-09-27 | 2019-09-27 | 2019-10-15 | 12 | 2019-10-21 | 2019-10-21 | 2020-02-10 | 58 | 12200 |  | 1386868 |  |  | 2020-06-18 | [5 empty] | N | Y
NIMO | Robert Tompkins (212 Solar Development, LLC) | 00219855 | 004 - Batavia | AKRON | 14001 | 36_04_22653 | KNAPP RD 226 | N | 5000 |  |  | CDG | Y | 2019-05-22 | 2019-05-31 | 9.0687 | 2019-06-03 | 2019-06-03 | 2019-06-04 | 1 | 2019-08-14 | 2019-08-14 | 2019-11-18 | 56 | 8800 |  | 689713 |  |  | 2019-12-06 | 2019-12-13 |  |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00315532 | 012 - Cortland | TRUXTON | 13158 | 36_12_23051 | LABRADOR 230 | N | 5000 |  |  | CDG | N | 2020-09-28 | 2020-10-07 | 6 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 0 | 2020-11-19 | 2020-11-19 |  |  | 8800 | [10 empty] | N | N
NIMO | Michael Roach (RER Energy Group LLC) | 00106164 |  | SARANAC LAKE | 12983 | 36_24_92758 | LAKE COLBY 927 | N | 1500 |  |  | CDG | Y | 2017-08-15 | 2017-08-15 | 0 | 2017-09-08 | 2017-09-08 | 2017-09-15 | 5 | 2018-01-31 | 2018-01-31 | 2018-05-08 | 59 | 16800 |  | 320711.71 |  |  | 2019-02-05 | [5 empty] | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00206362 | 032 - Schenectady | BALLSTON LAKE | 12019 | 36_32_322151 | LASHER RD | N | 2000 |  |  | CDG | Y | 2019-01-30 | 2019-02-08 | 9.1674 | 2019-02-11 | 2019-02-11 | 2019-02-21 | 7 | 2019-06-13 | 2019-06-13 | 2020-04-08 | 59 | 10000 |  | 206022 |  |  | 2020-08-14 | [5 empty] | N | Y
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00316603 | 034 - Amsterdam | GALWAY | 12074 | 36_32_322151 | LASHER RD | N | 3250 |  |  | CDG | N | 2020-10-05 | 2020-10-08 | 3 | 2020-10-09 | 2020-10-09 | 2020-10-27 | 12 |  |  |  |  | 10700 | [10 empty] | N | N
NIMO | Amanda Postma (Renovus Solar) | 00279867 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_32_322152 | LASHER RD | N | 5000 |  |  | CDG | N | 2020-03-11 | 2020-03-19 | 7 | 2020-03-19 | 2020-03-19 | 2020-03-19 | 0 | 2020-03-25 | 2020-03-25 |  |  | 9000 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00274542 | 032 - Schenectady | BALLSTON SPA | 12020 | 36_32_322153 | LASHER RD | N | 5000 |  |  | CDG | N | 2020-02-28 | 2020-03-11 | 9 | 2020-03-11 | 2020-03-11 | 2020-03-25 | 10 | 2020-06-09 | 2020-06-09 | 2020-09-21 | 59 | 10500 |  | 121955 | [8 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00274549 | 032 - Schenectady | BALLSTON SPA | 12020 | 36_32_322153 | LASHER RD | N | 5000 |  |  | CDG | N | 2020-02-28 | 2020-03-11 | 9 | 2020-03-11 | 2020-03-11 | 2020-03-25 | 10 | 2020-06-09 | 2020-06-09 | 2020-09-21 | 59 | 10500 |  | 121955 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00328674 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97652 | LAWRENCE AVE 976 | N | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-08 | 5 | 2020-12-08 | 2020-12-08 | 2020-12-08 | 0 |  |  |  |  | 10400 | [10 empty] | N | N
NIMO | Community Energy Solar | 00093447 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97653 | LAWRENCE AVE 976 | N | 2000 |  |  | RNM | N | 2013-04-30 | 2013-04-30 | 0 | 2013-04-30 | [15 empty] | 2014-11-21 | 2014-11-21 | 2014-11-21 | Y | N
NIMO | Elie Schecter (Potsdam Community Solar, LLC) | 00230901 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97653 | LAWRENCE AVE 976 | Y | 5000 | 2000 |  | CDG | Y | 2019-06-09 | 2019-06-28 | 18.6188 | 2019-07-01 | 2019-07-01 | 2019-07-11 | 7 | 2019-08-14 | 2019-08-14 | 2020-01-07 | 59 | 9900 |  | 151280.8 |  |  | 2020-01-28 | 2020-01-31 |  |  |  |  | N | Y
NIMO | Barton Pitts (Nexamp) | 00255150 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97654 | LAWRENCE AVE 976 | N | 3350 |  |  | CDG | Y | 2019-09-26 | 2019-10-10 | 13.9833 | 2019-10-11 | 2019-10-11 | 2019-10-28 | 11 | 2019-12-02 | 2019-12-02 | 2020-03-11 | 59 | 9900 |  | 386058 |  |  | 2020-07-17 | [5 empty] | N | Y
NIMO | Dan Leary (OurGeneration, LLC) | 00287874 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97654 | LAWRENCE AVE 976 | N | 4400 |  |  | CDG | N | 2020-04-27 | 2020-05-05 | 6 | 2020-05-05 | 2020-05-05 | 2020-05-05 | 0 | 2020-07-16 | 2020-07-16 | 2020-12-03 | 59 | 9400 |  | 191275 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00323324 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97654 | LAWRENCE AVE 976 | N | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-08 | 4 | 2020-11-08 | 2020-11-08 | 2020-11-08 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Michael Roach (RER Energy Group LLC) | 00102468 | 018 - Rome | CAMDEN | 13316 | 36_18_66951 | LEHIGH 669 | N | 1794 |  |  | RNM | N | 2014-07-09 | 2014-11-25 | 100 | 2014-11-25 | 2014-11-25 | 2014-12-03 | 0 | 2015-08-25 | 2015-08-25 | 2016-04-07 | 162 | 15700 |  | 619869 |  |  | 2016-06-28 |  |  |  | 2017-11-20 | 2017-11-20 | Y | N
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00276729 | 018 - Rome | CAMDEN | 13316 | 36_18_66952 | LEHIGH 669 | N | 5000 |  |  | CDG | N | 2020-01-28 | 2020-02-10 | 13.0799 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 0 | 2020-04-23 | 2020-04-23 | 2020-07-27 | 58 | 9400 |  | 764274 | [8 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00270386 | 018 - Rome | CAMDEN | 13316 | 36_18_66952 | LEHIGH 669 | N | 5000 |  |  | CDG | Y | 2020-01-24 | 2020-02-05 | 11.9896 | 2020-02-06 | 2020-02-06 | 2020-02-13 | 5 | 2020-03-16 | 2020-03-16 | 2020-06-24 | 59 | 9400 |  | 591469 |  |  | 2020-09-25 | [5 empty] | N | Y
NIMO | Samantha Lennon (Green Street Power Partners) | 00222726 | 018 - Rome | CAMDEN | 13316 | 36_18_66953 | LEHIGH 669 | N | 5000 |  |  | CDG | Y | 2019-04-26 | 2019-05-06 | 10.2382 | 2019-05-07 | 2019-05-07 | 2019-05-14 | 5 | 2019-10-17 | 2019-10-17 | 2020-02-27 | 58 | 11400 |  | 920205 |  |  | 2020-04-20 | 2020-10-28 |  |  |  |  | N | Y
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00279414 | 018 - Rome | CAMDEN | 13316 | 36_18_66954 | LEHIGH 669 | N | 5000 |  |  | CDG | N | 2020-02-14 | 2020-03-02 | 12 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 0 | 2020-04-23 | 2020-04-23 | 2020-07-27 | 58 | 8800 |  | 787414 | [8 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00292924 | 014 - Fulton/Volney | PARISH | 13131 | MALLORY-LIGHTHOUSE HILL #22 | LIGHTHOUSE HILL 61 | N | 5000 |  |  | CDG | N | 2020-05-29 | 2020-06-05 | 5 | 2020-06-08 | 2020-06-08 | 2020-06-09 | 1 | 2020-07-02 | 2020-07-02 | 2020-11-05 | 57 | 10900 |  | 1253946 | [8 empty] | N | N
NIMO | Dave Byrne (Renua Energy, Inc.) | 00325602 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-11-19 | 2020-11-19 | 0 | 2020-11-19 | 2020-11-19 | 2020-11-19 | 0 | [15 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00323316 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-08 | 4 | 2020-11-08 | 2020-11-08 | 2020-11-08 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00323318 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-12 | 5 | 2020-11-12 | 2020-11-12 | 2020-12-03 | 12 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00323322 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-09 | 4 | 2020-11-09 | 2020-11-09 | 2020-11-16 | 3 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00318632 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-11-06 | 2020-11-16 | 5 | 2020-11-16 | 2020-11-16 | 2020-12-01 | 8 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00285490 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-04-01 | 2020-04-09 | 6 | 2020-04-10 | 2020-04-10 | 2020-04-10 | 0 | 2020-05-21 | 2020-05-21 | 2020-09-04 | 59 | 9200 |  | 784651 | [8 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00318880 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-20 | 4 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 0 | 2020-12-08 | 2020-12-08 |  |  | 9800 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00321021 | 025 - Potsdam | CANTON | 13617 | 36_25_95555 | LITTLE RIVER 955 | N | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-02 | 6 | 2020-11-03 | 2020-11-03 | 2020-11-09 | 4 |  |  |  |  | 11700 | [10 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00285107 | 001 - Buffalo | NIAGARA FALLS | 14305 | 36_03_21651 | LOCKPORT RD 216 | N | 3500 |  |  | CDG | Y | 2020-04-21 | 2020-04-29 | 6 | 2020-04-29 | 2020-04-29 | 2020-04-29 | 0 | 2020-05-29 | 2020-05-29 | 2020-09-03 | 59 | 8800 |  | 696432 |  |  | 2020-09-25 | [5 empty] | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00183955 | 023 - Lowville | TURIN | 13473 | 36_23_77352 | LOWVILLE 773 | N | 2500 |  |  | CDG | Y | 2018-06-08 | 2018-06-08 | 0 | 2018-06-26 | 2018-06-26 | 2018-07-17 | 14 | 2018-08-22 | 2018-08-22 | 2019-01-26 | 58 | 14300 |  | 60000 |  |  | 2019-05-28 | 2019-05-28 | 2019-06-05 | 2020-03-18 |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00230094 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77352 | LOWVILLE 773 | N | 4800 |  |  | CDG | Y | 2019-05-22 | 2019-06-03 | 12.1285 | 2019-06-04 | 2019-06-04 | 2019-06-17 | 9 | 2019-07-17 | 2019-07-17 | 2019-10-18 | 59 | 9800 |  | 536065.19 |  |  | 2020-02-18 | 2020-02-19 | 2020-09-01 |  |  |  | N | Y
NIMO | Sachin Patel (LAST MILE ENERGY LLC) | 00302898 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77352 | LOWVILLE 773 | N | 2158 |  |  | CDG | N | 2020-08-07 | 2020-08-20 | 9 | 2020-09-22 | 2020-09-22 | 2020-09-28 | 4 | 2020-11-12 | 2020-11-12 |  |  | 9800 | [10 empty] | N | N
NIMO | Green Skies Renewable Energy LLC | 00102159 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77353 | LOWVILLE 773 | N | 1980 |  |  | RNM | N | 2016-03-11 | 2016-03-23 | 8 | 2016-03-23 | 2016-03-23 | 2016-04-13 | 15 | 2016-05-24 | 2016-05-24 | 2016-08-23 | 60 | 25000 |  | 213317 |  |  | 2017-03-20 |  |  | 2018-03-21 | 2018-05-03 | 2018-05-03 | Y | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00227249 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77354 | LOWVILLE 773 | N | 2000 |  |  | CDG | Y | 2019-05-13 | 2019-05-28 | 14.9313 | 2019-05-29 | 2019-05-29 | 2019-06-12 | 10 | 2019-07-17 | 2019-07-17 | 2019-10-14 | 59 | 9400 |  | 425699.45 |  |  | 2020-02-18 | 2020-02-19 | 2020-09-11 |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00219571 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77354 | LOWVILLE 773 | N | 5000 |  |  | CDG | Y | 2019-04-12 | 2019-04-17 | 4.5521 | 2019-04-18 | 2019-04-18 | 2019-04-30 | 8 | 2019-06-03 | 2019-06-03 | 2019-09-09 | 58 | 9400 |  | 897440.43 |  |  | 2020-01-27 | 2020-01-29 | 2020-09-11 |  |  |  | N | Y
NIMO |  | 00209758 | 023 - Lowville | GLENFIELD | 13343 | 36_23_77354 | LOWVILLE 773 | N | 1920 |  |  | CDG | Y | 2019-02-14 | 2019-02-27 | 12.7222 | 2019-02-28 | 2019-02-28 | 2019-03-05 | 3 | 2019-04-19 | 2019-04-19 | 2019-08-06 | 59 | 10000 |  | 435279.97 |  |  | 2019-12-18 | 2019-12-24 | 2020-09-01 |  |  |  | N | Y
NIMO | Mario Titolo (Convergent Energy & Power) | 00203745 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73351 | LYME 733 | Y | 5000 | 6000 |  | CDG | Y | 2018-12-28 | 2019-01-31 | 33.7312 | 2019-02-01 | 2019-02-01 | 2019-02-08 | 5 | 2019-04-02 | 2019-04-02 | 2019-09-04 | 59 | 12400 |  | 703182 |  |  | 2019-12-04 | 2019-12-04 |  |  |  |  | N | Y
NIMO | Matt Vanderbrook (GreenSpark Solar) | 00207359 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73351 | LYME 733 | Y | 3150 | 6000 |  | CDG | Y | 2019-01-28 | 2019-01-31 | 3.0125 | 2019-02-04 | 2019-02-04 | 2019-02-13 | 7 | 2019-06-06 | 2019-06-06 | 2019-09-16 | 58 | 12400 |  | 33871.85 |  |  | 2019-12-04 | 2019-12-04 |  |  |  |  | N | Y
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00201774 | 013 - Watertown | CLAYTON | 13624 | 36_13_73351 | LYME 733 | Y | 1250 | 1250 |  | CDG | Y | 2018-11-30 | 2018-12-13 | 12.8299 | 2018-12-14 | 2018-12-14 | 2018-12-19 | 3 | 2019-02-06 | 2019-02-06 | 2019-04-29 | 57 | 10100 |  | 249584 |  |  | 2019-10-09 | 2019-10-09 | 2020-04-01 |  |  |  | N | Y
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00280313 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73352 | LYME 733 | N | 5000 |  |  | CDG | N | 2020-03-06 | 2020-03-17 | 9 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-03-26 | 2020-03-26 |  |  | 9400 | [10 empty] | N | N
NIMO | Derek Longo (Convergent Energy & Power) | 00204896 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73352 | LYME 733 | Y | 5000 | 6000 |  | CDG | Y | 2018-12-28 | 2019-01-31 | 33.8257 | 2019-02-01 | 2019-02-01 | 2019-02-08 | 5 | 2019-04-02 | 2019-04-02 | 2019-09-06 | 59 | 12400 |  | 121306.32 |  |  | 2019-12-04 | 2019-12-04 |  |  |  |  | N | Y
NIMO | John Vigants (Bright Solar LLC) | 00321846 | 013 - Watertown | DEXTER | 13634 | 36_13_73353 | LYME 733 | N | 5000 |  |  | CDG | N | 2020-10-29 | 2020-11-03 | 3 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 |  |  |  |  | 12500 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00327616 | 013 - Watertown | DEXTER | 13634 | 36_13_73353 | LYME 733 | N | 5000 |  |  | CDG | N | 2020-11-25 | 2020-12-03 | 4 | 2020-12-03 | [18 empty] | N | N
NIMO | Kevin Schulte (GreenSpark Solar) | 00206335 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73353 | LYME 733 | Y | 5000 | 6000 |  | CDG | Y | 2019-01-17 | 2019-01-31 | 13.8361 | 2019-02-01 | 2019-02-01 | 2019-02-08 | 5 | 2019-03-18 | 2019-03-18 | 2019-09-11 | 59 | 12400 |  | 32696.17 |  |  | 2019-12-04 | 2019-12-04 |  |  |  |  | N | Y
NIMO | Matt Vanderbrook (GreenSpark Solar) | 00207355 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73353 | LYME 733 | Y | 5000 | 6000 |  | CDG | Y | 2019-01-28 | 2019-01-31 | 2.9486 | 2019-02-01 | 2019-02-01 | 2019-02-08 | 5 | 2019-03-18 | 2019-03-18 | 2019-09-13 | 58 | 12400 |  | 32696.17 |  |  | 2019-12-04 | 2019-12-04 |  |  |  |  | N | Y
NIMO | David Spotts (SSC Lysander LLC) | 00250467 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_29754 | LYSANDER 297 | Y | 3500 | 5000 |  | CDG | Y | 2019-09-19 | 2019-09-30 | 11.4271 | 2019-10-01 | 2019-10-01 | 2019-10-17 | 12 | 2019-10-31 | 2019-10-31 | 2020-02-18 | 59 | 9700 |  | 215219.52 |  |  | 2020-03-31 | 2020-09-22 |  |  |  |  | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00320217 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_29755 | LYSANDER 297 | Y | 5000 | 5000 |  | CDG | N | 2020-10-22 | 2020-10-29 | 5 | 2020-10-29 | 2020-10-29 | 2020-10-29 | 0 |  |  |  |  | 9300 | [10 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development, LLC) | 00250050 | 010 - Olean | MACHIAS | 14101 | 36_10_1361 | MACHIAS 13 | N | 2000 |  |  | CDG | Y | 2019-10-11 | 2019-10-23 | 11.9632 | 2019-10-24 | 2019-10-24 | 2019-11-14 | 14 | 2019-11-25 | 2019-11-25 | 2020-03-18 | 57 | 9200 |  | 246560 |  |  | 2020-05-14 | 2020-11-02 |  |  |  |  | N | Y
NIMO | Gordon Woodcock (Pivot Energy) | 00312217 | 010 - Olean | FRANKLINVILLE | 14737 | 36_10_1362 | MACHIAS 13 | N | 1000 |  |  | CDG | N | 2020-10-15 | 2020-10-22 | 5 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2020-11-17 | 2020-11-17 |  |  | 10300 | [10 empty] | N | N
NIMO | Alicia Scott (BQ Energy, LLC.) | 00194050 | 010 - Olean | WEST VALLEY | 14171 | DAKE HILL-MACHIAS #803 | MACHIAS 13 | Y | 5000 | 3300 |  | CDG | Y | 2018-08-22 | 2018-10-26 | 65.0694 | 2018-10-29 | 2018-10-29 | 2018-11-07 | 7 | 2019-01-10 | 2019-01-10 | 2019-03-22 | 49 | 13300 |  | 275059 |  |  | 2019-08-27 | 2019-10-14 | 2019-08-29 | 2019-10-14 |  |  | N | Y
NIMO | Alicia Scott (BQ Energy, LLC.) | 00194084 | 010 - Olean | WEST VALLEY | 14171 | DAKE HILL-MACHIAS #803 | MACHIAS 13 | Y | 5000 | 3300 |  | CDG | Y | 2018-08-22 | 2018-10-26 | 65.0514 | 2018-10-29 | 2018-10-29 | 2018-11-07 | 7 | 2019-01-10 | 2019-01-10 | 2019-03-22 | 49 | 13300 |  | 275059 |  |  | 2019-08-27 | 2019-10-10 | 2019-08-29 | 2019-10-10 |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00284063 | 016 - Pulaski | PULASKI | 13142 | LIGHTHOUSE HILL-MALLORY 22 | MALLORY | N | 5000 |  |  | CDG | N | 2020-03-18 | 2020-03-26 | 6 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-17 | 58 | 10900 |  | 1191873 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00284084 | 016 - Pulaski | PULASKI | 13142 | LIGHTHOUSE HILL-MALLORY 22 | MALLORY | N | 5000 |  |  | CDG | N | 2020-03-18 | 2020-03-26 | 6 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-17 | 58 | 10900 |  | 1191873 | [8 empty] | N | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00306946 | 027 - Malone | MALONE | 12953 | 36_27_89551 | MALONE 895 | N | 2000 |  |  | CDG | N | 2020-08-20 | 2020-08-27 | 5 | 2020-08-27 | 2020-08-27 | 2020-08-27 | 0 | 2020-09-24 | 2020-09-24 |  |  | 8800 | [10 empty] | N | N
NIMO | Joe Fiori (Nexamp) | 00228734 | 027 - Malone | NORTH BANGOR | 12966 | 36_27_89552 | MALONE 895 | N | 5000 |  |  | CDG | Y | 2019-05-24 | 2019-06-06 | 13.2257 | 2019-06-07 | 2019-06-07 | 2019-06-14 | 5 | 2019-08-02 | 2019-08-02 | 2019-10-30 | 59 | 10100 |  | 795397.18 |  |  | 2020-03-13 | 2020-09-15 | 2020-09-17 |  |  |  | N | Y
NIMO | Joe Fiori (Nexamp) | 00250999 | 027 - Malone | BANGOR | 12966 | 36_27_89552 | MALONE 895 | N | 5000 |  |  | CDG | Y | 2019-09-11 | 2019-10-04 | 23.0708 | 2019-10-07 | 2019-10-07 | 2019-10-25 | 14 | 2019-12-02 | 2019-12-02 | 2020-03-11 | 59 | 8300 |  | 970504 |  |  | 2020-07-17 | [5 empty] | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00310426 | 027 - Malone | MALONE | 12953 | 36_27_89553 | MALONE 895 | N | 5000 |  |  | CDG | N | 2020-09-02 | 2020-09-15 | 7 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2020-11-06 | 2020-11-06 |  |  | 10400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00319117 | 027 - Malone | MALONE | 12953 | 36_27_89553 | MALONE 895 | N | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-03 | 7 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Standard Solar | 00253939 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_50251 | MAPLE AVE 502 | N | 4500 |  |  | CDG | N | 2019-09-17 | 2020-01-23 | 128.3049 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 0 | 2020-05-19 | 2020-05-19 | 2020-11-06 | 69 | 9400 |  | 150367 | [8 empty] | N | N
NIMO | Standard Solar | 00253851 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_50251 | MAPLE AVE 502 | N | 5000 |  |  | CDG | N | 2019-09-16 | 2020-01-23 | 129.1201 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 0 | 2020-05-19 | 2020-05-19 | 2020-11-06 | 58 | 9400 |  | 150367 | [8 empty] | N | N
NIMO | Dave Ingalls (Solar Park Energy LLC) | 00297447 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50252 | MAPLE AVE 502 | N | 5000 |  |  | CDG | N | 2020-08-06 | 2020-08-12 | 4 | 2020-08-12 | 2020-08-12 | 2020-08-12 | 0 | 2020-10-12 | 2020-10-12 |  |  | 9400 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00259334 | 034 - Amsterdam | HAGAMAN | 12086 | 36_35_50253 | MAPLE AVE 502 | N | 5000 |  |  | CDG | Y | 2019-10-29 | 2019-11-08 | 10.1333 | 2019-11-12 | 2019-11-12 | 2019-11-18 | 4 | 2020-01-14 | 2020-01-14 | 2020-04-09 | 59 | 13000 |  | 495349 |  |  | 2020-05-26 | 2020-11-12 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00271503 | 001 - Buffalo | GETZVILLE | 14228 | 36_01_14058 | MAPLE RD 140 | N | 5000 |  |  | RNM | N | 2020-01-03 | 2020-01-17 | 14.1271 | 2020-01-21 | 2020-01-21 | 2020-02-01 | 9 | 2020-03-11 | 2020-03-11 | 2020-07-15 | 58 | 8100 |  | 270120 |  |  | 2020-09-21 | 2020-10-22 |  |  |  |  | N | N
NIMO | BQ Energy Inc. | 00100856 | 010 - Olean | OLEAN | 14760 | HOMER HILL-NILE #811 | MAPLEHURST | N | 1640 |  |  | RNM | N | 2015-05-12 | 2015-05-13 | 2 | 2015-05-13 | 2015-05-13 | 2015-06-03 | 3 | 2015-09-02 | 2015-09-02 | 2015-12-16 | 75 | 15000 |  | 165000 | [5 empty] | 2018-12-07 | 2019-05-10 | 2019-05-10 | Y | N
NIMO | BQ Energy Inc. | 00100858 | 010 - Olean | OLEAN | 14760 | HOMER HILL-NILE #811 | MAPLEHURST | N | 1640 |  |  | RNM | N | 2015-04-20 | 2015-05-31 | 2 | 2015-05-31 | 2015-05-31 | 2015-06-03 | 0 | 2015-09-02 | 2015-09-02 | 2015-12-16 | 75 | 15000 |  | 48000 | [5 empty] | 2018-12-07 | 2019-05-10 | 2019-05-10 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100901 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_35651 | MAYFIELD 356 | N | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-23 | 0 | 2016-04-11 | 2016-04-11 | 2016-07-01 | 59 | 25000 |  | 1220457 |  |  | 2017-04-05 |  |  |  | 2018-12-19 | 2018-12-19 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100902 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_35651 | MAYFIELD 356 | N | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-23 | 0 | 2016-03-17 | 2016-03-17 | 2016-06-10 | 60 | 25000 |  | 148792 |  |  | 2017-04-05 |  |  |  | 2018-12-19 | 2018-12-19 | Y | N
NIMO | Margaret Campbell (EDF Renewables) | 00209913 | 028 - Ogdensburg | HEUVELTON | 13654 | 36_28_91451 | MCADOO 914 | N | 2000 |  |  | CDG | Y | 2019-02-25 | 2019-03-08 | 10.8688 | 2019-03-11 | 2019-03-11 | 2019-03-19 | 6 | 2019-04-09 | 2019-04-09 | 2019-11-27 | 59 | 14300 |  | 475337 |  |  | 2020-04-07 | 2020-11-16 |  |  |  |  | N | Y
NIMO | Michael Frateschi (TJA Clean Energy) | 00304893 | 028 - Ogdensburg | HEUVELTON | 13654 | 36_28_91451 | MCADOO 914 | N | 5000 |  |  | CDG | N | 2020-08-05 | 2020-08-16 | 8 | 2020-08-16 | 2020-08-16 | 2020-08-16 | 0 | 2020-09-08 | 2020-09-08 | 2020-12-09 | 58 | 10500 |  | 1336696 | [8 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00317371 | 028 - Ogdensburg | RENSSELAER FALLS | 13680 | 36_28_91451 | MCADOO 914 | N | 5000 |  |  | CDG | N | 2020-10-26 | 2020-10-26 | 0 | 2020-10-27 | 2020-10-27 | 2020-11-02 | 4 |  |  |  |  | 10400 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00308731 | 029 - Gouvernur | CANTON | 13617 | 36_28_91453 | MCADOO 914 | N | 5000 |  |  | CDG | N | 2020-08-26 | 2020-09-15 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2020-10-12 | 2020-10-12 |  |  | 9400 | [10 empty] | N | N
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00196764 | 029 - Gouvernur | RICHVILLE | 13681 | 36_28_91453 | MCADOO 914 | N | 3300 |  |  | CDG | Y | 2018-10-10 | 2018-10-24 | 13.7257 | 2018-10-25 | 2018-10-25 | 2018-11-02 | 6 | 2018-12-06 | 2018-12-06 | 2019-04-19 | 58 | 14300 |  | 678447.52 |  |  | 2019-09-13 | 2019-11-08 | 2019-09-16 | 2019-11-08 |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00262907 | 030 - Albany | ALBANY | 12222 | 36_30_32752 | MCKOWNVILLE 327 | N | 1500 |  |  | RNM | Y | 2019-10-30 | 2019-11-08 | 8.8528 | 2019-11-12 | 2019-11-12 | 2019-11-15 | 3 | 2019-12-11 | 2019-12-11 | 2020-04-24 | 58 | 8800 |  | 689355 |  |  | 2020-06-15 | [5 empty] | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00278766 | 037 - Cobleskill | SCHOHARIE | 12157 | 36_37_39051 | MIDDLEBURG 390 | N | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-16 | 9 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-03-24 | 2020-03-24 | 2020-08-03 | 57 | 9800 |  | 759072 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00291364 | 037 - Cobleskill | MIDDLEBURGH | 12023 | 36_37_39052 | MIDDLEBURG 390 | Y |  | 0 | 5000 | CDG | N | 2020-05-26 | 2020-06-02 | 5 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 0 | 2020-07-21 | 2020-07-21 |  |  | 14000 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00294444 | 037 - Cobleskill | MIDDLEBURGH | 12122 | 36_37_39052 | MIDDLEBURG 390 | Y |  | 0 | 5000 | CDG | N | 2020-07-09 | 2020-07-22 | 9 | 2020-07-22 | 2020-07-22 | 2020-07-22 | 0 | 2020-10-12 | 2020-10-12 |  |  | 14500 | [10 empty] | N | N
NIMO | Trevor Hardy (BlueWave Solar) | 00317430 | 019 - Herkimer | MIDDLEVILLE | 13406 | 36_19_66671 | MIDDLEVILLE 666 | N | 4800 |  |  | CDG | N | 2020-11-12 | 2020-11-17 | 3 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | Luke Spencer (GreenSpark Solar) | 00325852 | 003 - Niagara Falls | NIAGARA FALLS | 14304 | 36_03_21052 | MILITARY RD 210 | N | 4000 |  |  | RNM | N | 2020-11-25 | 2020-12-04 | 5 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 0 |  |  |  |  | 9200 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00237290 | 011 - Syracuse | CAMILLUS | 13031 | 36_11_26656 | MILTON AVE 266 | Y | 5000 | 5000 |  | CDG | Y | 2019-07-02 | 2019-07-25 | 22.8632 | 2019-07-26 | 2019-07-26 | 2019-07-31 | 3 | 2019-09-30 | 2019-09-30 | 2020-02-11 | 59 | 10400 |  | 2438777.32 |  |  | 2020-07-28 | [5 empty] | N | Y
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00246684 | 011 - Syracuse | CAMILLUS | 13031 | 36_11_26656 | MILTON AVE 266 | Y | 5000 | 5000 |  | CDG | Y | 2019-08-02 | 2019-08-13 | 11.1993 | 2019-08-14 | 2019-08-14 | 2019-08-21 | 5 | 2019-09-30 | 2019-09-30 | 2020-02-11 | 59 | 11400 |  | 2526011.96 |  |  | 2020-07-28 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS LLC) | 00232001 | 011 - Syracuse | WARNERS | 13164 | 36_11_26658 | MILTON AVE 266 | Y | 3000 | 3000 |  | CDG | Y | 2019-05-31 | 2019-06-12 | 11.7451 | 2019-06-13 | 2019-06-13 | 2019-06-28 | 11 | 2019-08-08 | 2019-08-08 | 2019-12-13 | 59 | 10300 |  | 835748 |  |  | 2020-01-06 | 2020-09-13 |  |  |  |  | N | Y
NIMO |  | 00187481 | 005 - Avon | SCOTTSVILLE | 14546 | 36_05_5051 | MUMFORD 50 | N | 4500 |  |  | CDG | Y | 2018-06-12 | 2018-06-12 | 0 | 2018-07-05 | 2018-07-05 | 2018-07-25 | 14 | 2018-11-09 | 2018-11-09 | 2019-02-27 | 59 | 15300 |  | 848193 |  |  | 2019-07-08 | 2019-07-16 |  |  |  |  | N | Y
NIMO |  | 00187483 | 005 - Avon | SCOTTSVILLE | 14546 | 36_05_5051 | MUMFORD 50 | N | 4500 |  |  | CDG | Y | 2018-06-12 | 2018-06-12 | 0 | 2018-07-05 | 2018-07-05 | 2018-07-25 | 14 | 2018-11-09 | 2018-11-09 | 2019-02-27 | 59 | 16400 |  | 195145 |  |  | 2019-07-08 | 2019-07-16 |  |  |  |  | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00270095 | 005 - Avon | CHURCHVILLE | 14428 | 36_05_5053 | MUMFORD 50 | N | 5000 |  |  | CDG | N | 2020-02-12 | 2020-02-27 | 12 | 2020-02-27 | 2020-02-27 | 2020-03-04 | 4 | 2020-05-05 | 2020-05-05 | 2020-08-20 | 59 | 9400 |  | 692356 | [8 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00285638 | 005 - Avon | CHURCHVILLE | 14428 | 36_05_5053 | MUMFORD 50 | N | 5000 |  |  | CDG | N | 2020-03-31 | 2020-04-08 | 6 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 0 | 2020-04-23 | 2020-04-23 | 2020-08-05 | 58 | 10100 |  | 1079909 | [8 empty] | N | N
NIMO | Ian Diamond (Consolidated Edison Solutions, Inc) | 00170662 | 027 - Malone | BOMBAY | 12914 | 36_27_86652 | N. BOMBAY 866 | N | 900 |  |  | CDG | Y | 2018-03-01 | 2018-03-01 | 0 | 2018-03-13 | 2018-03-13 | 2018-03-27 | 10 | 2018-04-09 | 2018-04-09 | 2018-09-14 | 1 | 16400 |  | 191046.72 |  |  | 2019-02-07 | 2019-12-30 | 2019-05-01 | 2019-12-30 | 2019-12-30 | 2019-12-30 | Y | Y
NIMO | Ivaylo Tomchev (Wilna PV, LLC) | 00276518 | 022 - Carthage | NATURAL BRIDGE | 13665 | 36_23_81652 | N. CARTHAGE 816 | N | 5000 |  |  | CDG | Y | 2020-01-28 | 2020-02-10 | 12.966 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 0 | 2020-04-03 | 2020-04-03 | 2020-07-14 | 56 | 9800 |  | 392442 |  |  | 2020-10-12 | [5 empty] | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00251499 | 022 - Carthage | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | N | 3300 |  |  | CDG | Y | 2019-08-30 | 2019-09-11 | 12.1403 | 2019-09-12 | 2019-09-12 | 2019-09-17 | 3 | 2019-11-27 | 2019-11-27 | 2020-03-06 | 59 | 10900 |  | 196124 |  |  | 2020-07-14 | [5 empty] | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00227976 | 022 - Carthage | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | N | 5000 |  |  | CDG | Y | 2019-05-15 | 2019-05-28 | 12.9819 | 2019-05-29 | 2019-05-29 | 2019-06-03 | 3 | 2019-07-17 | 2019-07-17 | 2019-12-04 | 59 | 10900 |  | 240880.96 |  |  | 2020-05-01 | 2020-10-19 | 2020-10-23 |  |  |  | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00320093 | 023 - Lowville | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | N | 5000 |  |  | CDG | N | 2020-11-05 | 2020-11-12 | 4 | 2020-11-12 | 2020-11-12 | 2020-11-23 | 6 | 2020-12-07 | 2020-12-07 |  |  | 11700 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00320105 | 023 - Lowville | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | N | 5000 |  |  | CDG | N | 2020-11-05 | 2020-11-12 | 4 | 2020-11-12 | 2020-11-12 | 2020-11-12 | 0 | 2020-12-07 | 2020-12-07 |  |  | 12500 | [10 empty] | N | N
NIMO | Samantha Lennon (Green Street Power Partners) | 00200416 | 023 - Lowville | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | Y | 875 | 1000 |  | CDG | Y | 2018-11-06 | 2018-11-27 | 21.0188 | 2018-11-28 | 2018-11-28 | 2018-11-29 | 1 | 2019-01-15 | 2019-01-15 | 2019-05-15 | 55 | 14300 |  | 128865.24 |  |  | 2020-02-21 | 2020-02-24 | 2020-09-11 |  |  |  | N | Y
NIMO | Samantha Lennon (GSPP 24757 County Route 47 North, | 00200426 | 023 - Lowville | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | Y | 875 | 1000 |  | CDG | Y | 2018-11-06 | 2018-11-27 | 20.8583 | 2018-11-28 | 2018-11-28 | 2018-11-29 | 1 | 2019-01-15 | 2019-01-15 | 2019-05-15 | 56 | 14300 |  | 277230 |  |  | 2020-02-21 | 2020-02-24 | 2020-09-11 |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00183966 | 023 - Lowville | CARTHAGE | 13327 | 36_23_81654 | N. CARTHAGE 816 | N | 5000 |  |  | CDG | Y | 2018-06-08 | 2018-06-08 | 0 | 2018-06-25 | 2018-06-25 | 2018-07-10 | 10 | 2018-08-20 | 2018-08-20 | 2019-01-18 | 51 | 13300 |  | 328103 |  |  | 2019-03-25 | 2019-06-13 | 2019-05-29 | 2019-06-13 | 2020-02-28 | 2020-02-28 | Y | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00320132 | 023 - Lowville | CARTHAGE | 13619 | 36_23_81654 | N. CARTHAGE 816 | N | 5000 |  |  | CDG | N | 2020-11-06 | 2020-11-17 | 6 | 2020-11-17 | 2020-11-17 | 2020-12-01 | 7 | 2020-12-08 | 2020-12-08 |  |  | 9800 | [10 empty] | N | N
NIMO | Bartolo Jimenez (Cipriani Energy Group Corp.) | 00310065 | 040 - Warrensburg | NORTH CREEK | 12853 | 36_40_12252 | N. CREEK 122 | N | 5000 |  |  | CDG | N | 2020-09-01 | 2020-09-10 | 5 | 2020-09-10 | 2020-09-10 | 2020-09-10 | 0 | 2020-09-15 | 2020-09-15 |  |  | 9800 | [10 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00169583 | 007 - Angola | EDEN | 14057 | 36_07_8251 | N. EDEN 82 | Y | 3750 | 3750 |  | CDG | Y | 2018-01-26 | 2018-01-26 | 0 | 2018-02-14 | 2018-02-14 | 2018-02-26 | 0 | 2018-05-30 | 2018-05-30 | 2018-08-22 | 59 | 16800 |  | 752272 |  |  | 2019-04-19 |  | 2020-01-21 | 2020-03-03 |  |  | N | Y
NIMO | Amanda Lennon (GSPP 126 Little Bow Rd S, LLC) | 00225659 | 029 - Gouvernur | GOUVERNEUR | 13642 | 36_29_98352 | N. GOVERNEUR 983 | N | 4750 |  |  | CDG | Y | 2019-05-08 | 2019-05-22 | 14.0826 | 2019-05-23 | 2019-05-23 | 2019-06-03 | 6 | 2019-10-11 | 2019-10-11 | 2020-01-21 | 59 | 10900 |  | 969863.62 |  |  | 2020-07-14 | [5 empty] | N | Y
NIMO | Samantha Lennon (GSPP 126 Little Bow Rd N, LLC) | 00225639 | 029 - Gouvernur | GOUVERNEUR | 13642 | 36_29_98352 | N. GOVERNEUR 983 | N | 4750 |  |  | CDG | Y | 2019-06-10 | 2019-06-20 | 10.1868 | 2019-06-21 | 2019-06-21 | 2019-07-09 | 11 | 2019-10-09 | 2019-10-09 | 2020-01-29 | 59 | 10900 |  | 969017.6 |  |  | 2020-07-14 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00100867 | 029 - Gouvernur | GOUVERNEUR | 13642 | 36_29_98353 | N. GOVERNEUR 983 | N | 996 |  |  | RNM | N | 2015-05-13 | 2015-05-28 | 3 | 2015-05-28 | 2015-05-28 | 2015-06-17 | 0 | 2016-06-10 | 2016-06-10 | 2016-09-01 | 59 | 35000 |  | 218350 |  |  |  | 2017-06-09 | 2017-06-12 | 2017-12-21 | 2017-12-21 | 2017-12-21 | Y | N
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00196805 | 029 - Gouvernur | RICHVILLE | 13681 | 36_29_98353 | N. GOVERNEUR 983 | N | 1484 |  |  | CDG | Y | 2018-09-24 | 2018-10-25 | 30.7757 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 0 | 2018-12-13 | 2018-12-13 | 2019-05-29 | 58 | 13300 |  | 696561.53 |  |  | 2019-09-23 | 2019-10-29 | 2019-09-25 | 2019-10-29 |  |  | N | Y
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00196798 | 029 - Gouvernur | GOUVERNEUR | 13642 | 36_29_98353 | N. GOVERNEUR 983 | N | 4000 |  |  | CDG | Y | 2018-09-25 | 2018-10-25 | 30.1514 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 0 | 2018-12-13 | 2018-12-13 | 2019-04-19 | 58 | 13600 |  | 485218.49 |  |  | 2019-09-23 | 2019-10-29 | 2019-09-25 | 2019-10-29 |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00268581 | 031 - Troy | MELROSE | 12121 | 36_31_12351 | N. TROY 123 | N | 5000 |  |  | CDG | N | 2019-12-06 | 2019-12-17 | 11.0062 | 2019-12-17 | 2019-12-17 | 2019-12-17 | 0 | 2020-02-18 | 2020-02-18 | 2020-07-20 | 57 | 9400 |  | 1160246 |  |  | 2020-10-05 | [5 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00213284 | 031 - Troy | TROY | 12180 | 36_31_12353 | N. TROY 123 | N | 5000 |  |  | CDG | Y | 2019-03-13 | 2019-03-26 | 12.7556 | 2019-03-27 | 2019-03-27 | 2019-04-05 | 6 | 2019-06-18 | 2019-06-18 | 2019-09-04 | 54 | 9200 |  | 352330 |  |  | 2019-09-25 | 2019-09-30 |  |  |  |  | N | Y
NIMO | John J. Watson (CAERO) | 00290192 | 031 - Troy | TROY | 12182 | 36_31_12354 | N. TROY 123 | N | 5000 |  |  | CDG | N | 2020-05-08 | 2020-05-15 | 5 | 2020-05-15 | 2020-05-15 | 2020-05-15 | 0 | 2020-07-09 | 2020-07-09 | 2020-11-18 | 59 | 9300 |  | 154427 | [8 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00267202 | 014 - Fulton/Volney | CENTRAL SQUARE | 13036 | 36_14_25652 | NEW HAVEN 256 | N | 3000 |  |  | CDG | Y | 2019-11-25 | 2019-12-05 | 9.9931 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 0 | 2019-12-11 | 2019-12-11 | 2020-04-02 | 55 | 10900 |  | 943304 |  |  | 2020-08-20 | [5 empty] | N | Y
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00280314 | 015 - Oswego | OSWEGO | 13126 | 36_14_25653 | NEW HAVEN 256 | Y | 5000 | 0 |  | CDG | N | 2020-05-20 | 2020-05-28 | 5 | 2020-05-28 | 2020-05-28 | 2020-05-28 | 0 | 2020-07-15 | 2020-07-15 |  |  | 11800 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00270612 | 015 - Oswego | OSWEGO | 13126 | 36_14_25653 | NEW HAVEN 256 | N | 5000 |  |  | CDG | Y | 2019-12-23 | 2020-01-06 | 13.9236 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 0 | 2020-02-18 | 2020-02-18 | 2020-05-27 | 56 | 9400 |  | 759705 |  |  | 2020-10-19 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00257391 | 030 - Albany | ALBANY | 12203 | 36_30_42153 | NEW KRUMKILL 421 | N | 3840 |  |  | CDG | Y | 2019-09-30 | 2019-10-15 | 14.6694 | 2019-10-16 | 2019-10-16 | 2019-10-25 | 7 | 2019-12-24 | 2019-12-24 | 2020-04-17 | 59 | 10400 |  | 2178353 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00257389 | 030 - Albany | ALBANY | 12203 | 36_30_42153 | NEW KRUMKILL 421 | N | 5000 |  |  | CDG | Y | 2019-09-30 | 2019-10-15 | 14.6868 | 2019-10-16 | 2019-10-16 | 2019-10-25 | 7 | 2019-12-24 | 2019-12-24 | 2020-04-17 | 59 | 9900 |  | 1017470 |  |  | 2020-06-15 | 2020-12-11 |  |  |  |  | N | Y
NIMO | John McDonough (Omni-Navitas Holdings, LLC) | 00261625 | 011 - Syracuse | AUBURN | 13021 | 36_11_29451 | NILES 294 | N | 5000 |  |  | CDG | N | 2019-11-12 | 2019-11-20 | 7.859 | 2019-11-21 | 2019-11-21 | 2019-12-10 | 11 | 2020-03-25 | 2020-03-25 | 2020-06-30 | 59 | 9400 |  | 689356 |  |  | 2020-11-09 | [5 empty] | N | N
NIMO | Bradley Beament (Aura Power Solar USA (LLC)) | 00305575 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | NORTH LEROY | N | 5000 |  |  | CDG | N | 2020-08-24 | 2020-09-15 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2020-09-21 | 2020-09-21 |  |  | 9800 | [10 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00259059 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | NORTH LEROY | N | 2200 |  |  | CDG | Y | 2020-01-31 | 2020-02-13 | 12.8715 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 0 | 2020-03-16 | 2020-03-16 | 2020-06-22 | 58 | 9400 |  | 689356 |  |  | 2020-10-28 | [5 empty] | N | Y
NIMO | Bartolo Jimenez (Cipriani Energy Group Corp.) | 00291928 | 035 - Gloversville | MAYFIELD | 12117 | 36_35_33251 | NORTHVILLE 332 | N | 3000 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-03 | 2020-06-03 | 2020-09-29 | 58 | 8800 |  | 692355 | [8 empty] | N | N
NIMO | Ryan Storke (Storke, LLC) | 00273915 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_6261 | OAK HILL 62 | N | 3000 |  |  | CDG | N | 2020-05-07 | 2020-05-14 | 5 | 2020-05-15 | 2020-05-15 | 2020-05-18 | 1 | 2020-08-04 | 2020-08-04 |  |  | 10100 | [10 empty] | N | N
NIMO | Stephen Mockler (Brookfield Renewable) | 00307399 | 038 - Glens Falls | QUEENSBURY | 12804 | 36_38_42357 | OGDEN BROOK 423 | N | 3600 |  |  | CDG | N | 2020-08-26 | 2020-10-05 | 29 | 2020-10-05 | 2020-10-05 | 2020-10-05 | 0 | 2020-11-13 | 2020-11-13 |  |  | 9400 | [10 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00263111 | 028 - Ogdensburg | OGDENSBURG | 13669 | 36_28_93852 | OGDENSBURG 938 | N | 5000 |  |  | CDG | Y | 2019-11-25 | 2019-12-05 | 10.1153 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 0 | 2019-12-23 | 2019-12-23 | 2020-03-31 | 59 | 10800 |  | 1527954.17 |  |  | 2020-08-07 | [5 empty] | N | Y
NIMO | Ryan McCune (Nexamp) | 00291843 | 028 - Ogdensburg | OGDENSBURG | 13669 | 36_28_93852 | OGDENSBURG 938 | N | 5000 |  |  | CDG | N | 2020-06-16 | 2020-06-23 | 5 | 2020-06-24 | 2020-06-24 | 2020-06-24 | 0 | 2020-08-12 | 2020-08-12 |  |  | 11300 | [10 empty] | N | N
NIMO | Thomas Murphy (Environomics.Co) | 00244401 | 028 - Ogdensburg | OGDENSBURG | 13369 | 36_28_93854 | OGDENSBURG 938 | N | 5000 |  |  | CDG | Y | 2019-07-19 | 2019-08-06 | 17.5812 | 2019-08-07 | 2019-08-07 | 2019-09-12 | 10 | 2019-09-24 | 2019-09-24 | 2020-02-05 | 59 | 11700 |  | 1334049 |  |  | 2020-06-29 | [5 empty] | N | Y
NIMO | TJ Murphy (Environomics.Co) | 00255905 | 028 - Ogdensburg | OGDENSBURG | 13669 | 36_28_93854 | OGDENSBURG 938 | N | 5000 |  |  | CDG | N | 2019-10-11 | 2019-10-23 | 12.1583 | 2019-10-24 | 2019-10-24 | 2019-11-14 | 14 | 2020-02-03 | 2020-02-03 | 2020-05-12 | 59 | 9600 |  | 1335961 |  |  | 2020-09-18 | [5 empty] | N | N
NIMO | BWC Cowaselon Creek, LLC (BlueWave Solar) | 00265931 | 020 - Oneida | ONEIDA | 13461 | 36_20_50150 | ONEIDA 501 | Y | 5000 | 0 |  | CDG | N | 2020-03-12 | 2020-03-19 | 7 | 2020-03-19 | 2020-03-19 | 2020-03-19 | 0 | 2020-05-18 | 2020-05-18 | 2020-10-27 | 59 | 11400 |  | 1471048 | [8 empty] | N | N
NIMO | Mike Roach (RER Energy Group) | 00103308 | 020 - Oneida | CANASTOTA | 13032 | 36_20_50150 | ONEIDA 501 | N | 1836 |  |  | RNM | N | 2014-06-20 | 2014-07-01 | 8 | 2014-07-01 | 2014-07-01 | 2014-07-16 | 0 | 2015-09-01 | 2015-09-01 | 2016-02-16 | 120 | 25000 |  | 219550 |  |  | 2016-07-26 | 2017-08-10 | 2017-08-11 | 2017-08-11 | 2017-08-16 | 2017-08-16 | Y | N
NIMO | Craig Livingston (ReneSola Power Holdings LLC) | 00173136 | 020 - Oneida | MUNNSVILLE | 13409 | 36_20_50151 | ONEIDA 501 | N | 1925 |  |  | CDG | Y | 2018-09-19 | 2018-10-24 | 34.7556 | 2018-10-25 | 2018-10-25 | 2018-11-05 | 7 | 2019-02-15 | 2019-02-15 | 2019-09-09 | 59 | 15300 |  | 455953.93 |  |  | 2019-12-30 | 2020-01-02 |  |  |  |  | N | Y
NIMO | Margaret Campbell (EDF Renewables) | 00209907 | 020 - Oneida | ONEIDA | 13421 | 36_20_50151 | ONEIDA 501 | N | 5000 |  |  | CDG | Y | 2019-02-25 | 2019-03-04 | 6.9868 | 2019-03-05 | 2019-03-05 | 2019-03-19 | 10 | 2019-07-22 | 2019-07-22 | 2019-10-14 | 59 | 11600 |  | 134622 |  |  | 2019-10-28 | 2019-10-28 |  |  |  |  | N | Y
NIMO | Margaret Campbell (EDF - RE) | 00244042 | 020 - Oneida | ONEIDA | 13421 | 36_20_50153 | ONEIDA 501 | N | 5000 |  |  | CDG | N | 2019-07-19 | 2019-07-19 | 0 | 2019-07-22 | 2019-07-22 | 2019-07-24 | 2 | 2019-09-10 | 2019-09-10 | 2020-06-05 | 59 | 9900 |  | 277962 |  |  | 2020-10-14 | [5 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00241074 | 020 - Oneida | VERNON | 13476 | 36_20_50153 | ONEIDA 501 | N | 5000 |  |  | CDG | Y | 2019-06-27 | 2019-07-10 | 13.0708 | 2019-07-11 | 2019-07-11 | 2019-07-22 | 7 | 2019-09-05 | 2019-09-05 | 2020-04-10 | 52 | 9900 |  | 331346.25 |  |  | 2020-07-28 | [5 empty] | N | Y
NIMO | Chris Matthews (AES Distributed Energy, Inc.) | 00293453 | 020 - Oneida | VERNON | 13476 | 36_20_50155 | ONEIDA 501 | N | 3750 |  |  | CDG | N | 2020-06-22 | 2020-06-27 | 5 | 2020-06-27 | 2020-06-27 | 2020-06-27 | 0 | 2020-07-14 | 2020-07-14 |  |  | 10900 | [10 empty] | N | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00207957 | 020 - Oneida | VERONA | 13478 | 36_20_50155 | ONEIDA 501 | N | 2500 |  |  | CDG | Y | 2019-02-01 | 2019-02-12 | 10.7389 | 2019-02-13 | 2019-02-13 | 2019-02-19 | 3 | 2019-03-15 | 2019-03-15 | 2019-07-16 | 58 | 8600 |  | 181750 |  |  | 2019-11-01 | 2019-11-15 |  |  |  |  | N | Y
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00287857 | 020 - Oneida | VERONA | 13478 | 36_20_50156 | ONEIDA 501 | N | 3000 |  |  | CDG | N | 2020-04-23 | 2020-05-04 | 7 | 2020-05-04 | 2020-05-04 | 2020-05-04 | 0 | 2020-06-10 | 2020-06-10 | 2020-09-21 | 58 | 10900 |  | 677254 | [8 empty] | N | N
NIMO | Margaret Campbell (EDF Renewables) | 00209909 | 020 - Oneida | ONEIDA | 13421 | 36_20_50156 | ONEIDA 501 | N | 4000 |  |  | CDG | Y | 2019-02-25 | 2019-03-04 | 7.0396 | 2019-03-05 | 2019-03-05 | 2019-03-19 | 10 | 2019-07-22 | 2019-07-22 | 2019-10-14 | 59 | 11100 |  | 614438.75 |  |  | 2019-10-28 | 2019-10-28 |  |  |  |  | N | Y
NIMO | Christopher Stroud (Cipriani Energy Group Corp) | 00261056 | 014 - Fulton/Volney | OSWEGO | 13126 | 36_14_25455 | PALOMA 254 | N | 4750 |  |  | CDG | Y | 2019-11-18 | 2019-12-24 | 35.859 | 2019-12-24 | 2019-12-24 | 2019-12-24 | 0 | 2020-01-06 | 2020-01-06 | 2020-04-14 | 58 | 9400 |  | 1040379 |  |  | 2020-08-24 | [5 empty] | N | Y
NIMO | David Spotts (Summit Solar Capital, LLC) | 00253373 | 014 - Fulton/Volney | OSWEGO | 13126 | 36_14_25456 | PALOMA 254 | Y | 2500 | 5000 |  | CDG | Y | 2019-10-09 | 2019-10-21 | 11.6347 | 2019-10-22 | 2019-10-22 | 2019-11-06 | 11 | 2020-01-06 | 2020-01-06 | 2020-03-30 | 57 | 10600 |  | 309447 |  |  | 2020-04-23 | 2020-10-23 |  |  |  |  | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315542 | 015 - Oswego | OSWEGO | 13126 | 36_14_25458 | PALOMA 254 | N | 5000 |  |  | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 |  |  |  |  | 8800 | [10 empty] | N | N
NIMO | Adam Rowles (Saturn Power Corp.) | 00305428 | 011 - Syracuse | CANASTOTA | 13032 | 36_11_5027 | PERRYVILLE 50 | N | 5000 |  |  | CDG | N | 2020-08-17 | 2020-09-14 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-22 | 5 | 2020-10-13 | 2020-10-13 |  |  | 11300 | [10 empty] | N | N
NIMO | Kevin Bailey (High Peaks Solar/Sycaway Solar and W | 00190582 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51452 | PETERBORO 514 | N | 2900 |  |  | CDG | Y | 2018-07-17 | 2018-07-27 | 9.9396 | 2018-07-30 | 2018-07-30 | 2018-08-16 | 13 | 2018-11-15 | 2018-11-15 | 2019-03-06 | 59 | 13300 |  | 379162.19 |  |  | 2019-04-02 | [5 empty] | N | Y
NIMO | Kevin Bailey (High Peaks Solar/Sycaway Solar and W | 00172193 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51452 | PETERBORO 514 | N | 4400 |  |  | CDG | Y | 2018-03-26 | 2018-03-26 | 0 | 2018-04-12 | 2018-04-12 | 2018-04-24 | 8 | 2018-07-10 | 2018-07-10 | 2018-11-07 | 58 | 9700 |  | 559780.93 |  |  | 2019-02-12 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00291355 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51454 | PETERBORO 514 | N | 5000 |  |  | CDG | N | 2020-05-26 | 2020-06-02 | 5 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 0 | 2020-07-21 | 2020-07-21 |  |  | 8600 | [10 empty] | N | N
NIMO | Joe Fiori (Nexamp) | 00173939 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51454 | PETERBORO 514 | Y | 5000 | 5000 |  | CDG | Y | 2018-04-19 | 2018-04-19 | 0 | 2018-05-01 | 2018-05-01 | 2018-05-17 | 12 | 2018-08-01 | 2018-08-01 | 2019-01-25 | 69 | 9700 |  | 408826.79 |  |  | 2019-03-19 | 2019-04-10 | 2019-05-01 | 2020-03-23 |  |  | N | Y
NIMO | Bogdan Dinu (BW Solar Holding Inc.) | 00297264 | 020 - Oneida | ONEIDA | 13421 | 36_20_51455 | PETERBORO 514 | N | 5000 |  |  | CDG | N | 2020-06-24 | 2020-06-29 | 3 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 0 |  |  |  |  | 9500 | [10 empty] | N | N
NIMO | William Jurith (HELIOS LENOX 1 LLC) | 00170433 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51455 | PETERBORO 514 | Y | 1980 | 2000 |  | CDG | Y | 2018-02-27 | 2018-02-27 | 0 | 2018-02-28 | 2018-02-28 | 2018-03-10 | 8 | 2018-04-06 | 2018-04-06 | 2018-05-11 | 4 | 9700 |  | 206166 |  |  | 2018-09-28 | 2019-02-21 | 2018-10-03 | 2019-02-21 |  |  | N | Y
NIMO | Joe Fiori (Nexamp) | 00173942 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51456 | PETERBORO 514 | Y | 5000 | 5000 |  | CDG | Y | 2018-04-19 | 2018-04-19 | 0 | 2018-05-01 | 2018-05-01 | 2018-05-17 | 12 | 2018-08-01 | 2018-08-01 | 2019-01-25 | 69 | 9700 |  | 158370 |  |  | 2019-03-19 | 2019-04-10 | 2019-05-01 |  |  |  | N | Y
NIMO | Joe Fiori (Nexamp Solar LLC) | 00199116 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51457 | PETERBORO 514 | Y | 3258 | 788 |  | CDG | Y | 2018-10-23 | 2018-10-29 | 5.8382 | 2018-10-30 | 2018-10-30 | 2018-11-01 | 2 | 2018-11-28 | 2018-11-28 | 2019-08-22 | 55 | 12200 |  | 300722 |  |  | 2020-01-10 | 2020-01-21 | 2020-07-02 | 2020-08-13 |  |  | N | Y
NIMO | John Vigants (Bright Solar LLC) | 00316828 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51458 | PETERBORO 514 | N | 5000 |  |  | CDG | N | 2020-10-13 | 2020-10-19 | 4 | 2020-10-20 | 2020-10-20 | 2020-10-21 | 1 |  |  |  |  | 10100 | [10 empty] | N | N
NIMO | Jordana Jusidman (groSolar) | 00102114 | 020 - Oneida | ONEIDA | 13421 | 36_20_51458 | PETERBORO 514 | N | 1400 |  |  | RNM | N | 2016-06-22 | 2016-07-01 | 4 | 2016-07-01 | 2016-07-01 | 2016-07-08 | 0 | 2016-10-18 | 2016-10-18 | 2017-01-03 | 55 | 26200 |  | 159600 |  |  | 2017-05-03 | 2017-10-16 | 2017-08-01 | 2017-12-19 | 2017-12-19 | 2017-12-19 | Y | N
NIMO | William Jurith (HELIOS LENOX 1 LLC) | 00170444 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51458 | PETERBORO 514 | Y | 3000 | 3000 |  | CDG | Y | 2018-02-21 | 2018-02-21 | 0 | 2018-02-28 | 2018-02-28 | 2018-03-11 | 8 | 2018-04-06 | 2018-04-06 | 2018-05-17 | 8 | 9700 |  | 235656 |  |  | 2018-09-28 | 2019-02-21 | 2018-10-03 | 2019-02-21 |  |  | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00291077 | 011 - Syracuse | PHOENIX | 13135 | 36_11_5164 | PHOENIX 51 | Y | 2500 | 0 |  | CDG | N | 2020-06-18 | 2020-06-23 | 3 | 2020-06-24 | 2020-06-24 | 2020-06-24 | 0 | 2020-09-09 | 2020-09-09 |  |  | 11400 | [10 empty] | N | N
NIMO | Andy Isrealson (Convergent Energy Solutions New Yo | 00242287 | 011 - Syracuse | NORTH SYRACUSE | 13212 | 36_11_5952 | PINE GROVE 59 | Y | 5000 | 4999.98 |  | CDG | Y | 2019-07-08 | 2019-08-02 | 25.0139 | 2019-08-05 | 2019-08-05 | 2019-08-12 | 5 | 2019-08-28 | 2019-08-28 | 2019-12-05 | 58 | 9900 |  | 1106127 |  |  | 2019-12-03 | 2019-12-03 |  |  |  |  | N | Y
NIMO | Lluis Torrent (CAERO) | 00321432 | 011 - Syracuse | CICERO | 13039 | 36_11_5956 | PINE GROVE 59 | N | 5000 |  |  | CDG | N | 2020-11-25 | 2020-12-04 | 5 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 0 |  |  |  |  | 8800 | [10 empty] | N | N
NIMO | Andy Isrealson (Convergent Energy Solutions New Yo | 00245613 | 011 - Syracuse | CICERO | 13039 | 36_11_5958 | PINE GROVE 59 | Y | 5000 | 4999.98 |  | CDG | Y | 2019-07-30 | 2019-08-09 | 10.2146 | 2019-08-12 | 2019-08-12 | 2019-08-13 | 1 | 2019-08-28 | 2019-08-28 | 2019-12-12 | 58 | 9300 |  | 981363.82 |  |  | 2019-12-03 | 2019-12-03 |  |  |  |  | N | Y
NIMO | Greg Hering (NB Development LLC) | 00261672 | 017 - Utica | POLAND | 13431 | 36_17_62257 | POLAND 622 | Y | 5000 | 5000 |  | CDG | Y | 2019-10-24 | 2019-11-06 | 12.8243 | 2019-11-07 | 2019-11-07 | 2019-11-13 | 3 | 2019-11-21 | 2019-11-21 | 2020-03-18 | 58 | 11400 |  | 818727 |  |  | 2020-08-25 | [5 empty] | N | Y
NIMO | Teddy Epstein (Novis Renewables) | 00273261 | 017 - Utica | COLD BROOK | 13324 | 36_17_62258 | POLAND 622 | N | 5000 |  |  | CDG | Y | 2020-01-15 | 2020-02-07 | 22.7944 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 0 | 2020-02-12 | 2020-02-12 | 2020-06-08 | 59 | 9400 |  | 689355.43 |  |  | 2020-10-14 | [5 empty] | N | Y
NIMO | Brent Grundberg (East Side Solar Holdings LLC) | 00192130 | 041 - Ticonderoga | MORIAH | 12960 | 36_41_38552 | PORT HENRY 385 | N | 5000 |  |  | CDG | Y | 2018-10-11 | 2018-10-22 | 10.8833 | 2018-10-23 | 2018-10-23 | 2018-10-26 | 3 | 2019-01-23 | 2019-01-23 | 2019-05-17 | 67 | 13300 |  | 627747.38 |  |  | 2019-11-15 | 2019-11-15 |  |  |  |  | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00284817 | 041 - Ticonderoga | MORIAH | 12960 | 36_41_38552 | PORT HENRY 385 | N | 5000 |  |  | CDG | N | 2020-04-16 | 2020-04-24 | 6 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 0 | 2020-04-28 | 2020-04-28 | 2020-08-22 | 59 | 9800 |  | 908475 | [8 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00321349 | 023 - Lowville | BOONVILLE | 13309 | 36_23_75563 | PORT LEYDEN 755 | N | 5000 |  |  | CDG | N | 2020-11-06 | 2020-11-16 | 5 | 2020-11-16 | 2020-11-16 | 2020-11-16 | 0 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | Solar City | 00102643 | 031 - Troy | CLIFTON PARK | 12065 | 36_31_41352 | PROSPECT HILL 413 | N | 1008 |  |  | RNM | N | 2014-08-19 | 2014-09-10 | 2 | 2014-09-10 | 2014-09-10 | 2014-09-16 | 0 | 2015-01-02 | 2015-01-02 | 2015-03-27 | 60 | 13700 | [8 empty] | 2017-06-19 | 2017-06-19 | Y | N
NIMO | John Vigants (Bright Solar LLC) | 00327615 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_8963 | RANSOMVILLE 89 | N | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-08 | 5 | 2020-12-08 | 2020-12-08 | 2020-12-09 | 0 |  |  |  |  | 10700 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00328476 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_8963 | RANSOMVILLE 89 | N | 5000 |  |  | CDG | N | 2020-11-30 | 2020-12-07 | 5 | 2020-12-07 | 2020-12-07 | 2020-12-07 | 0 |  |  |  |  | 11700 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00290750 | 024 - Saranac Lake | RAYBROOK | 12977 | 36_24_83952 | RAYBROOK 839 | N | 5000 |  |  | CDG | N | 2020-05-20 | 2020-05-28 | 5 | 2020-05-28 | 2020-05-28 | 2020-05-28 | 0 | 2020-07-01 | 2020-07-01 | 2020-11-16 | 59 | 9400 |  | 689151 | [8 empty] | N | N
NIMO | Jennifer hoeffner (Monolith Solar Assoc. LLC) | 00170011 | 031 - Troy | TROY | 12180 | 36_31_33457 | REYNOLDS RD 334 | N | 2000 |  |  | RNM | N | 2018-02-05 | 2018-02-05 | 0 | 2018-03-21 | 2018-03-21 | 2018-04-04 | 9 | 2018-06-07 | 2018-06-07 | 2018-08-24 | 55 | 14300 |  | 317954.38 |  |  | 2019-03-25 | 2019-04-03 |  |  | 2020-12-10 | 2020-12-10 | Y | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00316797 | 005 - Avon | HEMLOCK | 14466 | 36_05_3251 | RICHMOND 32 | N | 5000 |  |  | CDG | N | 2020-10-05 | 2020-10-12 | 5 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-12-14 | 2020-12-14 |  |  | 10900 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00317416 | 005 - Avon | LIVONIA | 14487 | 36_05_3253 | RICHMOND 32 | N | 5000 |  |  | CDG | N | 2020-10-07 | 2020-10-12 | 3 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-10-28 | 2020-10-28 |  |  | 9400 | [10 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power (Richmond) LLC.) | 00238572 | 005 - Avon | HONEOYE | 14471 |  | RICHMOND 32 | N | 5000 |  |  | CDG | Y | 2019-06-18 | 2019-08-19 | 61.9382 | 2019-08-20 | 2019-08-20 | 2019-08-27 | 5 | 2019-10-28 | 2019-10-28 | 2020-03-06 | 56 | 9400 |  | 567400.02 |  |  | 2020-07-20 | [5 empty] | N | Y
NIMO | Craig Livingston (Renesola Power Holdings LLC) | 00277358 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15454 | ROBERTS RD 154 | N | 3649.5 |  |  | CDG | N | 2020-02-20 | 2020-03-02 | 9 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 0 | 2020-06-18 | 2020-06-18 | 2020-09-11 | 57 | 8600 |  | 692356 | [8 empty] | N | N
NIMO | Elie Schecter (OurGeneration LLC) | 00299896 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15454 | ROBERTS RD 154 | Y | 5000 | 5000 |  | CDG | N | 2020-07-29 | 2020-08-05 | 5 | 2020-08-06 | 2020-08-06 | 2020-08-10 | 2 | 2020-10-26 | 2020-10-26 |  |  | 9100 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables LLC) | 00328120 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_62370 | ROCK CITY 623 | N | 5000 |  |  | CDG | N | 2020-11-30 | 2020-12-03 | 3 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00325765 | 039 - Saratoga | ROCK CITY FALLS | 12863 | 36_39_40415 | ROCK CITY FALLS 404 | N | 5000 |  |  | CDG | N | 2020-11-17 | 2020-11-30 | 7 | 2020-11-30 | 2020-11-30 | [17 empty] | N | N
NIMO | Bradley Davis (RENESOLA) | 00302519 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N | 4200 |  |  | CDG | N | 2020-07-30 | 2020-08-05 | 4 | 2020-08-05 | 2020-08-05 | 2020-08-05 | 0 | 2020-10-12 | 2020-10-12 |  |  | 9000 | [10 empty] | N | N
NIMO | groSolar | 00104500 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N | 1978 |  |  | RNM | N | 2014-08-21 | 2014-08-21 | 0 | 2014-08-21 |  |  |  | 2015-04-29 | 2015-04-29 | 2015-07-30 | 66 | 15100 |  | 97945 | [6 empty] | 2016-10-24 | 2016-10-24 | Y | N
NIMO | John Vigants (Bright Solar LLC) | 00308723 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N | 5000 |  |  | CDG | N | 2020-08-27 | 2020-09-04 | 6 | 2020-09-04 | 2020-09-04 | 2020-09-04 | 0 | 2020-10-12 | 2020-10-12 |  |  | 10100 | [10 empty] | N | N
NIMO | Jordana Jusidman (groSolar) | 00100936 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N | 1997.6 |  |  | RNM | N | 2014-12-19 | 2015-01-15 | 6 | 2015-01-15 | 2015-01-15 | 2015-02-10 | 0 | 2015-08-05 | 2015-08-05 | 2015-10-26 | 58 | 20000 |  | 167126 |  |  | 2016-04-01 | 2017-08-10 | 2017-06-02 | 2017-08-10 | 2017-09-04 | 2017-09-04 | Y | N
NIMO | John Vigants (Bright Solar LLC) | 00315282 | 018 - Rome | ROME | 13440 | 36_18_76252 | ROME 762 | N | 5000 |  |  | CDG | N | 2020-09-26 | 2020-10-07 | 8 | 2020-10-08 | 2020-10-08 | 2020-10-22 | 10 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00244500 | 018 - Rome | ROME | 13340 | 36_18_76257 | ROME 762 | N | 4840 |  |  | CDG | Y | 2019-07-29 | 2019-08-09 | 10.6264 | 2019-08-12 | 2019-08-12 | 2019-08-13 | 1 | 2019-08-20 | 2019-08-20 | 2019-11-14 | 59 | 9000 |  | 292449.65 |  |  | 2019-12-02 | 2020-05-29 |  |  |  |  | N | Y
NIMO | AES Distributed Energy, Inc. | 00100872 | 018 - Rome | ROME | 13440 | 36_18_76258 | ROME 762 | N | 2000 |  |  | RNM | N | 2015-05-18 | 2015-06-01 | 8 | 2015-06-01 | 2015-06-01 | 2015-06-30 | 0 | 2015-10-23 | 2015-10-23 | 2016-05-10 | 142 | 25000 |  | 179250 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-24 | 2018-05-31 | 2018-06-29 | 2018-06-29 | Y | N
NIMO | Borrego Solar Systems, Inc | 00103305 | 017 - Utica | ROME | 13440 | 36_18_76258 | ROME 762 | N | 1899 |  |  | RNM | N | 2014-06-20 | 2014-06-20 | 0 | 2014-06-20 | 2014-06-20 | 2014-07-14 | 0 | 2014-09-16 | 2014-09-16 | 2014-12-05 | 58 | 25000 |  | 185970 | [5 empty] | 2015-12-23 | 2015-12-21 | 2015-12-21 | Y | N
NIMO | Borrego Solar Systems, Inc | 00103304 | 017 - Utica | ROME | 13440 | 36_18_76258 | ROME 762 | N | 1910 |  |  | RNM | N | 2014-06-20 | 2014-06-20 | 0 | 2014-06-20 | 2014-06-20 | 2014-07-18 | 0 | 2014-09-16 | 2014-09-16 | 2014-12-05 | 58 | 25000 |  | 198560 | [5 empty] | 2015-12-22 | 2015-12-21 | 2015-12-21 | Y | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00315524 | 018 - Rome | ROME | 13440 | 36_18_76258 | ROME 762 | N | 5000 |  |  | CDG | N | 2020-09-28 | 2020-10-05 | 4 | 2020-10-19 | 2020-10-19 | 2020-10-26 | 5 |  |  |  |  | 10100 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00279596 | 018 - Rome | ROME | 13440 | 36_18_76258 | ROME 762 | N | 5000 |  |  | CDG | N | 2020-02-18 | 2020-03-02 | 10 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 0 | 2020-04-07 | 2020-04-07 | 2020-08-12 | 59 | 8600 |  | 343353 | [8 empty] | N | N
NIMO | Theresa Baker (General Electric International Inc) | 00186064 | 032 - Schenectady | SCHENECTADY | 12308 | 36_32_13755 | ROSA RD 137 | N | 1000 |  |  | CDG | Y | 2018-06-05 | 2018-06-05 | 0 | 2018-07-02 | 2018-07-02 | 2018-07-13 | 8 | 2018-08-01 | 2018-08-01 | 2019-01-04 | 55 | 12200 |  | 96649.49 |  |  | 2019-01-30 | 2019-07-19 | 2019-01-31 | 2019-07-19 | 2020-03-27 | 2020-03-27 | Y | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00301193 | 032 - Schenectady | PATTERSONVILLE | 12137 | 36_32_13853 | ROTTERDAM 138 | N | 5000 |  |  | CDG | N | 2020-08-25 | 2020-09-14 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-22 | 5 | 2020-11-02 | 2020-11-02 |  |  | 11700 | [10 empty] | N | N
NIMO | Theresa Baker (Distributed Solar Development, LLC) | 00186075 | 032 - Schenectady | SCOTIA | 12302 | 36_32_13853 | ROTTERDAM 138 | Y | 2475 | 2500 |  | CDG | Y | 2018-06-07 | 2018-06-07 | 0 | 2018-06-19 | 2018-06-19 | 2018-07-03 | 10 | 2018-07-30 | 2018-07-30 | 2019-01-14 | 58 | 14000 |  | 820712 |  |  | 2019-02-01 | 2019-07-19 | 2019-01-31 | 2019-07-19 |  |  | N | Y
NIMO | Theresa Baker (Distributed Solar Development, LLC) | 00186117 | 032 - Schenectady | PATTERSONVILLE | 12137 | 36_32_13853 | ROTTERDAM 138 | Y | 2500 | 2500 |  | CDG | Y | 2018-06-07 | 2018-06-07 | 0 | 2018-06-29 | 2018-06-29 | 2018-07-17 | 11 | 2018-09-26 | 2018-09-26 | 2019-04-18 | 35 | 17900 |  | 550765 |  |  | 2019-05-16 | [5 empty] | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00235255 | 032 - Schenectady | SCHENECTADY | 12303 | 36_32_38154 | RUTH RD 381 | Y | 4980 | 5000 |  | CDG | Y | 2019-06-10 | 2019-06-18 | 7.9076 | 2019-06-19 | 2019-06-19 | 2019-07-02 | 9 | 2019-09-09 | 2019-09-09 | 2019-12-18 | 40 | 9400 |  | 973744 |  |  | 2020-02-05 | 2020-02-05 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00252627 | 032 - Schenectady | SCHENECTADY | 12303 | 36_32_38154 | RUTH RD 381 | Y | 5000 | 4500 |  | CDG | Y | 2019-09-09 | 2019-09-20 | 10.7424 | 2019-09-23 | 2019-09-23 | 2019-10-07 | 10 | 2020-01-28 | 2020-01-28 | 2020-04-21 | 59 | 9400 |  | 3264903 |  |  | 2020-08-28 | [5 empty] | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00318877 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_76462 | S. PHILADELPHIA 764 | N | 4500 |  |  | CDG | N | 2020-10-14 | 2020-10-22 | 6 | 2020-10-23 | 2020-10-23 | 2020-11-03 | 7 | 2020-12-14 | 2020-12-14 |  |  | 11300 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00320938 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_76462 | S. PHILADELPHIA 764 | N | 5000 |  |  | CDG | N | 2020-10-30 | 2020-11-10 | 7 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 0 | 2020-12-09 | 2020-12-09 |  |  | 11300 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00304916 | 019 - Herkimer | MOHAWK | 13407 | 36_19_61452 | S. WASHINGTON 614 | N | 5000 |  |  | CDG | N | 2020-08-05 | 2020-08-18 | 9 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-10-15 | 2020-10-15 |  |  | 9400 | [10 empty] | N | N
NIMO | Andy Cerrato (DG New York CS II, LLC) | 00307699 | 010 - Olean | WELLSVILLE | 14895 | 36_10_2363 | S. WELLSVILLE 23 | Y | 5000 | 8494.46 |  | CDG | N | 2020-09-16 | 2020-10-23 | 5 | 2020-10-26 | 2020-10-26 | 2020-10-27 | 1 |  |  |  |  | 12200 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00317577 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67852 | SALISBURY 678 | N | 4975 |  |  | CDG | N | 2020-10-23 | 2020-11-02 | 6 | 2020-11-03 | 2020-11-03 | 2020-11-09 | 4 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Mrunmayee Gujar (Nexamp) | 00165199 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67852 | SALISBURY 678 | Y | 2000 | 2000 |  | CDG | Y | 2017-12-12 | 2017-12-12 | 0 | 2017-12-15 | 2017-12-15 | 2018-01-04 | 13 | 2018-03-20 | 2018-03-20 | 2018-06-11 | 56 | 15600 |  | 481533 |  |  | 2018-09-05 | 2018-10-16 |  |  | 2020-10-21 | 2020-10-21 | Y | Y
NIMO | Michael Cucchiara (Nexamp) | 00108713 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67853 | SALISBURY 678 | Y | 1980 | 2000 |  | CDG | Y | 2017-09-19 | 2017-09-19 | 0 | 2017-09-28 | 2017-09-28 | 2017-10-09 | 7 | 2017-12-06 | 2017-12-06 | 2018-04-05 | 53 | 16800 |  | 697929 |  |  | 2018-06-28 | 2019-09-27 | 2019-07-05 | 2019-09-27 | 2020-09-11 | 2020-09-11 | Y | Y
NIMO | Kyle Talbot (DynaSolar DevCo) | 00319866 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67856 | SALISBURY 678 | N | 4980 |  |  | RNM | Y | 2020-10-22 | 2020-10-29 | 5 | 2020-10-29 | 2020-10-29 | 2020-10-29 | 0 |  |  |  |  | 9400 | [10 empty] | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00253674 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67857 | SALISBURY 678 | Y | 5000 | 0 |  | CDG | Y | 2019-09-13 | 2019-09-25 | 8 | 2019-09-26 | 2019-09-26 | 2019-09-30 | 2 | 2019-10-16 | 2019-10-16 | 2020-06-19 | 59 | 9900 |  | 511679 |  |  | 2020-10-30 | [5 empty] | N | Y
NIMO | Timothy Ahrens (CleanChoice Energy) | 00315492 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67857 | SALISBURY 678 | N | 5000 |  |  | CDG | N | 2020-09-29 | 2020-10-08 | 6 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | High Peaks Solar/Sycaway Solar and Wind | 00102989 | 016 - Pulaski | SANDY CREEK | 13145 | 36_16_6651 | SANDY CREEK 66 | N | 1980 |  |  | CDG | Y | 2017-01-29 | 2017-02-01 | 2 | 2017-02-01 | 2017-02-01 | 2017-02-15 | 10 | 2017-03-29 | 2017-03-29 | 2017-06-01 | 34 | 18700 |  | 593032 |  |  | 2018-02-27 | 2018-10-01 | 2018-09-28 | 2018-10-01 | 2020-05-08 | 2020-05-08 | Y | Y
NIMO | Kayti Curtis (Cypress Creek Renewables LLC) | 00101847 | 016 - Pulaski | SANDY CREEK | 13145 | 36_16_6651 | SANDY CREEK 66 | N | 2000 |  |  | CDG | N | 2016-08-30 | 2016-09-08 | 6 | 2016-09-08 | 2016-09-08 | 2016-09-12 | 2 | 2017-01-10 | 2017-01-10 | 2017-04-06 | 60 | 20000 |  | 593032 |  |  | 2017-06-30 | 2017-12-07 | 2017-12-08 | 2017-12-08 | 2018-12-28 | 2018-12-28 | Y | N
NIMO | Alexander McMenemy (Solar Generation Projects LLC) | 00242504 | 016 - Pulaski | SANDY CREEK | 13145 | 36_16_6652 | SANDY CREEK 66 | N | 2150 |  |  | CDG | Y | 2019-08-06 | 2019-08-15 | 9.0333 | 2019-08-16 | 2019-08-16 | 2019-08-28 | 8 | 2019-11-01 | 2019-11-01 | 2020-04-03 | 56 | 10000 |  | 400230 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Giovanni Maruca (White River Solar, LLC) | 00168774 | 030 - Albany | CASTLETON | 12033 | 36_30_45151 | SCHODACK 451 | Y | 4980 | 4980 |  | CDG | Y | 2018-01-11 | 2018-01-11 | 0 | 2018-01-23 | 2018-01-23 | 2018-02-06 | 10 | 2018-04-20 | 2018-04-20 | 2018-10-24 | 59 | 16800 |  | 447631.91 |  |  | 2019-04-23 | 2019-07-11 |  |  |  |  | N | Y
NIMO | Michael Frateschi (TJA Solar, LLC) | 00168448 | 030 - Albany | CASTLETON | 12033 | 36_30_45151 | SCHODACK 451 | N | 5000 |  |  | CDG | Y | 2018-04-03 | 2018-04-03 | 0 | 2018-04-19 | 2018-04-19 | 2018-05-02 | 9 | 2018-08-10 | 2018-08-10 | 2019-03-19 | 55 | 13300 |  | 1039234 |  |  | 2019-09-06 | 2019-09-12 |  |  |  |  | N | Y
NIMO | Tory Hanna (Davis Hill Development) | 00306915 | 030 - Albany | CASTLETON | 12033 | 36_30_45152 | SCHODACK 451 | N | 4875 |  |  | CDG | N | 2020-09-02 | 2020-09-22 | 5 | 2020-09-23 | 2020-09-23 | 2020-09-29 | 4 | 2020-10-14 | 2020-10-14 |  |  | 9400 | [10 empty] | N | N
NIMO | Giovanni Maruca (Elmbrook Solar, LLC) | 00185060 | 030 - Albany | CASTLETON | 12033 | 36_30_45153 | SCHODACK 451 | Y | 5000 | 4500 |  | CDG | Y | 2018-05-11 | 2018-05-11 | 0 | 2018-05-31 | 2018-05-31 | 2018-06-15 | 11 | 2018-09-07 | 2018-09-07 | 2018-12-05 | 58 | 12200 |  | 521296.02 |  |  | 2019-04-23 | 2019-07-11 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (New PowerCo Inc.) | 00208829 | 030 - Albany | CASTLETON | 12033 | 36_30_45153 | SCHODACK 451 | N | 4980 |  |  | CDG | Y | 2019-02-08 | 2019-02-21 | 13.0757 | 2019-02-22 | 2019-02-22 | 2019-03-04 | 6 | 2019-05-15 | 2019-05-15 | 2019-08-27 | 56 | 9400 |  | 1000722 |  |  | 2020-01-22 | 2020-01-22 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171646 | 037 - Cobleskill | SCHOHARIE | 12157 | 36_37_23451 | SCHOHARIE 234 | N | 5000 |  |  | CDG | Y | 2018-03-15 | 2018-03-15 | 0 | 2018-03-26 | 2018-03-26 | 2018-04-06 | 9 | 2018-06-06 | 2018-06-06 | 2018-08-17 | 51 | 12200 |  | 695061 |  |  | 2019-04-03 | [5 empty] | N | Y
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00193998 | 037 - Cobleskill | BERNE | 12023 | 36_37_23452 | SCHOHARIE 234 | N | 4250 |  |  | CDG | Y | 2018-08-30 | 2018-09-14 | 14.8326 | 2018-09-17 | 2018-09-17 | 2018-10-04 | 13 | 2019-07-12 | 2019-07-12 | 2019-09-24 | 51 | 17400 |  | 529905.64 |  |  | 2020-04-14 | 2020-10-06 |  |  |  |  | N | Y
NIMO | Elie Schecter (OurGeneration LLC) | 00313312 | 017 - Utica | FRANKFORT | 13340 | 36_17_66352 | SCHUYLER 663 | N | 5000 |  |  | CDG | N | 2020-09-17 | 2020-10-03 | 5 | 2020-10-05 | 2020-10-05 | 2020-10-22 | 13 |  |  |  |  | 8600 | [10 empty] | N | N
NIMO | Kyle Talbot (DynaSolar DevCo) | 00316693 | 017 - Utica | FRANKFORT | 13340 | 36_17_66352 | SCHUYLER 663 | N | 4980 |  |  | RNM | Y | 2020-10-15 | 2020-10-16 | 2 | 2020-10-19 | 2020-10-19 | 2020-10-28 | 7 |  |  |  |  | 9400 | [10 empty] | N | Y
NIMO | Kyle Talbot (DynaSolar DevCo) | 00316700 | 017 - Utica | FRANKFORT | 13340 | 36_17_66354 | SCHUYLER 663 | N | 4980 |  |  | RNM | Y | 2020-10-15 | 2020-10-22 | 5 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 |  |  |  |  | 8800 | [10 empty] | N | Y
NIMO | Margaret Campbell (EDF Renewables) | 00279701 | 017 - Utica | FRANKFORT | 13340 | 36_17_66356 | SCHUYLER 663 | N | 5000 |  |  | CDG | N | 2020-02-26 | 2020-03-09 | 9 | 2020-03-09 | 2020-03-09 | 2020-03-09 | 0 | 2020-05-04 | 2020-05-04 | 2020-10-20 | 59 | 9000 |  | 499948 | [8 empty] | N | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00273422 | 017 - Utica | UTICA | 13502 | 36_17_66356 | SCHUYLER 663 | Y | 4500 | 3697.5 |  | CDG | N | 2020-01-15 | 2020-01-30 | 14.7708 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 0 | 2020-02-27 | 2020-02-27 | 2020-06-25 | 59 | 8600 |  | 328500 |  |  | 2020-12-03 | [5 empty] | N | N
NIMO | Kyle Talbot (DynaSolar DevCo) | 00285039 | 019 - Herkimer | HERKIMER | 13350 | SCHUYLER-VALLEY #24 | SCHUYLER 663 | N | 996 |  |  | RNM | Y | 2020-04-08 | 2020-04-17 | 7 | 2020-04-17 | 2020-04-17 | 2020-04-17 | 0 | 2020-05-08 | 2020-05-08 |  |  | 11300 | [10 empty] | N | Y
NIMO | Kyle Talbot (DynaSolar DevCo) | 00284807 | 019 - Herkimer | HERKIMER | 13350 | SCHUYLER-VALLEY #24 | SCHUYLER 663 | N | 3154 |  |  | RNM | Y | 2020-04-03 | 2020-04-10 | 5 | 2020-04-10 | 2020-04-10 | 2020-04-10 | 0 | 2020-05-08 | 2020-05-08 | 2020-11-16 | 58 | 11300 |  | 469329 | [8 empty] | N | Y
NIMO | NEXTera Energy Resources | 00103259 | 030 - Albany | SELKIRK | 12158 | 36_30_14951 | SELKIRK 149 | N | 957 |  |  | RNM | N | 2014-06-24 | 2014-06-24 | 0 | 2014-06-24 | 2014-06-24 | 2014-07-29 | 2 | 2014-09-08 | 2014-09-08 | 2014-09-08 | 0 | 10000 | [8 empty] | 2016-03-08 | 2016-03-08 | Y | N
NIMO | NEXTera Energy Resources | 00103260 | 030 - Albany | SELKIRK | 12158 | 36_30_14951 | SELKIRK 149 | N | 1791 |  |  | RNM | N | 2014-06-24 | 2014-06-24 | 0 | 2014-06-24 | 2014-06-24 | 2014-07-29 | 2 | 2014-09-08 | 2014-09-08 | 2015-01-28 | 102 | 25000 |  | 185470 | [6 empty] | 2016-03-08 | 2016-03-08 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00197571 | 030 - Albany | SELKIRK | 12158 | 36_30_14952 | SELKIRK 149 | N | 5000 |  |  | CDG | Y | 2018-10-19 | 2018-12-12 | 53.9521 | 2018-12-13 | 2018-12-13 | 2018-12-21 | 6 | 2019-06-17 | 2019-06-17 | 2019-10-29 | 57 | 9800 |  | 173220.91 |  |  | 2020-02-28 | 2020-03-02 |  |  |  |  | N | Y
NIMO | Josh katz (Onyx Development Grou) | 00101079 | 037 - Cobleskill | SHARON SPRINGS | 13459 | 36_37_36351 | SHARON 363 | N | 1980 |  |  | RNM | N | 2015-03-17 | 2015-03-17 | 0 | 2015-05-13 | 2015-05-13 | 2015-06-29 | 0 | 2015-09-28 | 2015-09-28 | 2016-01-22 | 84 | 35000 |  | 755094 |  |  | 2017-01-27 |  |  | 2018-03-01 | 2018-03-29 | 2018-03-29 | Y | N
NIMO | Dallas Manson (Nexamp) | 00253007 | 037 - Cobleskill | SHARON SPRINGS | 13459 | 36_37_36352 | SHARON 363 | N | 4750 |  |  | CDG | N | 2019-09-18 | 2019-11-07 | 49.9271 | 2019-11-08 | 2019-11-08 | 2019-11-12 | 1 | 2019-12-20 | 2019-12-20 | 2020-11-18 | 58 | 9000 |  | 1862887 | [8 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00284814 | 037 - Cobleskill | SHARON SPRINGS | 13459 | 36_37_36352 | SHARON 363 | N | 3590 |  |  | CDG | N | 2020-05-06 | 2020-05-12 | 4 | 2020-05-12 | 2020-05-12 | 2020-05-12 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-28 | 59 | 9000 |  | 1607067 | [8 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316692 | 003 - Niagara Falls | SANBORN | 14132 | 36_03_7652 | SHAWNEE 76 | N | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-26 | 2020-10-26 | 2020-11-03 | 6 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316695 | 003 - Niagara Falls | SANBORN | 14132 | 36_03_7652 | SHAWNEE 76 | N | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-26 | 2020-10-26 | 2020-11-03 | 6 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00252179 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_7652 | SHAWNEE 76 | N | 5000 |  |  | CDG | N | 2019-09-05 | 2019-10-01 | 26.1549 | 2019-10-02 | 2019-10-02 | 2019-10-20 | 13 | 2019-11-07 | 2019-11-07 | 2020-10-07 | 59 | 9100 |  | 1324438 | [8 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00278662 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_7654 | SHAWNEE 76 | N | 3300 |  |  | CDG | N | 2020-04-15 | 2020-09-02 | 101 | 2020-09-03 | 2020-09-03 | 2020-09-14 | 6 | 2020-11-04 | 2020-11-04 |  |  | 10900 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00252698 | 001 - Buffalo | SANBORN | 14120 | 36_03_7655 | SHAWNEE 76 | Y | 5000 | 5000 |  | CDG | Y | 2019-09-13 | 2019-09-26 | 13.1285 | 2019-09-27 | 2019-09-27 | 2019-10-15 | 12 | 2019-10-22 | 2019-10-22 | 2020-02-12 | 57 | 10100 |  | 1165465 |  |  | 2020-06-18 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS II, LLC) | 00283660 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_7656 | SHAWNEE 76 | Y | 5000 | 0 |  | CDG | N | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 0 | 2020-04-10 | 2020-04-10 | 2020-09-02 | 57 | 10300 |  | 12810405 | [8 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America) | 00296735 | 001 - Buffalo | SANBORN | 14132 | 36_03_7656 | SHAWNEE 76 | Y | 4000 | 0 |  | CDG | N | 2020-06-18 | 2020-06-25 | 5 | 2020-06-26 | 2020-06-26 | 2020-06-29 | 1 | 2020-08-25 | 2020-08-25 |  |  | 10300 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315549 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7653 | SHELBY 76 | Y |  | 0 | 5000 | CDG | N | 2020-10-30 | 2020-11-04 | 3 | 2020-11-04 | 2020-11-04 | 2020-11-04 | 0 |  |  |  |  | 13000 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315550 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7653 | SHELBY 76 | Y |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 11200 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00188910 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7654 | SHELBY 76 | N | 3500 |  |  | CDG | Y | 2018-06-27 | 2018-06-27 | 0 | 2018-07-09 | 2018-07-09 | 2018-07-27 | 14 | 2018-10-26 | 2018-10-26 | 2019-01-28 | 52 | 12500 |  | 847650 |  |  | 2019-02-08 |  |  |  | 2020-05-29 | 2020-05-29 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00189798 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7654 | SHELBY 76 | N | 5000 |  |  | CDG | Y | 2018-07-16 | 2018-07-23 | 6.7965 | 2018-07-24 | 2018-07-24 | 2018-08-02 | 7 | 2018-09-18 | 2018-09-18 | 2019-01-28 | 59 | 13300 |  | 294335 |  |  | 2019-02-11 |  |  |  | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00247694 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7655 | SHELBY 76 | Y | 3000 | 2000 |  | CDG | Y | 2019-08-13 | 2019-08-21 | 7.8486 | 2019-08-22 | 2019-08-22 | 2019-08-27 | 3 | 2019-09-05 | 2019-09-05 | 2020-01-15 | 59 | 9900 |  | 395728 |  |  | 2020-05-26 | 2020-12-01 |  |  |  |  | N | Y
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00240295 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7655 | SHELBY 76 | Y | 5000 | 4000 |  | CDG | Y | 2019-08-01 | 2019-08-14 | 12.8319 | 2019-08-15 | 2019-08-15 | 2019-08-21 | 4 | 2019-08-30 | 2019-08-30 | 2019-12-11 | 58 | 11400 |  | 341207 |  |  | 2020-04-21 | 2020-10-21 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00257925 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7656 | SHELBY 76 | N |  |  | 4093.6 | CDG | N | 2019-10-08 | 2019-11-01 | 23.9111 | 2019-11-04 | 2019-11-04 | 2019-11-15 | 8 | 2020-01-14 | 2020-01-14 | 2020-08-05 | 58 | 12900 |  | 13914749 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00257328 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7656 | SHELBY 76 | N |  |  | 4760 | CDG | N | 2019-10-02 | 2019-10-25 | 23.191 | 2019-10-28 | 2019-10-28 | 2019-11-05 | 6 | 2020-01-14 | 2020-01-14 | 2020-08-05 | 58 | 12500 |  | 1194367 | [8 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00271225 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7656 | SHELBY 76 | N |  |  | 2000 | CDG | N | 2020-03-31 | 2020-04-02 | 2 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 | 2020-07-01 | 2020-07-01 | 2020-11-12 | 56 | 9000 |  | 12981667 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00315540 | 004 - Batavia | PAVILION | 14525 | 36_04_2951 | SHEPPARD RD 29 | N | 5000 |  |  | CDG | N | 2020-09-28 | 2020-10-06 | 5 | 2020-10-06 | 2020-10-06 | 2020-10-06 | 0 | 2020-11-19 | 2020-11-19 |  |  | 9400 | [10 empty] | N | N
NIMO | Michael Kennedy (Citizens Energy Corporation) | 00101357 | 017 - Utica | BARNEVELD | 13304 | 36_17_33351 | SHERMAN 333 | N | 1000 |  |  | RNM | N | 2015-05-29 | 2016-01-20 | 13 | 2016-01-20 | 2016-01-20 | 2016-02-12 | 0 | 2016-10-03 | 2016-10-03 | 2016-12-19 | 55 | 25000 |  |  |  |  | 2017-05-31 | 2017-11-30 | 2018-06-22 | 2019-05-09 | 2019-05-10 | 2019-05-10 | Y | N
NIMO | William Jordan (Jordan Energy & Food Enterprises, | 00299803 | 017 - Utica | BARNEVELD | 13304 | 36_17_33351 | SHERMAN 333 | N | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-04 | 2020-08-04 | 2020-08-06 | 2 | 2020-09-24 | 2020-09-24 |  |  | 9400 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00282042 | 017 - Utica | REMSEN | 13438 | 36_17_33352 | SHERMAN 333 | N | 3500 |  |  | CDG | N | 2020-03-04 | 2020-03-17 | 10 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-04-21 | 2020-04-21 | 2020-07-22 | 59 | 10800 |  | 833149 |  |  | 2020-11-23 | [5 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00284867 | 017 - Utica | REMSEN | 13438 | 36_17_33352 | SHERMAN 333 | N | 5000 |  |  | CDG | N | 2020-03-25 | 2020-04-06 | 8 | 2020-04-07 | 2020-04-07 | 2020-04-09 | 2 | 2020-05-14 | 2020-05-14 | 2020-08-30 | 59 | 11700 |  | 1005874 | [8 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00322725 | 009 - Lakewood/Stow | SHERMAN | 14781 | 36_09_5461 | SHERMAN 54 | N | 5000 |  |  | CDG | N | 2020-11-02 | 2020-11-10 | 6 | 2020-11-10 | 2020-11-10 | 2020-11-18 | 4 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00207475 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130151 | SODEMAN ROAD | N | 4999 |  |  | CDG | Y | 2019-01-30 | 2019-02-11 | 11.7049 | 2019-02-12 | 2019-02-12 | 2019-02-22 | 7 | 2019-05-23 | 2019-05-23 | 2019-09-23 | 41 | 10100 |  | 266847.2 |  |  | 2019-08-02 |  |  | 2020-01-13 | 2020-01-13 | 2020-01-13 | Y | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00313771 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130151 | SODEMAN ROAD | N | 5000 |  |  | CDG | N | 2020-09-22 | 2020-10-11 | 6 | 2020-10-12 | 2020-10-12 | 2020-10-28 | 12 | 2020-11-09 | 2020-11-09 |  |  | 9600 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00270608 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130152 | SODEMAN ROAD | N | 5000 |  |  | CDG | Y | 2020-01-07 | 2020-01-20 | 13.0132 | 2020-01-21 | 2020-01-21 | 2020-01-23 | 2 | 2020-03-09 | 2020-03-09 | 2020-06-26 | 56 | 9200 |  | 121955 |  |  | 2020-10-22 | [5 empty] | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00274596 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130152 | SODEMAN ROAD | N | 5000 |  |  | CDG | Y | 2020-01-30 | 2020-02-13 | 13.8799 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 0 | 2020-04-29 | 2020-04-29 | 2020-07-06 | 37 | 9900 |  | 121955 |  |  | 2020-08-10 | [5 empty] | N | Y
NIMO | Andy Melka (Horizon Solar Power) | 00266300 | 005 - Avon | GENESEO | 14454 | 36_05_438151 | SONORA WAY | N | 5000 |  |  | CDG | Y | 2019-12-09 | 2019-12-19 | 10.1319 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 0 | 2019-12-31 | 2019-12-31 | 2020-05-14 | 51 | 9800 |  | 310798 |  |  | 2020-09-23 | [5 empty] | N | Y
NIMO | Michael Roach (RER Energy Group LLC) | 00187608 | 005 - Avon | GENESEO | 14454 | 36_05_438152 | SONORA WAY | N | 3036 |  |  | CDG | Y | 2018-06-20 | 2018-06-20 | 0 | 2018-07-11 | 2018-07-11 | 2018-07-26 | 11 | 2018-11-01 | 2018-11-01 | 2019-02-04 | 60 | 6200 |  | 421240.1 |  |  | 2019-07-31 | 2019-08-28 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00218919 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26951 | SORRELL HILL 269 | Y | 5000 | 5000 |  | CDG | Y | 2019-04-15 | 2019-04-30 | 15.0076 | 2019-05-01 | 2019-05-01 | 2019-05-09 | 6 | 2019-07-18 | 2019-07-18 | 2019-11-21 | 58 | 11400 |  | 1255615.04 |  |  | 2020-03-30 | 2020-09-14 |  |  |  |  | N | Y
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00101328 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26952 | SORRELL HILL 269 | N | 2000 |  |  | RNM | N | 2015-05-29 | 2015-06-12 | 8 | 2015-06-12 | 2015-06-12 | 2015-07-06 | 0 | 2016-02-09 | 2016-02-09 | 2016-05-18 | 71 | 25000 |  | 144500 |  |  | 2017-01-31 | 2017-07-21 | 2017-07-24 | 2018-06-01 | 2018-06-20 | 2018-06-20 | Y | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00229118 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26952 | SORRELL HILL 269 | Y | 5000 | 5000 |  | CDG | Y | 2019-05-29 | 2019-06-10 | 12.0611 | 2019-06-11 | 2019-06-11 | 2019-06-13 | 2 | 2019-06-25 | 2019-06-25 | 2019-12-16 | 55 | 11800 |  | 992083.75 |  |  | 2020-02-19 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00229121 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26952 | SORRELL HILL 269 | Y | 5001 | 5000 |  | CDG | N | 2019-05-29 | 2019-06-10 | 12.1125 | 2019-06-11 | 2019-06-11 | 2019-06-13 | 2 | 2019-06-25 | 2019-06-25 | 2019-12-16 | 55 | 9900 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00302942 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26953 | SORRELL HILL 269 | N | 5000 |  |  | CDG | N | 2020-07-27 | 2020-08-03 | 5 | 2020-08-03 | 2020-08-03 | 2020-08-03 | 0 | 2020-08-20 | 2020-08-20 | 2020-11-19 | 58 | 10900 |  | 1283329 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00297642 | 011 - Syracuse | MEMPHIS | 13027 | 36_11_26953 | SORRELL HILL 269 | N | 5000 |  |  | CDG | N | 2020-06-23 | 2020-06-30 | 5 | 2020-06-30 | 2020-06-30 | 2020-06-30 | 0 | 2020-09-08 | 2020-09-08 |  |  | 8800 | [10 empty] | N | N
NIMO | Neil Libidinsky (Solar City) | 00101332 | 011 - Syracuse | JAMESVILLE | 13078 | 36_11_24451 | SOUTHWOOD 244 | N | 1988 |  |  | RNM | N | 2015-06-01 | 2015-06-29 | 7 | 2015-06-29 | 2015-06-29 | 2015-07-10 | 0 | 2015-10-28 | 2015-10-28 | 2016-07-22 | 60 | 25000 |  | 184167 |  |  | 2017-01-06 | 2017-10-17 | 2017-06-19 | 2018-03-26 | 2018-03-26 | 2018-03-26 | Y | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00287862 | 011 - Syracuse | JAMESVILLE | 13078 | 36_11_24452 | SOUTHWOOD 244 | N | 5000 |  |  | CDG | N | 2020-04-28 | 2020-05-06 | 6 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 0 | 2020-06-10 | 2020-06-10 | 2020-09-25 | 59 | 10000 |  | 915034 | [8 empty] | N | N
NIMO | Elie Schecter (C2 Energy Development, LLC) | 00231488 | 011 - Syracuse | LAFAYETTE | 13084 | 36_11_24453 | SOUTHWOOD 244 | Y | 5000 | 2500 |  | CDG | Y | 2019-06-18 | 2019-07-12 | 23.8882 | 2019-07-15 | 2019-07-15 | 2019-07-22 | 5 | 2019-10-03 | 2019-10-03 | 2020-02-13 | 58 | 9600 |  | 907804.72 |  |  | 2020-06-25 | [5 empty] | N | Y
NIMO | Samantha Lennon (GSPP Sentinel Heights Road, LLC) | 00224987 | 011 - Syracuse | LAFAYETTE | 13084 | 36_11_24453 | SOUTHWOOD 244 | N | 3750 |  |  | CDG | Y | 2019-05-02 | 2019-05-15 | 12.5785 | 2019-05-16 | 2019-05-16 | 2019-05-29 | 8 | 2019-10-17 | 2019-10-17 | 2020-01-28 | 59 | 10500 |  | 792870 |  |  | 2020-07-14 | [5 empty] | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00208401 | 035 - Gloversville | FORT PLAIN | 13339 | 36_35_33551 | ST JOHNSVILLE 335 | N | 2000 |  |  | CDG | Y | 2019-02-05 | 2019-02-14 | 8.6438 | 2019-02-15 | 2019-02-15 | 2019-02-22 | 4 | 2019-05-24 | 2019-05-24 | 2019-09-20 | 59 | 9800 |  | 322709 |  |  | 2020-05-07 | 2020-11-02 |  |  |  |  | N | Y
NIMO | Theresa Baker (DISTRIBUTED SOLAR OPERATIONS LLC) | 00286153 | 035 - Gloversville | FORT PLAIN | 13339 | 36_35_33551 | ST JOHNSVILLE 335 | N | 3450 |  |  | CDG | N | 2020-04-03 | 2020-05-25 | 8 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 0 | 2020-06-16 | 2020-06-16 |  |  | 13300 | [10 empty] | N | N
NIMO | Theresa Baker (Distributed Solar Operations, LLC) | 00286146 | 035 - Gloversville | FORT PLAIN | 13339 | 36_35_33551 | ST JOHNSVILLE 335 | N | 4500 |  |  | CDG | N | 2020-04-03 | 2020-05-25 | 8 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-16 | 2020-06-16 |  |  | 13300 | [10 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00102371 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_33554 | ST JOHNSVILLE 335 | N | 2000 |  |  | CDG | N | 2016-04-04 | 2016-04-04 | 0 | 2016-04-27 | 2016-04-27 | 2016-05-06 | 7 | 2016-10-17 | 2016-10-17 | 2017-01-12 | 60 | 17500 |  | 851650 |  |  | 2017-05-26 | 2017-12-07 | 2017-05-26 | 2017-12-07 |  |  | N | N
NIMO | Anna Hedgcock (C2 Energy Capital) | 00101594 | 012 - Cortland | CORTLAND | 13045 | 36_12_33451 | STARR RD 334 | N | 1992 |  |  | CDG | N | 2016-11-03 | 2016-11-15 | 7 | 2016-11-15 | 2016-11-15 | 2016-11-18 | 3 | 2017-01-17 | 2017-01-17 | 2017-04-11 | 60 | 18700 |  | 199599 |  |  | 2017-06-13 |  | 2018-11-20 |  |  |  | N | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00266966 |  | Cortland | 13045 | 36_12_33453 | STARR RD 334 | N | 3000 |  |  | CDG | Y | 2019-12-11 | 2020-01-06 | 25.9535 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 0 | 2020-01-08 | 2020-01-08 | 2020-04-21 | 59 | 8100 |  | 16950448 |  |  | 2020-08-11 | [5 empty] | N | Y
NIMO | Timothy Ahrens (CleanChoice Energy) | 00322858 | 012 - Cortland | CORTLAND | 13045 | 36_12_33453 | STARR RD 334 | N | 5000 |  |  | CDG | N | 2020-11-02 | 2020-11-06 | 4 | 2020-11-06 | 2020-11-06 | 2020-11-16 | 4 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00252200 | 012 - Cortland | CORTLAND | 13045 | 36_12_33454 | STARR RD 334 | Y | 5000 | 5000 |  | CDG | Y | 2019-09-03 | 2019-09-17 | 13.4951 | 2019-09-18 | 2019-09-18 | 2019-09-24 | 4 | 2019-12-26 | 2019-12-26 | 2020-05-05 | 59 | 10600 |  | 452923 |  |  | 2020-09-15 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00229753 | 012 - Cortland | CORTLAND | 13045 | 36_12_33454 | STARR RD 334 | Y | 5000 | 5000 |  | CDG | Y | 2019-05-29 | 2019-06-10 | 11.9049 | 2019-06-11 | 2019-06-11 | 2019-06-24 | 9 | 2019-08-08 | 2019-08-08 | 2019-12-23 | 58 | 12200 |  | 1659756 |  |  | 2020-01-06 | 2020-01-15 |  |  |  |  | N | Y
NIMO | Bullitt Farm Solar (Cypress Creek Renewables LLC) | 00169960 | 017 - Utica | MARCY | 13403 | 36_17_67053 | STITTVILLE 670 | N | 5000 |  |  | CDG | Y | 2018-02-03 | 2018-02-03 | 0 | 2018-03-08 | 2018-03-08 | 2018-03-20 | 8 | 2018-09-12 | 2018-09-12 | 2018-12-04 | 54 | 15900 |  | 699406 |  |  | 2019-04-15 | 2019-04-16 |  |  |  |  | N | Y
NIMO | Samantha Lennon (GSPP 7024 Fox Rd, LLCp LLC) | 00214653 | 017 - Utica | MARCY | 13403 | 36_17_67053 | STITTVILLE 670 | Y | 5000 | 5000 |  | CDG | Y | 2019-03-20 | 2019-04-02 | 12.7347 | 2019-04-03 | 2019-04-03 | 2019-04-08 | 3 | 2019-05-21 | 2019-05-21 | 2019-08-22 | 58 | 9900 |  | 306532.71 |  |  | 2020-02-21 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00272862 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_35851 | STONER 358 | N | 5000 |  |  | CDG | Y | 2020-01-17 | 2020-02-12 | 26.0451 | 2020-02-12 | 2020-02-12 | 2020-02-12 | 0 | 2020-02-18 | 2020-02-18 | 2020-05-21 | 59 | 8600 |  | 121955.27 |  |  | 2020-08-25 | [5 empty] | N | Y
NIMO | Bartolo Jimenez (Cipriani Energy Group Corp.) | 00286132 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_35852 | STONER 358 | N | 2400 |  |  | CDG | N | 2020-04-06 | 2020-04-15 | 7 | 2020-04-16 | 2020-04-16 | 2020-04-22 | 4 | 2020-05-06 | 2020-05-06 | 2020-09-17 | 57 | 8800 |  | 121955.41 | [8 empty] | N | N
NIMO | Customer | 00101050 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35853 | STONER 358 | N | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-21 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 147909 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Customer | 00101051 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35853 | STONER 358 | N | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-21 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 730737 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Josh katz (Onyx Development Grou) | 00100807 | 035 - Gloversville | JOHNSTOWN | 12885 | 36_35_35853 | STONER 358 | N | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-12 | 3 | 2015-06-12 | 2015-06-12 | 2015-06-17 | 0 | 2015-12-15 | 2015-12-15 | 2016-04-27 | 96 | 35000 | [7 empty] | 2018-03-01 | 2018-03-21 | 2018-03-21 | Y | N
NIMO | Keith Sandor (Nexus Renewables) | 00309442 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_35853 | STONER 358 | N | 5000 |  |  | CDG | N | 2020-09-17 | 2020-09-28 | 7 | 2020-09-28 | 2020-09-28 | 2020-09-28 | 0 | 2020-10-12 | 2020-10-12 |  |  | 9400 | [10 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00170284 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_35853 | STONER 358 | Y | 3500 | 3500 |  | CDG | Y | 2018-02-09 | 2018-02-09 | 0 | 2018-03-05 | 2018-03-05 | 2018-03-14 | 7 | 2018-05-23 | 2018-05-23 | 2018-08-10 | 55 | 17500 |  | 127367 |  |  | 2018-12-20 |  | 2020-02-03 |  | 2020-10-21 | 2020-10-21 | Y | Y
NIMO | Customer | 00101052 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35854 | STONER 358 | N | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-03 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 205273 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Customer | 00101053 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35854 | STONER 358 | N | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-21 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 147909 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Finney Solar (Cypress Creek Renewables LLC) | 00169964 | 034 - Amsterdam | FORT JOHNSON | 12070 | 36_35_35854 | STONER 358 | N | 5000 |  |  | CDG | Y | 2018-02-03 | 2018-02-03 | 0 | 2018-02-27 | 2018-02-27 | 2018-03-13 | 10 | 2018-06-21 | 2018-06-21 | 2018-11-27 | 48 | 17200 |  | 127083.01 |  |  | 2019-04-09 | 2019-04-10 | 2019-05-06 |  |  |  | N | Y
NIMO | Joe Fiori (Nexamp) | 00204039 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35854 | STONER 358 | Y | 2400 | 5000 |  | CDG | Y | 2018-12-27 | 2019-01-28 | 31.8201 | 2019-01-29 | 2019-01-29 | 2019-02-04 | 4 | 2019-03-28 | 2019-03-28 | 2019-10-08 | 53 | 9400 |  | 275640.6 |  |  | 2020-02-20 | 2020-02-20 |  |  |  |  | N | Y
NIMO | Cypress Creek Renewables LLC | 00102216 | 011 - Syracuse | JAMESVILLE | 13078 | PEBBLE HILL-TILDEN #32 | SUBT 11 | N | 2000 |  |  | CDG | N | 2016-03-17 | 2016-03-17 | 0 | 2016-04-14 | 2016-04-14 | 2016-04-19 | 0 | 2016-10-24 | 2016-10-24 | 2017-03-03 | 60 | 17500 |  | 334000 |  |  | 2017-07-07 |  |  | 2015-11-25 |  |  | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00101486 | 011 - Syracuse | JAMESVILLE | 13078 | PEBBLE HILL-TILDEN #32 | SUBT 11 | N | 2000 |  |  | CDG | N | 2016-01-06 | 2016-03-30 | 4 | 2016-03-30 | 2016-03-30 | 2016-04-12 | 0 | 2016-10-24 | 2016-10-24 | 2017-03-03 | 60 | 17500 |  | 334000 |  |  | 2017-07-07 | [5 empty] | N | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00231911 | 011 - Syracuse | LAFAYETTE | 13084 | TILDEN-TULLY #24 | SUBT 11 | Y | 4000 | 4000 |  | CDG | Y | 2019-05-30 | 2019-06-10 | 11.0764 | 2019-06-11 | 2019-06-11 | 2019-06-24 | 9 | 2019-07-15 | 2019-07-15 | 2019-11-12 | 58 | 11700 |  | 295081.18 |  |  | 2019-11-25 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00295478 | 012 - Cortland | CORTLAND | 13045 | CORTLAND #20 | SUBT 12 | N | 5000 |  |  | CDG | N | 2020-06-10 | 2020-06-18 | 6 | 2020-06-19 | 2020-06-19 | 2020-06-19 | 0 | 2020-09-04 | 2020-09-04 |  |  | 10900 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00213829 | 013 - Watertown | PHILADELPHIA | 13673 | SOUTH PHILADELPHIA-INDIAN RIVER #25 | SUBT 13 | N | 2000 |  |  | RNM | N | 2019-03-20 | 2019-05-01 | 41.8993 | 2019-05-02 | 2019-05-02 | 2019-05-10 | 6 | 2019-07-02 | 2019-07-02 | 2019-10-01 | 59 | 10100 |  | 384595.21 |  |  | 2019-12-18 | 2019-12-24 | 2020-09-11 |  |  |  | N | N
NIMO | GREEN POWER DEVELOPERS LLC | 00101084 | 027 - Malone | MALONE | 12953 | SPENCERS CORNERS-MALONE #26 | SUBT 27 | N | 1188 |  |  | RNM | N | 2015-03-18 | 2015-04-21 | 25 | 2015-04-21 | 2015-04-21 | 2015-05-20 | 0 | 2016-01-27 | 2016-01-27 | 2016-03-10 | 31 | 21800 |  |  |  |  | 2017-04-21 | 2017-10-02 | 2017-05-05 | 2017-10-02 | 2018-12-21 | 2018-12-21 | Y | N
NIMO | GREEN POWER DEVELOPERS LLC | 00101565 | 027 - Malone | MALONE | 12953 | SPENCERS CORNERS-MALONE #26 | SUBT 27 | N | 1692 |  |  | RNM | N | 2015-11-02 | 2015-12-16 | 4 | 2015-12-16 | 2015-12-16 | 2016-01-07 | 0 | 2016-02-01 | 2016-02-01 | 2016-05-17 | 76 | 28000 |  |  |  |  | 2017-04-21 | 2017-10-02 | 2017-05-05 | 2017-10-02 | 2018-12-21 | 2018-12-21 | Y | N
NIMO | Advanced Energy Design, LLC | 00100967 | 028 - Ogdensburg | LISBON | 13658 | DAVID-MCINTYRE #21 | SUBT 28 | N | 2000 |  |  | RNM | N | 2015-01-15 | 2015-04-11 | 2 | 2015-04-11 | 2015-04-11 | 2015-07-11 | 0 | 2015-09-24 | 2015-09-24 | 2016-06-10 | 186 | 30000 |  | 645004.55 |  |  | 2017-02-08 |  |  | 2018-08-22 | 2018-08-22 | 2018-08-22 | Y | N
NIMO | Advanced Energy Design, LLC | 00100968 | 028 - Ogdensburg | LISBON | 13658 | DAVID-MCINTYRE #21 | SUBT 28 | N | 2000 |  |  | RNM | N | 2015-01-15 | 2015-04-14 | 2 | 2015-04-14 | 2015-04-14 | 2015-07-08 | 0 | 2015-09-24 | 2015-09-24 | 2016-05-20 | 171 | 30000 |  | 50695.45 |  |  | 2017-02-08 |  |  | 2018-08-23 | 2018-08-24 | 2018-08-24 | Y | N
NIMO | Kevin Betz (Heuvelton Solar LLC) | 00238207 | 028 - Ogdensburg | OGDENSBURG | 13669 | MCINTYRE-HEUVELTON #23 | SUBT 28 | N | 5000 |  |  | CDG | Y | 2019-08-06 | 2019-09-25 | 49.8257 | 2019-09-26 | 2019-09-26 | 2019-10-04 | 6 | 2019-12-17 | 2019-12-17 | 2020-04-16 | 59 | 10800 |  | 486787 |  |  | 2020-09-03 | [5 empty] | N | Y
NIMO | Elie Schecter (Selkirk Solar) | 00255702 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N | 5000 |  |  | CDG | Y | 2019-09-23 | 2019-10-04 | 10.4743 | 2019-10-07 | 2019-10-07 | 2019-10-21 | 10 | 2019-11-14 | 2019-11-14 | 2020-03-05 | 58 | 11300 |  | 262756 |  |  | 2020-07-02 | [5 empty] | N | Y
NIMO | NEXTera Energy Resources | 00101028 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | NEXTera Energy Resources | 00101033 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | NEXTera Energy Resources | 00101034 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Jordana jusidman (groSolar) | 00100810 | 040 - Warrensburg | JOHNSBURG | 12853 | INDIAN LAKE - NORTH CREEK #1 | SUBT 40 | N | 1980 |  |  | RNM | N | 2015-05-29 | 2015-06-09 | 6 | 2015-06-09 | 2015-06-09 | 2015-07-23 | 0 | 2016-02-08 | 2016-02-08 | 2016-06-28 | 101 | 20000 |  | 243850 |  |  | 2017-06-06 | 2017-10-16 | 2017-08-21 | 2018-07-20 | 2018-07-20 | 2018-07-20 | Y | N
NIMO | Sean McCleneghen (Active Solar Development) | 00315771 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36453 | SWAGGERTOWN 364 | N | 5000 |  |  | CDG | N | 2020-10-12 | 2020-10-19 | 4 | 2020-10-19 | 2020-10-19 | 2020-11-03 | 10 | 2020-11-09 | 2020-11-09 |  |  | 8800 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00315821 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36453 | SWAGGERTOWN 364 | N | 5000 |  |  | CDG | N | 2020-09-30 | 2020-10-28 | 5 | 2020-10-29 | 2020-10-29 | 2020-11-04 | 4 | 2020-11-17 | 2020-11-17 |  |  | 9400 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00197574 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_10557 | SWANN RD 105 | N | 4000 |  |  | CDG | Y | 2018-11-05 | 2018-11-14 | 8.8306 | 2018-11-15 | 2018-11-15 | 2018-11-16 | 1 | 2019-05-16 | 2019-05-16 | 2019-08-13 | 59 | 14300 |  | 1165559.67 |  |  | 2019-09-20 | 2019-09-23 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00234010 | 003 - Niagara Falls | LEWISTON | 14092 | 36_03_10557 | SWANN RD 105 | N | 4000 |  |  | CDG | Y | 2019-06-14 | 2019-06-26 | 12.1264 | 2019-06-27 | 2019-06-27 | 2019-07-09 | 7 | 2019-09-23 | 2019-09-23 | 2019-12-29 | 59 | 11300 |  | 528081 |  |  | 2020-02-28 | 2020-03-04 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00173381 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_10557 | SWANN RD 105 | N | 5000 |  |  | CDG | Y | 2018-04-16 | 2018-04-16 | 0 | 2018-04-26 | 2018-04-26 | 2018-05-11 | 11 | 2018-06-20 | 2018-06-20 | 2018-09-11 | 57 | 15300 |  | 1321277 |  |  | 2018-10-04 |  |  |  | 2019-12-31 | 2019-12-31 | Y | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00237538 | 003 - Niagara Falls | YOUNGSTOWN | 14174 | 36_03_10558 | SWANN RD 105 | N | 5000 |  |  | CDG | Y | 2019-06-28 | 2019-07-17 | 19.0861 | 2019-07-18 | 2019-07-18 | 2019-07-19 | 1 | 2019-09-05 | 2019-09-05 | 2019-12-16 | 58 | 10600 |  | 1259207.01 |  |  | 2020-03-30 | [5 empty] | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00308358 | 031 - Troy | TROY | 12180 | 36_31_37252 | SYCAWAY 372 | Y | 4000 | 0 |  | CDG | N | 2020-08-25 | 2020-09-09 | 12 | 2020-09-10 | 2020-09-10 | 2020-09-23 | 9 | 2020-10-28 | 2020-10-28 |  |  | 10400 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00311053 | 031 - Troy | TROY | 12180 | 36_31_37253 | SYCAWAY 372 | N | 4000 |  |  | CDG | N | 2020-09-22 | 2020-10-05 | 10 | 2020-10-05 | 2020-10-05 | 2020-10-05 | 0 | 2020-10-27 | 2020-10-27 |  |  | 9400 | [10 empty] | N | N
NIMO | High Peaks Solar/Sycaway Solar and Wind | 00102169 | 031 - Troy | TROY | 12180 | 36_31_37256 | SYCAWAY 372 | N | 1980 |  |  | CDG | N | 2016-06-27 | 2016-07-02 | 5 | 2016-07-02 | 2016-07-02 | 2016-07-13 | 6 | 2016-10-21 | 2016-10-21 | 2017-01-17 | 60 | 27500 |  | 883650 |  |  | 2018-03-07 | 2019-12-31 | 2018-08-02 | 2019-12-31 | 2019-12-31 | 2019-12-31 | Y | N
NIMO | Lluis Torrent (CAERO) | 00321431 | 031 - Troy | TROY | 12180 | 36_31_37256 | SYCAWAY 372 | N | 5000 |  |  | CDG | N | 2020-11-12 | 2020-11-18 | 4 | 2020-11-18 | 2020-11-18 | 2020-11-30 | 5 | 2020-12-16 | 2020-12-16 |  |  | 9400 | [10 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00317740 | 017 - Utica | UTICA | 13502 | 36_17_65150 | TERMINAL 651 | N | 1625 |  |  | CDG | N | 2020-10-29 | 2020-10-29 | 0 | 2020-10-29 | 2020-10-29 | 2020-10-29 | 0 |  |  |  |  | 8800 | [10 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00304928 | 017 - Utica | UTICA | 13502 | 36_17_65150 | TERMINAL 651 | N | 2850 |  |  | CDG | N | 2020-08-20 | 2020-08-26 | 4 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 0 | 2020-09-14 | 2020-09-14 | 2020-12-11 | 59 | 8800 |  | 396093 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00328542 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_21672 | THIRD ST 216 | N | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-09 | 6 | 2020-12-09 | 2020-12-09 | 2020-12-09 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, LP.) | 00172442 | 026 - Clayton | CLAYTON | 13624 | 36_26_81452 | THOUSAND ISLANDS 814 | N | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-04-17 | 2018-04-17 | 2018-04-21 | 4 | 2018-07-06 | 2018-07-06 | 2018-09-27 | 56 | 15300 |  | 799495.46 |  |  | 2018-12-14 | 2019-08-23 | 2019-08-26 | 2019-08-26 | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00280309 | 026 - Clayton | CLAYTON | 13624 | 36_26_81453 | THOUSAND ISLANDS 814 | Y | 5000 | 5000 |  | CDG | N | 2020-03-19 | 2020-03-31 | 10 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 0 | 2020-04-09 | 2020-04-09 |  |  | 9100 | [10 empty] | N | N
NIMO | Mithun Vyas (OYA Great Lakes Seaway LLC) | 00172437 | 026 - Clayton | CLAYTON | 13624 | 36_26_81453 | THOUSAND ISLANDS 814 | N | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-04-05 | 2018-04-05 | 2018-04-21 | 0 | 2018-07-02 | 2018-07-02 | 2018-09-25 | 59 | 14300 |  | 696979.05 |  |  | 2018-12-14 | 2019-08-23 | 2019-08-26 | 2019-08-26 | 2020-06-15 | 2020-06-15 | Y | Y
NIMO | Yogesh Kumar (OYA Solar NY, LP.) | 00172439 | 026 - Clayton | CLAYTON | 13624 | 36_26_81454 | THOUSAND ISLANDS 814 | N | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-04-17 | 2018-04-17 | 2018-04-21 | 4 | 2018-07-06 | 2018-07-06 | 2018-09-27 | 58 | 15300 |  | 799495.46 |  |  | 2018-12-17 | 2019-08-23 | 2019-08-26 | 2019-08-26 | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Adam Ellis (Nexamp) | 00320656 | 026 - Clayton | CLAYTON | 13624 | 36_26_81456 | THOUSAND ISLANDS 814 | N | 5000 |  |  | CDG | N | 2020-11-12 | 2020-11-19 | 5 | 2020-11-19 | 2020-11-19 | 2020-12-03 | 7 |  |  |  |  | 8600 | [10 empty] | N | N
NIMO | Mithun Vyas (OYA Blanchard Road LLC) | 00172438 | 026 - Clayton | CLAYTON | 13624 | 36_26_81456 | THOUSAND ISLANDS 814 | N | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-05-01 | 2018-05-01 | 2018-05-17 | 12 | 2018-06-29 | 2018-06-29 | 2018-09-29 | 59 | 15600 |  | 810495.46 |  |  | 2019-01-07 | 2019-08-23 | 2019-08-26 | 2019-08-26 | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00282083 | 026 - Clayton | REDWOOD | 13679 | 36_26_81458 | THOUSAND ISLANDS 814 | N | 4950 |  |  | CDG | N | 2020-04-01 | 2020-04-09 | 6 | 2020-04-09 | 2020-04-09 | 2020-04-09 | 0 | 2020-04-13 | 2020-04-13 |  |  | 13300 | [10 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, LP.) | 00171595 | 026 - Clayton | CLAYTON | 13624 | 36_26_81458 | THOUSAND ISLANDS 814 | N | 5000 |  |  | CDG | Y | 2018-03-09 | 2018-03-09 | 0 | 2018-03-26 | 2018-03-26 | 2018-04-11 | 12 | 2019-06-11 | 2019-06-11 | 2019-12-05 | 59 | 13300 |  | 140363 |  |  | 2020-01-06 | 2020-01-07 |  |  |  |  | N | Y
NIMO | Romer Beato (EnterSolar) | 00266030 | 030 - Albany | ALBANY | 12202 | 36_30_16458 | TRINITY 164 | N | 2250 |  |  | RNM | Y | 2019-11-19 | 2019-12-02 | 12.7625 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 0 | 2020-02-10 | 2020-02-10 | 2020-06-05 | 44 | 8100 |  | 141844 |  |  | 2020-10-14 | [5 empty] | N | Y
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00274292 | 012 - Cortland | CORTLAND | 13045 | 36_12_24651 | TULLER HILL 246 | Y | 5000 | 5000 |  | CDG | Y | 2020-02-19 | 2020-03-02 | 10 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 0 | 2020-03-04 | 2020-03-04 | 2020-07-16 | 59 | 10300 |  | 1270353 |  |  | 2020-09-11 | [5 empty] | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00240225 | 011 - Syracuse | TULLY | 13159 | 36_12_27851 | TULLY CENTER 278 | Y | 5000 | 0 |  | CDG | Y | 2019-07-15 | 2019-07-19 | 4 | 2019-07-22 | 2019-07-22 | 2019-08-01 | 8 | 2019-09-13 | 2019-09-13 | 2019-12-23 | 59 | 9900 |  | 57152.14 |  |  | 2020-06-08 | 2020-12-11 |  |  |  |  | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00243968 | 011 - Syracuse | TULLY | 13159 | 36_12_27852 | TULLY CENTER 278 | Y | 5000 | 0 |  | CDG | Y | 2019-08-05 | 2019-08-13 | 6 | 2019-08-14 | 2019-08-14 | 2019-08-21 | 5 | 2019-12-19 | 2019-12-19 | 2020-03-17 | 59 | 9900 |  | 252315.73 |  |  | 2020-06-08 | [5 empty] | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00240219 | 011 - Syracuse | TULLY | 13159 | 36_12_27852 | TULLY CENTER 278 | Y | 5000 | 0 |  | CDG | Y | 2019-07-15 | 2019-07-19 | 4 | 2019-07-22 | 2019-07-22 | 2019-07-31 | 7 | 2019-08-19 | 2019-08-19 | 2019-12-10 | 58 | 9900 |  | 698473.53 |  |  | 2020-06-18 | 2020-12-11 |  |  |  |  | N | Y
NIMO | ERNEST PORTNER (Dynamic Energy) | 00102339 | 018 - Rome | ROME | 13440 | 36_18_65355 | TURIN RD 653 | N | 1980 |  |  | CDG | N | 2016-07-18 | 2016-08-10 | 3 | 2016-08-10 | 2016-08-10 | 2016-08-16 | 0 | 2016-11-21 | 2016-11-21 | 2016-12-22 | 23 | 20300 |  | 697800 |  |  | 2017-05-22 | 2018-03-07 | 2017-05-23 | 2018-11-30 | 2018-12-04 | 2018-12-04 | Y | N
NIMO | groSolar | 00104406 | 018 - Rome | ROME | 13440 | 36_18_65355 | TURIN RD 653 | N | 2000 |  |  | RNM | N | 2014-03-24 | 2014-03-24 | 0 | 2014-03-24 |  |  |  | 2014-06-25 | 2014-06-25 | 2014-12-15 | 123 | 15000 |  | 561330 | [5 empty] | 2016-08-04 | 2016-08-04 | 2016-08-04 | Y | N
NIMO | Samantha Lennon (GSPP 4575 State Route 69, LLC) | 00227418 | 018 - Rome | TABERG | 13471 | 36_18_65355 | TURIN RD 653 | N | 5000 |  |  | CDG | Y | 2019-06-10 | 2019-06-18 | 7.7778 | 2019-06-19 | 2019-06-19 | 2019-06-21 | 2 | 2019-10-17 | 2019-10-17 | 2020-01-27 | 59 | 10100 |  | 47823.96 |  |  | 2020-04-27 | 2020-10-26 |  |  |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282261 | 018 - Rome | LEE CENTER | 13363 | 36_18_65357 | TURIN RD 653 | N | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-17 | 9 | 2020-03-17 | 2020-03-17 | 2020-03-19 | 2 | 2020-05-14 | 2020-05-14 | 2020-08-12 | 58 | 9400 |  | 121956 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282310 | 018 - Rome | ROME | 13440 | 36_18_65357 | TURIN RD 653 | N | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-16 | 9 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-05-14 | 2020-05-14 | 2020-10-30 | 58 | 9400 |  | 165841 | [8 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00293847 | 018 - Rome | AVA | 13303 | 36_18_65357 | TURIN RD 653 | N | 5000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 0 | 2020-07-09 | 2020-07-09 | 2020-12-15 | 59 | 10100 |  | 1435755 | [8 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar Holdings NY, LLC) | 00300534 |  | ROME | 13440 | 36_18_65358 | TURIN RD 653 | N | 4975 |  |  | CDG | N | 2020-09-18 | 2020-10-08 | 4 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 | 2020-12-03 | 2020-12-03 |  |  | 8500 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00322653 | 039 - Saratoga | CAMBRIDGE | 12816 | 36_39_37653 | UNION ST 376 | N | 5000 |  |  | CDG | N | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | 2020-11-19 | 2020-11-19 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Will Fischer (SRE Solar Origination 2, LLC) | 00298190 | 030 - Albany | FEURA BUSH | 12067 | 36_30_27651 | UNIONVILLE 276 | N | 5000 |  |  | CDG | N | 2020-06-26 | 2020-07-05 | 5 | 2020-07-06 | 2020-07-06 | 2020-07-07 | 1 | 2020-10-16 | 2020-10-16 |  |  | 10100 | [10 empty] | N | N
NIMO | FOREFRONT POWER LLC | 00101403 | 030 - Albany | DELMAR | 12054 | 36_30_27652 | UNIONVILLE 276 | N | 1700 |  |  | RNM | N | 2016-02-08 | 2016-12-15 | 11 | 2016-12-15 | 2016-12-15 | 2017-01-05 | 0 | 2017-02-09 | 2017-02-09 | 2017-05-19 | 60 | 21600 |  | 829500 |  |  | 2017-08-15 | 2018-01-02 | 2017-09-11 | 2018-01-02 | 2019-06-06 | 2019-06-06 | Y | N
NIMO | NEXTera Energy Resources | 00101072 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N | 2000 |  |  | RNM | N | 2015-03-16 | 2015-05-03 | 35 | 2015-05-03 | 2015-05-03 | 2015-05-05 | 0 | 2016-02-26 | 2016-02-26 | 2016-05-26 | 64 | 20000 |  | 819473 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | NEXTera Energy Resources | 00101385 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N | 2000 |  |  | RNM | N | 2015-12-01 | 2015-12-02 | 2 | 2015-12-02 | 2015-12-02 | 2016-01-07 | 23 | 2016-02-26 | 2016-02-26 | 2016-06-06 | 71 | 20000 |  | 147908 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Robert Jendrysek (Solar Liberty Energy Systems, In | 00101554 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N | 1475 |  |  | RNM | N | 2015-10-26 | 2015-11-03 | 4 | 2015-11-03 | 2015-11-03 | 2015-11-17 | 0 | 2016-05-09 | 2016-05-09 | 2017-03-09 | 60 | 25000 |  | 293400 |  |  | 2017-07-12 |  |  |  | 2018-08-16 | 2018-08-16 | Y | N
NIMO | Ryan Marrone (Solops, LLC) | 00201064 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N | 2000 |  |  | CDG | Y | 2019-07-16 | 2019-08-08 | 23.0569 | 2019-08-09 | 2019-08-09 | 2019-08-13 | 2 | 2019-08-29 | 2019-08-29 | 2020-01-03 | 55 | 9400 |  | 122017.58 |  |  | 2020-05-12 | [5 empty] | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00318440 |  | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N | 5000 |  |  | CDG | N | 2020-10-26 | 2020-11-03 | 6 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 | 2020-11-09 | 2020-11-09 |  |  | 8800 | [10 empty] | N | N
NIMO | Craig Livingston (ReneSola Power Holdings LLC) | 00198522 | 035 - Gloversville | MIDDLE GROVE | 12850 | 36_35_39252 | VAIL MILLS 392 | N | 2749 |  |  | CDG | Y | 2019-02-25 | 2019-03-01 | 3.9528 | 2019-03-04 | 2019-03-04 | 2019-03-08 | 4 | 2019-04-24 | 2019-04-24 | 2019-10-08 | 57 | 11200 |  | 340294.4 |  |  | 2020-01-24 | 2020-01-27 |  |  |  |  | N | Y
NIMO | Josh katz (Onyx Development Grou) | 00100805 | 035 - Gloversville | BROADALBIN | 12025 | 36_35_39252 | VAIL MILLS 392 | N | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 3 | 2015-06-11 | 2015-06-11 | 2015-06-16 | 0 | 2015-12-15 | 2015-12-15 | 2016-05-17 | 110 | 25000 |  | 239130 | [5 empty] | 2018-03-01 | 2018-03-21 | 2018-03-21 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00218937 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_39253 | VAIL MILLS 392 | N | 2500 |  |  | CDG | Y | 2019-04-15 | 2019-04-24 | 8.9118 | 2019-04-25 | 2019-04-25 | 2019-05-09 | 10 | 2019-06-11 | 2019-06-11 | 2019-08-30 | 56 | 11300 |  | 135151.58 |  |  | 2019-09-13 | 2019-09-17 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00173052 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_39253 | VAIL MILLS 392 | N | 4000 |  |  | CDG | Y | 2018-04-16 | 2018-04-16 | 0 | 2018-04-26 | 2018-04-26 | 2018-05-08 | 8 | 2018-10-26 | 2018-10-26 | 2019-02-21 | 50 | 12200 |  | 1380241 |  |  | 2019-07-01 | 2019-07-05 |  |  |  |  | N | Y
NIMO | Thibaut Delespaul (CVE North America) | 00301686 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_39253 | VAIL MILLS 392 | Y | 5000 | 0 |  | CDG | N | 2020-07-22 | 2020-07-29 | 5 | 2020-07-29 | 2020-07-29 | 2020-07-29 | 0 | 2020-09-02 | 2020-09-02 |  |  | 9900 | [10 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00294574 | 033 - Hudson | NASSAU | 12123 | 36_33_42754 | VALKIN 427 | N | 5000 |  |  | CDG | N | 2020-06-09 | 2020-06-16 | 5 | 2020-06-17 | 2020-06-17 | 2020-06-22 | 3 | 2020-10-09 | 2020-10-09 |  |  | 9400 | [10 empty] | N | N
NIMO | Wendy DeWolf (East Light Partners) | 00197190 | 033 - Hudson | VALATIE | 12184 | 36_33_42754 | VALKIN 427 | Y | 5000 | 0 |  | CDG | Y | 2018-11-26 | 2018-11-30 | 3.85 | 2018-12-03 | 2018-12-03 | 2018-12-10 | 5 | 2018-12-18 | 2018-12-18 | 2019-04-12 | 58 | 11700 |  | 801563.38 |  |  | 2019-07-25 | 2019-09-30 |  |  | 2020-11-18 | 2020-11-18 | Y | Y
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00322339 | 010 - Olean | ELLICOTTVILLE | 14731 | 36_10_4451 | VALLEY 44 | N | 2500 |  |  | CDG | N | 2020-11-09 | 2020-11-17 | 5 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00291376 | 010 - Olean | ELLICOTTVILLE | 14731 | 36_10_4451 | VALLEY 44 | N | 2170 |  |  | CDG | N | 2020-05-12 | 2020-05-19 | 5 | 2020-05-19 | 2020-05-19 | 2020-05-19 | 0 | 2020-06-18 | 2020-06-18 | 2020-11-05 | 59 | 9400 |  | 972767 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248154 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4456 | VALLEY 44 | N | 4000 |  |  | CDG | Y | 2019-08-12 | 2019-09-11 | 30.1347 | 2019-09-12 | 2019-09-12 | 2019-09-23 | 7 | 2019-11-06 | 2019-11-06 | 2020-02-28 | 58 | 9800 |  | 976056 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248162 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4456 | VALLEY 44 | N | 4000 |  |  | CDG | Y | 2019-08-12 | 2019-09-11 | 30.1493 | 2019-09-12 | 2019-09-12 | 2019-09-23 | 7 | 2019-11-06 | 2019-11-06 | 2020-02-28 | 58 | 9800 |  | 976056 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248166 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4456 | VALLEY 44 | N | 5000 |  |  | CDG | Y | 2019-08-12 | 2019-09-11 | 30.1562 | 2019-09-12 | 2019-09-12 | 2019-09-23 | 7 | 2019-11-06 | 2019-11-06 | 2020-03-02 | 59 | 9800 |  | 976056 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00247945 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4458 | VALLEY 44 | N | 4000 |  |  | CDG | Y | 2019-08-09 | 2019-08-22 | 12.7306 | 2019-08-23 | 2019-08-23 | 2019-08-30 | 5 | 2019-10-10 | 2019-10-10 | 2020-02-28 | 58 | 10900 |  | 673146.87 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00247931 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4458 | VALLEY 44 | N | 5000 |  |  | CDG | Y | 2019-08-09 | 2019-08-22 | 12.6875 | 2019-08-23 | 2019-08-23 | 2019-08-30 | 5 | 2019-10-10 | 2019-10-10 | 2020-02-28 | 58 | 10400 |  | 976056.51 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00247951 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4458 | VALLEY 44 | N | 5000 |  |  | CDG | Y | 2019-08-09 | 2019-08-22 | 12.7389 | 2019-08-23 | 2019-08-23 | 2019-08-30 | 0 | 2019-10-10 | 2019-10-10 | 2020-02-28 | 58 | 10900 |  | 669608.46 |  |  | 2020-07-13 | [5 empty] | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00325168 | 010 - Olean | ALLEGANY | 14706 | 36_10_10451 | VANDALIA 104 | N | 5000 |  |  | CDG | N | 2020-11-12 | 2020-11-16 | 2 | 2020-11-16 | 2020-11-16 | 2020-11-16 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00270629 | 030 - Albany | EAST BERNE | 12059 | 36_30_17851 | VOORHEESVILLE 178 | N | 4400 |  |  | CDG | N | 2019-12-23 | 2020-02-03 | 42.0257 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 0 | 2020-03-11 | 2020-03-11 | 2020-07-13 | 51 | 10500 |  | 911930 |  |  | 2020-11-19 | [5 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00324125 | 030 - Albany | EAST BERNE | 12059 | 36_30_17851 | VOORHEESVILLE 178 | N | 5000 |  |  | CDG | N | 2020-11-09 | 2020-11-17 | 5 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 |  |  |  |  | 10500 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar Holding NY, LLC) | 00299913 |  | SLINGERLANDS | 12159 | 36_30_17852 | VOORHEESVILLE 178 | N | 4975 |  |  | CDG | N | 2020-09-15 | 2020-10-08 | 4 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 | 2020-12-03 | 2020-12-03 |  |  | 10900 | [10 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00276421 | 030 - Albany | SLINGERLANDS | 12159 | 36_30_17852 | VOORHEESVILLE 178 | N | 2750 |  |  | CDG | N | 2020-03-10 | 2020-03-17 | 7 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-04-03 | 2020-04-03 | 2020-08-26 | 57 | 8600 |  | 1919572 | [8 empty] | N | N
NIMO | Will Jurith (Standard Solar) | 00101899 | 030 - Albany | SLINGERLANDS | 12159 | 36_30_17852 | VOORHEESVILLE 178 | N | 1875 |  |  | CDG | Y | 2016-05-19 | 2016-06-02 | 8 | 2016-06-02 | 2016-06-02 | 2016-06-13 | 0 | 2017-05-19 | 2017-05-19 | 2017-08-14 | 58 | 19300 |  | 204368.53 |  |  | 2018-06-29 | 2019-01-09 | 2018-07-13 | 2019-01-09 |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00257886 | 030 - Albany | VOORHEESVILLE | 12186 | 36_30_17853 | VOORHEESVILLE 178 | N | 5000 |  |  | CDG | Y | 2019-10-15 | 2019-10-24 | 9.0521 | 2019-10-25 | 2019-10-25 | 2019-11-05 | 7 | 2020-01-14 | 2020-01-14 | 2020-04-20 | 56 | 10800 |  | 1087482 |  |  | 2020-06-30 | [5 empty] | N | Y
NIMO | Joe Fiori (Nexamp) | 00169786 | 013 - Watertown | ADAMS | 13605 | 36_13_87551 | W. ADAMS 875 | Y | 3332 | 3000 |  | CDG | Y | 2018-02-01 | 2018-02-01 | 0 | 2018-03-05 | 2018-03-05 | 2018-03-14 | 7 | 2018-06-18 | 2018-06-18 | 2018-09-11 | 59 | 15300 |  | 132509.08 |  |  | 2019-02-06 |  | 2019-02-07 |  |  |  | N | Y
NIMO | Nexamp Interconnections (Nexamp) | 00206459 | 013 - Watertown | HENDERSON | 13650 | 36_13_87551 | W. ADAMS 875 | Y | 4375 | 2500 |  | CDG | Y | 2019-01-18 | 2019-01-29 | 11.0972 | 2019-01-30 | 2019-01-30 | 2019-02-08 | 7 | 2019-03-25 | 2019-03-25 | 2019-06-19 | 58 | 10100 |  | 967157.38 |  |  | 2019-12-16 | 2019-12-17 | 2020-09-14 |  |  |  | N | Y
NIMO | Alex Curlin (Nexamp) | 00263438 | 013 - Watertown | ADAMS | 13605 | 36_13_87552 | W. ADAMS 875 | N | 2500 |  |  | CDG | N | 2019-11-25 | 2019-12-05 | 10.0931 | 2019-12-06 | 2019-12-06 | 2019-12-19 | 9 | 2020-01-30 | 2020-01-30 | 2020-05-06 | 59 | 11600 |  | 946447 |  |  | 2020-09-14 | [5 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00280311 | 013 - Watertown | WATERTOWN | 13601 | 36_13_87552 | W. ADAMS 875 | Y | 5000 | 5000 |  | CDG | N | 2020-03-19 | 2020-03-31 | 10 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 0 | 2020-04-09 | 2020-04-09 | 2020-12-04 | 58 | 11800 | [10 empty] | N | N
NIMO | Chris Matthews (AES Distributed Energy, Inc.) | 00293458 | 013 - Watertown | ADAMS | 13605 | 36_13_87554 | W. ADAMS 875 | N | 5000 |  |  | CDG | N | 2020-06-30 | 2020-07-08 | 5 | 2020-07-09 | 2020-07-09 | 2020-07-09 | 0 | 2020-08-13 | 2020-08-13 | 2020-11-20 | 59 | 9400 | [10 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00303196 | 013 - Watertown | ADAMS | 13605 | 36_13_87554 | W. ADAMS 875 | N | 5000 |  |  | CDG | N | 2020-08-06 | 2020-08-19 | 9 | 2020-08-20 | 2020-08-20 | 2020-08-26 | 4 | 2020-09-04 | 2020-09-04 |  |  | 10900 | [10 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy) | 00230071 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7951 | W. ALBION 79 | Y | 4500 | 4500 |  | CDG | Y | 2019-08-22 | 2019-08-29 | 7.0271 | 2019-08-30 | 2019-08-30 | 2019-09-04 | 2 | 2019-11-18 | 2019-11-18 | 2020-05-08 | 58 | 9400 |  | 976056 |  |  | 2020-09-15 | [5 empty] | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00230061 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7952 | W. ALBION 79 | N | 4500 |  |  | CDG | Y | 2019-07-10 | 2019-09-09 | 60.8778 | 2019-09-10 | 2019-09-10 | 2019-09-24 | 10 | 2019-10-02 | 2019-10-02 | 2020-02-26 | 59 | 11700 |  | 1792761 | [8 empty] | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00168256 | 006 - Albion/Medina | HAMLIN | 14464 | 36_06_8251 | W. HAMLIN 82 | N | 5000 |  |  | CDG | Y | 2018-01-09 | 2018-01-09 | 0 | 2018-01-16 | 2018-01-16 | 2018-01-31 | 11 | 2018-04-30 | 2018-04-30 | 2018-07-23 | 58 | 15600 |  | 754907 |  |  | 2018-10-15 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00196184 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8252 | W. HAMLIN 82 | N | 1500 |  |  | CDG | Y | 2018-09-19 | 2018-10-23 | 34.0917 | 2018-10-24 | 2018-10-24 | 2018-11-02 | 7 | 2019-02-11 | 2019-02-11 | 2019-04-22 | 44 | 13300 |  | 289514 |  |  | 2019-08-23 | 2019-08-29 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00196186 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8252 | W. HAMLIN 82 | N | 5000 |  |  | CDG | Y | 2018-09-19 | 2018-10-23 | 34.0743 | 2018-10-24 | 2018-10-24 | 2018-11-02 | 7 | 2019-02-11 | 2019-02-11 | 2019-04-22 | 44 | 12200 |  | 350688 |  |  | 2019-08-23 | 2019-08-29 |  |  |  |  | N | Y
NIMO | Janet Ward (Nextera Energy) | 00242005 | 006 - Albion/Medina | HILTON | 14468 | 36_06_8253 | W. HAMLIN 82 | N | 5000 |  |  | CDG | Y | 2019-07-09 | 2019-07-15 | 6.1174 | 2019-07-16 | 2019-07-16 | 2019-07-23 | 5 | 2019-09-06 | 2019-09-06 | 2020-01-30 | 58 | 10100 |  | 355204 |  |  | 2020-06-10 | 2020-12-11 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS LLC) | 00252737 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8253 | W. HAMLIN 82 | Y | 5000 | 5000 |  | CDG | Y | 2019-09-23 | 2019-10-04 | 11.0868 | 2019-10-07 | 2019-10-07 | 2019-10-18 | 9 | 2019-10-22 | 2019-10-22 | 2020-04-08 | 58 | 9900 |  | 429595 |  |  | 2020-06-29 | [5 empty] | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00173171 | 006 - Albion/Medina | HAMLIN | 14464 | 36_06_8254 | W. HAMLIN 82 | N | 4500 |  |  | CDG | Y | 2018-04-06 | 2018-04-06 | 0 | 2018-04-19 | 2018-04-19 | 2018-05-02 | 9 | 2018-10-26 | 2018-10-26 | 2019-01-30 | 59 | 14300 |  | 278506.01 |  |  | 2019-06-10 | 2019-06-11 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00173173 | 006 - Albion/Medina | HAMLIN | 14464 | 36_06_8254 | W. HAMLIN 82 | N | 4500 |  |  | CDG | Y | 2018-04-06 | 2018-04-06 | 0 | 2018-04-19 | 2018-04-19 | 2018-05-02 | 9 | 2018-10-26 | 2018-10-26 | 2019-01-30 | 59 | 14300 |  | 285247 |  |  | 2019-06-10 | 2019-06-11 |  |  |  |  | N | Y
NIMO | Kevin Lynch (Nexamp) | 00283994 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8255 | W. HAMLIN 82 | N | 5000 |  |  | CDG | N | 2020-04-08 | 2020-04-17 | 7 | 2020-04-22 | 2020-04-22 | 2020-04-23 | 1 | 2020-05-20 | 2020-05-20 | 2020-08-28 | 59 | 9000 |  | 12930098 | [8 empty] | N | N
NIMO | Michael Cucchiara (Nexamp Solar LLC) | 00194894 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8255 | W. HAMLIN 82 | Y | 5000 | 5000 |  | CDG | Y | 2018-09-04 | 2018-10-25 | 50.966 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 0 | 2018-11-28 | 2018-11-28 | 2019-04-25 | 60 | 12200 |  | 247369 |  |  | 2019-09-03 | 2019-09-03 |  |  |  |  | N | Y
NIMO | Andrew Day (Source Renewables, LLC) | 00306964 | 019 - Herkimer | MOHAWK | 13407 | 36_19_67651 | W. HERKIMER 676 | N | 3150 |  |  | CDG | N | 2020-08-17 | 2020-08-26 | 7 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 0 | 2020-09-24 | 2020-09-24 |  |  | 8800 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00321628 | 019 - Herkimer | MOHAWK | 13407 | 36_19_67651 | W. HERKIMER 676 | N | 5000 |  |  | CDG | N | 2020-10-29 | 2020-11-05 | 5 | 2020-11-05 | 2020-11-05 | 2020-11-05 | 0 | 2020-12-09 | 2020-12-09 |  |  | 9800 | [10 empty] | N | N
NIMO | Allegany CSG LLC | 00239550 | 010 - Olean | ALLEGANY | 14706 | 36_10_3352 | W. OLEAN 33 | Y | 2730 | 2218.5 |  | CDG | Y | 2019-06-28 | 2019-07-11 | 12.8167 | 2019-07-12 | 2019-07-12 | 2019-07-19 | 5 | 2019-07-26 | 2019-07-26 | 2019-11-25 | 56 | 9700 |  | 457741.7 |  |  | 2019-12-02 | 2019-12-06 |  |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00318897 | 010 - Olean | ALLEGANY | 14706 | 36_10_3354 | W. OLEAN 33 | N | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-03 | 7 | 2020-11-04 | 2020-11-04 | 2020-11-08 | 3 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Kevin Rabbitt (River Valley Solar LLC) | 00198731 | 010 - Olean | OLEAN | 14760 | 36_10_3354 | W. OLEAN 33 | N | 5000 |  |  | CDG | Y | 2018-11-06 | 2018-11-19 | 12.9146 | 2018-11-20 | 2018-11-20 | 2018-12-04 | 8 | 2019-02-05 | 2019-02-05 | 2019-06-07 | 59 | 10000 |  | 411039 |  |  | 2019-10-08 | 2019-10-10 | 2020-01-31 | 2020-03-26 |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00304370 | 007 - Angola | PERRYSBURG | 14129 | 36_07_18151 | W. PERRYSBURG 181 | N | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-14 | 9 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 0 | 2020-10-28 | 2020-10-28 |  |  | 11300 | [10 empty] | N | N
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00328541 | 010 - Olean | MACHIAS | 14101 | 36_10_2561 | W. VALLEY 25 | N | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-09 | 6 | 2020-12-09 | 2020-12-09 | [17 empty] | N | N
NIMO | SOLARCITY CORP. (Solar City) | 00102968 | 017 - Utica | ORISKANY | 13424 | 36_17_33152 | WALESVILLE 331 | N | 1476 |  |  | RNM | N | 2014-03-25 | 2014-03-25 | 0 | 2014-03-25 | 2014-03-25 | 2014-05-02 | 1 | 2014-05-23 | 2014-05-23 | 2014-08-20 | 63 | 15000 |  | 46355 |  |  | 2014-10-10 |  |  |  | 2017-10-30 | 2017-10-30 | Y | N
NIMO | Teddy Epstein (Novis Renewables) | 00272161 | 017 - Utica | ORISKANY | 13424 | 36_17_33152 | WALESVILLE 331 | Y | 5000 | 0 |  | CDG | Y | 2020-01-07 | 2020-01-20 | 12.941 | 2020-01-21 | 2020-01-21 | 2020-01-23 | 2 | 2020-01-31 | 2020-01-31 | 2020-05-08 | 59 | 9400 |  | 689356 |  |  | 2020-06-17 | 2020-12-08 |  |  |  |  | N | Y
NIMO | Michael Kennedy (Citizens Energy Corporation) | 00280888 | 017 - Utica | WESTMORELAND | 13490 | 36_17_33153 | WALESVILLE 331 | N | 4800 |  |  | RNM | N | 2020-03-17 | 2020-03-24 | 7 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 0 | 2020-04-16 | 2020-04-16 | 2020-09-30 | 58 | 9600 |  | 787589 | [8 empty] | N | N
NIMO | Robert Garrity (Finlo, LLC) | 00287422 | 017 - Utica | ROME | 13440 | 36_17_33153 | WALESVILLE 331 | Y | 5000 | 0 |  | NM | N | 2020-05-08 | 2020-05-14 | 4 | 2020-05-15 | 2020-05-15 | 2020-05-15 | 0 | 2020-06-25 | 2020-06-25 | 2020-10-07 | 59 | 10600 |  | 944184 | [8 empty] | N | N
NIMO | Robert Garrity (Finlo, LLC) | 00287428 | 017 - Utica | ROME | 13440 | 36_17_33153 | WALESVILLE 331 | Y | 5000 | 0 |  | NM | N | 2020-05-14 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-24 | 2020-07-24 | 2020-11-18 | 58 | 12200 |  | 1281289 | [8 empty] | N | N
NIMO | William Jordan (Jordan Energy & Food Enterprises, | 00300676 | 017 - Utica | WESTMORELAND | 13490 | 36_17_33153 | WALESVILLE 331 | N | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-04 | 2020-08-04 | 2020-08-06 | 2 | 2020-09-25 | 2020-09-25 |  |  | 10100 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171574 | 003 - Niagara Falls | SANBORN | 14132 | 36_03_21751 | WALMORE 217 | N | 5000 |  |  | CDG | Y | 2018-03-12 | 2018-03-12 | 0 | 2018-03-22 | 2018-03-22 | 2018-03-31 | 7 | 2018-05-15 | 2018-05-15 | 2018-07-26 | 50 | 13300 |  | 753581 |  |  | 2018-09-17 | 2018-09-24 |  |  | 2020-10-23 | 2020-10-23 | Y | Y
NIMO | Lluis Torrent (CAERO) | 00314131 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_21753 | WALMORE 217 | N | 3060 |  |  | CDG | N | 2020-10-05 | 2020-10-11 | 5 | 2020-10-11 | 2020-10-11 | 2020-10-11 | 0 | 2020-10-27 | 2020-10-27 |  |  | 10800 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318805 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_21753 | WALMORE 217 | N | 5000 |  |  | CDG | N | 2020-10-22 | 2020-10-22 | 0 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2020-11-16 | 2020-11-16 |  |  | 9800 | [10 empty] | N | N
NIMO | Christopher Stroud (Cipriani Energy Group Corp.) | 00297629 | 040 - Warrensburg | WARRENSBURG | 12885 | 36_40_32151 | WARRENSBURG 321 | N | 3200 |  |  | CDG | N | 2020-08-09 | 2020-08-09 | 0 | 2020-08-09 | 2020-08-09 | 2020-08-09 | 0 | 2020-08-28 | 2020-08-28 |  |  | 10800 | [10 empty] | N | N
NIMO | Tory Hanna (Davis Hill Development) | 00325790 | 040 - Warrensburg | WARRENSBURG | 12885 | 36_40_32152 | WARRENSBURG 321 | N | 5000 |  |  | CDG | N | 2020-11-18 | 2020-11-30 | 6 | 2020-11-30 | 2020-11-30 | 2020-11-30 | 0 |  |  |  |  | 9200 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00305444 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7363 | WATERPORT 73 | N | 5000 |  |  | CDG | N | 2020-11-05 | 2020-11-12 | 4 | 2020-11-12 | 2020-11-12 | 2020-12-01 | 10 | 2020-12-08 | 2020-12-08 |  |  | 10400 | [10 empty] | N | N
NIMO | Michelle Ruffolo (Sky Solar Inc.) | 00309500 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_41551 | WEIBEL AVE 415 | N | 5000 |  |  | CDG | N | 2020-09-17 | 2020-10-03 | 5 | 2020-10-03 | 2020-10-03 | 2020-10-03 | 0 | 2020-11-09 | 2020-11-09 |  |  | 12500 | [10 empty] | N | N
NIMO | John McDonough (Lumens Holdings 3 LLC) | 00206012 | 039 - Saratoga | GANSEVOORT | 12831 | 36_39_41556 | WEIBEL AVE 415 | N | 5000 |  |  | CDG | Y | 2019-01-15 | 2019-02-19 | 34.7472 | 2019-02-20 | 2019-02-20 | 2019-02-22 | 2 | 2019-06-03 | 2019-06-03 | 2019-08-22 | 55 | 10100 |  | 207603.35 |  |  | 2019-12-30 | 2020-01-03 | 2020-09-16 |  |  |  | N | Y
NIMO | John McDonough (Omni Industria NY LLC) | 00192254 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_41556 | WEIBEL AVE 415 | N | 5000 |  |  | CDG | Y | 2018-10-11 | 2018-10-24 | 12.6826 | 2018-10-25 | 2018-10-25 | 2018-11-02 | 6 | 2018-12-20 | 2018-12-20 | 2019-04-11 | 52 | 14300 |  | 389816 |  |  | 2019-09-25 | 2019-11-07 | 2019-09-27 | 2019-11-07 |  |  | N | Y
NIMO | Kevin O'Neill (Seaboard Solar) | 00306124 | 011 - Syracuse | CLAY | 13041 | 36_11_690055 | WETZEL ROAD | N | 4975 |  |  | CDG | N | 2020-10-21 | 2020-10-28 | 5 | 2020-10-28 | 2020-10-28 | 2020-10-28 | 0 |  |  |  |  | 10100 | [10 empty] | N | N
NIMO | Rich Gulden (Omni Navitas Holdings LLC) | 00309585 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29651 | WHITAKER 296 | N | 5000 |  |  | CDG | N | 2020-08-31 | 2020-09-05 | 5 | 2020-09-05 | 2020-09-05 | 2020-09-05 | 0 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00218596 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | Y | 3190 | 5000 |  | CDG | Y | 2019-04-30 | 2019-05-09 | 8.9299 | 2019-05-10 | 2019-05-10 | 2019-05-14 | 2 | 2019-05-22 | 2019-05-22 | 2019-10-21 | 59 | 9900 |  | 430282 |  |  | 2019-10-25 | 2020-01-17 | 2019-12-23 | 2020-01-17 |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00227448 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | Y | 3264 | 4000 |  | CDG | N | 2019-05-28 | 2019-06-06 | 8.9701 | 2019-06-07 | 2019-06-07 | 2019-06-19 | 8 | 2019-06-25 | 2019-06-25 | 2019-12-09 | 55 | 10600 | [10 empty] | N | N
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00206724 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | Y | 5000 | 5000 |  | CDG | Y | 2019-01-28 | 2019-02-07 | 9.7632 | 2019-02-08 | 2019-02-08 | 2019-02-15 | 5 | 2019-04-02 | 2019-04-02 | 2019-06-25 | 57 | 10100 |  | 342800.26 |  |  | 2019-10-21 | 2019-10-21 | 2020-04-03 |  |  |  | N | Y
NIMO | SOLARCITY CORP. (Solar City) | 00101198 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | N | 1988 |  |  | RNM | N | 2015-07-16 | 2015-08-07 | 4 | 2015-08-07 | 2015-08-07 | 2015-09-09 | 0 | 2015-10-01 | 2015-10-01 | 2016-07-18 | 60 | 25000 |  | 846046 |  |  | 2017-03-07 | 2017-10-27 | 2017-09-18 | 2017-10-27 | 2018-06-25 | 2018-06-25 | Y | N
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00268863 | 014 - Fulton/Volney | FULTON | 13039 | 36_14_29653 | WHITAKER 296 | N | 5000 |  |  | CDG | N | 2019-12-09 | 2019-12-20 | 10.7917 | 2019-12-20 | 2019-12-20 | 2019-12-20 | 0 | 2020-03-25 | 2020-03-25 | 2020-07-30 | 59 | 9600 |  | 453019 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00096556 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N | 2000 |  |  | RNM | N | 2014-10-29 | 2014-11-10 | 9 | 2014-11-10 | 2014-11-10 | 2014-11-17 | 0 | 2015-04-24 | 2015-04-24 | 2015-06-15 | 36 | 32600 | [8 empty] | 2016-09-02 | 2016-09-02 | Y | N
NIMO | Borrego Solar Systems, Inc | 00096559 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N | 2000 |  |  | RNM | N | 2014-10-29 | 2014-10-29 | 0 | 2014-10-29 | 2014-10-29 | 2014-11-17 | 7 | 2015-04-24 | 2015-04-24 | 2015-06-15 | 36 | 32600 | [8 empty] | 2016-09-02 | 2016-09-02 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100827 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N | 2000 |  |  | RNM | N | 2015-06-01 | 2015-06-28 | 7 | 2015-06-28 | 2015-06-28 | 2015-07-02 | 0 | 2016-04-13 | 2016-04-13 | 2016-07-06 | 60 | 25000 |  | 225100 |  |  |  |  | 2017-04-05 | 2018-06-25 | 2018-06-25 | 2018-06-25 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00101082 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N | 2000 |  |  | RNM | N | 2015-03-17 | 2015-07-17 | 5 | 2015-07-17 | 2015-07-17 | 2015-07-30 | 0 | 2016-04-11 | 2016-04-11 | 2016-07-06 | 60 | 25000 |  | 271800 |  |  |  |  | 2017-04-05 | 2018-06-25 | 2018-06-25 | 2018-06-25 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100826 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18752 | WHITEHALL 187 | N | 2000 |  |  | RNM | N | 2015-05-28 | 2015-05-28 | 0 | 2015-07-20 | 2015-07-20 | 2015-07-29 | 0 | 2016-03-17 | 2016-03-17 | 2016-07-14 | 60 | 25000 | [8 empty] | 2018-06-04 | 2018-06-04 | Y | N
NIMO | ReneSola Power Holdings LLC | 00167026 | 010 - Olean | WHITESVILLE | 14895 | 36_10_10161 | WHITESVILLE 101 | N | 1498.5 |  |  | CDG | Y | 2018-10-05 | 2018-11-13 | 39.1417 | 2018-11-14 | 2018-11-14 | 2018-11-26 | 6 | 2019-04-11 | 2019-04-11 | 2019-07-01 | 56 | 12200 |  | 691710 |  |  | 2019-11-07 | 2019-11-12 |  |  |  |  | N | Y
NIMO | Teddy Epstein (Novis Renewables) | 00273164 | 003 - Niagara Falls | WILSON | 14172 | 36_03_9363 | WILSON 93 | N | 4250 |  |  | CDG | N | 2020-01-14 | 2020-02-12 | 28.8986 | 2020-02-13 | 2020-02-13 | 2020-02-14 | 1 | 2020-02-25 | 2020-02-25 | 2020-06-04 | 56 | 10900 |  | 567400.02 |  |  | 2020-10-20 | [5 empty] | N | N
NIMO | Dave Byrne (Renua Energy, Inc.) | 00284819 | 038 - Glens Falls | GANSEVOORT | 12831 | 36_38_32952 | WILTON 329 | N | 4000 |  |  | CDG | N | 2020-03-24 | 2020-04-02 | 7 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 | 2020-05-13 | 2020-05-13 | 2020-10-14 | 59 | 10400 |  | 825607 | [8 empty] | N | N
NIMO | EnterSolar Engineering (EnterSolar) | 00291782 | 039 - Saratoga | GANSEVOORT | 12831 | 36_39_32951 | WILTON 329 | N | 5000 |  |  | RNM | Y | 2020-05-15 | 2020-05-20 | 3 | 2020-05-21 | 2020-05-21 | 2020-05-22 | 1 | 2020-06-12 | 2020-06-12 |  |  | 10800 | [10 empty] | N | Y
NIMO | David Spotts (SSC Oswego II LLC) | 00301231 | 015 - Oswego | OSWEGO | 13126 | 36_14_28354 | WINE CREEK 283 | N | 5000 |  |  | CDG | N | 2020-07-17 | 2020-07-24 | 5 | 2020-07-24 | 2020-07-24 | 2020-07-24 | 0 | 2020-08-17 | 2020-08-17 | 2020-11-30 | 59 | 9400 |  | 880413 | [8 empty] | N | N
NIMO | David Spotts (SSC Scriba LLC) | 00256774 | 014 - Fulton/Volney | OSWEGO | 13126 | 36_14_28354 | WINE CREEK 283 | Y | 5000 | 5000 |  | CDG | Y | 2019-10-03 | 2019-11-21 | 49.5889 | 2019-11-21 | 2019-11-21 | 2019-11-21 | 0 | 2019-12-06 | 2019-12-06 | 2020-04-17 | 59 | 10300 |  | 765438.28 |  |  | 2020-06-01 | 2020-11-19 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00321623 | 015 - Oswego | OSWEGO | 13126 | 36_14_28354 | WINE CREEK 283 | N | 5000 |  |  | CDG | N | 2020-10-29 | 2020-11-06 | 6 | 2020-11-06 | 2020-11-06 | 2020-11-06 | 0 |  |  |  |  | 10500 | [10 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00305789 | 017 - Utica | WHITESBORO | 13492 | 36_17_64655 | YAHNUNDASIS 646 | N | 5000 |  |  | CDG | N | 2020-08-28 | 2020-09-05 | 6 | 2020-09-05 | 2020-09-05 | 2020-09-05 | 0 | 2020-10-02 | 2020-10-02 |  |  | 8600 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00296047 | 017 - Utica | WHITESBORO | 13492 | 36_17_64655 | YAHNUNDASIS 646 | N | 5000 |  |  | CDG | N | 2020-07-09 | 2020-07-22 | 9 | 2020-07-22 | 2020-07-22 | 2020-07-22 | 0 | 2020-09-11 | 2020-09-11 |  |  | 9100 | [10 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00305797 | 017 - Utica | WHITESBORO | 13492 | 36_17_64656 | YAHNUNDASIS 646 | N | 3120 |  |  | CDG | N | 2020-08-28 | 2020-09-05 | 6 | 2020-09-05 | 2020-09-05 | 2020-09-05 | 0 | 2020-10-02 | 2020-10-02 |  |  | 8600 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00310986 | 017 - Utica | CLINTON | 13323 | 36_17_64656 | YAHNUNDASIS 646 | N | 5000 |  |  | CDG | N | 2020-09-04 | 2020-09-16 | 6 | 2020-09-16 | 2020-09-16 | 2020-09-16 | 0 | 2020-11-06 | 2020-11-06 |  |  | 9400 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318491 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_64659 | YAHNUNDASIS 646 | N | 4600 |  |  | CDG | N | 2020-10-12 | 2020-10-19 | 5 | 2020-10-20 | 2020-10-20 | 2020-11-03 | 10 | 2020-12-02 | 2020-12-02 |  |  | 8600 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318490 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_64659 | YAHNUNDASIS 646 | N | 5000 |  |  | CDG | N | 2020-10-12 | 2020-10-19 | 5 | 2020-10-20 | 2020-10-20 | 2020-10-27 | 5 | 2020-12-02 | 2020-12-02 |  |  | 8600 | [10 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00242193 | 005 - Avon | YORK | 14592 | 36_05_5352 | YORK CENTER 53 | N | 5000 |  |  | CDG | Y | 2019-08-12 | 2019-08-22 | 9 | 2019-08-22 | 2019-08-22 | 2019-08-28 | 4 | 2019-09-04 | 2019-09-04 | 2020-01-13 | 58 | 9900 |  | 692713 |  |  | 2020-03-30 | 2020-10-27 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221261 | 003 - Niagara Falls | RANSOMVILLE | 14131 | YOUNGSTOWN-SANBORN #403 | YOUNGSTOWN 88 | Y | 5000 | 5000 |  | CDG | Y | 2019-04-30 | 2019-05-10 | 10.2264 | 2019-05-13 | 2019-05-13 | 2019-05-24 | 9 | 2019-06-25 | 2019-06-25 | 2019-11-01 | 58 | 11400 |  | 265793 |  |  | 2019-11-13 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Brian DeMaio` (Onyx) | 00100935 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_41551 |  | N | 2000 |  |  | RNM | N | 2014-12-19 | 2015-01-12 | 5 | 2015-01-12 | 2015-01-12 | 2015-01-26 | 0 | 2015-05-21 | 2015-05-21 | 2015-05-27 | 4 | 35600 |  | 427338 |  |  | 2015-07-24 | 2017-07-17 | 2017-07-18 | 2017-08-04 | 2017-08-28 | 2017-08-28 | Y | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00300707 | 006 - Albion/Medina | ALBION | 14411 | ALBION-BROCKPORT #308 |  | N | 5000 |  |  | CDG | N | 2020-07-13 | 2020-07-23 | 8 | 2020-07-23 | 2020-07-23 | 2020-07-23 | 0 | 2020-10-23 | 2020-10-23 |  |  | 8600 | [10 empty] | N | N
NIMO | Michael Doud (Matrix Development, LLC.) | 00235408 | 038 - Glens Falls | HUDSON FALLS | 12839 | ASHLEY - GLENS FALLS #5 |  | N | 5000 |  |  | CDG | Y | 2019-06-13 | 2019-07-09 | 25.8618 | 2019-07-10 | 2019-07-10 | 2019-07-18 | 6 | 2019-08-13 | 2019-08-13 | 2020-02-24 | 58 | 11300 |  | 231459.88 |  |  | 2020-05-07 | 2020-10-29 |  |  |  |  | N | Y
NIMO | Michael Doud (Matrix Development, LLC.) | 00246765 | 038 - Glens Falls | HUDSON FALLS | 12839 | ASHLEY - GLENS FALLS #5 |  | N | 5000 |  |  | CDG | Y | 2019-08-05 | 2019-08-13 | 7.9306 | 2019-08-14 | 2019-08-14 | 2019-09-04 | 14 | 2019-09-05 | 2019-09-05 | 2020-02-24 | 58 | 11300 |  | 786065.22 |  |  | 2020-05-07 | 2020-11-14 |  |  |  |  | N | Y
NIMO | Scott Sabbagh (Matrix Development, LLC.) | 00234668 | 038 - Glens Falls | HUDSON FALLS | 12839 | ASHLEY - GLENS FALLS #5 |  | N | 5000 |  |  | CDG | Y | 2019-06-13 | 2019-07-12 | 29.0771 | 2019-07-15 | 2019-07-15 | 2019-07-19 | 4 | 2019-08-15 | 2019-08-15 | 2020-02-24 | 58 | 8000 |  | 764411.76 |  |  | 2020-05-07 | 2020-10-29 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00304905 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | ASHVILLE-S DOW #864 |  | N | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-11-03 | 2020-11-03 |  |  | 9800 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00304917 |  | JAMESTOWN | 14701 | ASHVILLE-S DOW #864 |  | N | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-11-05 | 2020-11-05 |  |  | 9800 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291574 | 010 - Olean | OTTO | 14719 | BAGDAD-DAKE HILL #815 |  | N | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-21 | 2020-05-21 | 2020-05-22 | 1 | 2020-07-24 | 2020-07-24 | 2020-11-03 | 57 | 11700 |  | 370383 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291577 | 010 - Olean | OTTO | 14719 | BAGDAD-DAKE HILL #815 |  | N | 5000 |  |  | CDG | N | 2020-05-28 | 2020-06-23 | 4 | 2020-06-24 | 2020-06-24 | 2020-06-24 | 0 | 2020-09-04 | 2020-09-04 | 2020-11-03 | 29 | 11700 |  | 370383 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291583 | 010 - Olean | OTTO | 14719 | BAGDAD-DAKE HILL #815 |  | N | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-21 | 2020-05-21 | 2020-05-22 | 1 | 2020-07-24 | 2020-07-24 | 2020-11-03 | 57 | 11700 |  | 370383 | [8 empty] | N | N
NIMO | NEXTera Energy Resources | 00101027 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 |  | N | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [6 empty] | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00321525 | 011 - Syracuse | PHOENIX | 13135 | BRISTOL HILL-PHOENIX #23 |  | N | 5000 |  |  | CDG | N | 2020-10-27 | 2020-11-03 | 5 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00172846 | 001 - Buffalo | TONAWANDA | 14150 | CA 34H #34 |  | N | 5000 |  |  | RNM | Y | 2018-04-03 | 2018-04-03 | 0 | 2018-04-19 | 2018-04-19 | 2018-06-21 | 10 | 2018-09-17 | 2018-09-17 | 2019-01-18 | 57 | 12200 |  | 320807.59 |  |  | 2019-06-07 | 2019-06-13 |  |  |  |  | N | Y
NIMO | Michael Prinzi (Solar Liberty) | 00101466 | 001 - Buffalo | TONAWANDA | 14150 | CA 34H #34 |  | N | 2000 |  |  | RNM | N | 2015-12-28 | 2016-02-26 | 3 | 2016-02-26 | 2016-02-26 | 2016-03-24 | 0 | 2016-05-17 | 2016-05-17 | 2016-08-11 | 60 | 19000 |  | 329550 |  |  | 2017-05-26 |  | 2017-09-12 |  | 2020-01-31 | 2020-01-31 | Y | N
NIMO | Solar City | 00093805 | 011 - Syracuse | CLAY | 13041 | Clay to Woodard 17 - OCWA Tap |  | N | 1000 |  |  | NM | N | 2014-03-26 | 2014-03-31 | 2 | 2014-03-31 | 2014-03-31 | 2014-04-14 | 0 | 2014-08-20 | 2014-08-20 | 2014-12-12 | 82 | 12000 |  | 23215 | [5 empty] | 2016-02-25 | 2016-02-11 | 2016-02-11 | Y | N
NIMO | SunCommon | 00102393 | 010 - Olean | STEAMBURG | 14783 | COLD SPRING-W SALAMANCA #804 |  | N | 1440 |  |  | RNM | Y | 2016-07-26 | 2016-08-02 | 4 | 2016-08-02 | 2016-08-02 | 2016-08-05 | 0 | 2016-09-30 | 2016-09-30 | 2016-12-28 | 60 | 26200 |  | 211050 | [5 empty] | 2017-10-10 | 2017-10-13 | 2017-10-13 | Y | Y
NIMO | Timothy Ahrens (CleanChoice Energy) | 00303321 | 010 - Olean | RANDOLPH | 14772 | COLD SPRING-W SALAMANCA #804 |  | N | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-04 | 5 | 2020-08-04 | 2020-08-04 | 2020-08-04 | 0 | 2020-08-13 | 2020-08-13 |  |  | 11300 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00322693 | 010 - Olean | RANDOLPH | 14772 | COLD SPRING-W SALAMANCA #804 |  | N | 5000 |  |  | CDG | N | 2020-11-02 | 2020-11-05 | 3 | 2020-11-05 | 2020-11-05 | 2020-11-05 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00322724 | 010 - Olean | RANDOLPH | 14772 | COLD SPRING-W SALAMANCA #804 |  | N | 5000 |  |  | CDG | N | 2020-11-02 | 2020-11-08 | 5 | 2020-11-08 | 2020-11-08 | 2020-11-08 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00252201 | 012 - Cortland | CORTLAND | 13045 | CORTLAND #23 |  | Y | 5000 | 5000 |  | CDG | Y | 2019-09-03 | 2019-09-17 | 13.491 | 2019-09-18 | 2019-09-18 | 2019-09-24 | 4 | 2019-12-26 | 2019-12-26 | 2020-05-05 | 57 | 10600 |  | 452923 |  |  | 2020-09-11 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS II, LLC) | 00284107 | 012 - Cortland | CORTLAND | 13045 | CORTLAND #23 |  | Y | 5000 | 0 |  | CDG | N | 2020-04-09 | 2020-04-21 | 8 | 2020-04-21 | 2020-04-21 | 2020-04-21 | 0 | 2020-04-29 | 2020-04-29 | 2020-08-17 | 59 | 11400 |  | 1191873 | [8 empty] | N | N
NIMO | Ivaylo Tomchev (East Otto PV, LLC) | 00290115 | 010 - Olean | CATTARAUGUS | 14719 | DAKE HILL-MACHIAS #803 |  | N | 5000 |  |  | CDG | N | 2020-05-04 | 2020-07-01 | 5 | 2020-07-01 | 2020-07-01 | 2020-07-01 | 0 | 2020-08-13 | 2020-08-13 |  |  | 10900 | [10 empty] | N | N
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00268873 | 010 - Olean | WEST VALLEY | 14042 | DAKE HILL-MACHIAS #803 |  | N | 5000 |  |  | CDG | N | 2019-12-09 | 2019-12-20 | 10.7646 | 2019-12-23 | 2019-12-23 | 2020-01-14 | 14 | 2020-03-25 | 2020-03-25 | 2020-07-17 | 58 | 11300 |  | 241232 | [8 empty] | N | N
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00270585 | 010 - Olean | WEST VALLEY | 14042 | DAKE HILL-MACHIAS #803 |  | N | 5000 |  |  | CDG | N | 2019-12-20 | 2020-01-06 | 16.7493 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 0 | 2020-06-08 | 2020-06-08 | 2020-09-24 | 59 | 11300 |  | 299296 | [8 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00301445 | 010 - Olean | CATTARAUGUS | 14719 | DAKE HILL-MACHIAS #803 |  | N | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-04 | 2020-08-04 | 2020-08-06 | 2 | 2020-08-13 | 2020-08-13 |  |  | 11700 | [10 empty] | N | N
NIMO | Elie Schecter (OurGeneration LLC) | 00298648 | 010 - Olean | SALAMANCA | 14779 | DAKE HILL-W SALAMANCA #816 |  | N | 5000 |  |  | CDG | N | 2020-07-07 | 2020-07-17 | 8 | 2020-07-20 | 2020-07-20 | 2020-07-23 | 3 | 2020-09-18 | 2020-09-18 |  |  | 10300 | [10 empty] | N | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00284399 | 010 - Olean | CATTARAUGUS | 14719 | DAKE HILL-W SALAMANCA #816 |  | N | 5000 |  |  | CDG | N | 2020-03-24 | 2020-04-01 | 6 | 2020-04-02 | 2020-04-02 | 2020-04-03 | 1 | 2020-04-23 | 2020-04-23 | 2020-08-18 | 59 | 11300 |  | 460178 | [8 empty] | N | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00284400 | 010 - Olean | CATTARAUGUS | 14719 | DAKE HILL-W SALAMANCA #816 |  | N | 5000 |  |  | CDG | N | 2020-03-24 | 2020-04-01 | 6 | 2020-04-02 | 2020-04-02 | 2020-04-03 | 1 | 2020-04-23 | 2020-04-23 | 2020-08-18 | 59 | 11300 |  | 231835.62 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00318905 | 010 - Olean | FREEDOM | 14065 | DELEVAN-MACHIAS #801 |  | N | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-21 | 5 | 2020-10-22 | 2020-10-22 | 2020-11-02 | 7 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00307970 | 010 - Olean | MACHIAS | 14101 | DELEVAN-MACHIAS #801 |  | N | 5000 |  |  | CDG | N | 2020-09-01 | 2020-09-14 | 7 | 2020-09-14 | 2020-09-14 | 2020-09-14 | 0 | 2020-10-13 | 2020-10-13 |  |  | 11300 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00314503 | 010 - Olean | MACHIAS | 14101 | DELEVAN-MACHIAS #801 |  | N | 5000 |  |  | CDG | N | 2020-09-24 | 2020-10-02 | 5 | 2020-10-05 | 2020-10-05 | 2020-10-22 | 13 | 2020-10-27 | 2020-10-27 |  |  | 10700 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00287070 | 013 - Watertown | WATERTOWN | 13601 | DEXTER-COFFEEN #25 |  | N | 5000 |  |  | CDG | N | 2020-08-10 | 2020-08-10 | 0 | 2020-08-11 | 2020-08-11 | 2020-08-12 | 1 | 2020-10-08 | 2020-10-08 |  |  | 9400 | [10 empty] | N | N
NIMO | Solar Liberty Energy Systems, Inc. | 00093418 | 009 - Lakewood/Stow | LAKEWOOD | 14750 | Dunkirk to Falconer 160 - Cummins Tap |  | N | 1750 |  |  | NM | N | 2013-08-16 | 2013-08-16 | 0 | 2013-08-16 | [7 empty] | 32200 | [7 empty] | 2014-06-16 | 2015-05-13 | 2015-05-13 | Y | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00300604 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | DUNKIRK-HARTFIELD #852 |  | N | 5000 |  |  | CDG | N | 2020-07-13 | 2020-07-23 | 8 | 2020-07-24 | 2020-07-24 | 2020-08-13 | 14 | 2020-10-20 | 2020-10-20 |  |  | 8600 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar Holdings, LLC) | 00321660 | 008 - Dunkirk/Fredoni | STOCKTON | 14784 | DUNKIRK-HARTFIELD #852 |  | N | 4975 |  |  | CDG | N | 2020-11-17 | 2020-11-30 | 7 | 2020-11-30 | 2020-11-30 | 2020-11-30 | 0 |  |  |  |  | 11700 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00305446 | 008 - Dunkirk/Fredoni | CASSADAGA | 14718 | DUNKIRK-HARTFIELD #852 |  | N | 5000 |  |  | CDG | N | 2020-08-28 | 2020-09-16 | 14 | 2020-09-17 | 2020-09-17 | 2020-09-29 | 8 | 2020-10-13 | 2020-10-13 |  |  | 10900 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282689 | 008 - Dunkirk/Fredoni | DEWITTVILLE | 14728 | DUNKIRK-HARTFIELD #852 |  | N | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-18 | 8 | 2020-03-18 | 2020-03-18 | 2020-03-19 | 1 | 2020-05-14 | 2020-05-14 | 2020-08-28 | 57 | 10900 |  | 300585 | [8 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00282517 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | DUNKIRK-W PORTLAND #851 |  | N | 3450 |  |  | CDG | N | 2020-04-01 | 2020-04-09 | 6 | 2020-04-09 | 2020-04-09 | 2020-04-09 | 0 | 2020-04-13 | 2020-04-13 |  |  | 8600 | [10 empty] | N | N
NIMO | Joe Tassone (ABOVEgrid LLC) | 00319532 | 027 - Malone | FORT COVINGTON | 12937 | FT COVINGTON-MALONE #26 |  | N | 5000 |  |  | CDG | N | 2020-10-20 | 2020-10-28 | 6 | 2020-10-28 | 2020-10-28 | 2020-10-28 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Neil Libidinsky (Solar City) | 00265382 | 001 - Buffalo | BUFFALO | 14220 | Gardenville to Buffalo River Switch 145 - Solar City Tap |  | N | 1976.4 |  |  | NA | Y | 2019-11-15 | 2019-12-02 | 12 | 2019-12-02 |  |  |  | 2019-12-05 | 2019-12-05 | 2020-02-07 | 43 | 10000 | [10 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS II, LLC) | 00284096 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 |  | Y | 5000 | 0 |  | CDG | N | 2020-04-24 | 2020-05-04 | 6 | 2020-05-04 | 2020-05-04 | 2020-05-04 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-31 | 57 | 10000 |  | 467137 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221274 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 |  | Y | 5000 | 5000 |  | CDG | Y | 2019-04-30 | 2019-05-09 | 8.8813 | 2019-05-10 | 2019-05-10 | 2019-05-14 | 2 | 2019-08-22 | 2019-08-22 | 2019-11-23 | 56 | 9500 |  | 307999 |  |  | 2019-11-27 | 2020-09-13 |  |  |  |  | N | Y
NIMO | BQ Energy Inc. | 00100854 | 010 - Olean | OLEAN | 14760 | HOMER HILL-NILE #811 |  | N | 1512 |  |  | RNM | N | 2015-05-12 | 2015-05-13 | 2 | 2015-05-13 | 2015-05-13 | 2015-06-03 | 3 | 2015-09-02 | 2015-09-02 | 2015-12-14 | 73 | 18800 |  | 84000 |  |  | 2016-01-31 | 2017-07-17 | 2017-06-05 | 2017-06-05 | 2017-07-21 | 2017-07-21 | Y | N
NIMO | BQ Energy Inc. | 00103447 | 010 - Olean | OLEAN | 14706 | HOMER HILL-NILE #811 |  | N | 2000 |  |  | RNM | N | 2014-10-17 | 2015-01-02 | 56 | 2015-01-02 | 2015-01-02 | 2015-01-23 | 0 | 2015-06-09 | 2015-06-09 | 2015-10-22 | 97 | 21100 |  | 173000 |  |  | 2015-11-10 | 2017-06-02 | 2017-06-05 | 2017-06-05 | 2017-07-25 | 2017-07-25 | Y | N
NIMO | BQ Energy Inc. | 00103448 | 010 - Olean | OLEAN | 14706 | HOMER HILL-NILE #811 |  | N | 2000 |  |  | RNM | N | 2014-10-17 | 2015-01-02 | 56 | 2015-01-02 | 2015-01-02 | 2015-01-23 | 0 | 2015-06-09 | 2015-06-09 | 2015-10-22 | 97 | 16250 |  | 24000 |  |  | 2015-11-10 | 2017-06-01 | 2017-06-02 | 2017-06-02 | 2017-07-25 | 2017-07-25 | Y | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291545 | 010 - Olean | HINSDALE | 14727 | HOMER HILL-NILE #811 |  | N | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-21 | 2020-05-21 | 2020-05-22 | 1 | 2020-07-29 | 2020-07-29 | 2020-11-02 | 56 | 11300 |  | 294399 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00294469 | 010 - Olean | CUBA | 14727 | HOMER HILL-NILE #811 |  | N | 5000 |  |  | CDG | N | 2020-06-03 | 2020-06-10 | 5 | 2020-06-10 | 2020-06-10 | 2020-06-10 | 0 | 2020-09-04 | 2020-09-04 |  |  | 10900 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00307874 | 023 - Lowville | BOONVILLE | 13309 | LOWVILLE-BOONVILLE #22 |  | N | 5000 |  |  | CDG | N | 2020-08-25 | 2020-09-14 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-29 | 10 | 2020-10-13 | 2020-10-13 |  |  | 11300 | [10 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00296701 | 011 - Syracuse | SYRACUSE | 13209 | MARCELLUS-SOLVAY #35 |  | N | 5000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00296722 | 011 - Syracuse | SYRACUSE | 13209 | MARCELLUS-SOLVAY #35 |  | N | 5000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00296731 | 011 - Syracuse | SYRACUSE | 13209 | MARCELLUS-SOLVAY #35 |  | N | 5000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 0 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00196516 | 028 - Ogdensburg | BRIER HILL | 13614 | MCINTYRE-HAMMOND #24 |  | Y | 5000 | 5000 |  | CDG | Y | 2018-09-20 | 2018-10-03 | 12.9549 | 2018-10-04 | 2018-10-04 | 2018-10-05 | 1 | 2019-04-17 | 2019-04-17 | 2019-11-22 | 119 | 12200 |  | 399822.22 |  |  | 2020-04-16 | 2020-10-07 |  |  |  |  | N | Y
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00310375 | 028 - Ogdensburg | HAMMOND | 13646 | MCINTYRE-HAMMOND #24 |  | N | 5000 |  |  | CDG | N | 2020-09-11 | 2020-09-29 | 13 | 2020-09-29 | 2020-09-29 | 2020-09-29 | 0 | 2020-11-04 | 2020-11-04 |  |  | 10300 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00268515 | 006 - Albion/Medina | ALBION | 14411 | MEDINA-ALBION #306 |  | N | 5000 |  |  | CDG | N | 2020-01-07 | 2020-01-20 | 12.9132 | 2020-01-21 | 2020-01-21 | 2020-01-23 | 2 | 2020-03-09 | 2020-03-09 | 2020-08-28 | 57 | 11700 |  | 939447 | [8 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00274339 | 006 - Albion/Medina | ALBION | 14411 | MEDINA-ALBION #306 |  | N | 5000 |  |  | CDG | N | 2020-01-24 | 2020-02-05 | 11.9979 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 0 | 2020-03-31 | 2020-03-31 | 2020-08-28 | 57 | 11700 |  | 939447 | [8 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00301833 | 007 - Angola | LAWTONS | 14091 | N ANGOLA-BAGDAD #862 |  | N | 5000 |  |  | CDG | N | 2020-07-20 | 2020-07-27 | 5 | 2020-07-28 | 2020-07-28 | 2020-07-30 | 2 | 2020-08-13 | 2020-08-13 |  |  | 11700 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00304373 | 007 - Angola | LAWTONS | 14091 | N ANGOLA-BAGDAD #862 |  | N | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-13 | 8 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 0 | 2020-08-27 | 2020-08-27 |  |  | 10100 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282254 | 007 - Angola | LAWTONS | 14091 | N ANGOLA-N ASHFORD #861 |  | N | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-17 | 9 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-24 | 57 | 11700 |  | 236047 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282682 | 007 - Angola | LAWTONS | 14091 | N ANGOLA-N ASHFORD #861 |  | N | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-18 | 8 | 2020-03-18 | 2020-03-18 | 2020-03-19 | 1 | 2020-05-14 | 2020-05-14 | 2020-09-24 | 59 | 11700 |  | 269827 | [8 empty] | N | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00217635 | 005 - Avon | GENESEO | 14454 | N LAKEVILLE-RIDGE #218 |  | N | 5000 |  |  | CDG | Y | 2019-04-04 | 2019-04-16 | 12.0153 | 2019-04-17 | 2019-04-17 | 2019-04-23 | 4 | 2019-08-09 | 2019-08-09 | 2020-01-16 | 57 | 11800 |  | 292376 |  |  | 2020-05-05 | 2020-11-02 |  |  |  |  | N | Y
NIMO | John Vigants (Bright Solar LLC) | 00315948 | 004 - Batavia | EAST BETHANY | 14054 | N LEROY-ATTICA #208 |  | N | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-21 | 5 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315949 | 004 - Batavia | EAST BETHANY | 14054 | N LEROY-ATTICA #208 |  | N | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-22 | 6 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315950 | 004 - Batavia | PAVILION | 14525 | N LEROY-ATTICA #208 |  | N | 5000 |  |  | CDG | N | 2020-10-05 | 2020-10-11 | 5 | 2020-10-11 | 2020-10-11 | 2020-10-11 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315951 | 004 - Batavia | PAVILION | 14525 | N LEROY-ATTICA #208 |  | N | 5000 |  |  | CDG | N | 2020-10-13 | 2020-10-19 | 4 | 2020-10-20 | 2020-10-20 | 2020-10-26 | 4 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315954 | 004 - Batavia | PAVILION | 14525 | N LEROY-ATTICA #208 |  | N | 5000 |  |  | CDG | N | 2020-10-13 | 2020-10-19 | 4 | 2020-10-20 | 2020-10-20 | 2020-10-21 | 1 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar LP.) | 00278557 | 004 - Batavia | EAST BETHANY | 14054 | N LEROY-ATTICA #208 |  | N | 5000 |  |  | CDG | N | 2020-03-17 | 2020-03-25 | 8 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 0 | 2020-03-31 | 2020-03-31 | 2020-07-31 | 57 | 10900 |  | 573521 |  |  | 2020-12-01 | [5 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy) | 00230056 | 005 - Avon | CALEDONIA | 14511 | N LEROY-CALEDONIA #203 |  | N | 5000 |  |  | CDG | Y | 2019-07-10 | 2019-09-06 | 57.9361 | 2019-09-09 | 2019-09-09 | 2019-09-23 | 10 | 2019-10-02 | 2019-10-02 | 2020-04-05 | 78 | 11400 |  | 362640 |  |  | 2020-06-04 | 2020-12-07 |  |  |  |  | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00230057 | 005 - Avon | CALEDONIA | 14487 | N LEROY-CALEDONIA #203 |  | N | 5000 |  |  | CDG | Y | 2019-07-10 | 2019-08-27 | 48.1069 | 2019-08-28 | 2019-08-28 | 2019-09-05 | 5 | 2019-09-11 | 2019-09-11 | 2020-04-05 | 61 | 10900 |  | 337702 |  |  | 2020-08-04 | [5 empty] | N | Y
NIMO | Constellation Solar NY LLC | 00093233 | 030 - Albany | DELMAR | 12054 | New Scotland to Feura Bush 9 - Owens Corning Tap |  | N | 2000 |  |  | NM | N | 2013-04-15 | 2013-04-15 | 0 | 2013-04-15 | [15 empty] | 2013-10-29 | 2013-10-17 | 2013-10-17 | Y | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00304175 | 010 - Olean | WELLSVILLE | 14895 | NILE-S WELLSVILLE #812 |  | N | 5000 |  |  | CDG | N | 2020-08-27 | 2020-09-03 | 5 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 0 | 2020-11-03 | 2020-11-03 |  |  | 10900 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00308701 | 011 - Syracuse | SKANEATELES | 13152 | NILES #509 |  | N | 4975 |  |  | CDG | N | 2020-11-10 | 2020-11-17 | 4 | 2020-11-17 | 2020-11-17 | 2020-11-23 | 3 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | Bogdan Dinu (BW Solar Holding Inc.) | 00293276 | 004 - Batavia | ELBA | 14058 | OAKFIELD-CALEDONIA #201 |  | N | 5000 |  |  | CDG | N | 2020-05-26 | 2020-06-02 | 5 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 0 | 2020-07-22 | 2020-07-22 |  |  | 9800 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315304 | 005 - Avon | CHURCHVILLE | 14428 | OAKFIELD-CALEDONIA #201 |  | N | 5000 |  |  | CDG | N | 2020-09-28 | 2020-10-05 | 6 | 2020-10-06 | 2020-10-06 | 2020-10-07 | 1 | 2020-11-05 | 2020-11-05 |  |  | 9800 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315952 | 005 - Avon | CHURCHVILLE | 14428 | OAKFIELD-CALEDONIA #201 |  | N | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-21 | 5 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 0 |  |  |  |  | 12100 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315953 | 005 - Avon | CHURCHVILLE | 14428 | OAKFIELD-CALEDONIA #201 |  | N | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-21 | 5 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 0 |  |  |  |  | 12100 | [10 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00290578 | 004 - Batavia | ELBA | 14058 | OAKFIELD-CALEDONIA #201 |  | N | 5000 |  |  | CDG | N | 2020-06-01 | 2020-06-08 | 5 | 2020-06-08 | 2020-06-08 | 2020-06-08 | 0 | 2020-07-08 | 2020-07-08 | 2020-11-03 | 58 | 11300 |  | 414883 | [8 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00288142 | 001 - Buffalo | BUFFALO | 14220 | OHIO ST-RIDGE #613 |  | Y | 5000 | 5000 |  | CDG | N | 2020-04-22 | 2020-04-30 | 6 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 0 | 2020-06-04 | 2020-06-04 | 2020-12-05 | 59 | 10600 |  | 393402 | [8 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00288786 | 001 - Buffalo | BUFFALO | 14220 | OHIO ST-RIDGE #613 |  | Y | 5000 | 5000 |  | CDG | N | 2020-04-22 | 2020-04-30 | 6 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 0 | 2020-06-04 | 2020-06-04 | 2020-12-05 | 59 | 10600 |  | 309239 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315947 | 006 - Albion/Medina | BARKER | 14012 | PHILLIPS RD-MEDINA #301 |  | N | 5000 |  |  | CDG | N | 2020-11-10 | 2020-11-10 | 0 | 2020-11-10 | 2020-11-10 | 2020-11-18 | 4 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00229758 | 006 - Albion/Medina | LYNDONVILLE | 14098 | PHILLIPS RD-MEDINA #301 |  | Y | 3000 | 4000 |  | CDG | Y | 2019-05-29 | 2019-06-10 | 11.8993 | 2019-06-11 | 2019-06-11 | 2019-06-17 | 4 | 2019-06-25 | 2019-06-25 | 2019-10-30 | 57 | 11700 |  | 262818 |  |  | 2019-11-08 | 2019-11-20 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00312459 | 003 - Niagara Falls | BURT | 14208 | PHILLIPS RD-MEDINA #301 |  | N | 5000 |  |  | CDG | N | 2020-09-24 | 2020-09-30 | 3 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 0 | 2020-10-07 | 2020-10-07 |  |  | 12500 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00312461 | 003 - Niagara Falls | BURT | 14208 | PHILLIPS RD-MEDINA #301 |  | N | 5000 |  |  | CDG | N | 2020-09-24 | 2020-10-01 | 4 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 0 | 2020-10-07 | 2020-10-07 |  |  | 12500 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00245228 | 006 - Albion/Medina | MIDDLEPORT | 14105 | PHILLIPS RD-TELEGRAPH RD #304 |  | Y | 5000 | 5000 |  | CDG | Y | 2019-07-24 | 2019-08-01 | 7.5792 | 2019-08-02 | 2019-08-02 | 2019-08-13 | 7 | 2019-08-16 | 2019-08-16 | 2020-01-10 | 56 | 11600 |  | 265918 |  |  | 2020-01-21 | 2020-02-04 |  |  |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291552 | 003 - Niagara Falls | BURT | 14028 | PHILLIPS RD-TELEGRAPH RD #304 |  | N | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-23 | 2020-07-23 | 2020-11-12 | 57 | 12100 |  | 510906 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00294996 | 003 - Niagara Falls | BURT | 14028 | RANSOMVILLE-PHILLIPS RD #402 |  | N | 5000 |  |  | CDG | N | 2020-06-05 | 2020-06-12 | 5 | 2020-06-12 | 2020-06-12 | 2020-06-12 | 0 | 2020-09-04 | 2020-09-04 |  |  | 10900 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00295002 | 003 - Niagara Falls | BURT | 14028 | RANSOMVILLE-PHILLIPS RD #402 |  | N | 5000 |  |  | CDG | N | 2020-06-08 | 2020-06-15 | 5 | 2020-06-15 | 2020-06-15 | 2020-06-15 | 0 | 2020-09-04 | 2020-09-04 |  |  | 11300 | [10 empty] | N | N
NIMO | Richard Gulden (Omni Navitas Holdings LLC) | 00291561 | 003 - Niagara Falls | BURT | 14108 | RANSOMVILLE-PHILLIPS RD #402 |  | N | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-23 | 2020-07-23 | 2020-11-16 | 58 | 11300 |  | 322361 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00308605 | 011 - Syracuse | CAZENOVIA | 13035 | RATHBUN-LABRADOR #39 |  | N | 5000 |  |  | CDG | N | 2020-08-27 | 2020-09-08 | 7 | 2020-09-08 | 2020-09-08 | 2020-09-08 | 0 | 2020-10-12 | 2020-10-12 |  |  | 9400 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00317664 | 011 - Syracuse | CAZENOVIA | 13035 | RATHBUN-LABRADOR #39 |  | N | 5000 |  |  | CDG | N | 2020-10-19 | 2020-10-24 | 5 | 2020-10-26 | 2020-10-26 | 2020-10-27 | 1 |  |  |  |  | 9400 | [10 empty] | N | N
NIMO | GENERAL ELECTRIC | 00101582 | 032 - Schenectady | SCHENECTADY | 12345 | Rotterdam to General Electric 14 |  | N | 1728 |  |  | RNM | N | 2015-11-13 | 2015-12-14 | 4 | 2015-12-14 | 2015-12-14 | 2016-01-06 | 0 | 2016-03-15 | 2016-03-15 | 2016-06-21 | 70 | 15000 |  | 24000 |  |  | 2016-05-31 |  |  |  | 2017-09-27 | 2017-09-27 | Y | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00292039 | 010 - Olean | WELLSVILLE | 14806 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-07-29 | 2020-07-29 |  |  | 11200 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00301635 | 010 - Olean | ANDOVER | 14806 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-04 | 2020-08-04 | 2020-08-05 | 1 | 2020-08-13 | 2020-08-13 |  |  | 10900 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00307487 | 010 - Olean | WELLSVILLE | 14895 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | N | 2020-09-23 | 2020-09-30 | 4 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 0 |  |  |  |  | 11700 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00307519 | 010 - Olean | WELLSVILLE | 14895 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | N | 2020-09-23 | 2020-09-30 | 4 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 0 | 2020-11-20 | 2020-11-20 |  |  | 11700 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY LP.) | 00282137 | 010 - Olean | WHITESVILLE | 14897 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | N | 2020-04-29 | 2020-04-29 | 0 | 2020-04-30 | 2020-04-30 | 2020-05-13 | 9 | 2020-05-15 | 2020-05-15 | 2020-09-23 | 56 | 10900 |  | 1608914 |  |  | 2020-12-01 | [5 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY LP) | 00281629 | 010 - Olean | WHITESVILLE | 14897 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | Y | 2020-04-09 | 2020-04-21 | 8 | 2020-04-22 | 2020-04-22 | 2020-04-22 | 0 | 2020-04-27 | 2020-04-27 | 2020-09-03 | 58 | 10900 |  | 285725 |  |  | 2020-09-22 | [5 empty] | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00241095 | 010 - Olean | WELLSVILLE | 14895 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | Y | 2019-06-28 | 2019-07-22 | 23.9882 | 2019-07-23 | 2019-07-23 | 2019-08-01 | 7 | 2019-09-03 | 2019-09-03 | 2020-01-14 | 56 | 12200 |  | 286322 |  |  | 2020-01-29 | 2020-02-03 |  |  |  |  | N | Y
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00310146 | 010 - Olean | WELLSVILLE | 14806 | S WELLSVILLE-ANDOVER #541 |  | N | 5000 |  |  | CDG | N | 2020-09-11 | 2020-09-16 | 2 | 2020-09-17 | 2020-09-17 | 2020-09-29 | 8 | 2020-10-01 | 2020-10-01 |  |  | 9900 | [10 empty] | N | N
NIMO | Matt Marino (Panama PV I, LLC) | 00312373 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N | 5000 |  |  | CDG | N | 2020-09-14 | 2020-09-24 | 7 | 2020-09-24 | 2020-09-24 | 2020-09-24 | 0 | 2020-10-08 | 2020-10-08 |  |  | 10700 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00295491 | 009 - Lakewood/Stow | CLYMER | 14724 | SHERMAN-ASHVILLE #863 |  | N | 5000 |  |  | CDG | N | 2020-06-10 | 2020-06-18 | 6 | 2020-06-18 | 2020-06-18 | 2020-06-18 | 0 | 2020-09-04 | 2020-09-04 |  |  | 11300 | [10 empty] | N | N
NIMO | SRE Solar Origination 2, LLC | 00294971 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N | 5000 |  |  | CDG | N | 2020-06-19 | 2020-06-26 | 5 | 2020-06-26 | 2020-06-26 | 2020-06-26 | 0 | 2020-07-17 | 2020-07-17 |  |  | 11700 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00303054 | 009 - Lakewood/Stow | CLYMER | 14724 | SHERMAN-ASHVILLE #863 |  | N | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-05 | 2020-08-05 | 2020-08-06 | 1 | 2020-08-13 | 2020-08-13 |  |  | 9900 | [10 empty] | N | N
NIMO | Will Fischer (SRE Solar Origination 2, LLC) | 00295510 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N | 4000 |  |  | CDG | N | 2020-06-12 | 2020-06-18 | 4 | 2020-06-18 | 2020-06-18 | 2020-06-18 | 0 | 2020-06-26 | 2020-06-26 |  |  | 11700 | [10 empty] | N | N
NIMO | Will Fischer (SRE Solar Origination 2, LLC) | 00294751 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N | 5000 |  |  | CDG | N | 2020-06-19 | 2020-06-25 | 4 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 0 | 2020-07-17 | 2020-07-17 |  |  | 11700 | [10 empty] | N | N
NIMO | Solar City | 00100897 | 015 - Oswego | OSWEGO | 13126 | South Oswego to Geres Lock 9 |  | N | 1960 |  |  | NM | N | 2015-05-27 | 2015-06-10 | 5 | 2015-06-10 | 2015-06-10 | 2015-07-01 | 0 | 2015-10-28 | 2015-10-28 | 2016-05-09 | 138 | 30000 |  | 24000 | [5 empty] | 2017-07-03 | 2017-07-05 | 2017-07-05 | Y | N
NIMO | John Vigants (Bright Solar LLC) | 00322117 | 013 - Watertown | EVANS MILLS | 13637 | SOUTH PHILADELPHIA-INDIAN RIVER #25 |  | N | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-08 | 4 | 2020-11-08 | 2020-11-08 | 2020-11-08 | 0 |  |  |  |  | 9800 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00322441 | 013 - Watertown | EVANS MILLS | 13637 | SOUTH PHILADELPHIA-INDIAN RIVER #25 |  | N | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-12 | 6 | 2020-11-12 | 2020-11-12 | 2020-11-12 | 0 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00262705 | 013 - Watertown | EVANS MILLS | 13637 | SOUTH PHILADELPHIA-INDIAN RIVER #25 |  | Y | 5000 | 5000 |  | CDG | Y | 2019-11-06 | 2019-11-19 | 13.0535 | 2019-11-19 | 2019-11-19 | 2019-11-19 | 0 | 2019-12-19 | 2019-12-19 | 2020-04-30 | 59 | 9500 |  | 1254710 |  |  | 2020-06-18 | 2020-12-04 |  |  |  |  | N | Y
NIMO | Richard Gulden (Omni Navitas Holdings LLC) | 00294430 | 008 - Dunkirk/Fredoni | WESTFIELD | 14787 | W PORTLAND-HARTFIELD #866 |  | N | 5000 |  |  | CDG | N | 2020-06-03 | 2020-06-10 | 5 | 2020-06-10 | 2020-06-10 | 2020-06-10 | 0 | 2020-09-04 | 2020-09-04 |  |  | 11200 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00293437 | 009 - Lakewood/Stow | SHERMAN | 14781 | W PORTLAND-SHERMAN #867 |  | N | 4650 |  |  | CDG | N | 2020-05-27 | 2020-06-03 | 5 | 2020-06-04 | 2020-06-04 | 2020-06-04 | 0 | 2020-07-28 | 2020-07-28 |  |  | 10900 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00305546 | 009 - Lakewood/Stow | SHERMAN | 14781 | W PORTLAND-SHERMAN #867 |  | N | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-24 | 9 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 0 | 2020-11-05 | 2020-11-05 |  |  | 10900 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00297280 | 009 - Lakewood/Stow | RIPLEY | 14775 | W PORTLAND-SHERMAN #867 |  | N | 5000 |  |  | CDG | N | 2020-07-17 | 2020-07-23 | 4 | 2020-07-24 | 2020-07-24 | 2020-07-28 | 2 | 2020-08-13 | 2020-08-13 |  |  | 11700 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00315457 | 010 - Olean | ALLEGANY | 14706 | W SALAMANCA-HOMER HILL #805 |  | N | 5000 |  |  | CDG | N | 2020-09-29 | 2020-10-07 | 5 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 0 | 2020-11-20 | 2020-11-20 |  |  | 9800 | [10 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy) | 00230053 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | N | 3000 |  |  | CDG | Y | 2019-08-23 | 2019-08-29 | 5.8736 | 2019-08-30 | 2019-08-30 | 2019-09-04 | 2 | 2019-09-25 | 2019-09-25 | 2020-01-27 | 56 | 11400 |  | 402270.44 |  |  | 2020-04-24 | 2020-10-21 | 2020-05-04 |  |  |  | N | Y
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00269042 | 006 - Albion/Medina | ALBION | 14571 | WATERPORT-ALBION #306 |  | N | 5000 |  |  | CDG | N | 2019-12-16 | 2019-12-29 | 12.7507 | 2019-12-30 | 2019-12-30 | 2020-01-21 | 14 | 2020-04-23 | 2020-04-23 | 2020-07-27 | 56 | 10900 |  | 844570 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00245209 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | Y | 5000 | 5000 |  | CDG | Y | 2019-07-24 | 2019-08-01 | 7.9514 | 2019-08-02 | 2019-08-02 | 2019-08-13 | 7 | 2019-10-28 | 2019-10-28 | 2020-01-27 | 59 | 11400 |  | 402271 |  |  | 2020-03-04 | 2020-03-05 |  |  |  |  | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00252182 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | N | 5000 |  |  | CDG | N | 2019-09-05 | 2019-10-18 | 43.0035 | 2019-10-21 | 2019-10-21 | 2019-11-04 | 10 | 2019-11-19 | 2019-11-19 | 2020-09-28 | 58 | 8100 |  | 878590 | [8 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00254677 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | N | 5000 |  |  | CDG | N | 2019-09-17 | 2019-10-18 | 31.0674 | 2019-10-21 | 2019-10-21 | 2019-11-04 | 10 | 2019-11-19 | 2019-11-19 | 2020-09-28 | 58 | 8800 |  | 883590 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00321847 | 006 - Albion/Medina | KENT | 14477 | WATERPORT-BROCKPORT #307 |  | N | 5000 |  |  | CDG | N | 2020-11-06 | 2020-11-16 | 5 | 2020-11-16 | 2020-11-16 | 2020-11-16 | 0 |  |  |  |  | 12900 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00322786 | 006 - Albion/Medina | KENT | 14477 | WATERPORT-BROCKPORT #307 |  | N | 5000 |  |  | CDG | N | 2020-11-02 | 2020-11-12 | 9 | 2020-11-12 | 2020-11-12 | 2020-11-12 | 0 |  |  |  |  | 14800 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00328470 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-BROCKPORT #307 |  | N | 5000 |  |  | CDG | N | 2020-11-30 | 2020-12-04 | 4 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 0 |  |  |  |  | 11700 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00328471 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-BROCKPORT #307 |  | N | 5000 |  |  | CDG | N | 2020-11-30 | 2020-12-04 | 4 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 0 |  |  |  |  | 10700 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221456 | 006 - Albion/Medina | KENDALL | 14476 | WATERPORT-BROCKPORT #307 |  | Y | 5000 | 5000 |  | CDG | Y | 2019-04-30 | 2019-05-24 | 23.6799 | 2019-05-28 | 2019-05-28 | 2019-06-06 | 7 | 2019-07-03 | 2019-07-03 | 2019-12-06 | 59 | 13000 |  | 203012 |  |  | 2019-12-18 | 2019-12-18 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221742 | 006 - Albion/Medina | KENDALL | 14476 | WATERPORT-BROCKPORT #307 |  | Y | 5000 | 5000 |  | CDG | Y | 2019-04-30 | 2019-05-10 | 9.6875 | 2019-05-13 | 2019-05-13 | 2019-05-24 | 9 | 2019-06-13 | 2019-06-13 | 2019-12-06 | 56 | 15300 |  | 236841 |  |  | 2019-12-18 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00307770 | 006 - Albion/Medina | BROCKPORT | 14420 | WATERPORT-BROCKPORT #307 |  | N | 5000 |  |  | CDG | N | 2020-08-26 | 2020-09-02 | 5 | 2020-09-03 | 2020-09-03 | 2020-09-14 | 6 | 2020-09-21 | 2020-09-21 |  |  | 9400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00325164 | 017 - Utica | SAUQUOIT | 13456 | WHITESBORO-SCHUYLER #29 |  | N | 5000 |  |  | CDG | N | 2020-11-12 | 2020-11-19 | 5 | 2020-11-19 | 2020-11-19 | 2020-11-19 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Mithun Vyas (Nextera Energy Resources, LLC) | 00172172 | 003 - Niagara Falls | RANSOMVILLE | 14131 | YOUNGSTOWN-SANBORN #403 |  | N | 5000 |  |  | CDG | Y | 2018-03-23 | 2018-03-23 | 0 | 2018-03-28 | 2018-03-28 | 2018-04-10 | 9 | 2018-06-11 | 2018-06-11 | 2018-11-14 | 56 | 12200 |  | 210903.87 |  |  | 2018-12-20 | 2019-08-23 | 2019-08-26 | 2019-08-26 | 2020-06-16 | 2020-06-16 | Y | Y
NIMO | Elie Schecter (C2 Energy Capital) | 00101873 | 012 - Cortland | CORTLAND | 13045 |  |  | N | 1925 |  |  | CDG | Y | 2017-01-11 | 2017-01-18 | 4 | 2017-01-18 | 2017-01-18 | 2017-01-27 | 7 | 2017-02-23 | 2017-02-23 | 2017-05-17 | 60 | 19300 |  | 127365 |  |  | 2017-08-11 |  | 2017-08-23 |  |  |  | N | Y
NIMO | Elie Schecter (C2 Energy Capital) | 00101595 | 012 - Cortland | CORTLAND | 13405 |  |  | N | 1950 |  |  | CDG | N | 2016-11-03 | 2016-11-15 | 7 | 2016-11-15 | 2016-11-15 | 2016-11-21 | 4 | 2017-01-17 | 2017-01-17 | 2017-04-11 | 60 | 25300 |  | 227807 |  |  | 2017-06-13 |  | 2018-11-20 |  |  |  | N | N
NIMO | Elie Schecter (C2 Energy Capital) | 00101596 | 012 - Cortland | CORTLAND | 13045 |  |  | N | 2000 |  |  | CDG | N | 2016-11-03 | 2016-11-15 | 7 | 2016-11-15 | 2016-11-15 | 2016-11-18 | 3 | 2017-01-17 | 2017-01-17 | 2017-04-11 | 60 | 20000 |  | 143707 |  |  | 2017-06-13 |  | 2018-11-20 |  |  |  | N | N
NIMO | Elie Schecter (C2 Energy Capital) | 00101986 | 012 - Cortland | CORTLAND | 13045 |  |  | N | 2000 |  |  | CDG | N | 2016-02-17 | 2016-06-10 | 6 | 2016-06-10 | 2016-06-10 | 2016-06-15 | 0 | 2017-01-17 | 2017-01-17 | 2017-04-07 | 58 | 21300 |  | 1048993 |  |  | 2017-06-13 |  | 2018-11-20 |  |  |  | N | N
NIMO | Elie Schecter (C2 Energy Capital) | 00101649 | 012 - Cortland | CORTLAND | 13045 |  |  | N | 3917 |  |  | CDG | N | 2016-11-07 | 2016-11-16 | 6 | 2016-11-16 | 2016-11-16 | 2016-12-06 | 12 | 2017-01-17 | 2017-01-17 | 2017-04-11 | 60 | 16200 |  | 658700 |  |  | 2017-06-13 |  | 2018-11-20 |  |  |  | N | N
NIMO | Green Street Power Partners | 00278928 |  | LOWVILLE | 13367 |  |  | N | 2250 |  |  | CDG | N | 2020-02-21 | 2020-03-04 | 9 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-24 | 42 | 10100 |  | 364989 |  |  | 2020-10-29 | [5 empty] | N | N
NIMO | Jamal Batar (Dimension NY 1 LLC) | 00286613 | 013 - Watertown | WATERTOWN | 13601 |  |  | N | 5000 |  |  | CDG | N | 2020-05-06 | 2020-05-12 | 4 | 2020-05-12 | [18 empty] | N | N
NIMO | John Bay (Acadia Energy) | 00101398 | 017 - Utica | CLINTON | 13323 |  |  | N | 2000 |  |  | CDG | N | 2016-02-16 | 2016-03-11 | 4 | 2016-03-11 | 2016-03-11 | 2016-04-13 | 0 | 2016-09-20 | 2016-09-20 | 2016-12-12 | 59 | 17500 |  | 213400 |  |  | 2017-06-01 | 2018-01-31 | 2017-06-14 | 2018-01-31 |  |  | N | N
NIMO | John Vigants (Bright Solar LLC) | 00322050 | 023 - Lowville | BOONVILLE | 13309 |  |  | N | 5000 |  |  | CDG | N | 2020-10-29 | [21 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00316102 | 038 - Glens Falls | GANSEVOORT | 12831 |  |  | N | 4975 |  |  | CDG | N | 2020-10-30 | [21 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00206375 | 013 - Watertown | PHILADELPHIA | 13673 |  |  | N | 2000 |  |  | RNM | N | 2019-01-30 | 2019-02-08 | 9.0868 | 2019-02-11 | 2019-02-11 | 2019-02-15 | 4 | 2019-06-05 | 2019-06-05 | 2019-09-17 | 59 | 9600 |  | 312484 |  |  | 2019-12-02 | 2019-12-05 | 2020-09-11 |  |  |  | N | N
NIMO | RIC Development, LLC | 00328128 | 009 - Lakewood/Stow | PANAMA | 14767 |  |  | N | 5005 |  |  | CDG | N | 2020-11-25 | [21 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00281855 | 029 - Gouvernur | EDWARDS | 13635 |  |  | N | 4000 |  |  | CDG | N | 2020-03-03 | 2020-03-13 | 9 | 2020-03-16 | 2020-03-16 | 2020-03-19 | 3 | 2020-05-14 | 2020-05-14 | 2020-09-21 | 59 | 9400 |  | 8869533 | [8 empty] | N | N
NIMO | Samantha Lennon (Green Street Power Partners) | 00278912 | 023 - Lowville | LOWVILLE | 13367 |  |  | N | 2250 |  |  | CDG | N | 2020-02-12 | 2020-02-26 | 12 | 2020-02-26 | 2020-02-26 | 2020-02-26 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-24 | 59 | 10100 |  | 803392 |  |  | 2020-10-29 | [5 empty] | N | N
NIMO | Samantha Lennon (Green Street Power Partners) | 00267330 | 027 - Malone | LAWRENCEVILLE | 12949 |  |  | N | 2500 |  |  | CDG | Y | 2019-11-26 | 2019-12-10 | 13.8097 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 0 | 2020-03-25 | 2020-03-25 | 2020-07-21 | 59 | 10900 |  | 986846 |  |  | 2020-11-24 | [5 empty] | N | Y
NIMO | Samantha Lennon (Green Street Power Partners) | 00276722 | 010 - Olean | ALLEGANY | 14076 |  |  | N | 3000 |  |  | CDG | N | 2020-01-28 | 2020-02-07 | 10.1743 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-07 | 48 | 9800 |  | 594107 |  |  | 2020-10-29 | [5 empty] | N | N
NIMO | Samantha Lennon (Green Street Power Partners) | 00267310 | 027 - Malone | NICHOLVILLE | 12965 |  |  | N | 5000 |  |  | CDG | Y | 2019-11-26 | 2019-12-09 | 13.0444 | 2019-12-10 | 2019-12-10 | 2019-12-16 | 1 | 2020-04-22 | 2020-04-22 | 2020-08-31 | 59 | 10900 |  | 986846 |  |  | 2020-11-24 | [5 empty] | N | Y
NIMO | Samantha Lennon (Green Street Power Partners) | 00267321 |  | LAWRENCEVILLE | 12949 |  |  | N | 5000 |  |  | CDG | N | 2019-11-26 | 2019-12-10 | 13.8285 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 0 | 2020-03-25 | 2020-03-25 | 2020-07-21 | 59 | 10900 |  | 913221 |  |  | 2020-11-23 | [5 empty] | N | N
NIMO | Samantha Lennon (Green Street Power Partners) | 00270158 | 010 - Olean | WELLSVILLE | 14895 |  |  | N | 5000 |  |  | CDG | N | 2019-12-18 | 2020-01-02 | 15.0132 | 2020-01-03 | 2020-01-03 | 2020-01-24 | 14 | 2020-03-25 | 2020-03-25 | 2020-07-17 | 58 | 11700 |  | 258908 | [8 empty] | N | N
NIMO | Samantha lennon (GSPP 5059 State Route 104, LLC) | 00282693 | 015 - Oswego | OSWEGO | 13126 |  |  | N | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-18 | 9 | 2020-03-18 | 2020-03-18 | 2020-03-18 | 0 | 2020-07-14 | 2020-07-14 | 2020-11-10 | 59 | 9800 |  | 761347 | [8 empty] | N | N
NIMO | Standard Solar | 00254732 |  | WADSWORTH | 14533 |  |  | N | 5000 |  |  | CDG | Y | 2019-09-17 | 2019-09-30 | 12.8396 | 2019-10-18 | 2019-10-18 | 2019-11-04 | 11 | 2019-12-09 | 2019-12-09 | 2020-04-24 | 26 | 10500 |  | 844270 |  |  | 2020-09-08 | [5 empty] | N | Y
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00255338 | 029 - Gouvernur | GOUVERNEUR | 13642 |  |  | N | 3500 |  |  | CDG | N | 2019-10-17 | 2019-10-29 | 11.5604 | 2019-10-30 | 2019-10-30 | 2019-11-18 | 12 | 2019-12-13 | 2019-12-13 | 2020-05-29 | 59 | 8800 |  | 1222766 |  |  | 2020-10-09 | 2020-11-28 | 2020-10-21 |  |  |  | N | N
NIMO | Theresa Baker (General Electric International Inc) | 00188378 | 032 - Schenectady | SCOTIA | 12302 |  |  | N | 1350 |  |  | CDG | Y | 2018-06-18 | 2018-06-18 | 0 | 2018-06-21 | 2018-06-21 | 2018-07-11 | 13 | 2018-09-19 | 2018-09-19 | 2018-12-07 | 37 | 16600 |  | 212968.46 |  |  | 2019-01-29 | 2019-07-19 | 2019-01-31 | 2019-07-19 | 2020-11-23 | 2020-11-23 | Y | Y
NIMO | Theresa Baker (General Electric International Inc) | 00186134 | 032 - Schenectady | SCHENECTADY | 12306 |  |  | N | 2750 |  |  | CDG | Y | 2018-06-07 | 2018-06-07 | 0 | 2018-06-29 | 2018-06-29 | 2018-07-17 | 11 | 2018-08-16 | 2018-08-16 | 2019-01-08 | 54 | 13300 |  | 634510.85 |  |  | 2019-01-30 | 2019-07-19 | 2019-01-31 | 2019-07-19 | 2020-07-10 | 2020-07-10 | Y | Y
NIMO | Theresa Baker (General Electric International Inc) | 00190778 | 032 - Schenectady | SCHENECTADY | 12309 |  |  | N | 3500 |  |  | CDG | Y | 2018-07-16 | 2018-07-23 | 6.6958 | 2018-07-24 | 2018-07-24 | 2018-08-03 | 8 | 2019-02-05 | 2019-02-05 | 2019-04-18 | 55 | 13300 |  | 375969.44 |  |  | 2019-05-16 |  |  |  | 2020-10-26 | 2020-10-26 | Y | Y
NIMO | Todd Friedman (RESunance, LLC) | 00323200 | 010 - Olean | SCIO | 14880 |  |  | N | 3625 |  |  | CDG | N | 2020-11-04 | 2020-11-12 | 5 | 2020-11-12 | 2020-11-12 | 2020-12-01 | 10 | 2020-12-14 | 2020-12-14 |  |  | 10900 | [10 empty] | N | N