## Grid
[8 empty] | System type |  |  |  |  | Metering |  | APPLICATION REVIEW |  |  |  | PRELIMINARY REVIEW |  |  | CESIR |  |  |  | SIR Costs |  |  |  |  | Construction
[15 empty] | 10 business days |  |  |  | 15 business days |  |  | 60 / 80 business days |  |  |  | CESIR Costs |  | Project Installation / Upgrade Costs |  |  | Payments
Company | Developer | Application / Job # | Division | City/Town | Zip Code | Circuit ID | Substation | Hybrid (Y/N) | Related Application/Job # | PV (kWAC) | ESS (kWAC) | WIND (kWAC) | Metering (NA / NM / RNM / CDG) | Value Stack (Y/N) | Start Date | End Date | Calculated Duration | Application Approved Date (Utility) | Start Date (Must Match Application Approved Date) | End Date | Calculated Duration | Payment Received Date | Start Date | End Date | Calculated Duration | CESIR cost to customer | CESIR cost to utility | Estimated Costs by Utility | Actual Customer Project Costs | Actual Utility Project Costs | Down Payment Date | Full Payment Date | Construction Start Date | Construction Complete Date | Verification Testing or Final Acceptance Date | Final Letter of Acceptance Date | Project Complete (Y/N) | Utility Retention of REC (Y/N)
NIMO | Nexamp Interconnections (Nexamp) | 00169786 | 013 - Watertown | ADAMS | 13605 | 36_13_87551 | W. ADAMS 875 | Y |  | 3332 | 3000 |  | CDG | Y | 2018-02-02 | 2018-03-02 | 1 | 2018-03-02 | 2018-03-02 | 2018-03-14 | 7 | 2018-06-18 | 2018-06-18 | 2018-09-11 | 59 | 15300 |  | 132509.08 |  |  | 2019-02-06 | [5 empty] | N | Y
NIMO | Alex Curlin (Nexamp) | 00263438 | 013 - Watertown | ADAMS | 13605 | 36_13_87552 | W. ADAMS 875 | N |  | 2500 |  |  | CDG | Y | 2019-12-05 | 2019-12-05 | 0 | 2019-12-05 | 2019-12-05 | 2019-12-19 | 9 | 2020-01-30 | 2020-01-30 | 2020-05-06 | 59 | 11600 |  | 554495.06 |  |  | 2020-09-14 | [5 empty] | N | Y
NIMO | Chris Matthews (AES Distributed Energy, Inc.) | 00293458 | 013 - Watertown | ADAMS | 13605 | 36_13_87554 | W. ADAMS 875 | N |  | 5000 |  |  | CDG | N | 2020-06-30 | 2020-07-08 | 5 | 2020-07-08 | 2020-07-08 | 2020-07-09 | 0 | 2020-08-13 | 2020-08-13 | 2020-11-20 | 59 | 9400 |  | 519771.76 |  |  | 2021-03-16 | [5 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00303196 | 013 - Watertown | ADAMS | 13605 | 36_13_87554 | W. ADAMS 875 | N |  | 5000 |  |  | CDG | N | 2020-08-06 | 2020-08-19 | 9 | 2020-08-19 | 2020-08-19 | 2020-08-26 | 4 | 2020-09-04 | 2020-09-04 | 2021-02-09 | 57 | 10900 | [10 empty] | N | N
NIMO | RIC Development, LLC | 00338309 | 013 - Watertown | ADAMS CENTER | 13606 | 36_13_87553 | W. ADAMS 875 | N |  | 5000 |  |  | CDG | N | 2021-01-28 | 2021-02-03 | 4 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 0 |  |  |  |  | 8100 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248818 | 004 - Batavia | AKRON | 14001 | 36_04_22652 | KNAPP RD 226 | N |  | 4000 |  |  | CDG | Y | 2019-08-15 | 2019-08-26 | 7 | 2019-08-26 | 2019-08-26 | 2019-09-04 | 5 | 2019-11-22 | 2019-11-22 | 2020-04-20 | 58 | 8800 |  | 1349153 |  |  | 2020-10-19 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00223799 | 004 - Batavia | AKRON | 14001 | 36_04_22651 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | Y | 2019-06-19 | 2019-06-21 | 2 | 2019-06-21 | 2019-06-21 | 2019-07-02 | 6 | 2019-08-29 | 2019-08-29 | 2019-12-06 | 57 | 9400 |  | 122018 |  |  | 2019-12-20 | 2020-05-15 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00223801 | 004 - Batavia | AKRON | 14001 | 36_04_22651 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | Y | 2019-06-07 | 2019-06-19 | 8 | 2019-06-19 | 2019-06-19 | 2019-07-02 | 8 | 2019-08-29 | 2019-08-29 | 2019-12-06 | 57 | 9400 |  | 122018 |  |  | 2019-12-20 | 2020-06-22 |  |  |  |  | N | Y
NIMO | Robert Tompkins (212 Solar Development, LLC) | 00219855 | 004 - Batavia | AKRON | 14001 | 36_04_22653 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | Y | 2019-05-23 | 2019-05-31 | 5 | 2019-05-31 | 2019-05-31 | 2019-06-04 | 1 | 2019-08-14 | 2019-08-14 | 2019-11-18 | 56 | 8800 |  | 689713 |  |  | 2019-12-06 | 2020-05-15 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248821 | 004 - Batavia | AKRON | 14001 | 36_04_22652 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | Y | 2019-09-13 | 2019-09-25 | 8 | 2019-09-25 | 2019-09-25 | 2019-10-15 | 13 | 2019-12-18 | 2019-12-18 | 2020-04-02 | 59 | 9400 |  | 1363924 |  |  | 2020-10-21 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00262907 | 030 - Albany | ALBANY | 12222 | 36_30_32752 | MCKOWNVILLE 327 | N |  | 1500 |  |  | RNM | Y | 2019-10-31 | 2019-11-08 | 6 | 2019-11-08 | 2019-11-08 | 2019-11-15 | 3 | 2019-12-11 | 2019-12-11 | 2020-04-24 | 58 | 8800 |  | 689355 |  |  | 2020-06-15 | [5 empty] | N | Y
NIMO | Romer Beato (EnterSolar) | 00266030 |  | ALBANY | 12202 | 36_30_16458 | TRINITY 164 | N |  | 2250 |  |  | RNM | Y | 2019-11-20 | 2019-12-02 | 6 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 0 | 2020-02-10 | 2020-02-10 | 2020-06-05 | 44 | 8100 |  | 141844 |  |  | 2020-10-14 | 2021-04-12 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00257391 | 030 - Albany | ALBANY | 12203 | 36_30_42153 | NEW KRUMKILL 421 | N |  | 3840 |  |  | CDG | Y | 2019-10-01 | 2019-10-15 | 10 | 2019-10-15 | 2019-10-15 | 2019-10-25 | 7 | 2019-12-24 | 2019-12-24 | 2020-04-17 | 59 | 10400 |  | 129450 |  |  | 2020-07-13 | 2020-12-22 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00257389 | 030 - Albany | ALBANY | 12203 | 36_30_42153 | NEW KRUMKILL 421 | N |  | 5000 |  |  | CDG | Y | 2019-10-01 | 2019-10-15 | 10 | 2019-10-15 | 2019-10-15 | 2019-10-25 | 7 | 2019-12-24 | 2019-12-24 | 2020-04-17 | 59 | 9900 |  | 1017470 |  |  | 2020-06-15 | 2020-12-11 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS LLC) | 00245209 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-08-01 | 2019-08-01 | 0 | 2019-08-01 | 2019-08-01 | 2019-08-13 | 7 | 2019-10-28 | 2019-10-28 | 2020-01-27 | 59 | 11400 |  | 402271 |  |  | 2020-03-04 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Solar City (Solar City) | 00100869 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7252 | BUTTS RD 72 | N |  | 912 |  |  | RNM | N | 2015-05-18 | 2016-09-15 | 3 | 2016-09-15 | 2016-09-15 | 2016-09-29 | 0 | 2016-11-30 | 2016-11-30 | 2017-02-23 | 60 | 16200 |  |  |  |  | 2017-11-02 |  |  | 2019-03-29 | 2019-03-29 | 2019-03-29 | Y | N
NIMO | Christopher Matthews (AES Distributed Energy) | 00230071 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7951 | W. ALBION 79 | N |  | 2500 |  |  | CDG | Y | 2019-08-29 | 2019-08-29 | 0 | 2019-08-29 | 2019-08-29 | 2019-09-04 | 2 | 2019-11-18 | 2019-11-18 | 2020-05-08 | 58 | 9400 |  | 973056.52 |  |  | 2020-09-16 | 2021-03-19 |  |  |  |  | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00230053 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | N |  | 3000 |  |  | CDG | Y | 2019-08-26 | 2019-08-29 | 3 | 2019-08-29 | 2019-08-29 | 2019-09-04 | 2 | 2019-09-25 | 2019-09-25 | 2020-01-27 | 56 | 11400 |  | 402270.44 |  |  | 2020-04-24 | 2020-10-21 |  |  |  |  | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00230061 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7952 | W. ALBION 79 | N |  | 4500 |  |  | CDG | Y | 2019-08-28 | 2019-09-09 | 7 | 2019-09-09 | 2019-09-09 | 2019-09-24 | 10 | 2019-10-02 | 2019-10-02 | 2020-02-26 | 59 | 11700 |  | 1792761 |  |  |  | 2021-01-12 |  |  |  |  | N | Y
NIMO | Matt Vanderbrook (GreenSpark Solar) | 00327314 | 006 - Albion/Medina | ALBION | 14411 | 36_06_7251 | BUTTS RD 72 | N |  | 5000 |  |  | CDG | N | 2020-12-14 | 2020-12-14 | 0 | 2020-12-14 | 2020-12-14 | 2020-12-14 | 0 |  |  |  |  | 10400 | [10 empty] | N | N
NIMO | Caroline Rizzo (Aura Power) | 00341889 | 006 - Albion/Medina | ALBION | 14411 | 36_06_8064 | ALBION 80 | N |  | 5000 |  |  | CDG | N | 2021-03-01 | 2021-03-03 | 2 | 2021-03-03 | 2021-03-03 | 2021-03-03 | 0 |  |  |  |  | 8200 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00252182 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | N |  | 5000 |  |  | CDG | Y | 2019-10-08 | 2019-10-18 | 8 | 2019-10-18 | 2019-10-18 | 2019-11-04 | 10 | 2019-11-19 | 2019-11-19 | 2020-09-28 | 58 | 8100 |  | 878590.44 |  |  | 2021-02-05 | [5 empty] | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00254677 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | N |  | 5000 |  |  | CDG | Y | 2019-10-08 | 2019-10-18 | 8 | 2019-10-18 | 2019-10-18 | 2019-11-04 | 10 | 2019-11-19 | 2019-11-19 | 2020-09-28 | 58 | 8800 |  | 305247.26 |  |  | 2021-02-04 | [5 empty] | N | Y
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00269042 |  | ALBION | 14571 | WATERPORT-ALBION #306 |  | N |  | 5000 |  |  | CDG | N | 2019-12-17 | 2019-12-29 | 8 | 2019-12-29 | 2019-12-29 | 2020-01-21 | 14 | 2020-04-23 | 2020-04-23 | 2020-07-27 | 56 | 10900 |  | 844570 |  |  | 2021-01-29 | [5 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00305444 | 006 - Albion/Medina | ALBION | 14411 | WATERPORT-ALBION #306 |  | N |  | 5000 |  |  | CDG | N | 2020-11-05 | 2020-11-12 | 4 | 2020-11-12 | 2020-11-12 | 2020-12-01 | 10 |  |  |  |  | 10400 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00268515 | 006 - Albion/Medina | ALBION | 14411 | MEDINA-ALBION #306 |  | N |  | 5000 |  |  | CDG | N | 2020-01-08 | 2020-01-20 | 8 | 2020-01-20 | 2020-01-20 | 2020-01-23 | 2 | 2020-03-09 | 2020-03-09 | 2020-08-28 | 57 | 11700 |  | 939447.25 |  |  | 2021-01-13 | [5 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00274339 | 006 - Albion/Medina | ALBION | 14411 | MEDINA-ALBION #306 |  | N |  | 5000 |  |  | CDG | Y | 2020-01-27 | 2020-02-05 | 7 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 0 | 2020-03-31 | 2020-03-31 | 2020-08-28 | 57 | 11700 |  | 939447.25 |  |  | 2021-01-13 | [5 empty] | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00300707 |  | ALBION | 14411 | ALBION-BROCKPORT #308 |  | N |  | 5000 |  |  | CDG | N | 2020-07-13 | 2020-07-23 | 8 | 2020-07-23 | 2020-07-23 | 2020-07-23 | 0 | 2020-10-23 | 2020-10-23 | 2021-03-08 | 58 | 8600 |  | 6317896 | [8 empty] | N | N
NIMO | Allegany CSG LLC | 00239550 | 010 - Olean | ALLEGANY | 14706 | 36_10_3352 | W. OLEAN 33 | Y |  | 2730 | 2218.5 |  | CDG | Y | 2019-07-01 | 2019-07-11 | 7 | 2019-07-11 | 2019-07-11 | 2019-07-19 | 5 | 2019-07-26 | 2019-07-26 | 2019-11-25 | 56 | 9700 |  | 457741.7 |  |  | 2019-12-02 | 2020-08-04 |  |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00338792 | 010 - Olean | ALLEGANY | 14706 | 36_10_3352 | W. OLEAN 33 | N |  | 2500 |  |  | CDG | N | 2021-01-27 | 2021-02-01 | 3 | 2021-02-01 | 2021-02-01 | 2021-02-22 | 13 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | GSPP 4474 Lower Birch Run Road, LLC | 00276722 |  | ALLEGANY | 14076 | 36_10_3354 | W. OLEAN 33 | N |  | 3000 |  |  | CDG | Y | 2020-01-29 | 2020-02-07 | 7 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-07 | 48 | 9800 |  | 526741 |  |  | 2020-10-29 | 2021-04-05 |  |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00318897 | 010 - Olean | ALLEGANY | 14706 | 36_10_3354 | W. OLEAN 33 | N |  | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-03 | 7 | 2020-11-03 | 2020-11-03 | 2020-11-08 | 3 | 2020-12-23 | 2020-12-23 |  |  | 9400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc) | 00349363 | 010 - Olean | ALLEGANY | 14706 | 36_10_3354 | W. OLEAN 33 | N |  | 5000 |  |  | CDG | N | 2021-03-29 | 2021-04-06 | 6 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 0 |  |  |  |  | 7800 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00315457 | 010 - Olean | ALLEGANY | 14706 | 36_10_3352 | W. OLEAN 33 | N |  | 5000 |  |  | CDG | N | 2020-09-30 | 2020-10-07 | 5 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 0 | 2021-02-12 | 2021-02-12 |  |  | 9800 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00325168 | 010 - Olean | ALLEGANY | 14706 | 36_10_10451 | VANDALIA 104 | N |  | 5000 |  |  | CDG | N | 2020-11-12 | 2020-11-16 | 2 | 2020-11-16 | 2020-11-16 | 2020-11-16 | 0 | 2021-02-18 | 2021-02-18 |  |  | 10900 | [10 empty] | N | N
NIMO | Patrick McGowin (Dynamic Energy) | 00102219 | 032 - Schenectady | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | N |  | 1980 |  |  | CDG | N | 2016-03-15 | 2016-09-29 | 14 | 2016-09-29 | 2016-09-29 | 2016-10-12 | 0 | 2017-01-27 | 2017-01-27 | 2017-04-20 | 59 | 18700 |  | 292000 |  |  | 2017-06-16 |  |  | 2018-12-20 | 2018-12-20 | 2018-12-20 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100904 | 030 - Albany | ALTAMONT | 12009 | 36_30_28356 | ALTAMONT 283 | N |  | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-10 | 4 | 2015-06-10 | 2015-06-10 | 2015-06-25 | 0 | 2016-04-11 | 2016-04-11 | 2016-07-06 | 62 | 25000 |  | 225100 | [5 empty] | 2018-06-11 | 2018-06-11 | 2018-06-11 | Y | N
NIMO | FOREFRONT POWER LLC | 00101370 | 030 - Albany | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | N |  | 2000 |  |  | RNM | N | 2015-11-17 | 2015-11-17 | 0 | 2016-03-15 | 2016-03-15 | 2016-04-08 | 0 | 2016-08-23 | 2016-08-23 | 2016-11-16 | 60 | 25000 |  | 226100 |  |  | 2017-01-31 |  |  | 2018-12-28 | 2018-12-28 | 2018-12-28 | Y | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00324337 | 030 - Albany | ALTAMONT | 12009 | 36_30_42552 | DEPOT RD 425 | N |  | 2375 |  |  | CDG | N | 2020-12-07 | 2020-12-10 | 3 | 2020-12-10 | 2020-12-10 | 2020-12-10 | 0 | 2020-12-15 | 2020-12-15 | 2021-04-12 | 57 | 9400 |  | 689151 | [8 empty] | N | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00208409 | 030 - Albany | ALTAMONT | 12009 | 36_30_28355 | ALTAMONT 283 | N |  | 5000 |  |  | CDG | Y | 2019-02-08 | 2019-02-19 | 6 | 2019-02-19 | 2019-02-19 | 2019-03-01 | 7 | 2019-03-15 | 2019-03-15 | 2019-09-23 | 60 | 8600 |  | 532191.78 |  |  | 2020-03-17 | 2020-09-11 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00271526 | 001 - Buffalo | AMHERST | 14228 | 36_01_99551 | FRANKHAUSER 995 | N |  | 1500 |  |  | RNM | Y | 2020-01-06 | 2020-01-21 | 9 | 2020-01-21 | 2020-01-21 | 2020-02-01 | 0 | 2020-03-11 | 2020-03-11 | 2020-08-13 | 52 | 8100 |  | 302174.6 |  |  | 2020-09-21 | 2020-10-15 |  |  |  |  | N | Y
NIMO | Dan Leary (OurGeneration, LLC) | 00272582 | 001 - Buffalo | AMHERST | 14228 | 36_03_23252 | BUFFALO STATION 232 - OAKWOOD DR | N |  | 5000 |  |  | CDG | Y | 2020-01-10 | 2020-01-24 | 9 | 2020-01-24 | 2020-01-24 | 2020-01-24 | 0 | 2020-04-01 | 2020-04-01 | 2020-07-27 | 58 | 8800 |  | 368399.9 |  |  | 2020-12-08 | [5 empty] | N | Y
NIMO | Brendan Mooney (AMP Solar US Holdings Inc.) | 00305541 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_04357 | CHURCH ST 43 | Y |  | 5000 | 0 |  | CDG | N | 2020-12-02 | 2020-12-03 | 1 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 0 | 2021-03-11 | 2021-03-11 |  |  | 10900 | [10 empty] | N | N
NIMO | Brendan Mooney (AMP Solar US Holdings Inc.) | 00305634 |  | AMSTERDAM | 12010 | 36_35_04357 | CHURCH ST 43 | Y |  | 5000 | 0 |  | CDG | Y | 2020-10-22 | 2020-10-29 | 5 | 2020-10-29 | 2020-10-29 | 2020-11-04 | 3 | 2021-03-11 | 2021-03-11 |  |  | 11000 | [10 empty] | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00303325 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | Y |  |  | 0 | 5000 | CDG | N | 2020-09-15 | 2020-09-20 | 4 | 2020-09-20 | 2020-09-20 | 2020-09-29 | 6 | 2020-11-13 | 2020-11-13 |  |  | 13000 | [10 empty] | N | N
NIMO | Robert Jendrysek (Solar Liberty Energy Systems, In | 00101554 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N |  | 1475 |  |  | RNM | N | 2015-10-26 | 2015-11-03 | 4 | 2015-11-03 | 2015-11-03 | 2015-11-17 | 0 | 2016-05-09 | 2016-05-09 | 2017-03-09 | 60 | 25000 |  | 293400 |  |  | 2017-07-12 |  |  | 2018-08-16 | 2018-08-16 | 2018-08-16 | Y | N
NIMO | Josh katz (Onyx Development Grou) | 00100909 | 034 - Amsterdam | AMSTERDAM | 10210 | 36_35_04356 | CHURCH ST 43 | N |  | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 3 | 2015-06-11 | 2015-06-11 | 2015-08-03 | 0 | 2015-12-15 | 2015-12-15 | 2016-05-18 | 111 | 25000 |  | 144467 |  |  | 2016-12-13 |  |  | 2018-03-26 | 2018-03-26 | 2018-03-26 | Y | N
NIMO | Josh Katz (Onyx Development Grou) | 00100910 | 034 - Amsterdam | AMSTERDAM | 10210 | 36_35_04356 | CHURCH ST 43 | N |  | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 3 | 2015-06-11 | 2015-06-11 | 2015-08-03 | 0 | 2015-12-15 | 2015-12-15 | 2016-05-18 | 111 | 25000 |  | 1195525 | [5 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | Y | N
NIMO | Borrego Solar Systems, Inc | 00101016 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_04356 | CHURCH ST 43 | N |  | 1992 |  |  | RNM | N | 2015-02-13 | 2015-04-14 | 6 | 2015-04-14 | 2015-04-14 | 2015-05-15 | 0 | 2015-07-23 | 2015-07-23 | 2015-10-23 | 66 | 25000 |  | 251383 | [5 empty] | 2016-12-23 | 2016-12-23 | 2016-12-23 | Y | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00103257 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N |  | 2000 |  |  | RNM | N | 2014-06-21 | 2014-06-21 | 0 | 2014-06-21 | [7 empty] | 17160 |  | 282250 |  |  | 2017-01-31 |  |  | 2018-10-25 | 2018-10-25 | 2018-10-25 | Y | N
NIMO | NEXTera Energy Resources | 00101072 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N |  | 2000 |  |  | RNM | N | 2015-03-16 | 2015-05-03 | 35 | 2015-05-03 | 2015-05-03 | 2015-05-05 | 0 | 2016-02-26 | 2016-02-26 | 2016-05-26 | 64 | 20000 |  | 819473 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100814 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N |  | 2000 |  |  | RNM | N | 2015-05-29 | 2015-07-20 | 4 | 2015-07-20 | 2015-07-20 | 2015-08-21 | 0 | 2016-06-17 | 2016-06-17 | 2016-09-13 | 60 |  |  | 264156 |  |  | 2017-04-05 |  |  | 2018-06-26 | 2018-06-26 | 2018-06-26 | Y | N
NIMO | Borrego Solar Systems, Inc | 00100815 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N |  | 2000 |  |  | RNM | N | 2015-05-29 | 2015-07-20 | 4 | 2015-07-20 | 2015-07-20 | 2015-08-21 | 0 | 2016-06-17 | 2016-06-17 | 2016-09-13 | 60 |  |  | 144500 |  |  | 2017-04-05 |  |  | 2018-06-26 | 2018-06-26 | 2018-06-26 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100816 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50152 | FLORIDA 501 | N |  | 2000 |  |  | RNM | N | 2015-05-29 | 2015-07-20 | 4 | 2015-07-20 | 2015-07-20 | 2015-08-21 | 0 | 2016-06-17 | 2016-06-17 | 2016-09-13 | 60 |  |  | 286940 |  |  | 2017-04-05 |  |  | 2018-06-26 | 2018-06-26 | 2018-06-26 | Y | N
NIMO | NEXTera Energy Resources | 00101385 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N |  | 2000 |  |  | RNM | N | 2015-12-01 | 2015-12-02 | 2 | 2015-12-02 | 2015-12-02 | 2016-01-07 | 23 | 2016-02-26 | 2016-02-26 | 2016-06-06 | 71 | 20000 |  | 147908 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Ryan Marrone (Solops, LLC) | 00201064 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N |  | 2000 |  |  | CDG | Y | 2019-07-30 | 2019-08-08 | 7 | 2019-08-08 | 2019-08-08 | 2019-08-13 | 2 | 2019-08-29 | 2019-08-29 | 2020-01-03 | 55 | 9400 |  | 122017.58 |  |  | 2020-05-12 | 2021-02-23 |  |  |  |  | N | Y
NIMO | Standard Solar | 00253939 |  | AMSTERDAM | 12010 | 36_35_50251 | MAPLE AVE 502 | N |  | 4500 |  |  | CDG | Y | 2020-01-23 | 2020-01-23 | 0 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 0 | 2020-05-19 | 2020-05-19 | 2020-11-06 | 69 | 9400 |  | 150366.86 |  |  | 2021-02-01 | [5 empty] | N | Y
NIMO | Mike Borkowski (Community Power Group) | 00273436 | 035 - Gloversville | AMSTERDAM | 12010 | 36_35_04356 | CHURCH ST 43 | N |  | 5000 |  |  | CDG | N | 2020-01-17 | 2020-01-31 | 9 | 2020-01-31 | 2020-01-31 | 2020-01-31 | 0 | 2020-04-15 | 2020-04-15 | 2021-02-04 | 60 | 9400 |  | 696320 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00344570 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_04353 | CHURCH ST 43 | N |  | 5000 |  |  | CDG | N | 2021-03-23 | 2021-03-26 | 3 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00318440 |  | AMSTERDAM | 12010 | 36_35_39251 | VAIL MILLS 392 | N |  | 5000 |  |  | CDG | N | 2020-10-26 | 2020-11-03 | 6 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 | 2020-11-09 | 2020-11-09 |  |  | 8800 | [10 empty] | N | N
NIMO | Dave Ingalls (Solar Park Energy LLC) | 00297447 | 034 - Amsterdam | AMSTERDAM | 12010 | 36_35_50252 | MAPLE AVE 502 | N |  | 5000 |  |  | CDG | N | 2020-08-06 | 2020-08-12 | 4 | 2020-08-12 | 2020-08-12 | 2020-08-12 | 0 | 2020-10-12 | 2020-10-12 | 2021-02-19 | 59 | 9400 |  | 284730.58 | [8 empty] | N | N
NIMO | Standard Solar (Standard Solar) | 00253851 |  | AMSTERDAM | 12010 | 36_35_50251 | MAPLE AVE 502 | N |  | 5000 |  |  | CDG | Y | 2019-12-09 | 2020-01-23 | 0 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 0 | 2020-05-19 | 2020-05-19 | 2020-11-06 | 58 | 9400 |  | 150366.86 |  |  | 2021-02-01 | [5 empty] | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00344508 | 034 - Amsterdam | AMSTERDAM | 12866 |  |  | N |  | 5000 |  |  | CDG | N | 2021-03-25 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00301635 | 010 - Olean | ANDOVER | 14806 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-03 | 2020-08-03 | 2020-08-05 | 1 | 2020-08-13 | 2020-08-13 | 2021-02-09 | 55 | 10900 | [10 empty] | N | N
NIMO | VANGUARD ENERGY PARTNERS LLC | 00102042 | 007 - Angola | ANGOLA | 14006 | 36_07_9353 | DELAMETER RD SUBSTATION | N |  | 930 |  |  | NA | Y | 2016-02-25 | 2016-03-31 | 7 | 2016-03-31 | 2016-03-31 | 2016-04-13 | 0 | 2016-09-13 | 2016-09-13 | 2016-12-12 | 60 | 21300 |  | 30000 |  |  | 2017-07-18 |  |  | 2018-12-13 | 2018-12-13 | 2018-12-13 | Y | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00286223 | 007 - Angola | ANGOLA | 14006 | 36_07_9351 | DELAMETER RD SUBSTATION | N |  | 3250 |  |  | RNM | Y | 2020-04-03 | 2020-04-10 | 5 | 2020-04-10 | 2020-04-10 | 2020-04-10 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-24 | 59 | 9400 |  | 689651 |  |  | 2021-01-13 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00339085 | 007 - Angola | ANGOLA | 14006 | 36_07_18253 | LAKEVIEW 182 | N |  | 5000 |  |  | CDG | N | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-02-26 | 2021-02-26 | 0 |  |  |  |  | 8700 | [10 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00194524 | 038 - Glens Falls | ARGYLE | 12809 | 36_38_33751 | BURGOYNE 337 | Y |  | 4980 | 5000 |  | CDG | Y | 2018-08-30 | 2018-09-11 | 7 | 2018-09-11 | 2018-09-11 | 2018-10-01 | 13 | 2018-12-06 | 2018-12-06 | 2019-03-11 | 58 | 15300 |  | 781786.8 |  |  | 2019-10-08 | 2020-05-14 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00254053 | 009 - Lakewood/Stow | ASHVILLE | 14710 | 36_09_15056 | BAKER ST 150 | N |  | 3750 |  |  | CDG | Y | 2019-09-16 | 2019-09-27 | 9 | 2019-09-27 | 2019-09-27 | 2019-10-16 | 12 | 2020-01-06 | 2020-01-06 | 2020-04-21 | 59 | 11200 |  | 1654643 |  |  | 2020-09-09 | 2021-03-03 |  |  |  |  | N | Y
NIMO | Will Fischer (SRE Solar Origination 2, LLC) | 00295510 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N |  | 4000 |  |  | CDG | N | 2020-06-12 | 2020-06-18 | 4 | 2020-06-18 | 2020-06-18 | 2020-06-18 | 0 | 2020-06-26 | 2020-06-26 | 2020-12-29 | 59 | 11700 |  | 1146031 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00254055 | 009 - Lakewood/Stow | ASHVILLE | 14710 | 36_09_15056 | BAKER ST 150 | N |  | 5000 |  |  | CDG | Y | 2019-09-16 | 2019-09-27 | 9 | 2019-09-27 | 2019-09-27 | 2019-10-16 | 12 | 2020-01-06 | 2020-01-06 | 2020-04-22 | 58 | 11200 |  | 1787870 |  |  | 2020-10-06 | [5 empty] | N | Y
NIMO | Will Fischer (SRE Solar Origination 2, LLC) | 00294751 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N |  | 5000 |  |  | CDG | N | 2020-06-19 | 2020-06-25 | 4 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 0 | 2020-07-17 | 2020-07-17 | 2020-12-29 | 41 | 11700 |  | 705201 | [8 empty] | N | N
NIMO | SRE Solar Origination 2, LLC | 00294971 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N |  | 5000 |  |  | CDG | N | 2020-06-19 | 2020-06-26 | 5 | 2020-06-26 | 2020-06-26 | 2020-06-26 | 0 | 2020-07-17 | 2020-07-17 | 2020-12-29 | 41 | 11700 |  | 702524 | [8 empty] | N | N
NIMO | Matt Marino (Panama PV I, LLC) | 00312373 | 009 - Lakewood/Stow | ASHVILLE | 14710 | SHERMAN-ASHVILLE #863 |  | N |  | 5000 |  |  | CDG | N | 2020-09-15 | 2020-09-24 | 7 | 2020-09-24 | 2020-09-24 | 2020-09-24 | 0 | 2020-10-08 | 2020-10-08 | 2021-02-08 | 59 | 10700 |  | 1038575 | [8 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00269517 | 004 - Batavia | ATTICA | 14011 | 36_04_1262 | ATTICA 12 | N |  | 5000 |  |  | CDG | Y | 2020-01-15 | 2020-01-27 | 7 | 2020-01-27 | 2020-01-27 | 2020-01-28 | 0 | 2020-02-14 | 2020-02-14 | 2020-06-12 | 58 | 10900 |  | 795737 |  |  | 2020-10-20 | [5 empty] | N | Y
NIMO | John McDonough (Omni-Navitas Holdings, LLC) | 00261625 | 011 - Syracuse | AUBURN | 13021 | 36_11_29451 | NILES 294 | N |  | 4625 |  |  | CDG | Y | 2019-11-13 | 2019-11-20 | 5 | 2019-11-20 | 2019-11-20 | 2019-12-10 | 11 | 2020-03-25 | 2020-03-25 | 2020-06-30 | 59 | 9400 |  | 689536 |  |  | 2020-11-09 | 2021-04-05 |  |  |  |  | N | Y
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00293847 | 018 - Rome | AVA | 13303 | 36_18_65357 | TURIN RD 653 | N |  | 5000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 0 | 2020-07-09 | 2020-07-09 | 2020-12-15 | 59 | 10100 |  | 1435755 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS II, LLC) | 00284096 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 |  | Y |  | 5000 | 0 |  | CDG | Y | 2020-04-24 | 2020-05-04 | 6 | 2020-05-04 | 2020-05-04 | 2020-05-04 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-31 | 57 | 10000 |  | 453245.69 |  |  | 2020-12-18 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221274 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-05-01 | 2019-05-09 | 6 | 2019-05-09 | 2019-05-09 | 2019-05-14 | 2 | 2019-08-22 | 2019-08-22 | 2019-11-23 | 56 | 9500 |  | 307999 |  |  | 2019-11-27 | 2020-09-13 |  |  |  |  | N | Y
NIMO | RER Energy Group | 00094520 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 | AVON 43 | N |  | 1080 |  |  | RNM | N | 2014-07-18 | 2014-12-30 | 118 | 2014-12-30 | 2014-12-30 | 2015-01-15 | 0 | 2015-03-06 | 2015-03-06 | 2015-06-17 | 73 | 14860 |  | 260420 | [5 empty] | 2016-07-12 | 2016-07-12 | 2016-07-12 | Y | N
NIMO | Jacob Fraatz (Dimension Energy LLC (Dimension Rene | 00302543 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 |  | N |  | 4250 |  |  | CDG | Y | 2020-08-20 | 2020-08-27 | 5 | 2020-08-27 | 2020-08-27 | 2020-08-27 | 0 | 2020-09-18 | 2020-09-18 | 2021-02-19 | 57 | 9800 |  | 329618 | [8 empty] | N | Y
NIMO | Ryan Lloyd (AVON SOLAR FARM, LLC) | 00171666 |  | AVON | 14414 | 36_05_5151 | E. GOLAH 51 | N |  | 5000 |  |  | CDG | Y | 2018-03-14 | 2018-03-26 | 5 | 2018-03-26 | 2018-03-26 | 2018-04-03 | 5 | 2018-04-25 | 2018-04-25 | 2018-06-28 | 45 | 13400 |  | 323917 |  |  | 2018-11-08 | 2019-06-14 |  |  |  |  | N | Y
NIMO | Sam Youneszadeh (Dimension NY 1, LLC) | 00313961 | 005 - Avon | AVON | 14414 | GOLAH-N LAKEVILLE #217 |  | N |  | 5000 |  |  | CDG | Y | 2020-10-05 | 2020-10-11 | 5 | 2020-10-11 | 2020-10-11 | 2020-10-11 | 0 | 2021-02-01 | 2021-02-01 |  |  | 10500 | [10 empty] | N | Y
NIMO | Raj Soi (SSC Lysander LLC) | 00250467 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_29754 | LYSANDER 297 | Y |  | 3500 | 5000 |  | CDG | Y | 2019-09-20 | 2019-09-30 | 6 | 2019-09-30 | 2019-09-30 | 2019-10-17 | 12 | 2019-10-31 | 2019-10-31 | 2020-02-18 | 59 | 9700 |  | 215219.52 |  |  | 2020-03-31 | 2020-09-22 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00229118 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26952 | SORRELL HILL 269 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-05-30 | 2019-06-10 | 7 | 2019-06-10 | 2019-06-10 | 2019-06-13 | 2 | 2019-06-25 | 2019-06-25 | 2019-12-16 | 55 | 11800 |  | 992083.75 |  |  | 2020-02-19 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00218919 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26951 | SORRELL HILL 269 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-04-25 | 2019-04-30 | 3 | 2019-04-30 | 2019-04-30 | 2019-05-09 | 6 | 2019-07-18 | 2019-07-18 | 2019-11-21 | 58 | 11400 |  | 1255615 |  |  | 2020-03-30 | 2020-09-09 |  |  |  |  | N | Y
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00101328 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26952 | SORRELL HILL 269 | N |  | 2000 |  |  | RNM | N | 2015-05-29 | 2015-06-12 | 8 | 2015-06-12 | 2015-06-12 | 2015-07-06 | 0 | 2016-02-09 | 2016-02-09 | 2016-05-18 | 71 | 25000 |  | 144500 |  |  | 2017-01-31 |  |  | 2018-06-20 | 2018-06-20 | 2018-06-20 | Y | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00309114 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26051 | BELMONT 260 | N |  | 5000 |  |  | CDG | N | 2020-09-02 | 2020-09-10 | 5 | 2020-09-10 | 2020-09-10 | 2020-09-10 | 0 | 2020-10-26 | 2020-10-26 | 2021-02-17 | 57 | 10100 |  | 1233812 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00329378 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_26051 | BELMONT 260 | N |  | 5000 |  |  | CDG | N | 2021-01-08 | 2021-01-13 | 3 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 0 |  |  |  |  | 7800 | [10 empty] | N | N
NIMO | Haley Orvedal (Galehead DG Solutions) | 00330807 | 011 - Syracuse | BALDWINSVILLE | 13027 | 36_11_29753 | LYSANDER 297 | N |  | 5000 |  |  | CDG | N | 2020-12-11 | 2020-12-21 | 6 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 0 | 2021-03-03 | 2021-03-03 |  |  | 9400 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00206362 | 032 - Schenectady | BALLSTON LAKE | 12019 | 36_32_322151 | LASHER RD | N |  | 2000 |  |  | CDG | Y | 2019-01-31 | 2019-02-08 | 6 | 2019-02-08 | 2019-02-08 | 2019-02-21 | 7 | 2019-06-13 | 2019-06-13 | 2020-04-08 | 59 | 10000 |  | 206022 |  |  | 2020-08-14 | 2021-02-09 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00170779 | 032 - Schenectady | BALLSTON LAKE | 12019 | 36_32_44256 | ELNORA 442 | N |  | 4000 |  |  | CDG | Y | 2018-03-01 | 2018-03-01 | 0 | 2018-03-13 | 2018-03-13 | 2018-03-27 | 10 | 2018-06-05 | 2018-06-05 | 2018-07-31 | 39 | 13300 |  | 765245 |  |  | 2018-10-04 |  |  | 2019-12-19 | 2019-12-19 | 2019-12-19 | Y | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00273180 | 032 - Schenectady | BALLSTON LAKE | 12019 | 36_32_44256 | ELNORA 442 | N |  | 5000 |  |  | CDG | Y | 2020-01-29 | 2020-02-07 | 7 | 2020-02-07 | 2020-02-07 | 2020-02-10 | 0 | 2020-02-27 | 2020-02-27 | 2020-07-02 | 46 | 8500 |  | 1169705.76 |  |  | 2020-11-12 | 2021-01-14 |  |  |  |  | N | Y
NIMO | Rob Garrity (Finlo, LLC) | 00345205 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_01252 | BALLSTON 12 | Y |  | 5000 | 0 |  | CDG | N | 2021-03-05 | 2021-03-11 | 4 | 2021-03-11 | 2021-03-11 | 2021-03-30 | 12 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Rob Garrity (Finlo, LLC) | 00317963 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_01252 | BALLSTON 12 | Y |  | 5000 | 5000 |  | CDG | N | 2020-10-12 | 2020-10-19 | 5 | 2020-10-19 | 2020-10-19 | 2020-11-03 | 10 |  |  |  |  | 10300 | [10 empty] | N | N
NIMO | Christopher Stroud (Cipriani Energy Group Corp.) | 00287224 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_01254 | BALLSTON 12 | N |  | 1400 |  |  | CDG | Y | 2020-04-13 | 2020-04-24 | 9 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 0 | 2020-05-04 | 2020-05-04 | 2020-07-28 | 55 | 8600 |  | 150473 |  |  | 2020-12-09 | [5 empty] | N | Y
NIMO | Lluis Torrent (CAERO) | 00321454 | 039 - Saratoga | BALLSTON SPA | 12020 | 36_39_36952 | BROOK RD 369 | N |  | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-08 | 5 | 2020-12-08 | 2020-12-08 | 2020-12-15 | 4 | 2021-03-24 | 2021-03-24 |  |  | 9800 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00274542 | 032 - Schenectady | BALLSTON SPA | 12020 | 36_32_322153 | LASHER RD | N |  | 5000 |  |  | CDG | Y | 2020-02-28 | 2020-03-10 | 7 | 2020-03-10 | 2020-03-10 | 2020-03-25 | 10 | 2020-06-09 | 2020-06-09 | 2020-09-21 | 59 | 10500 |  | 121955.41 |  |  | 2021-02-03 | [5 empty] | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00274549 | 032 - Schenectady | BALLSTON SPA | 12020 | 36_32_322153 | LASHER RD | N |  | 5000 |  |  | CDG | Y | 2020-02-28 | 2020-03-10 | 7 | 2020-03-10 | 2020-03-10 | 2020-03-25 | 10 | 2020-06-09 | 2020-06-09 | 2020-09-21 | 59 | 10500 |  | 121955.41 |  |  | 2021-03-19 | [5 empty] | N | Y
NIMO | Amanda Postma (Renovus Solar) | 00279867 | 039 - Saratoga | BALLSTON SPA | 12020 |  |  | N |  | 5000 |  |  | CDG | N | 2020-03-11 | 2020-03-18 | 5 | 2020-03-18 | 2020-03-18 | 2020-03-19 | 0 | 2020-03-25 | 2020-03-25 | 2020-12-16 | 55 | 9000 | [10 empty] | N | N
NIMO | Joe Fiori (Nexamp) | 00250999 | 027 - Malone | BANGOR | 12966 | 36_27_89552 | MALONE 895 | N |  | 3400 |  |  | CDG | Y | 2019-09-25 | 2019-10-04 | 7 | 2019-10-04 | 2019-10-04 | 2019-10-25 | 14 | 2019-12-02 | 2019-12-02 | 2020-03-11 | 59 | 8300 |  | 970504 |  |  | 2020-07-17 | 2021-01-07 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00278548 | 006 - Albion/Medina | BARKER | 14012 | 36_06_7861 | BARKER 78 | N |  | 1025 |  |  | RNM | N | 2020-02-10 | 2020-02-24 | 9 | 2020-02-24 | 2020-02-24 | 2020-02-27 | 2 | 2020-03-27 | 2020-03-27 | 2020-08-03 | 56 | 10400 |  | 710788 |  |  | 2021-01-08 | [5 empty] | N | N
NIMO | Michael Kennedy (Citizens Energy Corporation) | 00101357 | 017 - Utica | BARNEVELD | 13304 | 36_17_33351 | SHERMAN 333 | N |  | 1000 |  |  | RNM | N | 2015-05-29 | 2016-01-20 | 13 | 2016-01-20 | 2016-01-20 | 2016-02-12 | 0 | 2016-10-03 | 2016-10-03 | 2016-12-19 | 55 | 25000 |  |  |  |  | 2017-05-31 |  |  | 2019-05-10 | 2019-05-10 | 2019-05-10 | Y | N
NIMO | William Jordan (Jordan Energy & Food Enterprises, | 00299803 | 017 - Utica | BARNEVELD | 13304 | 36_17_33351 | SHERMAN 333 | N |  | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-03 | 2020-08-03 | 2020-08-06 | 2 | 2020-09-24 | 2020-09-24 | 2021-02-08 | 59 | 9400 |  | 756454 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00340615 | 004 - Batavia | BASOM | 14013 |  |  | Y |  |  | 0 | 5000 | CDG | N | 2021-04-01 | 2021-04-01 | 5 | 2021-04-01 | [18 empty] | N | N
NIMO | guo qing Zhou (Advanced Solar Power Holdings INC) | 00254704 |  | BATAVIA | 14020 | 36_04_0152 | BATAVIA 1 | Y |  | 5040 | 5040 |  | CDG | Y | 2019-10-21 | 2019-10-29 | 6 | 2019-10-29 | 2019-10-29 | 2019-11-18 | 12 | 2020-02-03 | 2020-02-03 | 2020-06-17 | 54 | 9100 |  | 243646.68 |  |  | 2020-10-29 | [5 empty] | N | Y
NIMO | Sanket Kolte (YSG Solar) | 00265575 | 004 - Batavia | BATAVIA | 14020 | 36_04_2855 | E. BATAVIA 28 | N |  | 1650 |  |  | CDG | N | 2019-12-24 | 2020-01-08 | 9 | 2020-01-08 | 2020-01-08 | 2020-01-27 | 11 | 2020-03-30 | 2020-03-30 | 2020-09-11 | 60 | 7900 |  | 322030 | [8 empty] | N | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00100794 | 004 - Batavia | BATAVIA | 14020 | 36_04_2856 | E. BATAVIA 28 | N |  | 2000 |  |  | RNM | N | 2015-04-24 | 2015-04-24 | 0 | 2015-04-24 |  |  |  | 2016-02-05 | 2016-02-05 | 2016-06-17 | 95 |  |  | 213350 |  |  | 2017-01-31 |  |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00100862 | 004 - Batavia | BATAVIA | 14020 | 36_04_0154 | BATAVIA 1 | N |  | 2000 |  |  | RNM | N | 2015-05-13 | 2015-05-28 | 3 | 2015-05-28 | 2015-05-28 | 2015-06-17 | 0 | 2015-10-30 | 2015-10-30 | 2016-06-17 | 165 | 20600 |  | 144500 |  |  | 2017-01-31 |  |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00101327 | 004 - Batavia | BATAVIA | 14020 | 36_04_0154 | BATAVIA 1 | N |  | 2000 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 8 | 2015-06-11 | 2015-06-11 | 2015-07-02 | 0 | 2015-10-22 | 2015-10-22 | 2016-07-15 | 191 | 30000 |  | 213350 |  |  | 2017-01-31 |  |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Cypress Creek Renewables LLC | 00102232 | 004 - Batavia | BATAVIA | 14020 | 36_04_0153 | BATAVIA 1 | N |  | 2000 |  |  | CDG | Y | 2016-07-07 | 2016-07-13 | 4 | 2016-07-13 | 2016-07-13 | 2016-07-16 | 3 | 2016-09-13 | 2016-09-13 | 2017-01-07 | 60 | 21200 |  | 147500 |  |  | 2017-04-07 |  |  | 2018-12-28 | 2018-12-28 | 2018-12-28 | Y | Y
NIMO | Cypress Creek Renewables LLC | 00101629 | 004 - Batavia | BATAVIA | 14020 | 36_04_0153 | BATAVIA 1 | N |  | 2000 |  |  | CDG | Y | 2016-08-08 | 2016-08-15 | 5 | 2016-08-15 | 2016-08-15 | 2016-08-16 | 1 | 2016-11-29 | 2016-11-29 | 2017-02-27 | 60 | 21200 |  | 212250 |  |  | 2017-05-23 |  |  | 2018-12-28 | 2018-12-28 | 2018-12-28 | Y | Y
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00315638 | 004 - Batavia | BATAVIA | 14020 | 36_04_0158 | BATAVIA 1 | N |  | 2500 |  |  | CDG | N | 2020-10-02 | 2020-10-08 | 4 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 | 2020-12-22 | 2020-12-22 | 2021-03-26 | 56 | 9400 |  | 12736423 | [8 empty] | N | N
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00315631 | 004 - Batavia | BATAVIA | 14020 | 36_04_0158 | BATAVIA 1 | N |  | 3000 |  |  | CDG | N | 2020-09-29 | 2020-10-07 | 6 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 0 | 2020-11-09 | 2020-11-09 | 2021-03-26 | 56 | 9400 |  | 121920 | [8 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00196061 | 004 - Batavia | BATAVIA | 14020 | 36_04_0155 | BATAVIA 1 | N |  | 3000 |  |  | CDG | Y | 2018-09-21 | 2018-10-01 | 6 | 2018-10-01 | 2018-10-01 | 2018-10-04 | 2 | 2018-12-17 | 2018-12-17 | 2019-04-22 | 48 | 13300 |  | 216004 |  |  | 2019-05-07 | 2019-10-26 | 2019-10-26 | 2021-03-30 | 2021-03-30 | 2021-03-30 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00196062 | 004 - Batavia | BATAVIA | 14020 | 36_04_0155 | BATAVIA 1 | N |  | 4000 |  |  | CDG | Y | 2018-09-21 | 2018-10-02 | 7 | 2018-10-02 | 2018-10-02 | 2018-10-04 | 1 | 2018-12-21 | 2018-12-21 | 2019-04-22 | 48 | 13300 |  | 216997 |  |  | 2019-05-07 | 2020-10-26 | 2020-10-26 | 2021-03-23 | 2021-03-23 | 2021-03-23 | Y | Y
NIMO | Kevin Rabbitt (Bright Oak Solar LLC) | 00188994 | 004 - Batavia | BATAVIA | 14020 | 36_04_0152 | BATAVIA 1 | N |  | 4000 |  |  | CDG | Y | 2018-06-29 | 2018-07-10 | 4 | 2018-07-10 | 2018-07-10 | 2018-07-30 | 13 | 2018-08-20 | 2018-08-20 | 2019-01-23 | 59 | 13300 |  | 202776 |  |  | 2019-05-29 | 2020-02-19 |  |  |  |  | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables, LLC) | 00262232 | 004 - Batavia | BATAVIA | 14020 | 36_04_2851 | E. BATAVIA 28 | N |  | 4000 |  |  | CDG | Y | 2020-01-23 | 2020-01-23 | 0 | 2020-01-23 | 2020-01-23 | 2020-01-31 | 5 | 2020-03-26 | 2020-03-26 | 2020-07-06 | 60 | 9100 |  | 249314.24 |  |  | 2020-11-10 | [5 empty] | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00305239 | 004 - Batavia | BATAVIA | 14020 | 36_04_0154 | BATAVIA 1 | N |  | 5000 |  |  | CDG | N | 2020-09-25 | 2020-10-02 | 5 | 2020-10-02 | 2020-10-02 | 2020-10-02 | 0 | 2021-03-17 | 2021-03-17 |  |  | 9000 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00213630 | 004 - Batavia | BATAVIA | 14020 | 36_04_2856 | E. BATAVIA 28 | N |  | 5000 |  |  | CDG | Y | 2019-03-21 | 2019-03-27 | 4 | 2019-03-27 | 2019-03-27 | 2019-04-08 | 7 | 2019-06-17 | 2019-06-17 | 2019-11-22 | 56 | 9000 |  | 158311.69 |  |  | 2019-12-06 | 2020-04-14 |  |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc) | 00349348 | 004 - Batavia | BATAVIA | 14020 | 36_04_2855 | E. BATAVIA 28 | N |  | 5000 |  |  | CDG | N | 2021-03-29 | 2021-04-06 | 6 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 0 |  |  |  |  | 6900 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc) | 00349359 | 004 - Batavia | BATAVIA | 14020 | 36_04_2855 | E. BATAVIA 28 | N |  | 5000 |  |  | CDG | N | 2021-03-29 | 2021-04-06 | 6 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 0 |  |  |  |  | 6900 | [10 empty] | N | N
NIMO | Harsh Mehta (Cypress Creek Renewables LLC) | 00105725 | 004 - Batavia | BATAVIA | 14020 | 36_04_2851 | E. BATAVIA 28 | N |  | 5000 |  |  | CDG | Y | 2017-06-16 | 2017-06-16 | 1 | 2017-06-16 | 2017-06-16 | 2018-01-18 | 11 | 2018-04-05 | 2018-04-05 | 2018-09-24 | 58 | 15600 |  | 236940.9 |  |  | 2019-03-14 | 2019-09-03 |  |  |  |  | N | Y
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00193998 | 037 - Cobleskill | BERNE | 12023 | 36_37_23452 | SCHOHARIE 234 | N |  | 4250 |  |  | CDG | Y | 2018-09-14 | 2018-09-14 | 0 | 2018-09-14 | 2018-09-14 | 2018-10-04 | 13 | 2019-07-12 | 2019-07-12 | 2019-09-24 | 51 | 17400 |  | 529905.64 |  |  | 2020-04-14 | 2020-10-06 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00339089 | 027 - Malone | BOMBAY | 12914 | 36_27_86652 | N. BOMBAY 866 | N |  | 5000 |  |  | CDG | N | 2021-03-10 | 2021-03-16 | 4 | 2021-03-16 | 2021-03-16 | 2021-03-30 | 9 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00320064 | 025 - Potsdam | BOMBAY | 12914 | AKWESASNE-FT. COVINGTON #26 |  | N |  | 5000 |  |  | CDG | N | 2020-11-06 | 2020-11-17 | 6 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 | 2020-12-07 | 2020-12-07 |  |  | 12100 | [10 empty] | N | N
NIMO | Sachin Patel (NY Solar One, LLC) | 00334918 | 017 - Utica | BOONVILLE | 13309 | 36_17_70152 | ALDER CREEK 701 | N |  | 4980 |  |  | CDG | N | 2021-01-15 | 2021-01-20 | 2 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 0 | 2021-03-24 | 2021-03-24 |  |  | 8400 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00307874 | 023 - Lowville | BOONVILLE | 13309 | LOWVILLE-BOONVILLE #22 |  | N |  | 5000 |  |  | CDG | N | 2020-09-04 | 2020-09-14 | 5 | 2020-09-14 | 2020-09-14 | 2020-09-29 | 10 | 2020-10-13 | 2020-10-13 | 2021-03-04 | 59 | 11300 |  | 1687818 | [8 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00296976 | 011 - Syracuse | BREWERTON | 13029 | 36_11_32556 | BARTELL RD 325 | Y |  | 5000 | 2500 |  | CDG | N | 2020-07-01 | 2020-07-09 | 5 | 2020-07-09 | 2020-07-09 | 2020-07-17 | 0 | 2020-08-28 | 2020-08-28 | 2021-01-20 | 58 | 9300 |  | 689783 | [8 empty] | N | N
NIMO | Matt Marino (Galehead DG Solutions, LLC) | 00299975 | 011 - Syracuse | BREWERTON | 13029 | 36_11_32555 | BARTELL RD 325 | N |  | 4200 |  |  | CDG | N | 2020-07-21 | 2020-07-27 | 4 | 2020-07-27 | 2020-07-27 | 2020-07-28 | 0 | 2020-09-18 | 2020-09-18 | 2021-01-20 | 58 | 9400 |  | 759477.26 | [8 empty] | N | N
NIMO | David Spotts (SSC Cicero LLC) | 00298227 | 011 - Syracuse | BREWERTON | 13029 |  |  | N |  | 5000 |  |  | CDG | Y | 2020-06-26 | 2020-07-05 | 5 | 2020-07-05 | 2020-07-05 | 2020-07-05 | 0 | 2020-07-16 | 2020-07-16 | 2020-10-26 | 59 | 10400 |  | 235991.31 |  |  | 2020-12-07 | [5 empty] | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00343096 | 011 - Syracuse | BREWERTON | 13029 | WOODARD-TEALL #32 |  | N |  | 5000 |  |  | CDG | N | 2021-03-10 | 2021-03-17 | 5 | 2021-03-17 | 2021-03-17 | 2021-03-17 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00344158 | 011 - Syracuse | BREWERTON | 13029 | WOODARD-TEALL #32 |  | N |  | 5000 |  |  | CDG | N | 2021-03-10 | 2021-03-19 | 7 | 2021-03-19 | 2021-03-19 | 2021-03-19 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Jamal Batar (DSD Renewables) | 00196516 | 028 - Ogdensburg | BRIER HILL | 13614 | MCINTYRE-HAMMOND #24 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2018-09-21 | 2018-10-03 | 7 | 2018-10-03 | 2018-10-03 | 2018-10-05 | 1 | 2019-04-17 | 2019-04-17 | 2019-11-22 | 119 | 12200 |  | 533097 |  |  | 2020-04-14 | 2020-10-08 |  |  |  |  | N | Y
NIMO | Josh katz (Onyx Development Grou) | 00100805 | 035 - Gloversville | BROADALBIN | 12025 | 36_35_39252 | VAIL MILLS 392 | N |  | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-11 | 3 | 2015-06-11 | 2015-06-11 | 2015-06-16 | 0 | 2015-12-15 | 2015-12-15 | 2016-05-17 | 110 | 25000 |  | 239130 | [5 empty] | 2018-03-21 | 2018-03-21 | 2018-03-21 | Y | N
NIMO | Michael Cucchiara (Nexamp Solar LLC) | 00194894 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8255 | W. HAMLIN 82 | Y |  | 5000 | 5000 |  | CDG | Y | 2018-10-15 | 2018-10-25 | 8 | 2018-10-25 | 2018-10-25 | 2018-10-26 | 0 | 2018-11-28 | 2018-11-28 | 2019-04-25 | 60 | 12200 |  | 247369 |  |  | 2019-09-03 | 2020-03-13 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00196184 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8252 | W. HAMLIN 82 | N |  | 1500 |  |  | CDG | Y | 2018-10-11 | 2018-10-23 | 8 | 2018-10-23 | 2018-10-23 | 2018-11-02 | 7 | 2019-02-11 | 2019-02-11 | 2019-04-22 | 44 | 13300 |  | 289514 |  |  | 2019-08-23 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00252174 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7452 | BROCKPORT 74 | N |  | 3600 |  |  | CDG | Y | 2019-10-08 | 2019-10-18 | 8 | 2019-10-18 | 2019-10-18 | 2019-11-04 | 10 | 2019-11-18 | 2019-11-18 | 2020-10-01 | 57 | 7500 |  | 238932.12 |  |  | 2021-02-04 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248893 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7457 | BROCKPORT 74 | N |  | 4250 |  |  | CDG | N | 2019-08-16 | 2019-08-27 | 7 | 2019-08-27 | 2019-08-27 | 2019-09-04 | 4 | 2019-11-22 | 2019-11-22 | 2020-04-23 | 58 | 9400 |  | 331849 |  |  | 2021-01-20 | [5 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00251021 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7458 | BROCKPORT 74 | N |  | 4700 |  |  | CDG | Y | 2019-09-16 | 2019-09-26 | 8 | 2019-09-26 | 2019-09-26 | 2019-10-15 | 12 | 2019-12-20 | 2019-12-20 | 2020-04-14 | 59 | 8100 |  | 150464 |  |  | 2020-11-16 | [5 empty] | N | Y
NIMO | Ryan Lloyd (Helios Energy New York 3 LLC) | 00173286 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7459 | BROCKPORT 74 | N |  | 5000 |  |  | CDG | Y | 2018-04-10 | 2018-04-24 | 6 | 2018-04-24 | 2018-04-24 | 2018-07-09 | 12 | 2018-09-13 | 2018-09-13 | 2019-01-24 | 59 | 13300 |  | 188419 |  |  | 2019-06-07 | 2020-01-13 |  |  |  |  | N | Y
NIMO | Ryan Lloyd (HELIOS ENERGY NY 10 LLC) | 00173288 |  | BROCKPORT | 14420 | 36_06_7459 | BROCKPORT 74 | N |  | 5000 |  |  | CDG | Y | 2018-04-10 | 2018-04-24 | 6 | 2018-04-24 | 2018-04-24 | 2018-07-09 | 12 | 2018-09-13 | 2018-09-13 | 2019-01-24 | 59 | 13300 |  | 211615 |  |  | 2019-06-04 | 2020-01-13 |  |  |  |  | N | Y
NIMO | Haley Orvedal (Galehead DG Solutions, LLC) | 00350036 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7457 | BROCKPORT 74 | N |  | 5000 |  |  | CDG | N | 2021-04-01 | 2021-04-08 | 5 | 2021-04-08 | 2021-04-08 | [17 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00250373 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_7452 | BROCKPORT 74 | N |  | 5000 |  |  | CDG | Y | 2019-09-11 | 2019-09-23 | 8 | 2019-09-23 | 2019-09-23 | 2019-10-02 | 6 | 2019-11-07 | 2019-11-07 | 2020-09-28 | 57 | 8100 |  | 125017.58 |  |  | 2021-02-04 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00196186 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8252 | W. HAMLIN 82 | N |  | 5000 |  |  | CDG | Y | 2018-10-11 | 2018-10-23 | 8 | 2018-10-23 | 2018-10-23 | 2018-11-02 | 7 | 2019-02-11 | 2019-02-11 | 2019-04-22 | 44 | 12200 |  | 350688 |  |  | 2019-08-23 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00340660 | 006 - Albion/Medina | BROCKPORT | 14420 | 36_06_8252 | W. HAMLIN 82 | N |  | 5000 |  |  | CDG | N | 2021-02-25 | 2021-03-04 | 5 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 0 | 2021-03-25 | 2021-03-25 |  |  | 6600 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00307770 | 006 - Albion/Medina | BROCKPORT | 14420 | WATERPORT-BROCKPORT #307 |  | N |  | 5000 |  |  | CDG | N | 2020-08-26 | 2020-09-02 | 5 | 2020-09-02 | 2020-09-02 | 2020-09-14 | 6 | 2020-09-21 | 2020-09-21 | 2021-02-19 | 59 | 9400 |  | 5654772 | [8 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00221618 | 008 - Dunkirk/Fredoni | BROCTON | 14716 | 36_08_15353 | BERRY RD 153 | N |  |  |  | 2000 | CDG | N | 2019-05-20 | 2019-05-29 | 6 | 2019-05-29 | 2019-05-29 | 2019-06-03 | 2 | 2019-07-19 | 2019-07-19 | 2019-12-04 | 59 | 8700 |  | 65504.99 |  |  | 2020-05-05 | [5 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00221627 | 008 - Dunkirk/Fredoni | BROCTON | 14716 | 36_08_15353 | BERRY RD 153 | N |  |  |  | 2000 | CDG | N | 2019-05-20 | 2019-05-29 | 6 | 2019-05-29 | 2019-05-29 | 2019-06-03 | 2 | 2019-07-19 | 2019-07-19 | 2019-12-04 | 59 | 9200 |  | 65504.99 |  |  | 2020-05-05 | [5 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00221628 | 008 - Dunkirk/Fredoni | BROCTON | 14716 | 36_08_15353 | BERRY RD 153 | N |  |  |  | 1000 | CDG | N | 2019-05-20 | 2019-05-29 | 6 | 2019-05-29 | 2019-05-29 | 2019-06-04 | 3 | 2019-07-19 | 2019-07-19 | 2019-12-04 | 59 | 9200 |  | 262020 |  |  | 2020-05-05 | [5 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00288142 | 001 - Buffalo | BUFFALO | 14220 | OHIO ST-RIDGE #613 |  | Y |  | 5000 | 5000 |  | CDG | N | 2020-04-22 | 2020-04-30 | 6 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 0 | 2020-06-04 | 2020-06-04 | 2020-12-05 | 59 | 10600 |  | 393402 | [8 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00288786 | 001 - Buffalo | BUFFALO | 14220 | OHIO ST-RIDGE #613 |  | Y |  | 5000 | 5000 |  | CDG | N | 2020-04-22 | 2020-04-30 | 6 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 0 | 2020-06-04 | 2020-06-04 | 2020-12-05 | 59 | 10600 |  | 309238.66 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00271877 | 001 - Buffalo | BUFFALO | 14226 | 36_01_6051 | GETZVILLE 60 | N |  | 965.7 |  |  | NA | Y | 2020-02-27 | 2020-03-12 | 10 | 2020-03-12 |  |  |  | 2020-03-30 | 2020-03-30 | 2020-06-22 | 0 | 10000 | [10 empty] | N | Y
NIMO | Neil Libidinsky (Solar City) | 00265382 | 001 - Buffalo | BUFFALO | 14220 | Gardenville to Buffalo River Switch 145 - Solar City Tap |  | N |  | 1976.4 |  |  | NA | Y | 2019-11-15 | 2019-12-02 | 10 | 2019-12-02 |  |  |  | 2019-12-05 | 2019-12-05 | 2020-02-07 | 43 | 10000 | [10 empty] | N | Y
NIMO | Alicia Scott (BQ Energy Development, LLC.) | 00284584 | 001 - Buffalo | BUFFALO | 14210 | 36_01_5161 | BUFFALO STATION 51 - ELK & DOLE | N |  | 3500 |  |  | CDG | Y | 2020-03-27 | 2020-04-08 | 8 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 0 | 2020-04-21 | 2020-04-21 | 2020-10-01 | 58 | 9100 |  | 121955.41 |  |  | 2020-12-29 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00318995 | 001 - Buffalo | BUFFALO | 14218 | 36_01_21258 | HARBORFRONT 212 | N |  | 4000 |  |  | RNM | N | 2020-10-26 | 2020-11-03 | 6 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 | 2020-12-18 | 2020-12-18 | 2021-04-08 | 59 | 9000 |  | 245735 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291552 | 003 - Niagara Falls | BURT | 14028 | PHILLIPS RD-TELEGRAPH RD #304 |  | N |  | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-23 | 2020-07-23 | 2020-11-12 | 57 | 12100 |  | 510906 | [8 empty] | N | N
NIMO | Richard Gulden (Omni Navitas Holdings LLC) | 00291561 | 003 - Niagara Falls | BURT | 14108 | RANSOMVILLE-PHILLIPS RD #402 |  | N |  | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-23 | 2020-07-23 | 2020-11-16 | 58 | 11300 |  | 322361 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00294996 | 003 - Niagara Falls | BURT | 14028 | RANSOMVILLE-PHILLIPS RD #402 |  | N |  | 5000 |  |  | CDG | N | 2020-06-05 | 2020-06-12 | 5 | 2020-06-12 | 2020-06-12 | 2020-06-12 | 0 | 2020-09-04 | 2020-09-04 | 2021-02-04 | 58 | 10900 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00295002 | 003 - Niagara Falls | BURT | 14028 | RANSOMVILLE-PHILLIPS RD #402 |  | N |  | 5000 |  |  | CDG | N | 2020-06-08 | 2020-06-15 | 5 | 2020-06-15 | 2020-06-15 | 2020-06-15 | 0 | 2020-09-04 | 2020-09-04 | 2021-02-04 | 57 | 11300 |  | 2659978 | [8 empty] | N | N
NIMO | Dallas Manson (Nexamp) | 00237006 | 013 - Watertown | CALCIUM | 13616 | 36_13_32356 | INDIAN RIVER 323 | N |  | 5000 |  |  | CDG | Y | 2019-06-17 | 2019-06-27 | 8 | 2019-06-27 | 2019-06-27 | 2019-07-05 | 4 | 2019-09-16 | 2019-09-16 | 2019-12-16 | 59 | 13100 |  | 462464 |  |  | 2020-04-24 | 2020-10-16 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00229610 | 005 - Avon | CALEDONIA | 14423 | 36_05_5151 | E. GOLAH 51 | N |  | 1450 |  |  | RNM | Y | 2019-06-05 | 2019-06-18 | 13.1937 | 2019-06-19 | 2019-06-19 | 2019-07-02 | 8 | 2019-07-30 | 2019-07-30 | 2019-12-12 | 59 | 13300 |  | 331719 |  |  | 2020-04-01 | 2020-04-17 | 2020-04-17 | 2020-12-31 | 2020-12-31 | 2020-12-31 | Y | Y
NIMO | Mike Howell (C2 Energy Capital) | 00102158 | 005 - Avon | CALEDONIA | 14423 | 36_05_5151 | E. GOLAH 51 | N |  | 2000 |  |  | CDG | N | 2016-03-08 | 2016-06-14 | 10 | 2016-06-14 | 2016-06-14 | 2016-06-17 | 0 | 2017-02-01 | 2017-02-01 | 2017-04-25 | 59 | 24600 |  | 313152 |  |  | 2017-06-13 |  |  | 2020-02-28 | 2020-02-28 | 2020-02-28 | Y | N
NIMO | Margaret Campbell (EDF Renewables) | 00325669 | 005 - Avon | CALEDONIA | 14423 | CALEDONIA-GOLAH #213 |  | N |  | 3250 |  |  | CDG | N | 2021-01-15 | 2021-01-21 | 3 | 2021-01-21 | 2021-01-21 | 2021-01-22 | 0 | 2021-02-24 | 2021-02-24 |  |  | 8700 | [10 empty] | N | N
NIMO | Sam Youneszadeh (Dimension Energy LLC (Dimension R | 00296774 | 005 - Avon | CALEDONIA | 14487 | 36_05_5052 | MUMFORD 50 | N |  | 5000 |  |  | CDG | Y | 2020-06-25 | 2020-07-02 | 5 | 2020-07-02 | 2020-07-02 | 2020-07-13 | 5 | 2020-08-11 | 2020-08-11 | 2020-12-10 | 56 | 9200 |  | 791744 | [8 empty] | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00230056 | 005 - Avon | CALEDONIA | 14511 | N LEROY-CALEDONIA #203 |  | N |  | 5000 |  |  | CDG | Y | 2019-08-28 | 2019-09-06 | 6 | 2019-09-06 | 2019-09-06 | 2019-09-23 | 10 | 2019-10-02 | 2019-10-02 | 2020-04-05 | 78 | 11400 |  | 358419.34 |  |  | 2020-06-04 | 2020-12-07 |  |  |  |  | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00230057 | 005 - Avon | CALEDONIA | 14487 | N LEROY-CALEDONIA #203 |  | N |  | 5000 |  |  | CDG | Y | 2019-08-15 | 2019-08-27 | 8 | 2019-08-27 | 2019-08-27 | 2019-09-05 | 5 | 2019-09-11 | 2019-09-11 | 2020-04-05 | 61 | 10900 |  | 333480.55 |  |  | 2020-08-04 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00322653 | 039 - Saratoga | CAMBRIDGE | 12816 | 36_39_37653 | UNION ST 376 | N |  | 5000 |  |  | CDG | N | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | 2020-11-19 | 2020-11-19 | 0 | 2021-04-13 | 2021-04-13 |  |  | 9800 | [10 empty] | N | N
NIMO | Michael Roach (RER Energy Group LLC) | 00102468 | 018 - Rome | CAMDEN | 13316 | 36_18_66951 | LEHIGH 669 | N |  | 1794 |  |  | RNM | N | 2014-07-09 | 2014-11-25 | 100 | 2014-11-25 | 2014-11-25 | 2014-12-03 | 0 | 2015-08-25 | 2015-08-25 | 2016-04-07 | 162 | 15700 |  | 619869 |  |  | 2016-06-28 |  |  | 2017-11-20 | 2017-11-20 | 2017-11-20 | Y | N
NIMO | Khilan Munshi (Seaboard solar) | 00344926 | 018 - Rome | CAMDEN | 13316 | 36_18_66952 | LEHIGH 669 | N |  | 4975 |  |  | CDG | N | 2021-03-11 | 2021-03-18 | 5 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00279414 | 018 - Rome | CAMDEN | 13316 | 36_18_66954 | LEHIGH 669 | N |  | 5000 |  |  | CDG | Y | 2020-02-14 | 2020-02-28 | 9 | 2020-02-28 | 2020-02-28 | 2020-03-02 | 0 | 2020-04-23 | 2020-04-23 | 2020-07-27 | 58 | 8800 |  | 474117.71 |  |  | 2021-02-01 | [5 empty] | N | Y
NIMO | Green Street Power Partners | 00222726 | 018 - Rome | CAMDEN | 13316 | 36_18_66953 | LEHIGH 669 | N |  | 5000 |  |  | CDG | Y | 2019-04-29 | 2019-05-06 | 5 | 2019-05-06 | 2019-05-06 | 2019-05-14 | 5 | 2019-10-17 | 2019-10-17 | 2020-02-27 | 58 | 11400 |  | 920205 |  |  | 2020-04-20 | 2020-10-28 |  |  |  |  | N | Y
NIMO | Ryan McCune (Nexamp) | 00270386 | 018 - Rome | CAMDEN | 13316 | 36_18_66952 | LEHIGH 669 | N |  | 5000 |  |  | CDG | Y | 2020-01-27 | 2020-02-05 | 7 | 2020-02-05 | 2020-02-05 | 2020-02-13 | 5 | 2020-03-16 | 2020-03-16 | 2020-06-24 | 59 | 9400 |  | 591468.41 |  |  | 2020-09-28 | 2021-03-16 |  |  |  |  | N | Y
NIMO | Lluis Torrent (CAERO) | 00335257 |  | CAMILLUS | 13031 | 36_11_23557 | HARRIS RD 235 | N |  | 4000 |  |  | CDG | N | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-02-10 | 2021-02-10 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00306783 | 011 - Syracuse | CAMILLUS | 13031 | 36_11_23556 | HARRIS RD 235 | N |  | 5000 |  |  | CDG | N | 2020-08-17 | 2020-08-25 | 6 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 0 | 2020-10-13 | 2020-10-13 | 2021-02-04 | 58 | 8800 |  | 972767 | [8 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00237290 | 011 - Syracuse | CAMILLUS | 13031 | 36_11_26656 | MILTON AVE 266 | N |  | 5000 |  |  | CDG | Y | 2019-07-19 | 2019-07-25 | 4 | 2019-07-25 | 2019-07-25 | 2019-07-31 | 3 | 2019-09-30 | 2019-09-30 | 2020-02-11 | 59 | 10400 |  | 2438777.32 |  |  | 2020-07-28 | 2021-02-03 |  |  |  |  | N | Y
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00246684 | 011 - Syracuse | CAMILLUS | 13031 | 36_11_26656 | MILTON AVE 266 | N |  | 5000 |  |  | CDG | Y | 2019-08-05 | 2019-08-13 | 6 | 2019-08-13 | 2019-08-13 | 2019-08-21 | 5 | 2019-09-30 | 2019-09-30 | 2020-02-11 | 59 | 11400 |  | 2526011.96 |  |  | 2020-07-28 | 2021-02-03 |  |  |  |  | N | Y
NIMO |  | 00243856 | 035 - Gloversville | CANAJOHARIE | 13317 | 36_35_36654 | CLINTON 366 | N |  | 5000 |  |  | CDG | N | 2019-08-30 | 2019-09-13 | 9 | 2019-09-13 | 2019-09-13 | 2019-10-01 | 11 | 2019-12-16 | 2019-12-16 | 2020-09-03 | 57 | 11700 |  | 3074679 | [8 empty] | N | N
NIMO | William Jurith (HELIOS LENOX 1 LLC) | 00170433 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51455 | PETERBORO 514 | Y |  | 1980 | 2000 |  | CDG | Y | 2018-03-09 | 2018-03-09 | 0 | 2018-03-09 | 2018-03-09 | 2018-03-10 | 1 | 2018-04-06 | 2018-04-06 | 2018-05-11 | 4 | 9700 |  | 206166 |  |  | 2018-09-28 | 2019-05-06 |  |  |  |  | N | Y
NIMO | William Jurith (HELIOS LENOX 1 LLC) | 00170444 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51458 | PETERBORO 514 | Y |  | 3000 | 3000 |  | CDG | Y | 2018-02-22 | 2018-02-27 | 2 | 2018-02-27 | 2018-02-27 | 2018-03-11 | 8 | 2018-04-06 | 2018-04-06 | 2018-05-17 | 8 | 9700 |  | 235656 |  |  | 2018-09-28 | 2019-05-06 |  |  |  |  | N | Y
NIMO | Joe Fiori (Nexamp) | 00173939 |  | CANASTOTA | 13032 | 36_20_51454 | PETERBORO 514 | Y |  | 5000 | 5000 |  | CDG | Y | 2018-04-19 | 2018-04-19 | 0 | 2018-05-01 | 2018-05-01 | 2018-05-17 | 12 | 2018-08-01 | 2018-08-01 | 2019-01-25 | 69 | 9700 |  | 408826.79 |  |  | 2019-03-19 | 2020-03-21 | 2020-03-21 | 2020-12-16 | 2020-12-16 | 2020-12-16 | Y | Y
NIMO | Joe Fiori (Nexamp) | 00173942 |  | CANASTOTA | 13032 | 36_20_51456 | PETERBORO 514 | Y |  | 5000 | 5000 |  | CDG | Y | 2018-04-19 | 2018-04-19 | 0 | 2018-05-01 | 2018-05-01 | 2018-05-17 | 12 | 2018-08-01 | 2018-08-01 | 2019-01-25 | 69 | 9700 |  | 437330 |  |  | 2019-03-19 | 2019-09-27 | 2019-09-27 | 2020-12-16 | 2020-12-16 | 2020-12-16 | Y | Y
NIMO | Mike Roach (RER Energy Group) | 00103308 | 020 - Oneida | CANASTOTA | 13032 | 36_20_50150 | ONEIDA 501 | N |  | 1836 |  |  | RNM | N | 2014-06-20 | 2014-07-01 | 8 | 2014-07-01 | 2014-07-01 | 2014-07-16 | 0 | 2015-09-01 | 2015-09-01 | 2016-02-16 | 120 | 25000 |  | 219550 |  |  | 2016-07-26 |  |  | 2017-08-16 | 2017-08-16 | 2017-08-16 | Y | N
NIMO | Kevin Bailey (High Peaks Solar/Sycaway Solar and W | 00190582 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51452 | PETERBORO 514 | N |  | 2900 |  |  | CDG | Y | 2018-07-17 | 2018-07-27 | 9.9396 | 2018-07-30 | 2018-07-30 | 2018-08-16 | 13 | 2018-11-15 | 2018-11-15 | 2019-03-06 | 59 | 13300 |  | 379162.19 |  |  | 2019-04-02 |  |  | 2020-12-17 | 2020-12-17 | 2020-12-17 | Y | Y
NIMO | Joe Fiori (Nexamp Solar LLC) | 00199116 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51457 | PETERBORO 514 | N |  | 3258 |  |  | CDG | Y | 2018-10-24 | 2018-10-29 | 3 | 2018-10-29 | 2018-10-29 | 2018-11-01 | 2 | 2018-11-28 | 2018-11-28 | 2019-08-22 | 55 | 12200 |  | 141938.69 |  |  | 2020-01-10 | 2020-08-17 |  |  |  |  | N | Y
NIMO | Kevin Bailey (High Peaks Solar/Sycaway Solar and W | 00172193 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51452 | PETERBORO 514 | N |  | 4400 |  |  | CDG | Y | 2018-03-26 | 2018-03-26 | 0 | 2018-04-12 | 2018-04-12 | 2018-04-24 | 8 | 2018-07-10 | 2018-07-10 | 2018-11-07 | 58 | 9700 |  | 559780.93 |  |  | 2019-02-12 |  |  | 2020-12-18 | 2020-12-18 | 2020-12-18 | Y | Y
NIMO | Ryan Mccune (Nexamp) | 00339809 | 020 - Oneida | CANASTOTA | 13032 | 36_20_51454 | PETERBORO 514 | N |  | 5000 |  |  | CDG | N | 2021-02-02 | 2021-02-05 | 3 | 2021-02-05 | 2021-02-05 | 2021-02-05 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar CDG LLC) | 00349230 | 020 - Oneida | CANASTOTA | 13031 | 36_20_51453 | PETERBORO 514 | N |  | 5000 |  |  | CDG | N | 2021-03-29 | 2021-04-06 | 6 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 0 |  |  |  |  | 7700 | [10 empty] | N | N
NIMO | Adam Rowles (Saturn Power Corp.) | 00305428 | 011 - Syracuse | CANASTOTA | 13032 | 36_11_5027 | PERRYVILLE 50 | N |  | 5000 |  |  | CDG | N | 2020-09-04 | 2020-09-14 | 5 | 2020-09-14 | 2020-09-14 | 2020-09-22 | 5 | 2020-10-13 | 2020-10-13 | 2021-02-10 | 58 | 11300 |  | 1091032 | [8 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00343612 | 025 - Potsdam | CANTON | 13617 |  |  | N |  | 4999.96 |  |  | CDG | N | 2021-03-30 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00321021 | 025 - Potsdam | CANTON | 13617 | 36_25_95555 | LITTLE RIVER 955 | N |  | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-02 | 6 | 2020-11-02 | 2020-11-02 | 2020-11-09 | 4 | 2020-12-23 | 2020-12-23 | 2021-04-07 | 59 | 11700 |  | 1228977 | [8 empty] | N | N
NIMO | Katie Kearney (SolAmerica Energy) | 00333439 | 025 - Potsdam | CANTON | 13617 | 36_25_95555 | LITTLE RIVER 955 | N |  | 5000 |  |  | CDG | N | 2020-12-29 | 2021-01-06 | 5 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00285490 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N |  | 5000 |  |  | CDG | Y | 2020-04-01 | 2020-04-09 | 6 | 2020-04-09 | 2020-04-09 | 2020-04-10 | 0 | 2020-05-21 | 2020-05-21 | 2020-09-04 | 59 | 9200 |  | 784650.12 |  |  | 2021-01-21 | [5 empty] | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00318632 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N |  | 5000 |  |  | CDG | N | 2020-11-06 | 2020-11-16 | 5 | 2020-11-16 | 2020-11-16 | 2020-12-01 | 8 | 2021-03-29 | 2021-03-29 |  |  | 9400 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00318880 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N |  | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-20 | 4 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 0 | 2020-12-08 | 2020-12-08 | 2021-04-08 | 59 | 9800 |  | 920413 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00323318 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N |  | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-12 | 5 | 2020-11-12 | 2020-11-12 | 2020-12-03 | 12 | 2021-03-11 | 2021-03-11 |  |  | 9800 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00334405 | 025 - Potsdam | CANTON | 13617 | 36_25_95554 | LITTLE RIVER 955 | N |  | 5000 |  |  | CDG | N | 2020-12-31 | 2021-01-06 | 3 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00308731 | 029 - Gouvernur | CANTON | 13617 | 36_28_91453 | MCADOO 914 | N |  | 5000 |  |  | CDG | N | 2020-09-08 | 2020-09-15 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2020-10-12 | 2020-10-12 | 2021-02-10 | 59 | 9400 |  | 800626 | [8 empty] | N | N
NIMO | Andrew Varrow (NY Solar 1001 LLC) | 00216629 | 013 - Watertown | CARTHAGE | 13619 | 36_13_81756 | E. WATERTOWN 817 | N |  | 3000 |  |  | CDG | Y | 2019-04-29 | 2019-05-09 | 8 | 2019-05-09 | 2019-05-09 | 2019-05-14 | 2 | 2019-06-26 | 2019-06-26 | 2019-12-05 | 59 | 11700 |  | 430096.61 |  |  | 2020-04-16 | 2020-10-16 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00251499 | 022 - Carthage | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | N |  | 3300 |  |  | CDG | Y | 2019-09-03 | 2019-09-11 | 6 | 2019-09-11 | 2019-09-11 | 2019-09-17 | 3 | 2019-11-27 | 2019-11-27 | 2020-03-06 | 59 | 10900 |  | 196124 |  |  | 2020-07-14 | 2020-12-28 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00183966 | 023 - Lowville | CARTHAGE | 13327 | 36_23_81654 | N. CARTHAGE 816 | N |  | 5000 |  |  | CDG | Y | 2018-06-08 | 2018-06-08 | 0 | 2018-06-25 | 2018-06-25 | 2018-07-10 | 10 | 2018-08-20 | 2018-08-20 | 2019-01-18 | 51 | 13300 |  | 328103 |  |  | 2019-03-25 | 2019-08-19 | 2019-08-19 | 2020-02-28 | 2020-02-28 | 2020-02-28 | Y | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00227976 | 022 - Carthage | CARTHAGE | 13619 | 36_23_81653 | N. CARTHAGE 816 | N |  | 5000 |  |  | CDG | Y | 2019-05-16 | 2019-05-28 | 7 | 2019-05-28 | 2019-05-28 | 2019-06-03 | 3 | 2019-07-17 | 2019-07-17 | 2019-12-04 | 59 | 10900 |  | 240880.96 |  |  | 2020-05-01 | 2020-11-19 |  |  |  |  | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00305446 | 008 - Dunkirk/Fredoni | CASSADAGA | 14718 | DUNKIRK-HARTFIELD #852 |  | N |  | 5000 |  |  | CDG | N | 2020-09-16 | 2020-09-16 | 0 | 2020-09-16 | 2020-09-16 | 2020-09-29 | 8 | 2020-10-13 | 2020-10-13 | 2021-03-15 | 58 | 10900 |  | 1112015 | [8 empty] | N | N
NIMO | Giovanni Maruca (Elmbrook Solar, LLC) | 00185060 | 030 - Albany | CASTLETON | 12033 | 36_30_45153 | SCHODACK 451 | Y |  | 5000 | 4500 |  | CDG | Y | 2018-05-14 | 2018-05-30 | 4 | 2018-05-30 | 2018-05-30 | 2018-06-15 | 11 | 2018-09-07 | 2018-09-07 | 2018-12-05 | 58 | 12200 |  | 521296.02 |  |  | 2019-04-23 | 2019-12-10 |  |  |  |  | N | Y
NIMO | Nicole LeBlanc (AMP Solar Development Inc.) | 00168774 | 030 - Albany | CASTLETON | 12033 | 36_30_45151 | SCHODACK 451 | Y |  | 4980 | 4980 |  | CDG | Y | 2018-01-12 | 2018-01-22 | 1 | 2018-01-22 | 2018-01-22 | 2018-02-06 | 10 | 2018-04-20 | 2018-04-20 | 2018-10-24 | 59 | 16800 |  | 447631.91 |  |  | 2019-04-23 | 2020-02-20 |  |  |  |  | N | Y
NIMO | Tory Hanna (Davis Hill Development) | 00306915 | 030 - Albany | CASTLETON | 12033 | 36_30_45152 | SCHODACK 451 | N |  | 4875 |  |  | CDG | N | 2020-09-15 | 2020-09-22 | 5 | 2020-09-22 | 2020-09-22 | 2020-09-29 | 4 | 2020-10-14 | 2020-10-14 | 2021-01-28 | 58 | 9400 |  | 692673 | [8 empty] | N | N
NIMO | Nicole LeBlanc (AMP Solar Development Inc) | 00208829 | 030 - Albany | CASTLETON | 12033 | 36_30_45153 | SCHODACK 451 | N |  | 4980 |  |  | CDG | Y | 2019-02-11 | 2019-02-21 | 7 | 2019-02-21 | 2019-02-21 | 2019-03-04 | 6 | 2019-05-15 | 2019-05-15 | 2019-08-27 | 56 | 9400 |  | 1000722 |  |  | 2020-01-22 | 2020-09-04 |  |  |  |  | N | Y
NIMO | David Velasco (conductive power) | 00168448 | 030 - Albany | CASTLETON | 12033 | 36_30_45151 | SCHODACK 451 | N |  | 5000 |  |  | CDG | Y | 2018-04-04 | 2018-04-18 | 6 | 2018-04-18 | 2018-04-18 | 2018-05-02 | 9 | 2018-08-10 | 2018-08-10 | 2019-03-19 | 55 | 13300 |  | 1039234 |  |  | 2019-09-06 | 2020-03-06 |  |  |  |  | N | Y
NIMO | Tory Hanna (Davis Hill Development) | 00335868 | 030 - Albany | CASTLETON | 12033 | 36_30_45151 | SCHODACK 451 | N |  | 5000 |  |  | CDG | N | 2021-01-21 | 2021-01-27 | 4 | 2021-01-27 | 2021-01-27 | 2021-02-11 | 10 |  |  |  |  | 8000 | [10 empty] | N | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00284400 | 010 - Olean | CATTARAUGUS | 14719 | DAKE HILL-W SALAMANCA #816 |  | N |  | 5000 |  |  | CDG | Y | 2020-03-24 | 2020-04-01 | 6 | 2020-04-01 | 2020-04-01 | 2020-04-03 | 1 | 2020-04-23 | 2020-04-23 | 2020-08-18 | 59 | 11300 |  | 231835.62 |  |  | 2020-12-22 | [5 empty] | N | Y
NIMO | Ivaylo Tomchev (East Otto PV, LLC) | 00290115 | 010 - Olean | CATTARAUGUS | 14719 | DAKE HILL-MACHIAS #803 |  | N |  | 5000 |  |  | CDG | N | 2020-06-24 | 2020-07-01 | 5 | 2020-07-01 | 2020-07-01 | 2020-07-01 | 0 | 2020-08-13 | 2020-08-13 | 2021-01-06 | 58 | 10900 |  | 5794656 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00322650 | 011 - Syracuse | CAZENOVIA | 13035 | 36_11_22151 | BALLINA 221 | Y |  |  | 0 | 5000 | CDG | N | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 2020-12-29 | 2020-12-29 | 0 | 2021-02-04 | 2021-02-04 |  |  | 11800 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00286103 | 011 - Syracuse | CAZENOVIA | 13035 | 36_11_26253 | DELPHI 262 | Y |  |  | 0 | 5000 | CDG | N | 2020-04-13 | 2020-04-24 | 9 | 2020-04-24 | 2020-04-24 | 2020-04-27 | 0 | 2020-07-23 | 2020-07-23 |  |  | 11000 | [10 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00296545 | 011 - Syracuse | CAZENOVIA | 13035 | 36_11_22151 | BALLINA 221 | N |  | 5000 |  |  | CDG | N | 2020-07-01 | 2020-07-14 | 8 | 2020-07-14 | 2020-07-14 | 2020-07-14 | 0 | 2020-07-30 | 2020-07-30 | 2020-12-17 | 59 | 9400 |  | 824221 | [8 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00296551 | 011 - Syracuse | CAZENOVIA | 13035 | 36_11_22151 | BALLINA 221 | N |  | 5000 |  |  | CDG | N | 2020-07-08 | 2020-07-14 | 4 | 2020-07-14 | 2020-07-14 | 2020-07-14 | 0 | 2020-07-30 | 2020-07-30 | 2021-02-04 | 60 | 10900 |  | 824119 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00308605 | 011 - Syracuse | CAZENOVIA | 13035 | RATHBUN-LABRADOR #39 |  | N |  | 5000 |  |  | CDG | N | 2020-08-27 | 2020-09-08 | 7 | 2020-09-08 | 2020-09-08 | 2020-09-08 | 0 | 2020-10-12 | 2020-10-12 | 2021-02-10 | 58 | 9400 |  | 2676576 | [8 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00343775 | 011 - Syracuse | CAZENOVIA | 13035 | RATHBUN-LABRADOR #39 |  | N |  | 5000 |  |  | CDG | N | 2021-03-01 | 2021-03-08 | 5 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 0 | 2021-03-29 | 2021-03-29 |  |  | 8400 | [10 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00267202 | 014 - Fulton/Volney | CENTRAL SQUARE | 13036 | 36_14_25652 | NEW HAVEN 256 | N |  | 3000 |  |  | CDG | Y | 2019-11-26 | 2019-12-05 | 5 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 0 | 2019-12-11 | 2019-12-11 | 2020-04-02 | 55 | 10900 |  | 943304 |  |  | 2020-08-20 | [5 empty] | N | Y
NIMO | GSPP 1616 County Route 12, LLC | 00242804 | 011 - Syracuse | CENTRAL SQUARE | 13036 | 36_11_24751 | GILBERT MILLS 247 | N |  | 3100 |  |  | CDG | Y | 2019-07-12 | 2019-07-16 | 2 | 2019-07-16 | 2019-07-16 | 2019-07-26 | 7 | 2019-10-17 | 2019-10-17 | 2020-01-28 | 59 | 9600 |  | 812839.55 |  |  | 2020-04-27 | 2020-10-26 |  |  |  |  | N | Y
NIMO | Matt Vanderbrook (GreenSpark Solar) | 00207359 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73351 | LYME 733 | Y |  | 3150 | 3000 |  | CDG | Y | 2019-01-29 | 2019-01-31 | 2 | 2019-01-31 | 2019-01-31 | 2019-02-13 | 7 | 2019-06-06 | 2019-06-06 | 2019-09-16 | 58 | 12400 |  | 101615.52 |  |  | 2019-12-04 | 2020-06-01 |  |  |  |  | N | Y
NIMO | Mario Titolo (Convergent Energy & Power) | 00206335 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73353 | LYME 733 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-01-18 | 2019-01-31 | 8 | 2019-01-31 | 2019-01-31 | 2019-02-08 | 5 | 2019-03-18 | 2019-03-18 | 2019-09-11 | 59 | 12400 |  | 98088.51 |  |  | 2019-12-04 | 2020-06-01 |  |  |  |  | N | Y
NIMO | Matt Vanderbrook (GreenSpark Solar) | 00207355 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73353 | LYME 733 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-01-29 | 2019-01-31 | 2 | 2019-01-31 | 2019-01-31 | 2019-02-08 | 5 | 2019-03-18 | 2019-03-18 | 2019-09-13 | 58 | 12400 |  | 98088.51 |  |  | 2019-12-04 | 2020-06-01 |  |  |  |  | N | Y
NIMO | Mario Titolo (Convergent Energy & Power) | 00203745 | 013 - Watertown | CHAUMONT | 13622 | 36_13_73351 | LYME 733 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-01-28 | 2019-01-31 | 3 | 2019-01-31 | 2019-01-31 | 2019-02-08 | 5 | 2019-04-02 | 2019-04-02 | 2019-09-04 | 59 | 12400 |  | 527386.44 |  |  | 2019-12-04 | 2020-06-01 |  |  |  |  | N | Y
NIMO | Derek Longo (Convergent Energy & Power) | 00204896 | 013 - Watertown | CHAUMONT | 13622 |  |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-01-28 | 2019-01-31 | 3 | 2019-01-31 | 2019-01-31 | 2019-02-08 | 5 | 2019-04-02 | 2019-04-02 | 2019-09-06 | 59 | 12400 |  | 363918.96 |  |  | 2019-12-04 | 2020-06-01 |  |  |  |  | N | Y
NIMO | GSPP 183 Neilsen Rd, LLC | 00299797 | 037 - Cobleskill | CHERRY VALLEY | 13320 | 36_37_47751 | E. SPRINGFIELD 477 | N |  | 5000 |  |  | CDG | N | 2020-07-07 | 2020-07-17 | 8 | 2020-07-17 | 2020-07-17 | 2020-07-22 | 2 | 2020-10-16 | 2020-10-16 | 2021-01-26 | 52 | 9400 |  | 694020 | [8 empty] | N | N
NIMO | RIC Development, LLC | 00345582 | 011 - Syracuse | CHITTENANGO | 13037 | 36_11_16854 | BRIDGEPORT 168 | N |  | 5000 |  |  | CDG | N | 2021-03-11 | 2021-03-18 | 5 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 0 |  |  |  |  | 6900 | [10 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00270095 | 005 - Avon | CHURCHVILLE | 14428 | 36_05_5053 | MUMFORD 50 | N |  | 5000 |  |  | CDG | N | 2020-02-12 | 2020-02-26 | 9 | 2020-02-26 | 2020-02-26 | 2020-03-04 | 4 | 2020-05-05 | 2020-05-05 | 2020-08-20 | 59 | 9400 |  | 692355.43 |  |  | 2021-01-13 | [5 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00333307 | 005 - Avon | CHURCHVILLE | 14428 | 36_05_5053 | MUMFORD 50 | N |  | 5000 |  |  | CDG | N | 2020-12-22 | 2020-12-30 | 5 | 2020-12-30 | 2020-12-30 | 2020-12-30 | 0 |  |  |  |  | 10100 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315304 | 005 - Avon | CHURCHVILLE | 14428 | OAKFIELD-CALEDONIA #201 |  | N |  | 5000 |  |  | CDG | N | 2020-10-05 | 2020-10-05 | 0 | 2020-10-05 | 2020-10-05 | 2020-10-07 | 1 | 2020-11-05 | 2020-11-05 | 2021-03-15 | 58 | 9800 |  | 1083533 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315953 | 005 - Avon | CHURCHVILLE | 14428 | OAKFIELD-CALEDONIA #201 |  | N |  | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-21 | 5 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 0 | 2020-12-16 | 2020-12-16 | 2021-04-12 | 58 | 12100 |  | 5972394 | [8 empty] | N | N
NIMO | Andy Isrealson (Convergent Energy Solutions New Yo | 00245613 | 011 - Syracuse | CICERO | 13039 | 36_11_5958 | PINE GROVE 59 | Y |  | 5000 | 4999.98 |  | CDG | Y | 2019-07-31 | 2019-08-09 | 7 | 2019-08-09 | 2019-08-09 | 2019-08-13 | 1 | 2019-08-28 | 2019-08-28 | 2019-12-12 | 58 | 9300 |  | 128866 |  |  | 2019-12-03 | 2020-09-02 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00278235 | 011 - Syracuse | CICERO | 13039 | 36_11_16852 | BRIDGEPORT 168 | N |  | 4600 |  |  | CDG | Y | 2020-02-21 | 2020-03-04 | 8 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-07 | 59 | 9800 |  | 174007.57 |  |  | 2020-12-18 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00278216 | 011 - Syracuse | CICERO | 13030 | 36_11_16852 | BRIDGEPORT 168 | N |  | 5000 |  |  | CDG | Y | 2020-02-21 | 2020-03-04 | 8 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-07 | 59 | 9800 |  | 837056.86 |  |  | 2020-12-18 | [5 empty] | N | Y
NIMO | Grant Johns (BW Solar Holding Inc) | 00345327 | 011 - Syracuse | CICERO | 13039 | 36_11_5958 | PINE GROVE 59 | N |  | 5000 |  |  | CDG | N | 2021-03-17 | 2021-03-25 | 6 | 2021-03-25 | 2021-03-25 | 2021-03-25 | 0 |  |  |  |  | 8600 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00214967 | 011 - Syracuse | CLAY | 13041 | 36_11_26751 | EUCLID 267 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-04-04 | 2019-04-15 | 7 | 2019-04-15 | 2019-04-15 | 2019-04-24 | 6 | 2019-05-09 | 2019-05-09 | 2019-06-27 | 14 | 9900 |  | 975075.34 |  |  | 2019-10-29 | 2020-08-27 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS LLC) | 00257718 | 011 - Syracuse | CLAY | 13041 | 36_11_26751 | EUCLID 267 | Y |  | 5000 | 6000 |  | CDG | Y | 2019-10-10 | 2019-10-21 | 7 | 2019-10-21 | 2019-10-21 | 2019-11-08 | 13 | 2019-11-26 | 2019-11-26 | 2020-03-31 | 57 | 10300 |  | 1113699.05 |  |  | 2020-06-18 | 2020-12-29 |  |  |  |  | N | Y
NIMO | Solar City | 00093805 | 011 - Syracuse | CLAY | 13041 | Clay to Woodard 17 - OCWA Tap |  | N |  | 1000 |  |  | NM | N | 2014-03-26 | 2014-03-31 | 2 | 2014-03-31 | 2014-03-31 | 2014-04-14 | 0 | 2014-08-20 | 2014-08-20 | 2014-12-12 | 82 | 12000 |  | 23215 | [5 empty] | 2016-02-11 | 2016-02-11 | 2016-02-11 | Y | N
NIMO | SOLARCITY CORP. (Solar City) | 00103026 | 011 - Syracuse | CLAY | 13041 | 36_11_26751 | EUCLID 267 | N |  | 2000 |  |  | RNM | N | 2014-04-23 | 2014-04-24 | 2 | 2014-04-24 | 2014-04-24 | 2014-05-27 | 0 | 2014-09-16 | 2014-09-16 | 2014-12-12 | 63 | 20000 |  | 387100 | [5 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | Y | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00322367 | 011 - Syracuse | CLAY | 13041 | 36_11_26753 | EUCLID 267 | N |  | 2000 |  |  | CDG | N | 2020-10-29 | 2020-11-10 | 8 | 2020-11-10 | 2020-11-10 | 2020-11-18 | 4 | 2021-02-19 | 2021-02-19 |  |  | 9600 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00230713 | 011 - Syracuse | CLAY | 13041 | 36_11_32556 | BARTELL RD 325 | N |  | 2200 |  |  | CDG | Y | 2019-06-14 | 2019-06-25 | 7 | 2019-06-25 | 2019-06-25 | 2019-07-09 | 8 | 2019-07-31 | 2019-07-31 | 2019-10-31 | 58 | 9200 |  | 321059 |  |  | 2020-04-14 | [5 empty] | N | Y
NIMO | Grant Johns (BW Solar Holding Inc) | 00345400 | 011 - Syracuse | CLAY | 13041 | 36_11_32556 | BARTELL RD 325 | N |  | 3000 |  |  | CDG | N | 2021-03-08 | 2021-03-15 | 5 | 2021-03-15 | 2021-03-15 | 2021-03-15 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00306124 |  | CLAY | 13041 | 36_11_690055 | WETZEL ROAD | N |  | 4975 |  |  | CDG | N | 2020-10-21 | 2020-10-28 | 5 | 2020-10-28 | 2020-10-28 | 2020-10-28 | 0 | 2021-01-06 | 2021-01-06 | 2021-04-13 | 59 | 10100 |  | 810185 | [8 empty] | N | N
NIMO | Seaboard Solar | 00328918 | 011 - Syracuse | CLAY | 13041 | 36_11_690055 | WETZEL ROAD | N |  | 4975 |  |  | CDG | N | 2020-12-17 | 2020-12-17 | 0 | 2020-12-17 | 2020-12-17 | 2020-12-17 | 0 | 2021-01-06 | 2021-01-06 | 2021-04-13 | 59 | 10100 |  | 1370381 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00238767 | 011 - Syracuse | CLAY | 13041 | 36_11_26753 | EUCLID 267 | N |  | 5000 |  |  | CDG | Y | 2019-06-25 | 2019-07-02 | 5 | 2019-07-02 | 2019-07-02 | 2019-07-16 | 8 | 2019-08-29 | 2019-08-29 | 2020-04-17 | 98 | 8800 |  | 545810 |  |  | 2020-06-15 | 2020-12-28 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00238769 | 011 - Syracuse | CLAY | 13041 | 36_11_26753 | EUCLID 267 | N |  | 5000 |  |  | CDG | Y | 2019-06-25 | 2019-07-02 | 5 | 2019-07-02 | 2019-07-02 | 2019-07-16 | 8 | 2019-08-29 | 2019-08-29 | 2020-04-17 | 98 | 9400 |  | 586763 |  |  | 2020-06-15 | 2020-12-28 |  |  |  |  | N | Y
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00201774 | 013 - Watertown | CLAYTON | 13624 | 36_13_73351 | LYME 733 | Y |  | 1250 | 1250 |  | CDG | Y | 2018-12-03 | 2018-12-13 | 8 | 2018-12-13 | 2018-12-13 | 2018-12-19 | 3 | 2019-02-06 | 2019-02-06 | 2019-04-29 | 57 | 10100 |  | 249584 |  |  | 2019-10-09 | 2020-04-02 |  |  |  |  | N | Y
NIMO | Mithun Vyas (OYA Blanchard Road LLC) | 00172438 | 026 - Clayton | CLAYTON | 13624 | 36_26_81456 | THOUSAND ISLANDS 814 | N |  | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-05-01 | 2018-05-01 | 2018-05-17 | 12 | 2018-06-29 | 2018-06-29 | 2018-09-29 | 59 | 15600 |  | 810495.46 |  |  | 2019-01-07 |  |  | 2020-06-30 | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Yogesh Kumar (OYA Solar NY, LP.) | 00172439 | 026 - Clayton | CLAYTON | 13624 | 36_26_81454 | THOUSAND ISLANDS 814 | N |  | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-04-17 | 2018-04-17 | 2018-04-21 | 4 | 2018-07-06 | 2018-07-06 | 2018-09-27 | 58 | 15300 |  | 799495.46 |  |  | 2018-12-17 | 2019-08-23 | 2019-08-23 | 2020-06-30 | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Mithun Vyas (OYA Great Lakes Seaway LLC) | 00172437 | 026 - Clayton | CLAYTON | 13624 | 36_26_81453 | THOUSAND ISLANDS 814 | N |  | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-04-05 | 2018-04-05 | 2018-04-21 | 0 | 2018-07-02 | 2018-07-02 | 2018-09-25 | 59 | 14300 |  | 696979.05 |  |  | 2018-12-14 | 2019-08-23 | 2019-08-23 | 2020-06-15 | 2020-06-15 | 2020-06-15 | Y | Y
NIMO | Yogesh Kumar (OYA Solar NY, LP.) | 00172442 | 026 - Clayton | CLAYTON | 13624 | 36_26_81452 | THOUSAND ISLANDS 814 | N |  | 5000 |  |  | CDG | Y | 2018-03-28 | 2018-03-28 | 0 | 2018-04-17 | 2018-04-17 | 2018-04-21 | 4 | 2018-07-06 | 2018-07-06 | 2018-09-27 | 56 | 15300 |  | 799495.46 |  |  | 2018-12-14 | 2019-08-23 | 2019-08-23 | 2020-06-30 | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Yogesh Kumar (OYA Solar NY, LP.) | 00171595 | 026 - Clayton | CLAYTON | 13624 | 36_26_81458 | THOUSAND ISLANDS 814 | N |  | 5000 |  |  | CDG | Y | 2018-03-12 | 2018-03-25 | 4 | 2018-03-25 | 2018-03-25 | 2018-04-11 | 12 | 2019-06-11 | 2019-06-11 | 2019-12-05 | 59 | 13300 |  | 140363 |  |  | 2020-01-06 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Nick Ford (Hexagon Energy, LLC) | 00342164 | 026 - Clayton | CLAYTON | 13624 | 36_26_81455 | THOUSAND ISLANDS 814 | N |  | 5000 |  |  | CDG | N | 2021-02-16 | 2021-02-23 | 5 | 2021-02-23 | 2021-02-23 | 2021-02-23 | 0 |  |  |  |  | 6600 | [10 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00279346 | 032 - Schenectady | CLIFTON PARK | 12019 | 36_32_44256 | ELNORA 442 | Y |  | 2300 | 2500 |  | CDG | N | 2020-02-14 | 2020-02-28 | 9 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 0 | 2020-05-13 | 2020-05-13 | 2020-12-17 | 58 | 9500 |  | 783709 | [8 empty] | N | N
NIMO | Solar City | 00102643 | 031 - Troy | CLIFTON PARK | 12065 | 36_31_41352 | PROSPECT HILL 413 | N |  | 1008 |  |  | RNM | N | 2014-08-19 | 2014-09-10 | 2 | 2014-09-10 | 2014-09-10 | 2014-09-16 | 0 | 2015-01-02 | 2015-01-02 | 2015-03-27 | 60 | 13700 | [7 empty] | 2017-06-19 | 2017-06-19 | 2017-06-19 | Y | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00270253 | 017 - Utica | CLINTON | 13323 | 36_17_60451 | CLINTON 604 | Y |  | 5000 | 0 |  | CDG | Y | 2020-01-13 | 2020-01-22 | 6 | 2020-01-22 | 2020-01-22 | 2020-01-23 | 0 | 2020-02-04 | 2020-02-04 | 2020-06-15 | 59 | 9500 |  | 287031.08 |  |  | 2020-06-16 | 2020-12-04 |  |  |  |  | N | Y
NIMO | David Spotts (SSC Kirkland II LLC) | 00280860 | 017 - Utica | CLINTON | 13323 | 36_17_60454 | CLINTON 604 | Y |  | 5000 | 0 |  | CDG | Y | 2020-03-03 | 2020-03-13 | 8 | 2020-03-13 | 2020-03-13 | 2020-03-13 | 0 | 2020-04-29 | 2020-04-29 | 2020-08-19 | 58 | 9900 |  | 121955.41 |  |  | 2021-01-04 | [5 empty] | N | Y
NIMO | David Spotts (Summit Solar Capital, LLC) | 00267494 | 017 - Utica | CLINTON | 13323 | 36_17_60454 | CLINTON 604 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-12-02 | 2019-12-11 | 7 | 2019-12-11 | 2019-12-11 | 2019-12-16 | 2 | 2019-12-24 | 2019-12-24 | 2020-04-27 | 59 | 9900 |  | 176367 |  |  | 2020-10-01 | 2021-03-29 |  |  |  |  | N | Y
NIMO | John Bay (Acadia Energy) | 00101398 | 017 - Utica | CLINTON | 13323 | 36_17_64656 | YAHNUNDASIS 646 | N |  | 2000 |  |  | CDG | N | 2016-02-16 | 2016-03-11 | 4 | 2016-03-11 | 2016-03-11 | 2016-04-13 | 0 | 2016-09-20 | 2016-09-20 | 2016-12-12 | 59 | 17500 |  | 213400 |  |  | 2017-06-01 | [5 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00331797 | 009 - Lakewood/Stow | CLYMER | 14724 | 36_09_5562 | CLYMER 55 | N |  | 3250 |  |  | CDG | N | 2020-12-21 | 2020-12-29 | 5 | 2020-12-29 | 2020-12-29 | 2020-12-29 | 0 | 2021-01-22 | 2021-01-22 |  |  | 10900 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00295491 | 009 - Lakewood/Stow | CLYMER | 14724 | SHERMAN-ASHVILLE #863 |  | N |  | 5000 |  |  | CDG | N | 2020-06-10 | 2020-06-18 | 6 | 2020-06-18 | 2020-06-18 | 2020-06-18 | 0 | 2020-09-04 | 2020-09-04 | 2020-12-21 | 57 | 11300 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00303054 | 009 - Lakewood/Stow | CLYMER | 14724 | SHERMAN-ASHVILLE #863 |  | N |  | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-03 | 2020-08-03 | 2020-08-06 | 1 | 2020-08-13 | 2020-08-13 | 2021-03-01 | 58 | 9900 | [10 empty] | N | N
NIMO | RIC Development, LLC | 00335966 |  | CLYMER | 14724 | SHERMAN-ASHVILLE #863 |  | N |  | 5000 |  |  | CDG | N | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-01-12 | 2021-01-12 | 0 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00336701 | 037 - Cobleskill | COBLESKILL | 12043 | 36_37_21412 | COBLESKILL 214 | N |  | 2000 |  |  | CDG | N | 2021-01-14 | 2021-01-15 | 1 | 2021-01-15 | 2021-01-15 | 2021-01-25 | 4 | 2021-03-30 | 2021-03-30 |  |  | 8000 | [10 empty] | N | N
NIMO | Mithun Vyas (DG Northeast 1, LLC) | 00211551 | 031 - Troy | COHOES | 12110 | 36_31_35251 | JOHNSON RD 352 | N |  | 1000 |  |  | NA | Y | 2019-07-11 | 2019-07-15 | 2 | 2019-07-15 | 2019-07-15 | 2019-07-31 | 7 | 2019-10-15 | 2019-10-15 | 2020-01-08 | 55 | 8300 |  | 83672.73 |  |  | 2020-01-15 | 2020-01-17 |  |  |  |  | N | Y
NIMO | Teddy Epstein (Novis Renewables) | 00273261 | 017 - Utica | COLD BROOK | 13324 | 36_17_62258 | POLAND 622 | N |  | 5000 |  |  | CDG | Y | 2020-01-28 | 2020-02-07 | 8 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 0 | 2020-02-12 | 2020-02-12 | 2020-06-08 | 59 | 9400 |  | 689355.43 |  |  | 2020-10-14 | [5 empty] | N | Y
NIMO | Todd Friedman (RESunance, LLC) | 00319891 | 007 - Angola | COLLINS | 14034 | 36_07_8361 | COLLINS 83 | N |  | 5000 |  |  | CDG | N | 2020-10-30 | 2020-11-06 | 5 | 2020-11-06 | 2020-11-06 | 2020-11-06 | 0 | 2020-11-16 | 2020-11-16 |  |  | 11700 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00259198 | 022 - Carthage | COPENHAGEN | 13626 | 36_13_81757 | E. WATERTOWN 817 | N |  | 1400 |  |  | CDG | Y | 2019-10-29 | 2019-11-06 | 6 | 2019-11-06 | 2019-11-06 | 2019-11-18 | 6 | 2020-01-14 | 2020-01-14 | 2020-04-24 | 59 | 10900 |  | 374994 |  |  | 2020-08-28 | 2021-02-24 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00253145 | 022 - Carthage | COPENHAGEN | 13626 | 36_13_81757 | E. WATERTOWN 817 | N |  | 1500 |  |  | CDG | Y | 2019-09-10 | 2019-09-20 | 8 | 2019-09-20 | 2019-09-20 | 2019-09-25 | 2 | 2019-10-08 | 2019-10-08 | 2020-04-17 | 59 | 11700 |  | 519026 |  |  | 2020-08-25 | 2021-02-11 |  |  |  |  | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315537 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | Y |  |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-11-02 | 11 | 2020-12-17 | 2020-12-17 |  |  | 10300 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00301884 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | N | 2020-09-17 | 2020-09-23 | 4 | 2020-09-23 | 2020-09-23 | 2020-09-29 | 3 | 2020-11-10 | 2020-11-10 |  |  | 9400 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315567 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-24 | 2020-10-24 | 2020-11-03 | 6 | 2021-04-05 | 2021-04-05 |  |  | 9400 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315569 | 004 - Batavia | CORFU | 14036 | 36_04_22651 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-24 | 2020-10-24 | 2020-11-03 | 6 | 2021-04-08 | 2021-04-08 |  |  | 9400 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00334300 | 004 - Batavia | CORFU | 14063 | 36_04_22651 | KNAPP RD 226 | N |  | 5000 |  |  | CDG | N | 2021-01-27 | 2021-02-03 | 5 | 2021-02-03 | 2021-02-03 | 2021-02-11 | 5 |  |  |  |  | 7800 | [10 empty] | N | N
NIMO | Caroline Rizzo (Aura Power) | 00338656 |  | CORFU | 14036 | N AKRON-ATTICA #225 |  | N |  | 5000 |  |  | CDG | N | 2021-02-04 | 2021-02-15 | 7 | 2021-02-15 | 2021-02-15 | 2021-03-04 | 12 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | BlueWave Project Development, LLC (BlueWave Solar) | 00303657 | 039 - Saratoga | CORINTH | 12822 | 36_39_28552 | CORINTH 285 | N |  | 5000 |  |  | CDG | N | 2020-08-19 | 2020-08-25 | 4 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 0 | 2020-10-12 | 2020-10-12 | 2021-03-08 | 56 | 11300 |  | 919994 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS II, LLC) | 00284107 | 012 - Cortland | CORTLAND | 13045 | CORTLAND #23 |  | Y |  | 5000 | 0 |  | CDG | Y | 2020-04-09 | 2020-04-21 | 8 | 2020-04-21 | 2020-04-21 | 2020-04-21 | 0 | 2020-04-29 | 2020-04-29 | 2020-08-17 | 59 | 11400 |  | 1191873 |  |  | 2020-12-18 | [5 empty] | N | Y
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00274292 | 012 - Cortland | CORTLAND | 13045 | 36_12_24651 | TULLER HILL 246 | Y |  | 5000 | 5000 |  | CDG | Y | 2020-02-19 | 2020-03-02 | 8 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 0 | 2020-03-04 | 2020-03-04 | 2020-07-16 | 59 | 10300 |  | 1270353 |  |  | 2020-09-08 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00229753 | 012 - Cortland | CORTLAND | 13045 | 36_12_33454 | STARR RD 334 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-05-30 | 2019-06-10 | 7 | 2019-06-10 | 2019-06-10 | 2019-06-24 | 9 | 2019-08-08 | 2019-08-08 | 2019-12-23 | 58 | 12200 |  | 1659756 |  |  | 2020-01-06 | 2020-03-30 |  |  |  |  | N | Y
NIMO | Andrew Day (Source Renewables, LLC) | 00252200 | 012 - Cortland | CORTLAND | 13045 | 36_12_33454 | STARR RD 334 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-09-04 | 2019-09-17 | 9 | 2019-09-17 | 2019-09-17 | 2019-09-24 | 4 | 2019-12-26 | 2019-12-26 | 2020-05-05 | 59 | 10600 |  | 452923.68 |  |  | 2020-09-15 | 2021-03-11 |  |  |  |  | N | Y
NIMO | Andrew Day (Source Renewables, LLC) | 00252201 | 012 - Cortland | CORTLAND | 13045 | CORTLAND #23 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-09-04 | 2019-09-17 | 9 | 2019-09-17 | 2019-09-17 | 2019-09-24 | 4 | 2019-12-26 | 2019-12-26 | 2020-05-05 | 57 | 10600 |  | 884196.5 |  |  | 2020-09-11 | [5 empty] | N | Y
NIMO | Mithun Vyas (DG New York CS LLC) | 00245119 | 012 - Cortland | CORTLAND | 13045 | CORTLAND #20 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-07-25 | 2019-08-01 | 5 | 2019-08-01 | 2019-08-01 | 2019-08-13 | 7 | 2019-10-16 | 2019-10-16 | 2020-01-14 | 59 | 11400 |  | 949436 |  |  | 2020-02-19 | 2020-08-27 |  |  |  |  | N | Y
NIMO | Elie Schecter (C2 Energy Capital) | 00101873 |  | CORTLAND | 13045 |  |  | N |  | 1925 |  |  | CDG | Y | 2017-01-11 | 2017-01-18 | 4 | 2017-01-18 | 2017-01-18 | 2017-01-27 | 7 | 2017-02-23 | 2017-02-23 | 2017-05-17 | 60 | 19300 |  | 127365 |  |  | 2017-08-11 |  |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | Y | Y
NIMO | Elie Schecter (C2 Energy Capital) | 00101595 | 012 - Cortland | CORTLAND | 13405 | 36_12_33452 | STARR RD 334 | N |  | 1950 |  |  | CDG | N | 2016-11-03 | 2016-11-15 | 7 | 2016-11-15 | 2016-11-15 | 2016-11-21 | 4 | 2017-01-17 | 2017-01-17 | 2017-04-11 | 60 | 25300 |  | 227807 |  |  | 2017-06-13 |  |  | 2021-01-28 | 2021-01-28 | 2021-01-28 | Y | N
NIMO | Elie Schecter (C2 Energy Capital) | 00101986 | 012 - Cortland | CORTLAND | 13045 | 36_12_33452 | STARR RD 334 | N |  | 2000 |  |  | CDG | N | 2016-02-17 | 2016-06-10 | 6 | 2016-06-10 | 2016-06-10 | 2016-06-15 | 0 | 2017-01-17 | 2017-01-17 | 2017-04-07 | 58 | 21300 |  | 1048993 |  |  | 2017-06-13 |  |  | 2020-12-31 | 2020-12-31 | 2020-12-31 | Y | N
NIMO | Elie Schecter (C2 Energy Capital) | 00101596 | 012 - Cortland | CORTLAND | 13045 | 36_12_33451 | STARR RD 334 | N |  | 2000 |  |  | CDG | N | 2016-11-03 | 2016-11-15 | 7 | 2016-11-15 | 2016-11-15 | 2016-11-18 | 3 | 2017-01-17 | 2017-01-17 | 2017-04-11 | 60 | 20000 |  | 143707 |  |  | 2017-06-13 |  |  | 2021-02-09 | 2021-02-09 | 2021-02-09 | Y | N
NIMO | Adam Ellis (Nexamp) | 00338682 | 012 - Cortland | CORTLAND | 13045 | 36_12_33453 | STARR RD 334 | N |  | 2400 |  |  | CDG | N | 2021-02-09 | 2021-02-17 | 5 | 2021-02-17 | 2021-02-17 | 2021-03-19 | 11 | 2021-04-13 | 2021-04-13 |  |  | 6600 | [10 empty] | N | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00266966 | 012 - Cortland | CORTLAND | 13045 | 36_12_33453 | STARR RD 334 | N |  | 3000 |  |  | CDG | Y | 2019-12-20 | 2020-01-06 | 9 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 0 | 2020-01-08 | 2020-01-08 | 2020-04-21 | 59 | 8100 |  | 190279.24 |  |  | 2020-08-11 | 2021-02-04 |  |  |  |  | N | Y
NIMO | Elie Schecter (C2 Energy Capital) | 00101649 | 012 - Cortland | CORTLAND | 13045 | 36_12_27651 | LORINGS 276 | N |  | 3917 |  |  | CDG | N | 2016-11-07 | 2016-11-16 | 6 | 2016-11-16 | 2016-11-16 | 2016-12-06 | 12 | 2017-01-17 | 2017-01-17 | 2017-04-11 | 60 | 16200 |  | 658700 |  |  | 2017-06-13 | [5 empty] | N | N
NIMO | David Spotts (SSC Cortlandville III LLC) | 00343833 | 012 - Cortland | CORTLAND | 13045 | 36_12_27051 | FISHER 270 | N |  | 5000 |  |  | CDG | N | 2021-02-25 | 2021-03-04 | 5 | 2021-03-04 | 2021-03-04 | 2021-03-04 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00295478 | 012 - Cortland | CORTLAND | 13045 | CORTLAND #20 | SUBT 12 | N |  | 5000 |  |  | CDG | N | 2020-06-10 | 2020-06-18 | 6 | 2020-06-18 | 2020-06-18 | 2020-06-19 | 0 | 2020-09-04 | 2020-09-04 | 2021-01-27 | 58 | 10900 | [10 empty] | N | N
NIMO | Christopher Stroud (Cipriani Energy Group Corp.) | 00289878 | 041 - Ticonderoga | CROWN POINT | 12928 | 36_41_24951 | CROWN POINT 249 | N |  | 1200 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-02 | 2020-07-02 | 2020-10-19 | 59 | 9200 |  | 204152.47 |  |  | 2021-02-24 | [5 empty] | N | N
NIMO | Jacob Deyo (Larsen Engineers) | 00328081 | 010 - Olean | CUBA | 14727 |  |  | N |  | 5000 |  |  | CDG | N | 2021-03-30 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00294469 | 010 - Olean | CUBA | 14727 | HOMER HILL-NILE #811 |  | N |  | 5000 |  |  | CDG | N | 2020-06-03 | 2020-06-10 | 5 | 2020-06-10 | 2020-06-10 | 2020-06-10 | 0 | 2020-09-04 | 2020-09-04 | 2020-12-15 | 53 | 10900 | [10 empty] | N | N
NIMO | Johnson (Cypress Creek Renewables) | 00269320 | 012 - Cortland | DE RUYTER | 13052 | 36_11_26252 | DELPHI 262 | N |  | 5000 |  |  | CDG | Y | 2020-02-18 | 2020-03-02 | 9 | 2020-03-02 | 2020-03-02 | 2020-03-04 | 1 | 2020-05-06 | 2020-05-06 | 2020-08-17 | 58 | 9000 |  | 810234.53 |  |  | 2021-01-13 | [5 empty] | N | Y
NIMO | John McDonough (National Solar Group LLC) | 00195570 | 029 - Gouvernur | DEKALB JUNCTION | 13630 | 36_29_98455 | DEKALB 984 | N |  | 3000 |  |  | CDG | Y | 2018-10-08 | 2018-10-18 | 8 | 2018-10-18 | 2018-10-18 | 2018-10-26 | 5 | 2018-12-13 | 2018-12-13 | 2019-04-15 | 56 | 12200 |  | 696561 |  |  | 2019-09-03 | 2020-02-21 |  |  |  |  | N | Y
NIMO | John McDonough (National Solar Group LLC) | 00195434 | 029 - Gouvernur | DEKALB JUNCTION | 13630 | 36_29_98455 | DEKALB 984 | N |  | 5000 |  |  | CDG | Y | 2018-10-08 | 2018-10-18 | 8 | 2018-10-18 | 2018-10-18 | 2018-10-26 | 5 | 2018-12-13 | 2018-12-13 | 2019-04-15 | 56 | 13300 |  | 483676 |  |  | 2019-09-03 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Nicole LeBlanc (AMP Solar Dev. Inc.) | 00165990 | 037 - Cobleskill | DELANSON | 12053 | 36_37_26951 | DELANSON 269 | Y |  | 5000 | 4500 |  | CDG | Y | 2017-11-21 | 2017-12-04 | 5 | 2017-12-04 | 2017-12-04 | 2017-12-14 | 7 | 2018-03-12 | 2018-03-12 | 2018-08-16 | 56 | 19300 |  | 173436.44 |  |  | 2019-05-08 | 2019-10-29 |  |  |  |  | N | Y
NIMO | Nicole LeBlanc (AMP Solar Dev. Inc.) | 00166610 | 037 - Cobleskill | DELANSON | 12053 | 36_37_26951 | DELANSON 269 | Y |  | 5000 | 4500 |  | CDG | Y | 2017-12-06 | 2017-12-06 | 0 | 2017-12-06 | 2017-12-06 | 2017-12-14 | 5 | 2018-03-12 | 2018-03-12 | 2018-08-16 | 56 | 20600 |  | 153177 |  |  | 2019-05-08 | 2019-12-10 |  |  |  |  | N | Y
NIMO | Safari Energy | 00100806 | 037 - Cobleskill | DELANSON | 12817 | 36_37_26951 | DELANSON 269 | N |  | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-10 | 3 | 2015-06-10 | 2015-06-10 | 2015-06-17 | 0 | 2015-12-15 | 2015-12-15 | 2016-06-28 | 140 | 35000 |  | 862940 |  |  | 2016-12-13 |  |  | 2018-04-19 | 2018-04-19 | 2018-04-19 | Y | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00299301 | 010 - Olean | DELEVAN | 14042 | 36_10_1161 | DELEVAN 11 | N |  | 5000 |  |  | CDG | N | 2020-07-20 | 2020-07-20 | 0 | 2020-07-20 | 2020-07-20 | 2020-07-23 | 2 | 2020-08-19 | 2020-08-19 | 2021-01-05 | 58 | 10900 |  | 862954 | [8 empty] | N | N
NIMO | FOREFRONT POWER LLC | 00101403 | 030 - Albany | DELMAR | 12054 | 36_30_27652 | UNIONVILLE 276 | N |  | 1700 |  |  | RNM | N | 2016-02-08 | 2016-12-15 | 11 | 2016-12-15 | 2016-12-15 | 2017-01-05 | 0 | 2017-02-09 | 2017-02-09 | 2017-05-19 | 60 | 21600 |  | 829500 |  |  | 2017-08-15 |  |  | 2019-06-06 | 2019-06-06 | 2019-06-06 | Y | N
NIMO | Constellation Solar NY LLC | 00093233 | 030 - Albany | DELMAR | 12054 | New Scotland to Feura Bush 9 - Owens Corning Tap |  | N |  | 2000 |  |  | NM | N | 2013-04-15 | 2013-04-15 | 0 | 2013-04-15 | [15 empty] | 2013-10-17 | 2013-10-17 | 2013-10-17 | Y | N
NIMO | Lluis Torrent (CAERO) | 00349433 | 030 - Albany | DELMAR | 12054 |  |  | N |  | 3060 |  |  | CDG | N | 2021-03-29 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282689 |  | DEWITTVILLE | 14728 | DUNKIRK-HARTFIELD #852 |  | N |  | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-17 | 6 | 2020-03-17 | 2020-03-17 | 2020-03-19 | 1 | 2020-05-14 | 2020-05-14 | 2020-08-28 | 57 | 10900 |  | 296968 |  |  | 2021-03-10 | [5 empty] | N | N
NIMO | Kelsey Crane (Forefront Power) | 00208992 | 013 - Watertown | DEXTER | 13634 | 36_13_76056 | COFFEEN 760 | N |  | 5000 |  |  | CDG | Y | 2019-02-11 | 2019-02-20 | 6 | 2019-02-20 | 2019-02-20 | 2019-03-01 | 6 | 2019-07-22 | 2019-07-22 | 2019-10-17 | 59 | 9000 |  | 816401.74 |  |  | 2019-12-30 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00273428 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_6355 | E. DUNKIRK 63 | Y |  | 4550 | 3697.5 |  | CDG | Y | 2020-01-16 | 2020-01-30 | 9 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 0 | 2020-03-17 | 2020-03-17 | 2020-08-27 | 58 | 9900 |  | 124956 |  |  | 2021-02-25 | [5 empty] | N | Y
NIMO | Elie Schecter (OurGeneration LLC) | 00299896 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15454 | ROBERTS RD 154 | Y |  | 5000 | 5000 |  | CDG | N | 2020-07-29 | 2020-08-05 | 5 | 2020-08-05 | 2020-08-05 | 2020-08-10 | 2 | 2020-10-26 | 2020-10-26 | 2021-04-06 | 57 | 9100 |  | 692151 | [8 empty] | N | N
NIMO | RIC Development LLC | 00347391 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9955 | BENNETT RD 99 | N |  | 3000 |  |  | CDG | N | 2021-03-18 | 2021-03-19 | 1 | 2021-03-19 | 2021-03-19 | 2021-03-19 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | RIC Development | 00296550 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15352 | BERRY RD 153 | N |  | 3000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 0 | 2020-08-20 | 2020-08-20 | 2021-01-26 | 65 | 9400 |  | 12736424 | [8 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00279582 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9954 | BENNETT RD 99 | N |  | 3060 |  |  | CDG | N | 2020-04-08 | 2020-04-16 | 6 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 0 | 2020-06-10 | 2020-06-10 | 2020-12-15 | 62 | 8600 |  | 1277596 | [8 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00282517 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 |  |  | N |  | 3450 |  |  | CDG | N | 2020-04-01 | 2020-04-09 | 6 | 2020-04-09 | 2020-04-09 | 2020-04-09 | 0 | 2020-04-13 | 2020-04-13 |  |  | 8600 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00249978 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9954 | BENNETT RD 99 | N |  | 3750 |  |  | CDG | Y | 2019-08-22 | 2019-08-28 | 4 | 2019-08-28 | 2019-08-28 | 2019-09-05 | 4 | 2019-11-25 | 2019-11-25 | 2020-04-16 | 58 | 9600 |  | 440977.96 |  |  | 2020-09-01 | [5 empty] | N | Y
NIMO | Sam Youneszadeh (Dimension Energy LLC (Dimension R | 00341812 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15454 | ROBERTS RD 154 | N |  | 4500 |  |  | CDG | Y | 2021-02-25 | 2021-03-03 | 4 | 2021-03-03 | 2021-03-03 | 2021-03-19 | 11 |  |  |  |  | 7200 | [10 empty] | N | Y
NIMO | Sam Youneszadeh (Dimension Energy LLC (Dimension R | 00341861 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15454 | ROBERTS RD 154 | N |  | 4500 |  |  | CDG | Y | 2021-02-25 | 2021-03-03 | 4 | 2021-03-03 | 2021-03-03 | 2021-03-19 | 11 |  |  |  |  | 7200 | [10 empty] | N | Y
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00273425 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_6355 | E. DUNKIRK 63 | N |  | 4550 |  |  | CDG | Y | 2020-01-16 | 2020-01-30 | 9 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 0 | 2020-03-17 | 2020-03-17 | 2020-08-28 | 59 | 9900 |  | 291327.14 |  |  | 2021-02-09 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00254020 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_9955 | BENNETT RD 99 | N |  | 5000 |  |  | CDG | Y | 2019-09-16 | 2019-09-26 | 8 | 2019-09-26 | 2019-09-26 | 2019-10-04 | 5 | 2019-12-10 | 2019-12-10 | 2020-03-18 | 58 | 9000 |  | 251741 |  |  | 2020-08-12 | [5 empty] | N | Y
NIMO | Elie Schecter (OurGeneration LLC) | 00348781 | 008 - Dunkirk/Fredoni | DUNKIRK | 14048 | 36_08_15454 | ROBERTS RD 154 | N |  | 5000 |  |  | CDG | N | 2021-03-25 | 2021-03-26 | 1 | 2021-03-26 | 2021-03-26 | [6 empty] | 7200 | [10 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00270629 | 030 - Albany | EAST BERNE | 12059 | 36_30_17851 | VOORHEESVILLE 178 | N |  | 4400 |  |  | CDG | Y | 2020-01-23 | 2020-02-03 | 6 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 0 | 2020-03-11 | 2020-03-11 | 2020-07-13 | 51 | 10500 |  | 911928.25 |  |  | 2020-11-19 | [5 empty] | N | Y
NIMO | Ivaylo Tomchev (RIC Development) | 00324125 | 030 - Albany | EAST BERNE | 12059 | 36_30_17851 | VOORHEESVILLE 178 | N |  | 5000 |  |  | CDG | N | 2020-11-09 | 2020-11-17 | 5 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 | 2020-12-30 | 2020-12-30 | 2021-04-13 | 59 | 10500 |  | 1321369 | [8 empty] | N | N
NIMO | Yogesh kumar (OYA Solar LP.) | 00278557 | 004 - Batavia | EAST BETHANY | 14054 | N LEROY-ATTICA #208 |  | N |  | 5000 |  |  | CDG | Y | 2020-03-17 | 2020-03-25 | 6 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 0 | 2020-03-31 | 2020-03-31 | 2020-07-31 | 57 | 10900 |  | 573520.76 |  |  | 2020-12-01 | [5 empty] | N | Y
NIMO | John Vigants (Bright Solar LLC) | 00315948 | 004 - Batavia | EAST BETHANY | 14054 | N LEROY-ATTICA #208 |  | N |  | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-21 | 5 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 0 | 2020-12-16 | 2020-12-16 | 2021-03-30 | 58 | 10900 |  | 1228358 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315949 | 004 - Batavia | EAST BETHANY | 14054 | N LEROY-ATTICA #208 |  | N |  | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-22 | 6 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2020-12-22 | 2020-12-22 | 2021-03-31 | 58 | 10900 |  | 1344564 | [8 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00250816 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_151156 | COLLAMER CROSSING | Y |  | 5000 | 5000 |  | CDG | Y | 2019-08-27 | 2019-09-04 | 5 | 2019-09-04 | 2019-09-04 | 2019-09-09 | 2 | 2019-12-26 | 2019-12-26 | 2020-05-05 | 59 | 10300 |  | 851099.96 |  |  | 2020-09-11 | 2021-03-10 |  |  |  |  | N | Y
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00329241 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_151156 | COLLAMER CROSSING | Y |  | 5000 | 5000 |  | CDG | N | 2020-12-03 | 2020-12-08 | 3 | 2020-12-08 | 2020-12-08 | 2020-12-15 | 4 |  |  |  |  | 9900 | [10 empty] | N | N
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00272041 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_26154 | FLY RD 261 | N |  | 1625 |  |  | CDG | Y | 2020-01-14 | 2020-01-27 | 8 | 2020-01-27 | 2020-01-27 | 2020-01-27 | 0 | 2020-03-09 | 2020-03-09 | 2020-07-29 | 58 | 9900 |  | 241510.63 |  |  | 2020-12-08 | 2021-02-18 |  |  |  |  | N | Y
NIMO | Michael Roach (RER Energy Group LLC) | 00100828 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_25555 | BUTTERNUT 255 | N |  | 1980 |  |  | RNM | Y | 2015-06-01 | 2015-06-11 | 7 | 2015-06-11 | 2015-06-11 | 2015-07-01 | 0 | 2016-06-06 | 2016-06-06 | 2017-08-15 | 60 | 25000 |  | 144550 |  |  | 2017-11-07 | 2018-05-03 | 2018-05-03 | 2020-09-17 | 2020-09-17 | 2020-09-17 | Y | Y
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00326621 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_25555 | BUTTERNUT 255 | N |  | 5000 |  |  | CDG | N | 2020-11-18 | 2020-11-30 | 6 | 2020-11-30 | 2020-11-30 | 2020-12-11 | 8 | 2021-01-05 | 2021-01-05 |  |  | 9900 | [10 empty] | N | N
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00330653 | 011 - Syracuse | EAST SYRACUSE | 13057 | 36_11_25555 | BUTTERNUT 255 | N |  | 5000 |  |  | CDG | N | 2020-12-11 | 2020-12-16 | 3 | 2020-12-16 | 2020-12-16 | 2020-12-16 | 0 | 2021-01-19 | 2021-01-19 |  |  | 10900 | [10 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00169583 | 007 - Angola | EDEN | 14057 | 36_07_8251 | N. EDEN 82 | Y |  | 3750 | 3750 |  | CDG | Y | 2018-01-29 | 2018-02-13 | 5 | 2018-02-13 | 2018-02-13 | 2018-02-26 | 0 | 2018-05-30 | 2018-05-30 | 2018-08-22 | 59 | 16800 |  | 752272 |  |  | 2019-04-19 | [5 empty] | N | Y
NIMO | RIC Development, LLC | 00333561 | 007 - Angola | EDEN | 14057 | 36_07_9352 | DELAMETER RD SUBSTATION | N |  | 5000 |  |  | CDG | N | 2020-12-23 | 2021-01-04 | 6 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 0 | 2021-03-23 | 2021-03-23 |  |  | 7800 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00252421 | 004 - Batavia | ELBA | 14422 | 36_04_2856 | E. BATAVIA 28 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-09-09 | 2019-09-19 | 8 | 2019-09-19 | 2019-09-19 | 2019-10-02 | 8 | 2019-10-21 | 2019-10-21 | 2020-02-07 | 58 | 9500 |  | 990604 |  |  | 2020-06-15 | 2020-12-04 |  |  |  |  | N | Y
NIMO | Katie Kearney (SolAmerica Energy) | 00347021 | 004 - Batavia | ELBA | 14058 |  |  | N |  | 5000 |  |  | CDG | N | 2021-03-30 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00290578 | 004 - Batavia | ELBA | 14058 | OAKFIELD-CALEDONIA #201 |  | N |  | 5000 |  |  | CDG | Y | 2020-06-01 | 2020-06-08 | 5 | 2020-06-08 | 2020-06-08 | 2020-06-08 | 0 | 2020-07-08 | 2020-07-08 | 2020-11-03 | 58 | 11300 |  | 414883.04 |  |  | 2021-02-16 | [5 empty] | N | Y
NIMO | Bogdan Dinu (BW Solar Holding Inc.) | 00293276 | 004 - Batavia | ELBA | 14058 | OAKFIELD-CALEDONIA #201 |  | N |  | 5000 |  |  | CDG | N | 2020-05-26 | 2020-06-02 | 5 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 0 | 2020-07-22 | 2020-07-22 | 2021-02-11 | 55 | 9800 |  | 921396.99 | [8 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00291376 | 010 - Olean | ELLICOTTVILLE | 14731 | 36_10_4451 | VALLEY 44 | N |  | 2170 |  |  | CDG | N | 2020-05-12 | 2020-05-19 | 5 | 2020-05-19 | 2020-05-19 | 2020-05-19 | 0 | 2020-06-18 | 2020-06-18 | 2020-11-05 | 59 | 9400 |  | 972767 | [8 empty] | N | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00322339 | 010 - Olean | ELLICOTTVILLE | 14731 | 36_10_4451 | VALLEY 44 | N |  | 2500 |  |  | CDG | N | 2020-11-09 | 2020-11-17 | 5 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 | 2021-01-05 | 2021-01-05 |  |  | 11300 | [10 empty] | N | N
NIMO | Louisa Jones (Borrego Solar Systems, Inc) | 00343897 | 010 - Olean | ELLICOTTVILLE | 14731 | 36_10_4451 | VALLEY 44 | N |  | 5000 |  |  | CDG | N | 2021-03-25 | 2021-03-26 | 1 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00345585 | 010 - Olean | ELLICOTTVILLE | 14731 | 36_10_4451 | VALLEY 44 | N |  | 5000 |  |  | CDG | N | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-03-29 | 2021-03-29 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00262705 | 013 - Watertown | EVANS MILLS | 13637 | SOUTH PHILADELPHIA-INDIAN RIVER #25 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-11-07 | 2019-11-19 | 7 | 2019-11-19 | 2019-11-19 | 2019-11-19 | 0 | 2019-12-19 | 2019-12-19 | 2020-04-30 | 59 | 9500 |  | 1254710 |  |  | 2020-06-18 | 2020-12-04 |  |  |  |  | N | Y
NIMO | Nexamp Interconnections (Nexamp Solar, LLC.) | 00228771 | 013 - Watertown | EVANS MILLS | 13637 | 36_13_32356 | INDIAN RIVER 323 | N |  | 4000 |  |  | CDG | Y | 2019-05-20 | 2019-05-30 | 7 | 2019-05-30 | 2019-05-30 | 2019-06-10 | 6 | 2019-08-14 | 2019-08-14 | 2019-11-13 | 58 | 8800 |  | 289984 |  |  | 2020-03-26 | 2020-09-15 |  |  |  |  | N | Y
NIMO | Dallas Interconnections (Nexamp) | 00229020 | 013 - Watertown | EVANS MILLS | 13637 | 36_13_32358 | INDIAN RIVER 323 | N |  | 5000 |  |  | CDG | Y | 2019-05-20 | 2019-05-30 | 7 | 2019-05-30 | 2019-05-30 | 2019-06-10 | 6 | 2019-08-13 | 2019-08-13 | 2019-11-27 | 59 | 11800 |  | 2027807 |  |  | 2020-04-09 | 2020-09-29 |  |  |  |  | N | Y
NIMO | Dallas Manson (Nexamp) | 00313436 | 013 - Watertown | EVANS MILLS | 13637 | 36_13_32358 | INDIAN RIVER 323 | N |  | 5000 |  |  | CDG | N | 2020-10-08 | 2020-10-08 | 0 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 | 2021-03-26 | 2021-03-26 |  |  | 10900 | [10 empty] | N | N
NIMO | Caroline Rizzo (Aura Power) | 00340105 | 013 - Watertown | EVANS MILLS | 13639 | 36_13_32355 | INDIAN RIVER 323 | N |  | 5000 |  |  | CDG | N | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-03 | 2021-03-03 | 0 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00331981 | 011 - Syracuse | FABIUS | 13063 | 36_12_27851 | TULLY CENTER 278 | N |  | 5000 |  |  | CDG | N | 2020-12-23 | 2020-12-30 | 4 | 2020-12-30 | 2020-12-30 | 2020-12-30 | 0 | 2021-03-16 | 2021-03-16 |  |  | 10100 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00253463 | 011 - Syracuse | FAYETTEVILLE | 13066 | 36_11_26551 | DUGUID 265 | N |  | 5000 |  |  | CDG | Y | 2019-10-22 | 2019-11-01 | 8 | 2019-11-01 | 2019-11-01 | 2019-11-18 | 9 | 2019-12-05 | 2019-12-05 | 2020-03-13 | 59 | 9800 |  | 736971 |  |  | 2020-04-15 | 2020-10-07 |  |  |  |  | N | Y
NIMO | Will Fischer (SRE Solar Origination 2, LLC) | 00298190 | 030 - Albany | FEURA BUSH | 12067 | 36_30_27651 | UNIONVILLE 276 | N |  | 5000 |  |  | CDG | N | 2020-06-26 | 2020-07-05 | 5 | 2020-07-05 | 2020-07-05 | 2020-07-07 | 1 | 2020-10-16 | 2020-10-16 | 2021-04-12 | 58 | 10100 |  | 1053646 | [8 empty] | N | N
NIMO | BWC Indian Rd Pond, LLC (BlueWave Solar) | 00297826 | 035 - Gloversville | FONDA | 12068 | 36_35_37952 | CENTER ST 379 | N |  | 3620 |  |  | CDG | N | 2020-08-11 | 2020-08-21 | 8 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 2021-01-13 | 2021-01-13 | 2021-04-12 | 60 | 11700 |  | 2285708 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00317427 | 035 - Gloversville | FONDA | 12068 | 36_35_37953 | CENTER ST 379 | N |  | 5000 |  |  | RNM | N | 2020-10-14 | 2020-10-19 | 3 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 0 | 2020-12-23 | 2020-12-23 | 2021-04-02 | 58 | 9800 |  | 311503 | [8 empty] | N | N
NIMO | BWC Crum Run, LLC (BlueWave Solar) | 00297807 | 035 - Gloversville | FONDA | 12068 | 36_35_37952 | CENTER ST 379 | N |  | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-21 | 8 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 2020-10-06 | 2020-10-06 | 2021-04-12 | 60 | 11700 |  | 2018348 | [8 empty] | N | N
NIMO | Joe Fiori (Nexamp) | 00250985 | 027 - Malone | FORT COVINGTON | 12937 | 36_27_89642 | FORT COVINGTON 896 | N |  | 2000 |  |  | CDG | Y | 2019-10-03 | 2019-10-15 | 8 | 2019-10-15 | 2019-10-15 | 2019-11-04 | 13 | 2019-12-26 | 2019-12-26 | 2020-04-08 | 59 | 9200 |  | 833238.74 |  |  | 2020-08-14 | 2020-08-14 |  |  |  |  | N | Y
NIMO | Barton Pitts (Nexamp) | 00292086 | 027 - Malone | FORT COVINGTON | 12937 | 36_27_89642 | FORT COVINGTON 896 | N |  | 4500 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-16 | 2020-06-16 | 2020-09-23 | 59 | 11700 |  | 765915.89 |  |  | 2021-02-04 | [5 empty] | N | N
NIMO | Joe Tassone (ABOVEgrid LLC) | 00319532 | 027 - Malone | FORT COVINGTON | 12937 | FT COVINGTON-MALONE #26 |  | N |  | 5000 |  |  | CDG | N | 2020-10-20 | 2020-10-28 | 6 | 2020-10-28 | 2020-10-28 | 2020-10-28 | 0 | 2021-02-24 | 2021-02-24 |  |  | 9800 | [10 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00201351 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_33751 | BURGOYNE 337 | Y |  | 4980 | 5000 |  | CDG | Y | 2018-11-30 | 2018-12-10 | 6 | 2018-12-10 | 2018-12-10 | 2018-12-12 | 1 | 2019-08-14 | 2019-08-14 | 2020-08-28 | 83 | 9400 |  | 348713 |  |  | 2020-11-16 | [5 empty] | N | Y
NIMO | Mike Borkowski (Community Power Group) | 00282762 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_08851 | HUDSON FALLS 88 | N |  | 5000 |  |  | CDG | N | 2020-05-01 | 2020-05-11 | 6 | 2020-05-11 | 2020-05-11 | 2020-05-11 | 0 | 2020-10-02 | 2020-10-02 | 2021-01-04 | 59 | 10600 |  | 722437 |  |  | 2021-03-24 | [5 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00211371 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_36253 | BUTLER 362 | N |  | 5000 |  |  | CDG | Y | 2019-02-26 | 2019-03-08 | 8 | 2019-03-08 | 2019-03-08 | 2019-03-13 | 2 | 2019-05-08 | 2019-05-08 | 2019-08-28 | 59 | 9200 |  | 573532 |  |  | 2020-02-21 | 2021-02-18 |  |  |  |  | N | Y
NIMO |  | 00211385 | 038 - Glens Falls | FORT EDWARD | 12828 | 36_38_36253 | BUTLER 362 | N |  | 5000 |  |  | CDG | Y | 2019-02-26 | 2019-03-08 | 8 | 2019-03-08 | 2019-03-08 | 2019-03-13 | 2 | 2019-05-08 | 2019-05-08 | 2019-08-28 | 59 | 9800 |  | 321843 |  |  | 2020-02-21 | 2021-02-18 |  |  |  |  | N | Y
NIMO | Finney Solar (Cypress Creek Renewables LLC) | 00169964 | 034 - Amsterdam | FORT JOHNSON | 12070 | 36_35_35854 | STONER 358 | N |  | 5000 |  |  | CDG | Y | 2018-02-05 | 2018-02-26 | 2 | 2018-02-26 | 2018-02-26 | 2018-03-13 | 10 | 2018-06-21 | 2018-06-21 | 2018-11-27 | 48 | 17200 |  | 127083.01 |  |  | 2019-04-09 | 2019-09-27 |  |  |  |  | N | Y
NIMO | Theresa Baker (DISTRIBUTED SOLAR OPERATIONS LLC) | 00286153 | 035 - Gloversville | FORT PLAIN | 13339 | 36_35_33551 | ST JOHNSVILLE 335 | N |  | 3450 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-26 | 0 | 2020-06-16 | 2020-06-16 | 2021-01-29 | 59 | 13300 | [10 empty] | N | N
NIMO | Theresa Baker (Distributed Solar Operations, LLC) | 00286146 | 035 - Gloversville | FORT PLAIN | 13339 | 36_35_33551 | ST JOHNSVILLE 335 | N |  | 4500 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-16 | 2020-06-16 | 2021-01-29 | 59 | 13300 | [10 empty] | N | N
NIMO | Kyle Talbot (DynaSolar DevCo) | 00316700 | 017 - Utica | FRANKFORT | 13340 | 36_17_66354 | SCHUYLER 663 | N |  | 4980 |  |  | RNM | Y | 2020-10-15 | 2020-10-22 | 5 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2021-03-22 | 2021-03-22 |  |  | 8800 | [10 empty] | N | Y
NIMO | Margaret Campbell (EDF Renewables) | 00279701 | 017 - Utica | FRANKFORT | 13340 | 36_17_66356 | SCHUYLER 663 | N |  | 5000 |  |  | CDG | N | 2020-02-26 | 2020-03-09 | 8 | 2020-03-09 | 2020-03-09 | 2020-03-09 | 0 | 2020-05-04 | 2020-05-04 | 2020-10-20 | 59 | 9000 |  | 499947.01 |  |  | 2021-03-10 | [5 empty] | N | N
NIMO | Elie Schecter (OurGeneration LLC) | 00313312 | 017 - Utica | FRANKFORT | 13340 | 36_17_66352 | SCHUYLER 663 | N |  | 5000 |  |  | CDG | N | 2020-09-28 | 2020-10-03 | 5 | 2020-10-03 | 2020-10-03 | 2020-10-22 | 13 | 2020-12-23 | 2020-12-23 | 2021-04-07 | 59 | 9100 |  | 152343 | [8 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00273247 | 017 - Utica | FRANKFORT | 13340 | 36_17_66851 | CHADWICKS 668 | N |  | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-17 | 6 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-05-20 | 2020-05-20 | 2021-01-13 | 58 | 10800 |  | 1995683 | [8 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00273255 | 017 - Utica | FRANKFORT | 13340 | 36_17_66851 | CHADWICKS 668 | N |  | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-17 | 6 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-05-20 | 2020-05-20 | 2021-01-13 | 59 | 10800 |  | 1995683 | [8 empty] | N | N
NIMO | Gordon Woodcock (Pivot Energy) | 00312217 | 010 - Olean | FRANKLINVILLE | 14737 | 36_10_1362 | MACHIAS 13 | N |  | 1000 |  |  | CDG | N | 2020-10-15 | 2020-10-22 | 5 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2020-11-17 | 2020-11-17 |  |  | 10300 | [10 empty] | N | N
NIMO | Sam Youneszadeh (Dimension Energy LLC (Dimension R | 00302320 | 010 - Olean | FRANKLINVILLE | 14737 | MACHIAS-MAPLEHURST #802 |  | N |  | 4625 |  |  | CDG | Y | 2020-08-04 | 2020-08-16 | 9 | 2020-08-16 | 2020-08-16 | 2020-08-26 | 7 | 2020-09-18 | 2020-09-18 |  |  | 11300 | [10 empty] | N | Y
NIMO | Michael Prinzi (Solar Liberty Energy Systems, Inc. | 00217761 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_15352 | BERRY RD 153 | Y |  | 1625 | 787.5 |  | RNM | Y | 2019-05-03 | 2019-05-10 | 5 | 2019-05-10 | 2019-05-10 | 2019-05-16 | 3 | 2019-07-19 | 2019-07-19 | 2019-12-10 | 58 | 11200 |  | 251298 |  |  | 2020-03-09 | 2020-08-21 |  |  |  |  | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00252184 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_9956 | BENNETT RD 99 | N |  | 3500 |  |  | CDG | Y | 2019-10-08 | 2019-10-18 | 8 | 2019-10-18 | 2019-10-18 | 2019-11-04 | 10 | 2019-12-09 | 2019-12-09 | 2020-10-12 | 59 | 7900 |  | 121956 |  |  | 2021-02-22 | [5 empty] | N | Y
NIMO | RIC Development, LLC | 00341185 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_15352 | BERRY RD 153 | N |  | 4699.8 |  |  | CDG | N | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00262694 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | 36_08_9956 | BENNETT RD 99 | N |  | 5000 |  |  | CDG | Y | 2019-11-13 | 2019-11-25 | 8 | 2019-11-25 | 2019-11-25 | 2019-12-03 | 3 | 2020-01-21 | 2020-01-21 | 2020-10-12 | 59 | 10000 |  | 408437.88 |  |  | 2021-02-22 | [5 empty] | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00300604 | 008 - Dunkirk/Fredoni | FREDONIA | 14063 | DUNKIRK-HARTFIELD #852 |  | N |  | 5000 |  |  | CDG | N | 2020-07-13 | 2020-07-23 | 8 | 2020-07-23 | 2020-07-23 | 2020-08-13 | 14 | 2020-10-20 | 2020-10-20 | 2021-03-01 | 59 | 8600 |  | 327038 | [8 empty] | N | N
NIMO | Gordon Woodcock (Pivot Energy) | 00308812 |  | FREWSBURG | 14738 | 36_09_6962 | FREWSBURG 69 | N |  | 5000 |  |  | CDG | N | 2020-09-11 | 2020-09-20 | 6 | 2020-09-20 | 2020-09-20 | 2020-09-29 | 6 | 2020-11-05 | 2020-11-05 |  |  | 11300 | [10 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00318629 | 009 - Lakewood/Stow | FREWSBURG | 14738 | 36_09_6961 | FREWSBURG 69 | N |  | 5000 |  |  | CDG | N | 2020-10-30 | 2020-11-10 | 7 | 2020-11-10 | 2020-11-10 | 2020-11-18 | 4 | 2021-01-14 | 2021-01-14 |  |  | 10900 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00227448 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | Y |  | 3264 | 4000 |  | CDG | N | 2019-05-29 | 2019-06-06 | 6 | 2019-06-06 | 2019-06-06 | 2019-06-19 | 8 | 2019-06-25 | 2019-06-25 | 2019-12-09 | 55 | 10600 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00218596 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | Y |  | 3190 | 5000 |  | CDG | Y | 2019-04-30 | 2019-05-09 | 8.9299 | 2019-05-10 | 2019-05-10 | 2019-05-14 | 2 | 2019-05-22 | 2019-05-22 | 2019-10-21 | 59 | 9900 |  | 430282 |  |  | 2019-10-25 | 2020-01-17 | 2020-01-17 | 2021-02-12 | 2021-02-12 | 2021-02-12 | Y | Y
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00206724 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-01-29 | 2019-02-07 | 7 | 2019-02-07 | 2019-02-07 | 2019-02-15 | 5 | 2019-04-02 | 2019-04-02 | 2019-06-25 | 57 | 10100 |  | 595633 |  |  | 2019-10-21 | 2020-04-02 |  |  |  |  | N | Y
NIMO | SOLARCITY CORP. (Solar City) | 00101198 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29652 | WHITAKER 296 | N |  | 1988 |  |  | RNM | N | 2015-07-16 | 2015-08-07 | 4 | 2015-08-07 | 2015-08-07 | 2015-09-09 | 0 | 2015-10-01 | 2015-10-01 | 2016-07-18 | 60 | 25000 |  | 846046 |  |  | 2017-03-07 |  |  | 2018-06-25 | 2018-06-25 | 2018-06-25 | Y | N
NIMO | RIC Development LLC | 00347206 | 014 - Fulton/Volney | FULTON | 13069 | 36_14_29651 | WHITAKER 296 | N |  | 5000 |  |  | CDG | N | 2021-03-18 | 2021-03-19 | 1 | 2021-03-19 | 2021-03-19 | 2021-03-29 | 5 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00328542 | 014 - Fulton/Volney | FULTON | 13069 | FAY-CURTIS #26 |  | N |  | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-09 | 6 | 2020-12-09 | 2020-12-09 | 2020-12-09 | 0 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00294441 | 035 - Gloversville | FULTONVILLE | 12072 | 36_35_50151 | FLORIDA 501 | Y |  |  | 0 | 5000 | CDG | N | 2020-06-19 | 2020-06-29 | 6 | 2020-06-29 | 2020-06-29 | 2020-07-21 | 14 |  |  |  |  | 11800 | [10 empty] | N | N
NIMO | Ryan Lloyd (DG VEMV, LLC) | 00217483 | 035 - Gloversville | FULTONVILLE | 12072 | 36_35_37954 | CENTER ST 379 | Y |  | 4980 | 5000 |  | CDG | Y | 2019-04-04 | 2019-04-15 | 7 | 2019-04-15 | 2019-04-15 | 2019-04-23 | 5 | 2019-10-08 | 2019-10-08 | 2020-01-09 | 55 | 9200 |  | 1060500.94 |  |  | 2020-01-22 | 2020-09-03 |  |  |  |  | N | Y
NIMO | Ryan Lloyd (DG VEMV, LLC) | 00217569 | 035 - Gloversville | FULTONVILLE | 12072 | 36_35_37954 | CENTER ST 379 | Y |  | 4980 | 5000 |  | CDG | Y | 2019-04-05 | 2019-04-15 | 6 | 2019-04-15 | 2019-04-15 | 2019-04-23 | 5 | 2019-07-23 | 2019-07-23 | 2020-01-15 | 54 | 11300 |  | 309980.9 |  |  | 2020-01-22 | 2020-09-10 |  |  |  |  | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316699 | 034 - Amsterdam | FULTONVILLE | 12072 | 36_35_50151 | FLORIDA 501 | N |  | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-26 | 6 | 2020-10-26 | 2020-10-26 | 2020-11-02 | 4 | 2020-12-17 | 2020-12-17 |  |  | 10800 | [10 empty] | N | N
NIMO | RIC Development, LLC | 00345559 | 035 - Gloversville | FULTONVILLE | 12072 | 36_35_50151 | FLORIDA 501 | N |  | 5000 |  |  | CDG | N | 2021-03-11 | 2021-03-19 | 6 | 2021-03-19 | 2021-03-19 | 2021-03-19 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00316603 | 034 - Amsterdam | GALWAY | 12074 | 36_32_322151 | LASHER RD | N |  | 3250 |  |  | CDG | N | 2020-10-05 | 2020-10-08 | 3 | 2020-10-08 | 2020-10-08 | 2020-10-27 | 12 | 2020-12-16 | 2020-12-16 | 2021-04-08 | 59 | 10700 |  | 1016541 | [8 empty] | N | N
NIMO | Dave Byrne (Renua Energy, Inc.) | 00284819 | 038 - Glens Falls | GANSEVOORT | 12831 | 36_38_32952 | WILTON 329 | N |  | 4000 |  |  | CDG | N | 2020-03-24 | 2020-04-02 | 7 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 | 2020-05-13 | 2020-05-13 | 2020-10-14 | 59 | 10400 |  | 567400.02 |  |  | 2021-03-08 | [5 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00316102 | 038 - Glens Falls | GANSEVOORT | 12831 | 36_38_36251 | BUTLER 362 | N |  | 4975 |  |  | CDG | N | 2020-12-16 | 2020-12-18 | 2 | 2020-12-18 | 2020-12-18 | 2020-12-21 | 0 | 2021-02-26 | 2021-02-26 |  |  | 11300 | [10 empty] | N | N
NIMO | Dave Byrne (Renua Energy, Inc.) | 00318630 | 038 - Glens Falls | GANSEVOORT | 12831 | 36_38_36251 | BUTLER 362 | N |  | 5000 |  |  | CDG | N | 2020-11-04 | 2020-11-09 | 3 | 2020-11-09 | 2020-11-09 | 2020-11-16 | 3 | 2021-01-19 | 2021-01-19 |  |  | 11300 | [10 empty] | N | N
NIMO | EnterSolar Engineering (EnterSolar) | 00291782 | 039 - Saratoga | GANSEVOORT | 12831 | 36_39_32951 | WILTON 329 | N |  | 5000 |  |  | RNM | Y | 2020-05-15 | 2020-05-20 | 3 | 2020-05-20 | 2020-05-20 | 2020-05-22 | 1 | 2020-06-12 | 2020-06-12 | 2021-01-06 | 62 | 10800 |  | 689151 | [8 empty] | N | Y
NIMO | John McDonough (Lumens Holdings 3 LLC) | 00206012 | 039 - Saratoga | GANSEVOORT | 12831 | 36_39_41556 | WEIBEL AVE 415 | N |  | 5000 |  |  | CDG | Y | 2019-02-11 | 2019-02-19 | 5 | 2019-02-19 | 2019-02-19 | 2019-02-22 | 2 | 2019-06-03 | 2019-06-03 | 2019-08-22 | 55 | 10100 |  | 276806 |  |  | 2019-12-30 | 2020-09-11 |  |  |  |  | N | Y
NIMO | Michael Roach (RER Energy Group LLC) | 00187608 | 005 - Avon | GENESEO | 14454 | 36_05_438152 | SONORA WAY | N |  | 3036 |  |  | CDG | Y | 2018-06-21 | 2018-07-10 | 7 | 2018-07-10 | 2018-07-10 | 2018-07-26 | 11 | 2018-11-01 | 2018-11-01 | 2019-02-04 | 60 | 6200 |  | 421240.1 |  |  | 2019-07-31 | 2020-02-27 | 2020-02-27 | 2021-03-18 | 2021-03-18 | 2021-03-18 | Y | Y
NIMO | Caroline Rizzo (Aura Power) | 00341891 | 005 - Avon | GENESEO | 14454 | 36_05_5552 | GENESEO 55 | N |  | 5000 |  |  | CDG | N | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-02-26 | 2021-02-26 | 0 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | charles vogel (Oriden LLC) | 00330392 | 005 - Avon | GENESEO | 14454 | 36_05_438152 | SONORA WAY | N |  | 5000 |  |  | NA | N | 2020-12-23 | 2020-12-23 | 0 | 2020-12-23 | 2020-12-23 | 2020-12-23 | 0 | 2021-04-07 | 2021-04-07 |  |  | 9800 | [10 empty] | N | N
NIMO | Andy Melka (Horizon Solar Power) | 00266300 | 005 - Avon | GENESEO | 14454 | 36_05_438151 | SONORA WAY | N |  | 5000 |  |  | CDG | Y | 2019-12-10 | 2019-12-19 | 7 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 0 | 2019-12-31 | 2019-12-31 | 2020-05-14 | 51 | 9800 |  | 121955.41 |  |  | 2020-09-23 | 2021-03-25 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00217635 | 005 - Avon | GENESEO | 14454 | N LAKEVILLE-RIDGE #218 |  | N |  | 5000 |  |  | CDG | Y | 2019-04-05 | 2019-04-16 | 7 | 2019-04-16 | 2019-04-16 | 2019-04-23 | 4 | 2019-08-09 | 2019-08-09 | 2020-01-16 | 57 | 11800 |  | 292376.41 |  |  | 2020-05-05 | 2020-11-02 |  |  |  |  | N | Y
NIMO | Will Bliss (East Light Partners) | 00346840 | 033 - Hudson | GERMANTOWN | 12526 | 36_33_30354 | BLUE STORES 303 | N |  | 5000 |  |  | CDG | N | 2021-03-26 | 2021-04-02 | 5 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00271503 | 001 - Buffalo | GETZVILLE | 14228 | 36_01_14058 | MAPLE RD 140 | N |  | 5000 |  |  | RNM | Y | 2020-01-06 | 2020-01-17 | 8 | 2020-01-17 | 2020-01-17 | 2020-02-01 | 9 | 2020-03-11 | 2020-03-11 | 2020-07-15 | 58 | 8100 |  | 270120.38 |  |  | 2020-09-21 | 2020-10-22 |  |  |  |  | N | Y
NIMO |  | 00209758 | 023 - Lowville | GLENFIELD | 13343 | 36_23_77354 | LOWVILLE 773 | N |  | 1920 |  |  | CDG | Y | 2019-02-15 | 2019-02-27 | 7 | 2019-02-27 | 2019-02-27 | 2019-03-05 | 3 | 2019-04-19 | 2019-04-19 | 2019-08-06 | 59 | 10000 |  | 704322 |  |  | 2019-12-18 | 2020-08-31 |  |  |  |  | N | Y
NIMO | Pat McGowin | 00101326 | 030 - Albany | GLENMONT | 12077 | 36_30_02156 | BETHLEHEM 21 | N |  | 1990 |  |  | RNM | N | 2015-05-29 | 2015-05-29 | 0 | 2015-07-13 | 2015-07-13 | 2015-08-11 | 0 | 2015-10-14 | 2015-10-14 | 2016-04-21 | 136 | 30000 |  | 620000 |  |  | 2017-05-22 |  |  | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Mike Borkowski (Community Power Group) | 00273778 | 030 - Albany | GLENMONT | 12077 | 36_30_02156 | BETHLEHEM 21 | N |  | 5000 |  |  | CDG | N | 2020-01-21 | 2020-02-01 | 9 | 2020-02-01 | 2020-02-01 | 2020-02-05 | 2 | 2020-04-30 | 2020-04-30 | 2020-10-14 | 58 | 9000 |  |  |  |  | 2021-03-24 | [5 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America) | 00301686 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_39253 | VAIL MILLS 392 | Y |  | 5000 | 0 |  | CDG | N | 2020-07-22 | 2020-07-29 | 5 | 2020-07-29 | 2020-07-29 | 2020-07-29 | 0 | 2020-09-02 | 2020-09-02 | 2021-03-04 | 59 | 9900 |  | 1320262 | [8 empty] | N | N
NIMO | Giovanni Maruca (Eden Devco) | 00197660 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | Y |  | 4980 | 5000 |  | CDG | Y | 2018-10-16 | 2018-10-16 | 0 | 2018-10-16 | 2018-10-16 | 2018-10-17 | 0 | 2019-01-03 | 2019-01-03 | 2019-04-11 | 58 | 12200 |  | 630605.26 |  |  | 2019-10-04 | 2020-04-03 |  |  |  |  | N | Y
NIMO | Michael McNeley (Kearsarge Solar LLC) | 00100898 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | N |  | 1452 |  |  | CDG | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-18 | 0 | 2017-01-10 | 2017-01-10 | 2017-06-16 | 60 | 25000 |  | 230933 |  |  | 2017-06-29 |  |  | 2018-12-17 | 2018-12-17 | 2018-12-17 | Y | N
NIMO | Michael McNeley (Kearsarge Solar LLC) | 00100899 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | N |  | 1980 |  |  | CDG | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-18 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-24 | 53 | 25000 |  | 237000 |  |  | 2017-06-29 |  |  | 2018-12-17 | 2018-12-17 | 2018-12-17 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100901 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_35651 | MAYFIELD 356 | N |  | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-23 | 0 | 2016-04-11 | 2016-04-11 | 2016-07-01 | 59 | 25000 |  | 1220457 |  |  | 2017-04-05 |  |  | 2018-12-19 | 2018-12-19 | 2018-12-19 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100902 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_35651 | MAYFIELD 356 | N |  | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-12 | 4 | 2015-06-12 | 2015-06-12 | 2015-06-23 | 0 | 2016-03-17 | 2016-03-17 | 2016-06-10 | 60 | 25000 |  | 148792 |  |  | 2017-04-05 |  |  | 2018-12-19 | 2018-12-19 | 2018-12-19 | Y | N
NIMO | Mike Howell (C2 Energy Capital) | 00101997 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07253 | GLOVERSVILLE 72 | N |  | 2000 |  |  | CDG | N | 2016-02-22 | 2016-06-15 | 8 | 2016-06-15 | 2016-06-15 | 2016-06-24 | 0 | 2017-03-24 | 2017-03-24 | 2017-06-16 | 59 | 28400 |  | 379400 |  |  | 2017-07-17 |  |  | 2020-03-03 | 2020-03-03 | 2020-03-03 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00218937 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_39253 | VAIL MILLS 392 | N |  | 2500 |  |  | CDG | Y | 2019-04-15 | 2019-04-24 | 8.9118 | 2019-04-25 | 2019-04-25 | 2019-05-09 | 10 | 2019-06-11 | 2019-06-11 | 2019-08-30 | 56 | 11300 |  | 135151.58 |  |  | 2019-09-13 | 2020-02-18 | 2020-02-18 | 2020-12-21 | 2020-12-21 | 2020-12-21 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00172200 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07251 | GLOVERSVILLE 72 | N |  | 4000 |  |  | CDG | Y | 2018-03-26 | 2018-03-26 | 0 | 2018-04-03 | 2018-04-03 | 2018-04-17 | 10 | 2018-07-31 | 2018-07-31 | 2018-10-16 | 30 | 12200 |  | 128889 |  |  | 2018-11-27 |  |  | 2019-12-31 | 2019-12-31 | 2019-12-31 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00173052 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_39253 | VAIL MILLS 392 | N |  | 4000 |  |  | CDG | Y | 2018-04-16 | 2018-04-16 | 0 | 2018-04-26 | 2018-04-26 | 2018-05-08 | 8 | 2018-10-26 | 2018-10-26 | 2019-02-21 | 50 | 12200 |  | 1380241 |  |  | 2019-07-01 | 2019-12-26 | 2019-12-26 | 2020-12-28 | 2020-12-28 | 2020-12-28 | Y | Y
NIMO | Benjamin Rubin (Ameresco Inc.) | 00197711 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_07251 | GLOVERSVILLE 72 | N |  | 4980 |  |  | CDG | Y | 2018-11-27 | 2018-12-04 | 5 | 2018-12-04 | 2018-12-04 | 2018-12-06 | 1 | 2019-01-17 | 2019-01-17 | 2019-05-13 | 59 | 10100 |  | 413331 |  |  | 2019-08-26 | 2020-03-05 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00345430 | 035 - Gloversville | GLOVERSVILLE | 12078 | 36_35_39253 | VAIL MILLS 392 | N |  | 5000 |  |  | CDG | N | 2021-03-16 | 2021-03-24 | 6 | 2021-03-24 | 2021-03-24 | 2021-04-01 | 5 |  |  |  |  | 8300 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00100867 | 029 - Gouvernur | GOUVERNEUR | 13642 | 36_29_98353 | N. GOVERNEUR 983 | N |  | 996 |  |  | RNM | N | 2015-05-13 | 2015-05-28 | 3 | 2015-05-28 | 2015-05-28 | 2015-06-17 | 0 | 2016-06-10 | 2016-06-10 | 2016-09-01 | 59 | 35000 |  | 218350 | [5 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | Y | N
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00255338 | 029 - Gouvernur | GOUVERNEUR | 13642 | 36_29_98353 | N. GOVERNEUR 983 | N |  | 3500 |  |  | CDG | Y | 2019-10-18 | 2019-10-29 | 7 | 2019-10-29 | 2019-10-29 | 2019-11-18 | 12 | 2019-12-13 | 2019-12-13 | 2020-05-29 | 59 | 8800 |  | 763536.13 |  |  | 2020-10-09 | 2020-11-25 |  |  |  |  | N | Y
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00196798 | 029 - Gouvernur | GOUVERNEUR | 13642 | 36_29_98353 | N. GOVERNEUR 983 | N |  | 4000 |  |  | CDG | Y | 2018-10-18 | 2018-10-25 | 5 | 2018-10-25 | 2018-10-25 | 2018-10-26 | 0 | 2018-12-13 | 2018-12-13 | 2019-04-19 | 58 | 13600 |  | 485218.49 |  |  | 2019-09-23 | 2020-03-17 |  |  |  |  | N | Y
NIMO | GSPP 126 Little Bow Rd N, LLC | 00225639 | 029 - Gouvernur | GOUVERNEUR | 13642 |  |  | N |  | 4750 |  |  | CDG | Y | 2019-06-11 | 2019-06-20 | 7 | 2019-06-20 | 2019-06-20 | 2019-07-09 | 11 | 2019-10-09 | 2019-10-09 | 2020-01-29 | 59 | 10900 |  | 392153 |  |  | 2020-07-14 | 2021-01-21 |  |  |  |  | N | Y
NIMO | GSPP 126 Little Bow Rd S, LLC | 00225659 | 029 - Gouvernur | GOUVERNEUR | 13642 |  |  | N |  | 4750 |  |  | CDG | Y | 2019-05-09 | 2019-05-22 | 9 | 2019-05-22 | 2019-05-22 | 2019-06-03 | 6 | 2019-10-11 | 2019-10-11 | 2020-01-21 | 59 | 10900 |  | 587846 |  |  | 2020-07-14 | 2021-01-19 |  |  |  |  | N | Y
NIMO | Active Solar Development | 00101791 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_20952 | BUFFALO STATION 209 - LONG RD | N |  | 1992 |  |  | CDG | N | 2016-08-24 | 2016-09-20 | 5 | 2016-09-20 | 2016-09-20 | 2016-10-07 | 0 | 2017-01-27 | 2017-01-27 | 2017-04-21 | 60 | 16200 |  | 120494 |  |  | 2017-07-27 | 2018-04-19 | 2018-04-19 | 2020-04-08 | 2020-04-08 | 2020-04-08 | Y | N
NIMO | Geoff Fallon (Baywa-re) | 00169478 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6454 | GRAND ISLAND 64 | Y |  | 4000 |  |  | CDG | Y | 2018-03-01 | 2018-03-07 | 4 | 2018-03-07 | 2018-03-07 | 2018-03-19 | 7 | 2018-05-14 | 2018-05-14 | 2018-07-31 | 54 | 12200 |  | 223896 |  |  | 2018-08-21 | [5 empty] | N | Y
NIMO | Elie Schecter (OurGeneration LLC) | 00305463 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6457 | GRAND ISLAND 64 | N |  | 4300 |  |  | CDG | N | 2020-08-07 | 2020-08-20 | 9 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 0 | 2020-09-18 | 2020-09-18 | 2021-01-15 | 54 | 8600 |  | 121956 | [8 empty] | N | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00103018 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6454 | GRAND ISLAND 64 | N |  | 5000 |  |  | CDG | Y | 2017-04-27 | 2017-06-02 | 8 | 2017-06-05 | 2017-06-05 | 2017-06-20 | 11 | 2017-08-02 | 2017-08-02 | 2018-01-05 | 57 | 16200 |  | 288636 |  |  | 2018-03-14 |  |  | 2020-03-03 | 2020-03-03 | 2020-03-03 | Y | Y
NIMO | Elie Schecter (OurGeneration LLC) | 00305462 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6457 | GRAND ISLAND 64 | N |  | 5000 |  |  | CDG | N | 2020-08-07 | 2020-08-20 | 9 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 0 | 2020-09-18 | 2020-09-18 | 2021-01-15 | 54 | 8100 |  | 121956.41 | [8 empty] | N | N
NIMO | Benjamin Broder (Catalyze Energy) | 00290169 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_6454 | GRAND ISLAND 64 | N |  | 5000 |  |  | CDG | Y | 2020-05-05 | 2020-05-11 | 4 | 2020-05-11 | 2020-05-11 | 2020-05-12 | 0 | 2020-06-01 | 2020-06-01 | 2020-09-09 | 57 | 10100 |  | 986485 |  |  | 2020-12-04 | 2020-12-08 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00305861 | 003 - Niagara Falls | GRAND ISLAND | 14072 | 36_03_20952 | BUFFALO STATION 209 - LONG RD | N |  | 5000 |  |  | RNM | N | 2020-08-31 | 2020-09-05 | 5 | 2020-09-05 | 2020-09-05 | 2020-09-22 | 10 | 2020-11-02 | 2020-11-02 | 2021-03-26 | 57 | 9400 |  | 1251075 | [8 empty] | N | N
NIMO | Paul Vargovich (National Energy Development LLC) | 00343550 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4457 | VALLEY 44 | N |  | 3750 |  |  | CDG | N | 2021-03-15 | 2021-03-19 | 4 | 2021-03-19 | 2021-03-19 | 2021-03-19 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00247945 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4458 | VALLEY 44 | N |  | 4000 |  |  | CDG | Y | 2019-08-12 | 2019-08-22 | 8 | 2019-08-22 | 2019-08-22 | 2019-08-30 | 5 | 2019-10-10 | 2019-10-10 | 2020-02-28 | 58 | 10900 |  | 294879 |  |  | 2020-07-13 | 2021-01-25 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248154 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4456 | VALLEY 44 | N |  | 4000 |  |  | CDG | Y | 2019-08-29 | 2019-09-11 | 8 | 2019-09-11 | 2019-09-11 | 2019-09-23 | 7 | 2019-11-06 | 2019-11-06 | 2020-02-28 | 58 | 9800 |  | 121956 |  |  | 2020-07-13 | 2021-01-25 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248162 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4456 | VALLEY 44 | N |  | 4000 |  |  | CDG | Y | 2019-08-29 | 2019-09-11 | 8 | 2019-09-11 | 2019-09-11 | 2019-09-23 | 7 | 2019-11-06 | 2019-11-06 | 2020-02-28 | 58 | 9800 |  | 124956 |  |  | 2020-07-13 | 2021-01-25 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00247931 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4458 | VALLEY 44 | N |  | 5000 |  |  | CDG | Y | 2019-08-12 | 2019-08-22 | 8 | 2019-08-22 | 2019-08-22 | 2019-08-30 | 5 | 2019-10-10 | 2019-10-10 | 2020-02-28 | 58 | 10400 |  | 976056.51 |  |  | 2020-07-13 | 2021-01-25 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00247951 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4458 | VALLEY 44 | N |  | 5000 |  |  | CDG | Y | 2019-08-12 | 2019-08-22 | 8 | 2019-08-22 | 2019-08-22 | 2019-08-30 | 0 | 2019-10-10 | 2019-10-10 | 2020-02-28 | 58 | 10900 |  | 192720 |  |  | 2020-07-13 | 2021-01-25 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00248166 | 010 - Olean | GREAT VALLEY | 14741 | 36_10_4456 | VALLEY 44 | N |  | 5000 |  |  | CDG | Y | 2019-08-29 | 2019-09-11 | 8 | 2019-09-11 | 2019-09-11 | 2019-09-23 | 7 | 2019-11-06 | 2019-11-06 | 2020-03-02 | 59 | 9800 |  | 121956 |  |  | 2020-07-13 | 2021-01-25 |  |  |  |  | N | Y
NIMO | Dynamic Energy | 00082328 | 039 - Saratoga | GREENWICH | 12834 | 36_39_34258 | BATTENKILL 342 | N |  | 1932 |  |  | RNM | N | 2015-02-13 | 2015-03-25 | 2 | 2015-03-25 | 2015-03-25 | 2015-04-09 | 0 | 2015-05-14 | 2015-05-14 | 2015-10-02 | 101 | 40000 | [7 empty] | 2016-03-25 | 2016-03-25 | 2016-03-25 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00203564 |  | Greenwich | 12834 | 36_39_34258 | BATTENKILL 342 | N |  | 5000 |  |  | CDG | Y | 2019-01-02 | 2019-01-11 | 8.8681 | 2019-01-14 | 2019-01-14 | 2019-01-24 | 7 | 2019-03-20 | 2019-03-20 | 2019-06-21 | 55 | 9800 |  | 145198 |  |  | 2019-09-13 | 2020-01-16 | 2020-01-16 | 2020-12-15 | 2020-12-15 | 2020-12-15 | Y | Y
NIMO | Bradley Davis (RENESOLA) | 00311516 | 039 - Saratoga | GREENWICH | 12834 | 36_39_34257 | BATTENKILL 342 | N |  | 5000 |  |  | CDG | N | 2020-10-05 | 2020-10-11 | 5 | 2020-10-11 | 2020-10-11 | 2020-10-11 | 0 | 2020-12-03 | 2020-12-03 | 2021-04-10 | 58 | 8100 |  | 191614.73 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00328584 | 005 - Avon | GROVELAND | 14462 | N LAKEVILLE-RIDGE #218 |  | N |  | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-08 | 5 | 2020-12-08 | 2020-12-08 | 2020-12-16 | 5 | 2021-03-25 | 2021-03-25 |  |  | 11700 | [10 empty] | N | N
NIMO | Loren Pruskowski (Ecolegacy Values) | 00336919 | 030 - Albany | GUILDERLAND | 12084 | 36_30_37153 | PINEBUSH 371 | N |  | 5000 |  |  | CDG | N | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-01-29 | 2021-01-29 | 0 | 2021-04-02 | 2021-04-02 |  |  | 8000 | [10 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00283966 | 035 - Gloversville | HADLEY | 12822 | 36_39_28551 | CORINTH 285 | N |  | 5000 |  |  | CDG | N | 2020-04-23 | 2020-04-30 | 5 | 2020-04-30 | 2020-04-30 | 2020-05-04 | 1 | 2020-08-11 | 2020-08-11 | 2021-02-04 | 59 | 11300 |  | 1048392 | [8 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00340410 | 034 - Amsterdam | HAGAMAN | 12086 | 36_35_04353 | CHURCH ST 43 | N |  | 4000 |  |  | CDG | N | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-02-26 | 2021-02-26 | 0 |  |  |  |  | 8700 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315545 | 034 - Amsterdam | HAGAMAN | 12086 | 36_35_50254 | MAPLE AVE 502 | N |  | 5000 |  |  | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 10100 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00259334 | 034 - Amsterdam | HAGAMAN | 12086 | 36_35_50253 | MAPLE AVE 502 | N |  | 5000 |  |  | CDG | Y | 2019-10-30 | 2019-11-08 | 7 | 2019-11-08 | 2019-11-08 | 2019-11-18 | 4 | 2020-01-14 | 2020-01-14 | 2020-04-09 | 59 | 13000 |  | 495349 |  |  | 2020-05-26 | 2020-11-12 |  |  |  |  | N | Y
NIMO | Ryan Lloyd (Helios Energy New York 2 LLC) | 00173171 | 006 - Albion/Medina | HAMLIN | 14464 | 36_06_8254 | W. HAMLIN 82 | N |  | 4500 |  |  | CDG | Y | 2018-04-09 | 2018-04-18 | 2 | 2018-04-18 | 2018-04-18 | 2018-05-02 | 9 | 2018-10-26 | 2018-10-26 | 2019-01-30 | 59 | 14300 |  | 278496.61 |  |  | 2019-06-10 | 2020-01-13 |  |  |  |  | N | Y
NIMO | Ryan Lloyd (Helios Energy New York 9 LLC) | 00173173 |  | HAMLIN | 14464 | 36_06_8254 | W. HAMLIN 82 | N |  | 4500 |  |  | CDG | Y | 2018-04-09 | 2018-04-18 | 2 | 2018-04-18 | 2018-04-18 | 2018-05-02 | 9 | 2018-10-26 | 2018-10-26 | 2019-01-30 | 59 | 14300 |  | 285247.22 |  |  | 2019-06-10 | 2020-01-13 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00168256 | 006 - Albion/Medina | HAMLIN | 14464 | 36_06_8251 | W. HAMLIN 82 | N |  | 5000 |  |  | CDG | Y | 2018-01-09 | 2018-01-09 | 0 | 2018-01-16 | 2018-01-16 | 2018-01-31 | 11 | 2018-04-30 | 2018-04-30 | 2018-07-23 | 58 | 15600 |  | 754907 |  |  | 2018-10-15 |  |  | 2020-12-17 | 2020-12-17 | 2020-12-17 | Y | Y
NIMO | Adam Ellis (Nexamp) | 00301997 | 014 - Fulton/Volney | HANNIBAL | 13074 | 36_14_13564 | FAIRDALE 135 | N |  | 2700 |  |  | CDG | N | 2020-08-26 | 2020-09-03 | 6 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 0 | 2020-10-22 | 2020-10-22 | 2021-03-18 | 59 | 10900 |  | 770309 | [8 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00316797 | 005 - Avon | HEMLOCK | 14466 | 36_05_3251 | RICHMOND 32 | N |  | 5000 |  |  | CDG | N | 2020-10-05 | 2020-10-12 | 5 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-12-14 | 2020-12-14 | 2021-04-05 | 58 | 10900 |  | 1732157 | [8 empty] | N | N
NIMO | Nexamp Interconnections (Nexamp) | 00206459 | 013 - Watertown | HENDERSON | 13650 | 36_13_87551 | W. ADAMS 875 | Y |  | 4375 | 2500 |  | CDG | Y | 2019-01-22 | 2019-01-29 | 5 | 2019-01-29 | 2019-01-29 | 2019-02-08 | 7 | 2019-03-25 | 2019-03-25 | 2019-06-19 | 58 | 10100 |  | 967157.38 |  |  | 2019-12-16 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00331733 | 029 - Gouvernur | HERMON | 13652 | 36_29_98455 | DEKALB 984 | N |  | 2500 |  |  | CDG | N | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 2020-12-29 | 2020-12-29 | 0 | 2021-03-16 | 2021-03-16 |  |  | 9400 | [10 empty] | N | N
NIMO | Margaret Campbell (EDF Renewables) | 00209913 | 028 - Ogdensburg | HEUVELTON | 13654 | 36_28_91451 | MCADOO 914 | N |  | 2000 |  |  | CDG | Y | 2019-02-26 | 2019-03-08 | 8 | 2019-03-08 | 2019-03-08 | 2019-03-19 | 6 | 2019-04-09 | 2019-04-09 | 2019-11-27 | 59 | 14300 |  | 475337.09 |  |  | 2020-04-07 | 2020-11-16 |  |  |  |  | N | Y
NIMO | Michael Frateschi (TJA Clean Energy) | 00304893 | 028 - Ogdensburg | HEUVELTON | 13654 | 36_28_91451 | MCADOO 914 | N |  | 5000 |  |  | CDG | N | 2020-08-05 | 2020-08-16 | 8 | 2020-08-16 | 2020-08-16 | 2020-08-16 | 0 | 2020-09-08 | 2020-09-08 | 2020-12-09 | 58 | 10500 |  | 1082247.65 | [8 empty] | N | N
NIMO | Janet Ward (Nextera Energy) | 00242005 | 006 - Albion/Medina | HILTON | 14468 | 36_06_8253 | W. HAMLIN 82 | N |  | 5000 |  |  | CDG | Y | 2019-07-10 | 2019-07-15 | 3 | 2019-07-15 | 2019-07-15 | 2019-07-23 | 5 | 2019-09-06 | 2019-09-06 | 2020-01-30 | 58 | 10100 |  | 355283.28 |  |  | 2020-06-10 | 2020-12-11 |  |  |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291545 | 010 - Olean | HINSDALE | 14727 | HOMER HILL-NILE #811 |  | N |  | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-22 | 1 | 2020-07-29 | 2020-07-29 | 2020-11-02 | 56 | 11300 |  | 294399 | [8 empty] | N | N
NIMO | Jacob Fraatz (Dimension Energy LLC (Dimension Rene | 00302883 | 010 - Olean | HINSDALE | 14743 | MACHIAS-MAPLEHURST #802 |  | N |  | 5000 |  |  | CDG | Y | 2020-08-07 | 2020-08-20 | 9 | 2020-08-20 | 2020-08-20 | 2020-09-08 | 11 | 2020-10-02 | 2020-10-02 |  |  | 11300 | [10 empty] | N | Y
NIMO | Alexander Paul McMenemy (Solar Generation Projects | 00277306 |  | HOLLAND PATENT | 13354 | 36_17_60656 | DEERFIELD 606 | N |  | 4750 |  |  | CDG | N | 2020-02-21 | 2020-03-04 | 8 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-03-19 | 2020-03-19 | 2020-12-04 | 58 | 10400 |  | 828977.01 | [8 empty] | N | N
NIMO | Alexander Paul McMenemy (Solar Generation Projects | 00277347 | 017 - Utica | HOLLAND PATENT | 13354 | 36_17_60656 | DEERFIELD 606 | N |  | 5000 |  |  | CDG | N | 2020-02-21 | 2020-03-04 | 8 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-04-28 | 2020-04-28 | 2020-12-21 | 59 | 10400 |  | 2641961 | [8 empty] | N | N
NIMO | Joris Hay (Abundant Solar Power (Richmond) LLC.) | 00238572 |  | HONEOYE | 14471 | 36_05_3253 | RICHMOND 32 | N |  | 5000 |  |  | CDG | Y | 2019-08-12 | 2019-08-19 | 5 | 2019-08-19 | 2019-08-19 | 2019-08-27 | 5 | 2019-10-28 | 2019-10-28 | 2020-03-06 | 56 | 9400 |  | 567400.02 |  |  | 2020-07-20 | 2021-01-27 |  |  |  |  | N | Y
NIMO | Joseph Fiori (Nexamp) | 00187820 | 005 - Avon | HONEOYE FALLS | 14472 | 36_05_5156 | E. GOLAH 51 | Y |  | 5000 | 5000 |  | CDG | Y | 2018-07-06 | 2018-07-16 | 6 | 2018-07-16 | 2018-07-16 | 2018-08-01 | 11 | 2018-09-27 | 2018-09-27 | 2019-05-01 | 60 | 14300 |  | 661928 |  |  | 2019-09-11 | 2020-03-12 |  |  |  |  | N | Y
NIMO | Ryan McCune (Nexamp) | 00322599 | 031 - Troy | HOOSICK FALLS | 12090 | 36_31_31451 | HOOSICK 314 | N |  | 4950 |  |  | CDG | N | 2020-11-13 | 2020-11-16 | 1 | 2020-11-16 | 2020-11-16 | 2020-12-01 | 8 | 2020-12-21 | 2020-12-21 |  |  | 9800 | [10 empty] | N | N
NIMO | David Elliott (NY SOLAR FARMS INC) | 00283380 | 031 - Troy | HOOSICK FALLS | 12090 | 36_31_31451 | HOOSICK 314 | N |  | 5000 |  |  | CDG | N | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 0 | 2020-08-12 | 2020-08-12 |  |  | 9800 | [10 empty] | N | N
NIMO | David Elliott (NY SOLAR FARMS INC) | 00283374 | 031 - Troy | HOOSICK FALLS | 12090 | 36_31_33351 | BOYNTONVILLE 333 | N |  | 5000 |  |  | CDG | N | 2020-03-27 | 2020-04-02 | 4 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 |  |  |  |  | 10000 | [10 empty] | N | N
NIMO | Wendy De Wolf (East Light Partners) | 00173582 | 033 - Hudson | HUDSON | 12534 | 36_33_08751 | HUDSON 87 | Y | 00207300 | 5000 | 0 |  | CDG | Y | 2018-05-20 | 2018-05-20 | 0 | 2018-06-12 | 2018-06-12 | 2018-06-27 | 11 | 2018-08-23 | 2018-08-23 | 2019-01-04 | 56 | 14600 |  | 319451.12 |  |  | 2019-05-03 |  |  | 2020-06-01 | 2020-06-01 | 2020-06-01 | Y | Y
NIMO | Ryan Lloyd (NextEra) | 00190334 | 033 - Hudson | HUDSON | 12534 | 36_33_08752 | HUDSON 87 | Y |  | 5000 | 4500 |  | CDG | Y | 2018-07-12 | 2018-07-20 | 6 | 2018-07-20 | 2018-07-20 | 2018-08-07 | 11 | 2018-10-30 | 2018-10-30 | 2019-03-08 | 58 | 12200 |  | 862913.71 |  |  | 2019-10-16 | 2020-05-14 |  |  |  |  | N | Y
NIMO | Ryan Lloyd (NextEra) | 00201083 | 033 - Hudson | HUDSON | 12534 | 36_33_08752 | HUDSON 87 | Y |  | 5000 | 4500 |  | CDG | Y | 2018-11-29 | 2018-12-05 | 4 | 2018-12-05 | 2018-12-05 | 2018-12-12 | 4 | 2019-02-04 | 2019-02-04 | 2019-03-30 | 28 | 10400 |  | 122285.57 |  |  | 2019-10-15 | 2020-04-09 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Clover Meadow Solar, LLC) | 00235092 | 033 - Hudson | HUDSON | 12534 | 36_33_08755 | HUDSON 87 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-06-28 | 2019-06-28 | 0 | 2019-06-28 | 2019-06-28 | 2019-07-12 | 8 | 2020-02-19 | 2020-02-19 | 2020-05-12 | 59 | 9900 |  | 85438.01 |  |  | 2020-09-18 | [5 empty] | N | Y
NIMO | SunStream Partners | 00094626 | 033 - Hudson | HUDSON | 12208 | 36_33_45451 | BUCKLEY CORNERS 454 | N |  | 2000 |  |  | RNM | N | 2014-06-23 | 2014-07-10 | 6 | 2014-07-10 | 2014-07-10 | 2014-07-28 | 0 | 2015-03-18 | 2015-03-18 | 2015-07-20 | 88 | 17160 |  | 1018410 | [5 empty] | 2016-11-23 | 2016-11-23 | 2016-11-23 | Y | N
NIMO | SunStream Partners | 00094627 | 033 - Hudson | HUDSON | 12134 | 36_33_45451 | BUCKLEY CORNERS 454 | N |  | 2000 |  |  | RNM | N | 2014-07-01 | 2014-07-07 | 3 | 2014-07-07 | 2014-07-07 | 2014-07-28 | 4 | 2015-07-19 | 2015-07-19 | 2015-08-04 | 11 | 17160 |  | 218990 | [5 empty] | 2016-11-23 | 2016-11-23 | 2016-11-23 | Y | N
NIMO | Wendy DeWolf (East Light Partners) | 00265520 | 033 - Hudson | HUDSON | 12534 | 36_33_45451 | BUCKLEY CORNERS 454 | N |  | 3490 |  |  | CDG | Y | 2019-11-22 | 2019-12-04 | 6 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 0 | 2019-12-12 | 2019-12-12 | 2020-06-11 | 59 | 9800 |  | 197806.61 |  |  | 2020-10-19 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00233096 | 033 - Hudson | HUDSON | 12534 | 36_33_08755 | HUDSON 87 | N |  | 5000 |  |  | CDG | Y | 2019-06-17 | 2019-06-26 | 7 | 2019-06-26 | 2019-06-26 | 2019-07-09 | 7 | 2019-09-10 | 2019-09-10 | 2019-12-09 | 58 | 10100 |  | 321098 |  |  | 2020-03-09 | 2020-09-03 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00244865 | 033 - Hudson | HUDSON | 12534 | 36_33_08753 | HUDSON 87 | N |  | 5000 |  |  | RNM | Y | 2019-08-29 | 2019-09-09 | 6 | 2019-09-09 | 2019-09-09 | 2019-09-20 | 8 | 2019-10-22 | 2019-10-22 | 2020-02-28 | 53 | 9000 |  | 147850.04 |  |  | 2020-07-22 | 2021-01-15 |  |  |  |  | N | Y
NIMO | Wendy DeWolf (East Light Partners) | 00292700 | 033 - Hudson | HUDSON | 12534 | 36_33_08751 | HUDSON 87 | N |  | 5000 |  |  | CDG | Y | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-24 | 0 | 2020-09-11 | 2020-09-11 | 2020-12-08 | 59 | 9800 |  | 430927.43 |  |  | 2021-01-05 | [5 empty] | N | Y
NIMO | Wendy DeWolf (East Light Partners) | 00292694 | 033 - Hudson | HUDSON | 12534 | 36_33_30353 | BLUE STORES 303 | N |  | 5000 |  |  | CDG | Y | 2020-06-01 | 2020-06-08 | 5 | 2020-06-08 | 2020-06-08 | 2020-06-08 | 0 | 2020-06-17 | 2020-06-17 | 2020-09-22 | 59 | 9400 |  | 740831 |  |  | 2021-01-04 | [5 empty] | N | Y
NIMO | Andrea DeBernardis (AC Power) | 00302351 | 038 - Glens Falls | HUDSON FALLS | 12839 | 36_38_33754 | BURGOYNE 337 | N |  | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-09 | 5 | 2020-08-09 | 2020-08-09 | 2020-08-09 | 0 | 2020-09-17 | 2020-09-17 | 2021-01-21 | 59 | 9200 |  | 607310 | [8 empty] | N | N
NIMO | Scott Sabbagh (Matrix Development, LLC.) | 00234668 | 038 - Glens Falls | HUDSON FALLS | 12839 | ASHLEY - GLENS FALLS #5 |  | N |  | 5000 |  |  | CDG | Y | 2019-07-05 | 2019-07-12 | 5 | 2019-07-12 | 2019-07-12 | 2019-07-19 | 4 | 2019-08-15 | 2019-08-15 | 2020-02-24 | 58 | 8000 |  | 764411.76 |  |  | 2020-05-07 | 2020-10-29 |  |  |  |  | N | Y
NIMO | Michael Doud (Matrix Development, LLC.) | 00235408 | 038 - Glens Falls | HUDSON FALLS | 12839 | ASHLEY - GLENS FALLS #5 |  | N |  | 5000 |  |  | CDG | Y | 2019-07-01 | 2019-07-09 | 5 | 2019-07-09 | 2019-07-09 | 2019-07-18 | 6 | 2019-08-13 | 2019-08-13 | 2020-02-24 | 58 | 11300 |  | 231459.88 |  |  | 2020-05-07 | 2020-10-29 |  |  |  |  | N | Y
NIMO | Michael Doud (Matrix Development, LLC.) | 00246765 | 038 - Glens Falls | HUDSON FALLS | 12839 | ASHLEY - GLENS FALLS #5 |  | N |  | 5000 |  |  | CDG | Y | 2019-08-06 | 2019-08-13 | 5 | 2019-08-13 | 2019-08-13 | 2019-09-04 | 14 | 2019-09-05 | 2019-09-05 | 2020-02-24 | 58 | 11300 |  | 786065.22 |  |  | 2020-05-07 | 2020-11-14 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00231708 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_15054 | BAKER ST 150 | N |  | 1250 |  |  | CDG | Y | 2019-06-03 | 2019-06-12 | 7 | 2019-06-12 | 2019-06-12 | 2019-06-24 | 7 | 2019-07-29 | 2019-07-29 | 2019-12-13 | 59 | 9600 |  | 111660.6 |  |  | 2020-06-05 | 2020-12-16 |  |  |  |  | N | Y
NIMO | Ryan Storke (Storke, LLC) | 00290485 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_6561 | ELLICOTT 65 | N |  | 2280 |  |  | CDG | N | 2020-05-07 | 2020-05-14 | 5 | 2020-05-14 | 2020-05-14 | 2020-05-18 | 1 | 2020-08-04 | 2020-08-04 | 2021-02-03 | 59 | 10100 |  | 775268 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00231537 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_15054 | BAKER ST 150 | N |  | 2750 |  |  | CDG | Y | 2019-06-03 | 2019-06-12 | 7 | 2019-06-12 | 2019-06-12 | 2019-06-24 | 7 | 2019-10-07 | 2019-10-07 | 2020-01-06 | 56 | 9600 |  | 742073.68 |  |  | 2020-06-29 | 2021-01-26 |  |  |  |  | N | Y
NIMO | Ryan Storke (Storke, LLC) | 00273915 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_6261 | OAK HILL 62 | N |  | 3000 |  |  | CDG | N | 2020-05-07 | 2020-05-14 | 5 | 2020-05-14 | 2020-05-14 | 2020-05-18 | 1 | 2020-08-04 | 2020-08-04 | 2021-02-03 | 59 | 10100 |  | 730548 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00231545 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | 36_09_15054 | BAKER ST 150 | N |  | 5000 |  |  | CDG | Y | 2019-06-13 | 2019-06-24 | 7 | 2019-06-24 | 2019-06-24 | 2019-07-03 | 6 | 2019-07-29 | 2019-07-29 | 2019-12-13 | 59 | 10100 |  | 975450 |  |  | 2020-06-05 | 2020-12-16 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00304905 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | ASHVILLE-S DOW #864 |  | N |  | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-11-03 | 2020-11-03 | 2021-02-24 | 58 | 9800 |  | 685960 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00304917 | 009 - Lakewood/Stow | JAMESTOWN | 14701 | ASHVILLE-S DOW #864 |  | N |  | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-11-05 | 2020-11-05 | 2021-02-24 | 51 | 9800 |  | 685960 | [8 empty] | N | N
NIMO | Neil Libidinsky (Solar City) | 00101332 | 011 - Syracuse | JAMESVILLE | 13078 | 36_11_24451 | SOUTHWOOD 244 | N |  | 1988 |  |  | RNM | N | 2015-06-01 | 2015-06-29 | 7 | 2015-06-29 | 2015-06-29 | 2015-07-10 | 0 | 2015-10-28 | 2015-10-28 | 2016-07-22 | 60 | 25000 |  | 184167 |  |  | 2017-01-06 |  |  | 2018-03-26 | 2018-03-26 | 2018-03-26 | Y | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00101486 | 011 - Syracuse | JAMESVILLE | 13078 | PEBBLE HILL-TILDEN #32 | SUBT 11 | N |  | 2000 |  |  | CDG | N | 2016-01-06 | 2016-03-30 | 4 | 2016-03-30 | 2016-03-30 | 2016-04-12 | 0 | 2016-10-24 | 2016-10-24 | 2017-03-03 | 60 | 17500 |  | 334000 |  |  | 2017-07-07 | [5 empty] | N | N
NIMO | Cypress Creek Renewables LLC | 00102216 | 011 - Syracuse | JAMESVILLE | 13078 | PEBBLE HILL-TILDEN #32 | SUBT 11 | N |  | 2000 |  |  | CDG | N | 2016-03-17 | 2016-03-17 | 1 | 2016-03-17 | 2016-03-17 | 2016-04-19 | 0 | 2016-10-24 | 2016-10-24 | 2017-03-03 | 60 | 17500 |  | 334000 |  |  | 2017-07-07 | [5 empty] | N | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00287862 | 011 - Syracuse | JAMESVILLE | 13078 | 36_11_24452 | SOUTHWOOD 244 | N |  | 5000 |  |  | CDG | N | 2020-04-28 | 2020-05-06 | 6 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 0 | 2020-06-10 | 2020-06-10 | 2020-09-25 | 59 | 10000 |  | 915666.92 |  |  | 2021-02-16 | [5 empty] | N | N
NIMO | Jordana jusidman (groSolar) | 00100810 | 040 - Warrensburg | JOHNSBURG | 12853 | INDIAN LAKE - NORTH CREEK #1 | SUBT 40 | N |  | 1980 |  |  | RNM | N | 2015-05-29 | 2015-06-09 | 6 | 2015-06-09 | 2015-06-09 | 2015-07-23 | 0 | 2016-02-08 | 2016-02-08 | 2016-06-28 | 101 | 20000 |  | 243850 |  |  | 2017-06-06 |  |  | 2018-07-20 | 2018-07-20 | 2018-07-20 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00195264 | 031 - Troy | JOHNSONVILLE | 12094 | 36_31_33351 | BOYNTONVILLE 333 | N |  | 5000 |  |  | CDG | Y | 2018-09-12 | 2018-09-18 | 4 | 2018-09-18 | 2018-09-18 | 2018-10-05 | 12 | 2018-12-19 | 2018-12-19 | 2019-03-27 | 28 | 14300 |  | 847878 |  |  | 2019-09-06 | 2020-03-05 |  |  |  |  | N | Y
NIMO | Michael Cucchiara (Nexamp) | 00170284 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_35853 | STONER 358 | Y |  | 3500 | 3500 |  | CDG | Y | 2018-02-09 | 2018-02-09 | 0 | 2018-03-05 | 2018-03-05 | 2018-03-14 | 7 | 2018-05-23 | 2018-05-23 | 2018-08-10 | 55 | 17500 |  | 127367 |  |  | 2018-12-20 |  |  | 2020-10-21 | 2020-10-21 | 2020-10-21 | Y | Y
NIMO | Joe Fiori (Nexamp) | 00204039 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35854 | STONER 358 | Y |  | 2400 | 5000 |  | CDG | Y | 2019-01-17 | 2019-01-28 | 6 | 2019-01-28 | 2019-01-28 | 2019-02-04 | 4 | 2019-03-28 | 2019-03-28 | 2019-10-08 | 53 | 9400 |  | 367521 |  |  | 2020-02-20 | [5 empty] | N | Y
NIMO | Josh katz (Onyx Development Grou) | 00100807 | 035 - Gloversville | JOHNSTOWN | 12885 | 36_35_35853 | STONER 358 | N |  | 1988 |  |  | RNM | N | 2015-05-29 | 2015-06-12 | 3 | 2015-06-12 | 2015-06-12 | 2015-06-17 | 0 | 2015-12-15 | 2015-12-15 | 2016-04-27 | 96 | 35000 | [7 empty] | 2018-03-21 | 2018-03-21 | 2018-03-21 | Y | N
NIMO | Customer | 00101052 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35854 | STONER 358 | N |  | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-03 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 205273 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Customer | 00101053 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35854 | STONER 358 | N |  | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-21 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 147909 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Customer | 00101050 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35853 | STONER 358 | N |  | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-21 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 147909 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Customer | 00101051 | 034 - Amsterdam | JOHNSTOWN | 12095 | 36_35_35853 | STONER 358 | N |  | 2000 |  |  | RNM | N | 2015-03-03 | 2015-05-03 | 4 | 2015-05-03 | 2015-05-03 | 2015-05-21 | 0 | 2015-11-02 | 2015-11-02 | 2016-07-12 | 181 | 12500 |  | 730737 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Bartolo Jimenez (Cipriani Energy Group Corp.) | 00286132 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_35852 | STONER 358 | N |  | 2400 |  |  | CDG | Y | 2020-04-06 | 2020-04-15 | 7 | 2020-04-15 | 2020-04-15 | 2020-04-22 | 4 | 2020-05-06 | 2020-05-06 | 2020-09-17 | 57 | 8800 |  | 121955.41 |  |  | 2021-02-01 | 2021-02-01 |  |  |  |  | N | Y
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00300060 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_06125 | JOHNSTOWN 61 | N |  | 3125 |  |  | CDG | N | 2020-07-24 | 2020-07-31 | 5 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 0 | 2020-08-19 | 2020-08-19 | 2021-02-11 | 60 | 11300 |  | 250273 | [8 empty] | N | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00272862 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_35851 | STONER 358 | N |  | 5000 |  |  | CDG | Y | 2020-01-21 | 2020-02-03 | 9 | 2020-02-03 | 2020-02-03 | 2020-02-12 | 0 | 2020-02-18 | 2020-02-18 | 2020-05-21 | 59 | 8600 |  | 121955.27 |  |  | 2020-08-25 | 2021-03-01 |  |  |  |  | N | Y
NIMO | Trevor Hardy (BlueWave Solar) | 00297692 | 035 - Gloversville | JOHNSTOWN | 12095 | 36_35_37952 | CENTER ST 379 | N |  | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-21 | 8 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 2020-10-06 | 2020-10-06 | 2021-03-09 | 59 | 11700 |  | 1942363 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221456 | 006 - Albion/Medina | KENDALL | 14476 | WATERPORT-BROCKPORT #307 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-05-13 | 2019-05-24 | 9 | 2019-05-24 | 2019-05-24 | 2019-06-06 | 7 | 2019-07-03 | 2019-07-03 | 2019-12-06 | 59 | 13000 |  | 257444.85 |  |  | 2019-12-18 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221742 | 006 - Albion/Medina | KENDALL | 14476 | WATERPORT-BROCKPORT #307 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-05-01 | 2019-05-10 | 7 | 2019-05-10 | 2019-05-10 | 2019-05-24 | 9 | 2019-06-13 | 2019-06-13 | 2019-12-06 | 56 | 15300 |  | 499768 |  |  | 2019-12-18 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Timothy Ahrens (CleanChoice Energy) | 00346413 | 009 - Lakewood/Stow | KENNEDY | 14747 | 36_09_6662 | POLAND 66 | N |  | 5000 |  |  | CDG | N | 2021-03-26 | 2021-04-01 | 4 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 0 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00332467 | 011 - Syracuse | KIRKVILLE | 13082 | 36_11_16853 | BRIDGEPORT 168 | N |  | 5000 |  |  | CDG | N | 2020-12-17 | 2020-12-23 | 4 | 2020-12-23 | 2020-12-23 | 2020-12-23 | 0 | 2021-02-24 | 2021-02-24 |  |  | 9200 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00322024 | 011 - Syracuse | KIRKVILLE | 13082 | 36_11_26154 | FLY RD 261 | N |  | 5000 |  |  | CDG | N | 2020-10-30 | 2020-11-05 | 4 | 2020-11-05 | 2020-11-05 | 2020-11-05 | 0 | 2021-03-11 | 2021-03-11 |  |  | 9800 | [10 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00331484 | 011 - Syracuse | KIRKVILLE | 13082 | 36_11_26551 | DUGUID 265 | N |  | 5315 |  |  | CDG | N | 2021-01-28 | 2021-02-08 | 7 | 2021-02-08 | 2021-02-08 | 2021-02-09 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Steel Sun LLC | 00101824 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N |  | 1488 |  |  | RNM | N | 2016-12-28 | 2016-12-28 | 0 | 2016-12-28 | [15 empty] | 2017-01-25 | 2017-01-25 | 2017-01-25 | Y | N
NIMO | Steel Sun LLC | 00102925 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N |  | 1488 |  |  | RNM | N | 2017-01-25 | 2017-01-25 | 0 | 2017-01-25 | [15 empty] | 2017-01-25 | 2017-01-25 | 2017-01-25 | Y | N
NIMO | BQ Energy Inc. | 00100821 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N |  | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-03 | 4 | 2015-06-03 | 2015-06-03 | 2015-06-23 | 4 | 2015-10-20 | 2015-10-20 | 2016-05-17 | 150 | 45000 |  | 176050 |  |  | 2016-12-15 |  |  | 2019-06-04 | 2019-06-04 | 2019-06-04 | Y | N
NIMO | BQ Energy Inc. | 00100824 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21257 | HARBORFRONT 212 | N |  | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-03 | 4 | 2015-06-03 | 2015-06-03 | 2015-06-23 | 3 | 2015-10-20 | 2015-10-20 | 2016-05-17 | 150 | 15000 |  | 176050 |  |  | 2016-12-15 |  |  | 2019-06-04 | 2019-06-04 | 2019-06-04 | Y | N
NIMO | BQ Energy Inc. | 00100823 | 001 - Buffalo | LACKAWANNA | 14218 | 36_01_21252 | HARBORFRONT 212 | N |  | 2000 |  |  | RNM | N | 2015-05-28 | 2015-06-03 | 4 | 2015-06-03 | 2015-06-03 | 2015-06-23 | 3 | 2015-10-20 | 2015-10-20 | 2016-05-17 | 150 | 20000 |  | 191000 |  |  | 2016-12-15 |  |  | 2019-08-01 | 2019-08-01 | 2019-08-01 | Y | N
NIMO | Kyle Northway (One Sun) | 00284088 |  | LACKAWANNA | 14218 | 36_01_21253 | HARBORFRONT 212 | N |  | 2000 |  |  | RNM | Y | 2020-04-02 | 2020-04-02 | 0 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 0 | 2020-04-20 | 2020-04-20 | 2020-08-21 | 58 | 8500 |  | 235459 |  |  | 2020-12-31 | [5 empty] | N | Y
NIMO | Elie Schecter (C2 Energy Development, LLC) | 00231488 | 011 - Syracuse | LAFAYETTE | 13084 | 36_11_24453 | SOUTHWOOD 244 | Y |  | 5000 | 2500 |  | CDG | Y | 2019-07-03 | 2019-07-12 | 6 | 2019-07-12 | 2019-07-12 | 2019-07-22 | 5 | 2019-10-03 | 2019-10-03 | 2020-02-13 | 58 | 9600 |  | 915700 |  |  | 2020-06-25 | 2020-12-22 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS LLC) | 00231911 | 011 - Syracuse | LAFAYETTE | 13084 | TILDEN-TULLY #24 | SUBT 11 | Y |  | 4000 | 4000 |  | CDG | Y | 2019-05-31 | 2019-06-10 | 6 | 2019-06-10 | 2019-06-10 | 2019-06-24 | 9 | 2019-07-15 | 2019-07-15 | 2019-11-12 | 58 | 11700 |  | 295081.18 |  |  | 2019-11-25 | 2020-09-13 |  |  |  |  | N | Y
NIMO | GSPP Sentinel Heights Road, LLC | 00224987 | 011 - Syracuse | LAFAYETTE | 13084 | 36_11_24453 | SOUTHWOOD 244 | N |  | 3750 |  |  | CDG | Y | 2019-05-03 | 2019-05-15 | 8 | 2019-05-15 | 2019-05-15 | 2019-05-29 | 8 | 2019-10-17 | 2019-10-17 | 2020-01-28 | 59 | 10500 |  | 792870 |  |  | 2020-07-14 | 2021-01-14 |  |  |  |  | N | Y
NIMO | Solar Liberty Energy Systems, Inc. | 00093418 | 009 - Lakewood/Stow | LAKEWOOD | 14750 | Dunkirk to Falconer 160 - Cummins Tap |  | N |  | 1750 |  |  | NM | N | 2013-08-16 | 2013-08-16 | 0 | 2013-08-16 | [7 empty] | 32200 | [7 empty] | 2015-05-13 | 2015-05-13 | 2015-05-13 | Y | N
NIMO | Caroline Rizzo (Aura Power) | 00339867 |  | LAKEWOOD | 14750 | 36_09_15056 | BAKER ST 150 | N |  | 5000 |  |  | CDG | N | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Green Street Power Partners | 00267330 |  | LAWRENCEVILLE | 12949 | AKWESASNE-NICHOLVILLE #23 |  | N |  | 2500 |  |  | CDG | Y | 2019-11-27 | 2019-12-10 | 7 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 0 | 2020-03-25 | 2020-03-25 | 2020-07-21 | 59 | 10900 |  | 986846.05 |  |  | 2020-11-24 | [5 empty] | N | Y
NIMO | Green Street Power Partners | 00267321 |  | LAWRENCEVILLE | 12949 | AKWESASNE-NICHOLVILLE #23 |  | N |  | 5000 |  |  | CDG | Y | 2019-11-27 | 2019-12-10 | 7 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 0 | 2020-03-25 | 2020-03-25 | 2020-07-21 | 59 | 10900 |  | 913220.7 |  |  | 2020-11-23 | [5 empty] | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282254 |  | LAWTONS | 14091 | N ANGOLA-N ASHFORD #861 |  | N |  | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-16 | 7 | 2020-03-16 | 2020-03-16 | 2020-03-17 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-24 | 57 | 11700 |  | 236047.35 |  |  | 2021-03-15 | [5 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282682 |  | LAWTONS | 14091 | N ANGOLA-N ASHFORD #861 |  | N |  | 5000 |  |  | CDG | N | 2020-03-09 | 2020-03-17 | 6 | 2020-03-17 | 2020-03-17 | 2020-03-19 | 1 | 2020-05-14 | 2020-05-14 | 2020-09-24 | 59 | 11700 |  | 269827.53 |  |  | 2021-03-15 | [5 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00301833 | 007 - Angola | LAWTONS | 14091 | N ANGOLA-BAGDAD #862 |  | N |  | 5000 |  |  | CDG | N | 2020-07-20 | 2020-07-27 | 5 | 2020-07-27 | 2020-07-27 | 2020-07-30 | 2 | 2020-08-13 | 2020-08-13 | 2021-04-08 | 59 | 11700 |  | 1967224 | [8 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00304373 | 007 - Angola | LAWTONS | 14091 | N ANGOLA-BAGDAD #862 |  | N |  | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-13 | 8 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 0 | 2020-08-27 | 2020-08-27 | 2021-04-08 | 54 | 10100 | [10 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00259059 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | NORTH LEROY | N |  | 2200 |  |  | CDG | Y | 2020-02-03 | 2020-02-13 | 8 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 0 | 2020-03-16 | 2020-03-16 | 2020-06-22 | 58 | 9400 |  | 689356.41 |  |  | 2020-10-28 | [5 empty] | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00290891 | 004 - Batavia | LEROY | 14482 | 36_04_0457 | BUFFALO STATION | N |  | 2750 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-29 | 2020-06-29 | 2020-10-12 | 58 | 9400 |  | 689355.43 | [8 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00278950 | 004 - Batavia | LEROY | 14482 | 36_04_0457 | BUFFALO STATION | N |  | 3250 |  |  | CDG | Y | 2020-03-05 | 2020-03-16 | 7 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-03-24 | 2020-03-24 | 2020-08-08 | 59 | 9800 |  | 809048.51 |  |  | 2020-12-18 | [5 empty] | N | Y
NIMO | Timothy Ahrens (CleanChoice Energy) | 00271890 | 004 - Batavia | LEROY | 14482 | 36_04_0457 | BUFFALO STATION | N |  | 4950 |  |  | CDG | Y | 2020-02-03 | 2020-02-03 | 0 | 2020-02-03 | 2020-02-03 | 2020-02-04 | 0 | 2020-02-28 | 2020-02-28 | 2020-08-31 | 58 | 9800 |  | 904368.66 |  |  | 2021-01-12 | [5 empty] | N | Y
NIMO | Christopher Matthews (AES Distributed Energy) | 00229993 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | BUFFALO STATION | N |  | 5000 |  |  | CDG | Y | 2019-08-15 | 2019-08-22 | 5 | 2019-08-22 | 2019-08-22 | 2019-09-04 | 7 | 2019-10-31 | 2019-10-31 | 2020-02-04 | 58 | 11800 |  | 726918 |  |  | 2020-04-13 | [5 empty] | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00278951 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | BUFFALO STATION | N |  | 5000 |  |  | CDG | Y | 2020-03-05 | 2020-03-16 | 7 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-03-24 | 2020-03-24 | 2020-08-08 | 59 | 9800 |  | 822769.93 |  |  | 2020-12-18 | [5 empty] | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00338057 | 004 - Batavia | LEROY | 14482 | 36_04_2855 | E. BATAVIA 28 | N |  | 5000 |  |  | CDG | N | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-02-26 | 2021-03-11 | 8 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Bradley Beament (Aura Power Solar USA (LLC)) | 00305575 | 004 - Batavia | LEROY | 14482 | 36_04_0456 | NORTH LEROY | N |  | 5000 |  |  | CDG | N | 2020-09-08 | 2020-09-15 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2021-02-19 | 2021-02-19 |  |  | 9800 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00234010 | 003 - Niagara Falls | LEWISTON | 14092 | 36_03_10557 | SWANN RD 105 | N |  | 4000 |  |  | CDG | Y | 2019-06-17 | 2019-06-26 | 7 | 2019-06-26 | 2019-06-26 | 2019-07-09 | 7 | 2019-09-23 | 2019-09-23 | 2019-12-29 | 59 | 11300 |  | 528081 |  |  | 2020-02-28 | [5 empty] | N | Y
NIMO | Joe Fiori (Nexamp) | 00218932 | 025 - Potsdam | LISBON | 13658 | 36_25_95755 | BRADY 957 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-04-24 | 2019-05-02 | 6 | 2019-05-02 | 2019-05-02 | 2019-05-14 | 7 | 2019-06-05 | 2019-06-05 | 2019-08-30 | 59 | 9900 |  | 378360 |  |  | 2020-01-17 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Jordana Jusidman (groSolar) | 00101012 | 028 - Ogdensburg | LISBON | 13669 | DAVID-MCINTYRE #21 | DAVID 979 | N |  | 1000 |  |  | RNM | N | 2015-02-06 | 2015-03-01 | 16 | 2015-03-01 | 2015-03-01 | 2015-03-10 | 0 | 2015-06-02 | 2015-06-02 | 2015-11-05 | 112 | 28000 |  | 217831 |  |  | 2017-06-02 |  |  | 2018-12-19 | 2018-12-19 | 2018-12-19 | Y | N
NIMO | Advanced Energy Design, LLC | 00100967 | 028 - Ogdensburg | LISBON | 13658 | DAVID-MCINTYRE #21 | SUBT 28 | N |  | 2000 |  |  | RNM | N | 2015-01-15 | 2015-04-11 | 2 | 2015-04-11 | 2015-04-11 | 2015-07-11 | 0 | 2015-09-24 | 2015-09-24 | 2016-06-10 | 186 | 30000 |  | 645004.55 |  |  | 2017-02-08 |  |  | 2018-08-22 | 2018-08-22 | 2018-08-22 | Y | N
NIMO | Advanced Energy Design, LLC | 00100968 | 028 - Ogdensburg | LISBON | 13658 | DAVID-MCINTYRE #21 | SUBT 28 | N |  | 2000 |  |  | RNM | N | 2015-01-15 | 2015-04-14 | 2 | 2015-04-14 | 2015-04-14 | 2015-07-08 | 0 | 2015-09-24 | 2015-09-24 | 2016-05-20 | 171 | 30000 |  | 50695.45 |  |  | 2017-02-08 |  |  | 2018-08-24 | 2018-08-24 | 2018-08-24 | Y | N
NIMO | GSPP County Route 31, LLC | 00225692 | 025 - Potsdam | LISBON | 13658 | 36_25_95755 | BRADY 957 | N |  | 5000 |  |  | CDG | Y | 2019-05-09 | 2019-05-22 | 9 | 2019-05-22 | 2019-05-22 | 2019-05-28 | 2 | 2019-10-17 | 2019-10-17 | 2020-01-31 | 59 | 9800 |  | 265448.57 |  |  | 2020-07-14 | 2021-01-20 |  |  |  |  | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00253674 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67857 | SALISBURY 678 | Y |  | 5000 | 0 |  | CDG | Y | 2019-09-13 | 2019-09-25 | 8 | 2019-09-25 | 2019-09-25 | 2019-09-30 | 2 | 2019-10-16 | 2019-10-16 | 2020-06-19 | 59 | 9900 |  | 773354 |  |  | 2020-10-30 | [5 empty] | N | Y
NIMO | Michael Cucchiara (Nexamp) | 00108713 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67853 | SALISBURY 678 | Y |  | 1980 | 2000 |  | CDG | Y | 2017-09-19 | 2017-09-19 | 0 | 2017-09-28 | 2017-09-28 | 2017-10-09 | 7 | 2017-12-06 | 2017-12-06 | 2018-04-05 | 53 | 16800 |  | 697929 |  |  | 2018-06-28 |  |  | 2020-09-11 | 2020-09-11 | 2020-09-11 | Y | Y
NIMO | Mrunmayee Gujar (Nexamp) | 00165199 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_67852 | SALISBURY 678 | Y |  | 2000 | 2000 |  | CDG | Y | 2017-12-12 | 2017-12-12 | 0 | 2017-12-15 | 2017-12-15 | 2018-01-04 | 13 | 2018-03-20 | 2018-03-20 | 2018-06-11 | 56 | 15600 |  | 481533 |  |  | 2018-09-05 | 2019-04-10 | 2019-04-10 | 2020-10-21 | 2020-10-21 | 2020-10-21 | Y | Y
NIMO | RIC Development, LLC | 00333581 | 019 - Herkimer | LITTLE FALLS | 13365 | 36_19_62370 | ROCK CITY 623 | N |  | 5000 |  |  | CDG | N | 2020-12-24 | 2021-01-04 | 5 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 0 | 2021-03-09 | 2021-03-09 |  |  | 7500 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00317416 | 005 - Avon | LIVONIA | 14487 | 36_05_3253 | RICHMOND 32 | N |  | 5000 |  |  | CDG | N | 2020-10-07 | 2020-10-12 | 3 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-10-28 | 2020-10-28 | 2021-02-17 | 58 | 9400 |  | 6996403 | [8 empty] | N | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00328144 | 005 - Avon | LIVONIA | 14487 | 36_05_3253 | RICHMOND 32 | N |  | 5000 |  |  | CDG | N | 2021-01-21 | 2021-01-28 | 5 | 2021-01-28 | 2021-01-28 | 2021-01-28 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc) | 00344659 | 005 - Avon | LIVONIA | 14487 | N LAKEVILLE-RICHMOND #226 |  | N |  | 5000 |  |  | CDG | N | 2021-03-23 | 2021-03-24 | 1 | 2021-03-24 | 2021-03-24 | 2021-03-24 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc) | 00344653 | 005 - Avon | LIVONIA | 14487 | N LAKEVILLE-RICHMOND #226 |  | N |  | 5000 |  |  | CDG | N | 2021-03-03 | 2021-03-10 | 5 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Sam Youneszadeh (Dimension Energy) | 00319037 | 005 - Avon | LIVONIA | 14487 | GOLAH-N LAKEVILLE #216 |  | N |  | 5000 |  |  | CDG | Y | 2020-10-14 | 2020-10-22 | 6 | 2020-10-22 | 2020-10-22 | 2020-11-03 | 7 | 2021-02-01 | 2021-02-01 |  |  | 11300 | [10 empty] | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00278662 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_7654 | SHAWNEE 76 | N |  | 3300 |  |  | CDG | N | 2020-09-02 | 2020-09-02 | 0 | 2020-09-02 | 2020-09-02 | 2020-09-14 | 6 |  |  |  |  | 10900 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00236931 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_23253 | BUFFALO STATION 232 - OAKWOOD DR | N |  | 3750 |  |  | CDG | Y | 2019-06-25 | 2019-07-02 | 5 | 2019-07-02 | 2019-07-02 | 2019-07-11 | 5 | 2019-09-20 | 2019-09-20 | 2020-01-24 | 59 | 9000 |  | 458813 |  |  | 2020-04-13 | 2020-10-02 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00190121 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_23255 | BUFFALO STATION 232 - OAKWOOD DR | N |  | 5000 |  |  | CDG | Y | 2018-07-16 | 2018-07-23 | 6.8785 | 2018-07-24 | 2018-07-24 | 2018-08-02 | 7 | 2018-08-30 | 2018-08-30 | 2018-12-19 | 60 | 13300 |  | 190843 |  |  | 2019-03-21 | 2019-09-16 | 2019-09-16 | 2020-10-01 | 2020-10-01 | 2020-10-01 | Y | Y
NIMO | Borrego Solar Systems, Inc | 00340707 | 001 - Buffalo | LOCKPORT | 14094 | 36_03_23253 | BUFFALO STATION 232 - OAKWOOD DR | N |  | 5000 |  |  | CDG | N | 2021-03-01 | 2021-03-08 | 5 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 0 |  |  |  |  | 8100 | [10 empty] | N | N
NIMO | Greg Hering (NB Development LLC) | 00265065 | 023 - Lowville | LOWVILLE | 13367 | 36_23_81556 | BREMEN 815 | Y |  | 4000 | 3000 |  | CDG | Y | 2019-12-19 | 2019-12-28 | 6 | 2019-12-28 | 2019-12-28 | 2019-12-28 | 0 | 2020-01-30 | 2020-01-30 | 2020-05-20 | 59 | 10900 |  | 692355 |  |  | 2020-09-30 | 2021-04-09 |  |  |  |  | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00265070 | 023 - Lowville | LOWVILLE | 13367 | 36_23_81556 | BREMEN 815 | Y |  | 4000 | 3000 |  | CDG | Y | 2019-12-19 | 2019-12-28 | 6 | 2019-12-28 | 2019-12-28 | 2019-12-28 | 0 | 2020-02-03 | 2020-02-03 | 2020-05-20 | 59 | 9900 |  | 822100.46 |  |  | 2020-10-01 | 2021-04-09 |  |  |  |  | N | Y
NIMO | Green Skies Renewable Energy LLC | 00102159 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77353 | LOWVILLE 773 | N |  | 1980 |  |  | RNM | N | 2016-03-11 | 2016-03-23 | 8 | 2016-03-23 | 2016-03-23 | 2016-04-13 | 15 | 2016-05-24 | 2016-05-24 | 2016-08-23 | 60 | 25000 |  | 213317 |  |  | 2017-03-20 |  |  | 2018-05-03 | 2018-05-03 | 2018-05-03 | Y | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00227249 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77354 | LOWVILLE 773 | N |  | 2000 |  |  | CDG | Y | 2019-05-14 | 2019-05-28 | 9 | 2019-05-28 | 2019-05-28 | 2019-06-12 | 10 | 2019-07-17 | 2019-07-17 | 2019-10-14 | 59 | 9400 |  | 291023 |  |  | 2020-02-18 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Sachin Patel (LAST MILE ENERGY LLC) | 00302898 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77352 | LOWVILLE 773 | N |  | 2158 |  |  | CDG | N | 2020-08-07 | 2020-08-20 | 9 | 2020-08-20 | 2020-08-20 | 2020-09-28 | 4 | 2020-11-12 | 2020-11-12 | 2021-03-16 | 59 | 9800 |  | 971378 | [8 empty] | N | N
NIMO | Samantha Lennon (Green Street Power Partners) | 00278912 |  | LOWVILLE | 13367 | 36_23_77351 | LOWVILLE 773 | N |  | 2250 |  |  | CDG | Y | 2020-02-12 | 2020-02-26 | 9 | 2020-02-26 | 2020-02-26 | 2020-02-26 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-24 | 59 | 10100 |  | 69232 |  |  | 2020-10-29 | 2021-04-01 |  |  |  |  | N | Y
NIMO | Green Street Power Partners | 00278928 |  | LOWVILLE | 13367 | 36_23_77351 | LOWVILLE 773 | N |  | 2250 |  |  | CDG | Y | 2020-02-21 | 2020-03-04 | 8 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 0 | 2020-05-14 | 2020-05-14 | 2020-08-24 | 42 | 10100 |  | 364989 |  |  | 2020-10-29 | 2021-04-05 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00230094 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77352 | LOWVILLE 773 | N |  | 4800 |  |  | CDG | Y | 2019-05-23 | 2019-06-03 | 6 | 2019-06-03 | 2019-06-03 | 2019-06-17 | 9 | 2019-07-17 | 2019-07-17 | 2019-10-18 | 59 | 9800 |  | 751319 |  |  | 2020-02-18 | 2020-08-31 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00219571 | 023 - Lowville | LOWVILLE | 13367 | 36_23_77354 | LOWVILLE 773 | N |  | 5000 |  |  | CDG | Y | 2019-04-15 | 2019-04-17 | 2 | 2019-04-17 | 2019-04-17 | 2019-04-30 | 8 | 2019-06-03 | 2019-06-03 | 2019-09-09 | 58 | 9400 |  | 691356 |  |  | 2020-01-27 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Caroline Rizzo (Aura Power) | 00339852 |  | LOWVILLE | 13367 | LOWVILLE-BOONVILLE #22 |  | N |  | 5000 |  |  | CDG | N | 2021-02-08 | 2021-02-11 | 3 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 0 |  |  |  |  | 8000 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00229758 | 006 - Albion/Medina | LYNDONVILLE | 14098 | PHILLIPS RD-MEDINA #301 |  | Y |  | 3000 | 4000 |  | CDG | Y | 2019-05-30 | 2019-06-10 | 7 | 2019-06-10 | 2019-06-10 | 2019-06-17 | 4 | 2019-06-25 | 2019-06-25 | 2019-10-30 | 57 | 11700 |  | 262818 |  |  | 2019-11-08 | 2020-05-28 |  |  |  |  | N | Y
NIMO | Ivaylo Tomchev (RIC Development, LLC) | 00250050 |  | MACHIAS | 14101 | 36_10_1361 | MACHIAS 13 | N |  | 2000 |  |  | CDG | Y | 2019-10-14 | 2019-10-23 | 7 | 2019-10-23 | 2019-10-23 | 2019-11-14 | 14 | 2019-11-25 | 2019-11-25 | 2020-03-18 | 57 | 9200 |  | 246560 |  |  | 2020-05-14 | 2020-11-02 |  |  |  |  | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00307970 | 010 - Olean | MACHIAS | 14101 | DELEVAN-MACHIAS #801 |  | N |  | 5000 |  |  | CDG | N | 2020-09-02 | 2020-09-14 | 7 | 2020-09-14 | 2020-09-14 | 2020-09-14 | 0 | 2020-10-13 | 2020-10-13 | 2021-03-31 | 58 | 11300 |  | 1976631 | [8 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00314503 | 010 - Olean | MACHIAS | 14101 | DELEVAN-MACHIAS #801 |  | N |  | 5000 |  |  | CDG | N | 2020-09-25 | 2020-10-02 | 5 | 2020-10-02 | 2020-10-02 | 2020-10-22 | 13 | 2020-10-27 | 2020-10-27 | 2021-04-06 | 57 | 10700 |  | 1976631 | [8 empty] | N | N
NIMO | Nexamp Interconnections (Nexamp Inc.) | 00218997 | 025 - Potsdam | MADRID | 13660 | 36_25_95757 | BRADY 957 | Y |  | 2500 | 2500 |  | CDG | Y | 2019-04-22 | 2019-04-30 | 6 | 2019-04-30 | 2019-04-30 | 2019-05-03 | 2 | 2019-07-02 | 2019-07-02 | 2019-09-27 | 57 | 9900 |  | 320880 |  |  | 2020-02-10 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Joe Fiori (Nexamp) | 00219099 | 025 - Potsdam | MADRID | 13660 | 36_25_95757 | BRADY 957 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-04-12 | 2019-04-16 | 2 | 2019-04-16 | 2019-04-16 | 2019-04-22 | 3 | 2019-06-04 | 2019-06-04 | 2019-08-30 | 59 | 9900 |  | 699416 |  |  | 2020-01-17 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00343604 | 025 - Potsdam | MADRID | 13660 | 36_25_95757 | BRADY 957 | N |  | 5000 |  |  | CDG | N | 2021-03-18 | 2021-03-25 | 5 | 2021-03-25 | 2021-03-25 | 2021-03-25 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | GREEN POWER DEVELOPERS LLC | 00101084 | 027 - Malone | MALONE | 12953 | SPENCERS CORNERS-MALONE #26 | SUBT 27 | N |  | 1188 |  |  | RNM | N | 2015-03-18 | 2015-04-21 | 25 | 2015-04-21 | 2015-04-21 | 2015-05-20 | 0 | 2016-01-27 | 2016-01-27 | 2016-03-10 | 31 | 21800 |  |  |  |  | 2017-04-21 |  |  | 2018-12-21 | 2018-12-21 | 2018-12-21 | Y | N
NIMO | GREEN POWER DEVELOPERS LLC | 00101565 | 027 - Malone | MALONE | 12953 | SPENCERS CORNERS-MALONE #26 | SUBT 27 | N |  | 1692 |  |  | RNM | N | 2015-11-02 | 2015-12-16 | 4 | 2015-12-16 | 2015-12-16 | 2016-01-07 | 0 | 2016-02-01 | 2016-02-01 | 2016-05-17 | 76 | 28000 |  |  |  |  | 2017-04-21 |  |  | 2018-12-21 | 2018-12-21 | 2018-12-21 | Y | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00306946 | 027 - Malone | MALONE | 12953 | 36_27_89551 | MALONE 895 | N |  | 2000 |  |  | CDG | N | 2020-08-20 | 2020-08-27 | 5 | 2020-08-27 | 2020-08-27 | 2020-08-27 | 0 | 2020-09-24 | 2020-09-24 | 2021-01-11 | 59 | 8800 |  | 756453 | [8 empty] | N | N
NIMO | Nick Ford (Hexagon Energy, LLC) | 00336485 | 027 - Malone | MALONE | 12953 | FT COVINGTON-MALONE #26 |  | N |  | 4000 |  |  | CDG | N | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | 2021-02-01 | 2021-02-11 | 7 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00310426 | 027 - Malone | MALONE | 12953 | 36_27_89553 | MALONE 895 | N |  | 5000 |  |  | CDG | N | 2020-09-03 | 2020-09-15 | 7 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2020-11-06 | 2020-11-06 | 2021-03-02 | 59 | 10400 |  | 741891 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00319117 | 027 - Malone | MALONE | 12953 | 36_27_89553 | MALONE 895 | N |  | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-03 | 7 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 | 2020-12-23 | 2020-12-23 | 2021-03-31 | 59 | 9400 |  | 968178 | [8 empty] | N | N
NIMO | Andrew Day (SOURCE RENEWABLES LLC) | 00290464 | 011 - Syracuse | MANLIUS | 13041 | 36_11_26552 | DUGUID 265 | Y |  | 2500 | 2500 |  | CDG | N | 2020-05-21 | 2020-05-29 | 5 | 2020-05-29 | 2020-05-29 | 2020-06-01 | 0 | 2020-08-05 | 2020-08-05 | 2021-01-04 | 59 | 10300 |  | 689615.88 | [8 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00301894 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26553 | DUGUID 265 | Y |  | 5000 | 2500 |  | CDG | N | 2020-07-31 | 2020-08-10 | 6 | 2020-08-10 | 2020-08-10 | 2020-08-12 | 1 | 2020-08-28 | 2020-08-28 | 2021-02-23 | 59 | 9900 |  | 2480727 | [8 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00301895 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26553 | DUGUID 265 | Y |  | 5000 | 2500 |  | CDG | N | 2020-07-31 | 2020-08-10 | 6 | 2020-08-10 | 2020-08-10 | 2020-08-12 | 1 | 2020-08-28 | 2020-08-28 | 2021-02-23 | 59 | 9900 |  | 2480727 | [8 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00301893 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26553 | DUGUID 265 | Y |  | 5000 | 5000 |  | CDG | N | 2020-07-31 | 2020-08-10 | 6 | 2020-08-10 | 2020-08-10 | 2020-08-12 | 1 | 2020-08-28 | 2020-08-28 | 2021-02-23 | 59 | 9300 |  | 689151 | [8 empty] | N | N
NIMO | Andrew Day (SOURCE RENEWABLES LLC) | 00290463 | 011 - Syracuse | MANLIUS | 13401 | 36_11_26552 | DUGUID 265 | Y |  | 5000 | 5000 |  | CDG | N | 2020-05-21 | 2020-05-29 | 5 | 2020-05-29 | 2020-05-29 | 2020-06-01 | 0 | 2020-08-05 | 2020-08-05 | 2021-01-04 | 59 | 10300 |  | 887199.33 | [8 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00250670 | 011 - Syracuse | MANLIUS | 13104 | 36_11_26552 | DUGUID 265 | N |  | 5000 |  |  | CDG | Y | 2019-08-29 | 2019-09-11 | 8 | 2019-09-11 | 2019-09-11 | 2019-09-23 | 7 | 2019-10-04 | 2019-10-04 | 2020-01-15 | 59 | 8800 |  | 785728 |  |  | 2020-03-02 | 2020-09-10 |  |  |  |  | N | Y
NIMO | GSPP 7024 Fox Rd, LLCp LLC | 00214653 | 017 - Utica | MARCY | 13403 | 36_17_67053 | STITTVILLE 670 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-03-21 | 2019-04-02 | 8 | 2019-04-02 | 2019-04-02 | 2019-04-08 | 3 | 2019-05-21 | 2019-05-21 | 2019-08-22 | 58 | 9900 |  | 306532.71 |  |  | 2020-02-21 | 2021-01-07 |  |  |  |  | N | Y
NIMO | Lluis Torrent (CAERO) | 00298068 | 017 - Utica | MARCY | 13403 | 36_17_61651 | CAVANAUGH 616 | N |  | 3060 |  |  | CDG | N | 2020-06-25 | 2020-07-02 | 5 | 2020-07-02 | 2020-07-02 | 2020-07-02 | 0 | 2020-08-20 | 2020-08-20 | 2020-12-07 | 59 | 8800 |  | 365403.46 | [8 empty] | N | N
NIMO | Benjamin Rubin (Ameresco Inc.) | 00218905 | 017 - Utica | MARCY | 13403 | 36_17_61652 | CAVANAUGH 616 | N |  | 4482 |  |  | RNM | Y | 2019-05-15 | 2019-05-24 | 7 | 2019-05-24 | 2019-05-24 | 2019-06-06 | 7 | 2019-06-17 | 2019-06-17 | 2019-08-30 | 47 | 9400 |  | 698479 |  |  | 2020-01-14 | 2020-08-11 |  |  |  |  | N | Y
NIMO | Haley Orvedal (Galehead DG Solutions, LLC) | 00303754 | 017 - Utica | MARCY | 13403 | 36_17_61654 | CAVANAUGH 616 | N |  | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-10 | 5 | 2020-08-10 | 2020-08-10 | 2020-08-10 | 0 | 2020-09-18 | 2020-09-18 | 2021-01-28 | 59 | 9400 |  | 488419.73 | [8 empty] | N | N
NIMO | Bullitt Farm Solar (Cypress Creek Renewables LLC) | 00169960 | 017 - Utica | MARCY | 13403 | 36_17_67053 | STITTVILLE 670 | N |  | 5000 |  |  | CDG | Y | 2018-02-05 | 2018-03-07 | 3 | 2018-03-07 | 2018-03-07 | 2018-03-20 | 8 | 2018-09-12 | 2018-09-12 | 2018-12-04 | 54 | 15900 |  | 699406.08 |  |  | 2019-04-15 | 2019-09-27 |  |  |  |  | N | Y
NIMO | Bartolo Jimenez (Cipriani Energy Group Corp.) | 00291928 | 035 - Gloversville | MAYFIELD | 12117 | 36_35_33251 | NORTHVILLE 332 | N |  | 3000 |  |  | CDG | Y | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-06-03 | 2020-06-03 | 2020-09-29 | 58 | 8800 |  | 567400.02 |  |  | 2021-02-12 | [5 empty] | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00333071 | 009 - Lakewood/Stow | MAYVILLE | 14757 | 36_09_5762 | CHAUTAUQUA 57 | N |  | 4000 |  |  | CDG | N | 2020-12-21 | 2020-12-30 | 6 | 2020-12-30 | 2020-12-30 | 2020-12-30 | 0 | 2021-01-14 | 2021-01-14 |  |  | 11700 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00247694 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7655 | SHELBY 76 | Y |  | 3000 | 2000 |  | CDG | Y | 2019-08-14 | 2019-08-21 | 5 | 2019-08-21 | 2019-08-21 | 2019-08-27 | 3 | 2019-09-05 | 2019-09-05 | 2020-01-15 | 59 | 9900 |  | 176538.55 |  |  | 2020-05-26 | 2020-12-01 |  |  |  |  | N | Y
NIMO | Michael Frateschi (TJA Clean Energy, LLC) | 00240295 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7655 | SHELBY 76 | Y |  | 5000 | 4000 |  | CDG | Y | 2019-08-14 | 2019-08-14 | 0 | 2019-08-14 | 2019-08-14 | 2019-08-21 | 4 | 2019-08-30 | 2019-08-30 | 2019-12-11 | 58 | 11400 |  | 341207 |  |  | 2020-04-21 | 2020-10-21 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00188910 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7654 | SHELBY 76 | N |  | 3500 |  |  | CDG | Y | 2018-06-27 | 2018-06-27 | 0 | 2018-07-09 | 2018-07-09 | 2018-07-27 | 14 | 2018-10-26 | 2018-10-26 | 2019-01-28 | 52 | 12500 |  | 847650 |  |  | 2019-02-08 |  |  | 2020-05-29 | 2020-05-29 | 2020-05-29 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00189798 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7654 | SHELBY 76 | N |  | 5000 |  |  | CDG | Y | 2018-07-16 | 2018-07-23 | 6.7965 | 2018-07-24 | 2018-07-24 | 2018-08-02 | 7 | 2018-09-18 | 2018-09-18 | 2019-01-28 | 59 | 13300 |  | 294335 |  |  | 2019-02-11 |  |  | 2020-06-30 | 2020-06-30 | 2020-06-30 | Y | Y
NIMO | Borrego Solar Systems, Inc | 00257328 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7656 | SHELBY 76 | N |  |  |  | 5000 | CDG | N | 2019-10-17 | 2019-10-25 | 6 | 2019-10-25 | 2019-10-25 | 2019-11-05 | 6 | 2020-01-14 | 2020-01-14 | 2020-08-05 | 58 | 12500 |  | 1194367 |  |  | 2020-12-15 | [5 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00257925 | 006 - Albion/Medina | MEDINA | 14103 | 36_06_7656 | SHELBY 76 | N |  |  |  | 4093.6 | CDG | N | 2019-10-23 | 2019-11-01 | 7 | 2019-11-01 | 2019-11-01 | 2019-11-15 | 8 | 2020-01-14 | 2020-01-14 | 2020-08-05 | 58 | 12900 |  | 694765 |  |  | 2020-12-15 | [5 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00268581 | 031 - Troy | MELROSE | 12121 | 36_31_12351 | N. TROY 123 | N |  | 5000 |  |  | CDG | Y | 2019-12-09 | 2019-12-17 | 6 | 2019-12-17 | 2019-12-17 | 2019-12-17 | 0 | 2020-02-18 | 2020-02-18 | 2020-07-20 | 57 | 9400 |  | 720393 |  |  | 2020-10-05 | 2021-03-18 |  |  |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00297642 | 011 - Syracuse | MEMPHIS | 13027 | 36_11_26953 | SORRELL HILL 269 | N |  | 5000 |  |  | CDG | N | 2020-06-23 | 2020-06-30 | 5 | 2020-06-30 | 2020-06-30 | 2020-06-30 | 0 | 2020-09-08 | 2020-09-08 | 2020-12-30 | 57 | 8800 |  | 750093 | [8 empty] | N | N
NIMO | Kelli Wilson (Buffalo Solar) | 00329457 | 015 - Oswego | MEXICO | 13114 | 36_14_4361 | MALLORY Rd | N |  | 1250 |  |  | CDG | N | 2020-12-22 | 2020-12-30 | 5 | 2020-12-30 | 2020-12-30 | 2020-12-30 | 0 | 2021-01-05 | 2021-01-05 |  |  | 9400 | [10 empty] | N | N
NIMO | Craig Livingston (ReneSola Power Holdings LLC) | 00198522 | 035 - Gloversville | MIDDLE GROVE | 12850 | 36_35_39252 | VAIL MILLS 392 | N |  | 2749 |  |  | CDG | Y | 2019-02-26 | 2019-03-01 | 3 | 2019-03-01 | 2019-03-01 | 2019-03-08 | 4 | 2019-04-24 | 2019-04-24 | 2019-10-08 | 57 | 11200 |  | 358294 |  |  | 2020-01-24 | 2020-09-28 |  |  |  |  | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00207475 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130151 | SODEMAN ROAD | N |  | 4999 |  |  | CDG | Y | 2019-01-30 | 2019-02-11 | 11.7049 | 2019-02-12 | 2019-02-12 | 2019-02-22 | 7 | 2019-05-23 | 2019-05-23 | 2019-09-23 | 41 | 10100 |  | 266847.2 |  |  | 2019-08-02 |  |  | 2020-01-13 | 2020-01-13 | 2020-01-13 | Y | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00270608 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130152 | SODEMAN ROAD | N |  | 5000 |  |  | CDG | Y | 2020-01-08 | 2020-01-20 | 8 | 2020-01-20 | 2020-01-20 | 2020-01-23 | 2 | 2020-03-09 | 2020-03-09 | 2020-06-26 | 56 | 9200 |  | 121955.27 |  |  | 2020-10-26 | 2021-04-12 |  |  |  |  | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00274596 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130152 | SODEMAN ROAD | N |  | 5000 |  |  | CDG | Y | 2020-01-31 | 2020-02-13 | 9 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 0 | 2020-04-29 | 2020-04-29 | 2020-07-06 | 37 | 9900 |  | 121955.27 |  |  | 2020-08-11 | 2021-02-26 |  |  |  |  | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00313771 | 039 - Saratoga | MIDDLE GROVE | 12850 | 36_39_130152 | SODEMAN ROAD | N |  | 5000 |  |  | CDG | N | 2020-10-02 | 2020-10-11 | 6 | 2020-10-11 | 2020-10-11 | 2020-10-28 | 12 | 2020-11-09 | 2020-11-09 |  |  | 9600 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00291364 | 037 - Cobleskill | MIDDLEBURGH | 12023 | 36_37_39052 | MIDDLEBURG 390 | Y |  |  | 0 | 5000 | CDG | N | 2020-05-26 | 2020-06-02 | 5 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 0 | 2020-07-21 | 2020-07-21 | 2021-01-28 | 58 | 14000 |  | 3596320 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00294444 | 037 - Cobleskill | MIDDLEBURGH | 12122 | 36_37_39052 | MIDDLEBURG 390 | Y |  |  | 0 | 5000 | CDG | N | 2020-07-09 | 2020-07-22 | 9 | 2020-07-22 | 2020-07-22 | 2020-07-22 | 0 | 2020-10-12 | 2020-10-12 |  |  | 14500 | [10 empty] | N | N
NIMO | Mithun Vyas (DG New York CS LLC) | 00245228 | 006 - Albion/Medina | MIDDLEPORT | 14105 | PHILLIPS RD-TELEGRAPH RD #304 |  | Y |  | 5000 | 5000 |  | CDG | Y | 2019-07-25 | 2019-08-01 | 5 | 2019-08-01 | 2019-08-01 | 2019-08-13 | 7 | 2019-08-16 | 2019-08-16 | 2020-01-10 | 56 | 11600 |  | 265918 |  |  | 2020-01-21 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Trevor Hardy (BlueWave Solar) | 00317430 | 019 - Herkimer | MIDDLEVILLE | 13406 | 36_19_66671 | MIDDLEVILLE 666 | N |  | 4800 |  |  | CDG | N | 2020-11-12 | 2020-11-17 | 3 | 2020-11-17 | 2020-11-17 | 2020-11-17 | 0 | 2020-12-29 | 2020-12-29 |  |  | 11300 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc) | 00350067 | 019 - Herkimer | MOHAWK | 13407 | 36_19_61452 | S. WASHINGTON 614 | N |  | 2000 |  |  | CDG | N | 2021-04-01 | 2021-04-09 | 6 | 2021-04-09 | 2021-04-09 | 2021-04-09 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00304916 | 019 - Herkimer | MOHAWK | 13407 | 36_19_61452 | S. WASHINGTON 614 | N |  | 3000 |  |  | CDG | N | 2020-08-05 | 2020-08-18 | 9 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-10-15 | 2020-10-15 | 2021-03-17 | 59 | 9390 |  | 799788.47 | [8 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00306964 | 019 - Herkimer | MOHAWK | 13407 | 36_19_67651 | W. HERKIMER 676 | N |  | 3150 |  |  | CDG | N | 2020-08-17 | 2020-08-26 | 7 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 0 | 2020-09-24 | 2020-09-24 | 2021-01-04 | 59 | 8800 |  | 815392 | [8 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00321628 | 019 - Herkimer | MOHAWK | 13407 | 36_19_67651 | W. HERKIMER 676 | N |  | 4500 |  |  | CDG | N | 2020-10-29 | 2020-11-05 | 5 | 2020-11-05 | 2020-11-05 | 2020-11-05 | 0 | 2020-12-09 | 2020-12-09 | 2021-04-07 | 59 | 9800 |  | 912649 | [8 empty] | N | N
NIMO | Brent Grundberg (East Side Solar Holdings LLC) | 00192130 | 041 - Ticonderoga | MORIAH | 12960 | 36_41_38552 | PORT HENRY 385 | N |  | 5000 |  |  | CDG | Y | 2018-10-18 | 2018-10-22 | 2 | 2018-10-22 | 2018-10-22 | 2018-10-26 | 3 | 2019-01-23 | 2019-01-23 | 2019-05-17 | 67 | 13300 |  | 836997.51 |  |  | 2019-11-15 | 2020-09-23 |  |  |  |  | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00284817 | 041 - Ticonderoga | MORIAH | 12960 | 36_41_38552 | PORT HENRY 385 | N |  | 5000 |  |  | CDG | Y | 2020-04-16 | 2020-04-24 | 6 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 0 | 2020-04-28 | 2020-04-28 | 2020-08-22 | 59 | 9800 |  | 908475 |  |  | 2021-01-14 | [5 empty] | N | Y
NIMO | Craig Livingston (ReneSola Power Holdings LLC) | 00173136 | 020 - Oneida | MUNNSVILLE | 13409 | 36_20_50151 | ONEIDA 501 | N |  | 1925 |  |  | CDG | Y | 2018-10-11 | 2018-10-24 | 9 | 2018-10-24 | 2018-10-24 | 2018-11-05 | 7 | 2019-02-15 | 2019-02-15 | 2019-09-09 | 59 | 15300 |  | 455953.93 |  |  | 2019-12-30 | 2020-09-10 |  |  |  |  | N | Y
NIMO | RIC Development LLC | 00347161 | 020 - Oneida | MUNNSVILLE | 13409 | 36_20_50151 | ONEIDA 501 | N |  | 2900 |  |  | CDG | N | 2021-03-18 | 2021-03-19 | 1 | 2021-03-19 | 2021-03-19 | 2021-03-19 | 0 |  |  |  |  | 8700 | [10 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00294574 | 033 - Hudson | NASSAU | 12123 | 36_33_42754 | VALKIN 427 | N |  | 5000 |  |  | CDG | N | 2020-06-09 | 2020-06-16 | 5 | 2020-06-16 | 2020-06-16 | 2020-06-22 | 3 | 2020-10-09 | 2020-10-09 | 2021-02-25 | 55 | 9400 |  | 932189 | [8 empty] | N | N
NIMO | Ivaylo Tomchev (Wilna PV, LLC) | 00276518 | 022 - Carthage | NATURAL BRIDGE | 13665 | 36_23_81652 | N. CARTHAGE 816 | N |  | 5000 |  |  | CDG | Y | 2020-01-29 | 2020-02-10 | 8 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 0 | 2020-04-03 | 2020-04-03 | 2020-07-14 | 56 | 9800 |  | 392440.53 |  |  | 2020-10-12 | 2021-04-06 |  |  |  |  | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00315418 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_66852 | CHADWICKS 668 | N |  | 3750 |  |  | CDG | N | 2020-10-21 | 2020-10-21 | 0 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 0 | 2020-11-17 | 2020-11-17 | 2021-03-31 | 59 | 9800 |  | 841300 | [8 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318491 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_64659 | YAHNUNDASIS 646 | N |  | 4600 |  |  | CDG | N | 2020-10-12 | 2020-10-19 | 5 | 2020-10-19 | 2020-10-19 | 2020-11-03 | 10 | 2020-12-02 | 2020-12-02 | 2021-04-05 | 53 | 8600 |  | 272000 | [8 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318490 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_64659 | YAHNUNDASIS 646 | N |  | 5000 |  |  | CDG | N | 2020-10-12 | 2020-10-19 | 5 | 2020-10-19 | 2020-10-19 | 2020-10-27 | 5 | 2020-12-02 | 2020-12-02 | 2021-04-05 | 58 | 8600 |  | 152343 | [8 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00276811 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_68451 | DEBALSO 684 | N |  | 5000 |  |  | CDG | N | 2020-03-16 | 2020-03-25 | 7 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 0 | 2020-06-24 | 2020-06-24 | 2020-10-12 | 59 | 10400 |  | 567400.02 |  |  | 2021-03-31 | [5 empty] | N | N
NIMO | Mike Borkowski (Community Power Group) | 00321884 | 017 - Utica | NEW HARTFORD | 13413 | 36_17_68451 | DEBALSO 684 | N |  | 5000 |  |  | CDG | N | 2020-10-28 | 2020-11-06 | 7 | 2020-11-06 | 2020-11-06 | 2020-11-06 | 0 | 2020-11-30 | 2020-11-30 |  |  | 10400 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00339541 | 011 - Syracuse | NEW WOODSTOCK | 13122 | 36_11_26253 | DELPHI 262 | Y |  |  | 0 | 5000 | CDG | N | 2021-02-09 | 2021-02-17 | 5 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 0 |  |  |  |  | 8500 | [10 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00270379 | 011 - Syracuse | NEW WOODSTOCK | 13122 | 36_11_26253 | DELPHI 262 | N |  | 5000 |  |  | CDG | Y | 2020-01-27 | 2020-02-05 | 7 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 0 | 2020-02-13 | 2020-02-13 | 2020-05-29 | 59 | 10900 |  | 952966 |  |  | 2020-10-07 | 2021-04-06 |  |  |  |  | N | Y
NIMO | Ryan McCune (Nexamp) | 00285107 | 001 - Buffalo | NIAGARA FALLS | 14305 | 36_03_21651 | LOCKPORT RD 216 | N |  | 3500 |  |  | CDG | Y | 2020-04-21 | 2020-04-29 | 6 | 2020-04-29 | 2020-04-29 | 2020-04-29 | 0 | 2020-05-29 | 2020-05-29 | 2020-09-03 | 59 | 8800 |  | 696432.39 |  |  | 2020-09-28 | 2021-02-23 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00342228 | 003 - Niagara Falls | NIAGARA FALLS | 14305 | 36_03_21653 | LOCKPORT RD 216 | N |  | 5000 |  |  | RNM | N | 2021-02-16 | 2021-02-19 | 3 | 2021-02-19 | 2021-02-19 | 2021-03-10 | 12 |  |  |  |  | 8000 | [10 empty] | N | N
NIMO | Green Street Power Partners | 00267310 | 027 - Malone | NICHOLVILLE | 12965 | AKWESASNE-NICHOLVILLE #23 |  | N |  | 5000 |  |  | CDG | Y | 2019-11-27 | 2019-12-09 | 6 | 2019-12-09 | 2019-12-09 | 2020-01-30 | 4 | 2020-04-22 | 2020-04-22 | 2020-08-31 | 59 | 10900 |  | 360066.05 |  |  | 2020-11-24 | [5 empty] | N | Y
NIMO | Richard Marchetti (General Electric Co.) | 00109596 | 032 - Schenectady | NISKAYUNA | 12309 | General Electric R&D to Inman Road 20 |  | Y |  |  | 6711 |  | NA | N | 2017-12-08 | 2017-12-08 | 0 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 0 |  |  |  |  | 40000 | [7 empty] | 2018-07-19 | 2018-07-19 | 2018-07-19 | Y | N
NIMO | Joe Fiori (Nexamp) | 00228734 | 027 - Malone | NORTH BANGOR | 12966 | 36_27_89552 | MALONE 895 | N |  | 5000 |  |  | CDG | Y | 2019-05-28 | 2019-06-06 | 7 | 2019-06-06 | 2019-06-06 | 2019-06-14 | 5 | 2019-08-02 | 2019-08-02 | 2019-10-30 | 59 | 10100 |  | 1060530 |  |  | 2020-03-13 | 2020-09-15 |  |  |  |  | N | Y
NIMO | Bartolo Jimenez (Cipriani Energy Group Corp.) | 00310065 | 040 - Warrensburg | NORTH CREEK | 12853 | 36_40_12252 | N. CREEK 122 | N |  | 5000 |  |  | CDG | N | 2020-09-02 | 2020-09-10 | 5 | 2020-09-10 | 2020-09-10 | 2020-09-10 | 0 | 2020-09-15 | 2020-09-15 | 2021-01-19 | 59 | 9800 |  | 620006 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00330002 |  | NORTH CREEK | 12853 | 36_40_12252 | N. CREEK 122 | N |  | 5000 |  |  | CDG | N | 2020-12-08 | 2020-12-14 | 4 | 2020-12-14 | 2020-12-14 | 2020-12-14 | 0 | 2021-02-19 | 2021-02-19 |  |  | 9400 | [10 empty] | N | N
NIMO | Katie Kearney (SolAmerica Energy) | 00333429 | 027 - Malone | NORTH LAWRENCE | 12967 | AKWESASNE-NICHOLVILLE #23 |  | N |  | 3500 |  |  | CDG | N | 2020-12-29 | 2021-01-05 | 4 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 0 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Andy Isrealson (Convergent Energy Solutions New Yo | 00242287 | 011 - Syracuse | NORTH SYRACUSE | 13212 | 36_11_5952 | PINE GROVE 59 | Y |  | 5000 | 4999.98 |  | CDG | Y | 2019-07-26 | 2019-08-02 | 5 | 2019-08-02 | 2019-08-02 | 2019-08-12 | 5 | 2019-08-28 | 2019-08-28 | 2019-12-05 | 58 | 9900 |  | 128866 |  |  | 2019-12-03 | 2020-09-02 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS II, LLC) | 00283660 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_7656 | SHAWNEE 76 | Y |  | 5000 | 0 |  | CDG | N | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 0 | 2020-04-10 | 2020-04-10 | 2020-09-02 | 57 | 10300 |  | 1042772.79 |  |  | 2020-12-18 | [5 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00314131 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_21753 | WALMORE 217 | N |  | 3060 |  |  | CDG | N | 2020-10-05 | 2020-10-11 | 5 | 2020-10-11 | 2020-10-11 | 2020-10-11 | 0 | 2020-10-27 | 2020-10-27 | 2021-03-31 | 56 | 10800 |  | 423585 | [8 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00347692 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_9753 | SUMMIT PARK 97 | N |  | 4600 |  |  | CDG | N | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-03-30 | 2021-04-12 | 8 |  |  |  |  | 6500 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00347946 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_9753 | SUMMIT PARK 97 | N |  | 4600 |  |  | CDG | N | 2021-03-29 | 2021-04-06 | 6 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 0 |  |  |  |  | 6900 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318805 | 001 - Buffalo | NORTH TONAWANDA | 14120 | 36_03_21753 | WALMORE 217 | N |  | 5000 |  |  | CDG | N | 2020-10-22 | 2020-10-22 | 0 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2020-11-16 | 2020-11-16 | 2021-03-31 | 56 | 9800 |  | 484301 | [8 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00335258 | 035 - Gloversville | NORTHVILLE | 12134 | 36_35_33251 | NORTHVILLE 332 | N |  | 5000 |  |  | CDG | N | 2021-03-10 | 2021-03-11 | 1 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00291843 | 028 - Ogdensburg | OGDENSBURG | 13669 | 36_28_93852 | OGDENSBURG 938 | N |  | 4750 |  |  | CDG | N | 2020-06-16 | 2020-06-23 | 5 | 2020-06-23 | 2020-06-23 | 2020-06-24 | 0 | 2020-08-12 | 2020-08-12 | 2020-12-18 | 59 | 11300 |  | 572193.9 | [8 empty] | N | N
NIMO | Bradley Beament (Aura Power) | 00329693 |  | OGDENSBURG | 13669 | 36_28_93851 | OGDENSBURG 938 | N |  | 5000 |  |  | CDG | N | 2020-12-10 | 2020-12-14 | 2 | 2020-12-14 | 2020-12-14 | 2020-12-14 | 0 |  |  |  |  | 12500 | [10 empty] | N | N
NIMO | Thomas Murphy (Environomics.Co) | 00244401 | 028 - Ogdensburg | OGDENSBURG | 13369 | 36_28_93854 | OGDENSBURG 938 | N |  | 5000 |  |  | CDG | Y | 2019-07-30 | 2019-08-06 | 5 | 2019-08-06 | 2019-08-06 | 2019-09-12 | 10 | 2019-09-24 | 2019-09-24 | 2020-02-05 | 59 | 11700 |  | 1334049 |  |  | 2020-06-29 | 2020-12-29 |  |  |  |  | N | Y
NIMO | TJ Murphy (Environomics.Co) | 00255905 | 028 - Ogdensburg | OGDENSBURG | 13669 | 36_28_93854 | OGDENSBURG 938 | N |  | 5000 |  |  | CDG | Y | 2019-10-14 | 2019-10-23 | 7 | 2019-10-23 | 2019-10-23 | 2019-11-14 | 14 | 2020-02-03 | 2020-02-03 | 2020-05-12 | 59 | 9600 |  | 405656.41 |  |  | 2020-09-22 | 2021-03-09 |  |  |  |  | N | Y
NIMO | Ryan McCune (Nexamp) | 00263111 | 028 - Ogdensburg | OGDENSBURG | 13669 | 36_28_93852 | OGDENSBURG 938 | N |  | 5000 |  |  | CDG | Y | 2019-11-26 | 2019-12-05 | 5 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 0 | 2019-12-23 | 2019-12-23 | 2020-03-31 | 59 | 10800 |  | 960544 |  |  | 2020-08-07 | 2021-02-01 |  |  |  |  | N | Y
NIMO | Kevin Betz (Heuvelton Solar LLC) | 00238207 | 028 - Ogdensburg | OGDENSBURG | 13669 | MCINTYRE-HEUVELTON #23 | SUBT 28 | N |  | 5000 |  |  | CDG | Y | 2019-09-13 | 2019-09-25 | 8 | 2019-09-25 | 2019-09-25 | 2019-10-04 | 6 | 2019-12-17 | 2019-12-17 | 2020-04-16 | 59 | 10800 |  | 486787 |  |  | 2020-09-03 | 2021-02-24 |  |  |  |  | N | Y
NIMO | BQ Energy Inc. | 00100854 | 010 - Olean | OLEAN | 14760 | HOMER HILL-NILE #811 |  | N |  | 1512 |  |  | RNM | N | 2015-05-12 | 2015-05-13 | 2 | 2015-05-13 | 2015-05-13 | 2015-06-03 | 3 | 2015-09-02 | 2015-09-02 | 2015-12-14 | 73 | 18800 |  | 84000 |  |  | 2016-01-31 |  |  | 2017-07-21 | 2017-07-21 | 2017-07-21 | Y | N
NIMO | BQ Energy Inc. | 00100858 | 010 - Olean | OLEAN | 14760 | HOMER HILL-NILE #811 | MAPLEHURST | N |  | 1640 |  |  | RNM | N | 2015-04-20 | 2015-05-31 | 2 | 2015-05-31 | 2015-05-31 | 2015-06-03 | 0 | 2015-09-02 | 2015-09-02 | 2015-12-16 | 75 | 15000 |  | 48000 | [5 empty] | 2019-05-10 | 2019-05-10 | 2019-05-10 | Y | N
NIMO | BQ Energy Inc. | 00100856 | 010 - Olean | OLEAN | 14760 | HOMER HILL-NILE #811 | MAPLEHURST | N |  | 1640 |  |  | RNM | N | 2015-05-12 | 2015-05-13 | 2 | 2015-05-13 | 2015-05-13 | 2015-06-03 | 3 | 2015-09-02 | 2015-09-02 | 2015-12-16 | 75 | 15000 |  | 165000 | [5 empty] | 2019-05-10 | 2019-05-10 | 2019-05-10 | Y | N
NIMO | BQ Energy Inc. | 00103447 | 010 - Olean | OLEAN | 14706 | HOMER HILL-NILE #811 |  | N |  | 2000 |  |  | RNM | N | 2014-10-17 | 2015-01-02 | 56 | 2015-01-02 | 2015-01-02 | 2015-01-23 | 0 | 2015-06-09 | 2015-06-09 | 2015-10-22 | 97 | 21100 |  | 173000 |  |  | 2015-11-10 |  |  | 2017-07-25 | 2017-07-25 | 2017-07-25 | Y | N
NIMO | BQ Energy Inc. | 00103448 | 010 - Olean | OLEAN | 14706 | HOMER HILL-NILE #811 |  | N |  | 2000 |  |  | RNM | N | 2014-10-17 | 2015-01-02 | 56 | 2015-01-02 | 2015-01-02 | 2015-01-23 | 0 | 2015-06-09 | 2015-06-09 | 2015-10-22 | 97 | 16250 |  | 24000 |  |  | 2015-11-10 |  |  | 2017-07-25 | 2017-07-25 | 2017-07-25 | Y | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00269299 | 010 - Olean | OLEAN | 14760 | 36_10_2255 | DUGAN RD 22 | N |  | 4550 |  |  | CDG | Y | 2019-12-13 | 2019-12-19 | 4 | 2019-12-19 | 2019-12-19 | 2019-12-19 | 0 | 2019-12-27 | 2019-12-27 | 2020-08-06 | 58 | 10100 |  | 516280 |  |  | 2020-08-06 | 2021-02-08 |  |  |  |  | N | Y
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00271594 | 010 - Olean | OLEAN | 14760 | 36_10_2255 | DUGAN RD 22 | N |  | 4550 |  |  | CDG | Y | 2020-01-03 | 2020-01-16 | 9 | 2020-01-16 | 2020-01-16 | 2020-01-27 | 5 | 2020-01-30 | 2020-01-30 | 2020-09-03 | 55 | 9500 |  | 514333.21 |  |  | 2020-09-08 | 2021-02-08 |  |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00317327 | 010 - Olean | OLEAN | 14760 | 36_10_2257 | DUGAN RD 22 | N |  | 5000 |  |  | CDG | N | 2020-10-07 | 2020-10-12 | 3 | 2020-10-12 | 2020-10-12 | 2020-10-28 | 11 | 2020-12-23 | 2020-12-23 | 2021-04-05 | 55 | 10400 |  | 560693 | [8 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00296108 | 010 - Olean | OLEAN | 14760 | 36_10_2256 | DUGAN RD 22 | N |  | 5000 |  |  | CDG | N | 2020-06-15 | 2020-06-22 | 5 | 2020-06-22 | 2020-06-22 | 2020-06-22 | 0 | 2020-08-12 | 2020-08-12 | 2020-11-30 | 57 | 8800 |  | 181991.41 |  |  | 2021-01-20 | [5 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00173382 | 010 - Olean | OLEAN | 14760 | 36_10_2253 | DUGAN RD 22 | N |  | 5000 |  |  | CDG | Y | 2018-04-17 | 2018-05-16 | 6 | 2018-05-16 | 2018-05-16 | 2018-05-24 | 5 | 2018-09-12 | 2018-09-12 | 2018-12-19 | 55 | 12200 |  | 151694 |  |  | 2019-02-08 | [5 empty] | N | Y
NIMO | Kevin Rabbitt (River Valley Solar LLC) | 00198731 | 010 - Olean | OLEAN | 14760 | 36_10_3354 | W. OLEAN 33 | N |  | 5000 |  |  | CDG | Y | 2018-11-07 | 2018-11-19 | 7 | 2018-11-19 | 2018-11-19 | 2018-12-04 | 8 | 2019-02-05 | 2019-02-05 | 2019-06-07 | 59 | 10000 |  | 411039 |  |  | 2019-10-08 | 2020-03-26 |  |  |  |  | N | Y
NIMO | Jordana Jusidman (groSolar) | 00102114 | 020 - Oneida | ONEIDA | 13421 | 36_20_51458 | PETERBORO 514 | N |  | 1400 |  |  | RNM | N | 2016-06-22 | 2016-07-01 | 4 | 2016-07-01 | 2016-07-01 | 2016-07-08 | 0 | 2016-10-18 | 2016-10-18 | 2017-01-03 | 55 | 26200 |  | 159600 |  |  | 2017-05-03 |  |  | 2017-12-19 | 2017-12-19 | 2017-12-19 | Y | N
NIMO | Margaret Campbell (EDF Renewables) | 00209909 | 020 - Oneida | ONEIDA | 13421 | 36_20_50156 | ONEIDA 501 | N |  | 4000 |  |  | CDG | Y | 2019-02-26 | 2019-03-04 | 4 | 2019-03-04 | 2019-03-04 | 2019-03-19 | 10 | 2019-07-22 | 2019-07-22 | 2019-10-14 | 59 | 11100 |  | 819252 |  |  | 2019-10-28 | 2020-09-09 |  |  |  |  | N | Y
NIMO | Margaret Campbell (EDF - RE) | 00244042 | 020 - Oneida | ONEIDA | 13421 | 36_20_50153 | ONEIDA 501 | N |  | 5000 |  |  | CDG | Y | 2019-07-19 | 2019-07-19 | 0 | 2019-07-19 | 2019-07-19 | 2019-07-24 | 2 | 2019-09-10 | 2019-09-10 | 2020-06-05 | 59 | 9900 |  | 220927.55 |  |  | 2020-10-14 | 2021-04-14 |  |  |  |  | N | Y
NIMO | Margaret Campbell (EDF Renewables) | 00209907 | 020 - Oneida | ONEIDA | 13421 | 36_20_50151 | ONEIDA 501 | N |  | 5000 |  |  | CDG | Y | 2019-02-26 | 2019-03-04 | 4 | 2019-03-04 | 2019-03-04 | 2019-03-19 | 10 | 2019-07-22 | 2019-07-22 | 2019-10-14 | 59 | 11600 |  | 134622.06 |  |  | 2019-10-28 | 2020-09-09 |  |  |  |  | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00328723 | 020 - Oneida | ONEIDA | 13421 | 36_20_51455 | PETERBORO 514 | N |  | 5000 |  |  | CDG | N | 2021-01-28 | 2021-02-08 | 7 | 2021-02-08 | 2021-02-08 | 2021-02-12 | 3 |  |  |  |  | 6600 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00272161 | 017 - Utica | ORISKANY | 13424 | 36_17_33152 | WALESVILLE 331 | Y |  | 5000 | 0 |  | CDG | Y | 2020-01-08 | 2020-01-20 | 8 | 2020-01-20 | 2020-01-20 | 2020-01-23 | 2 | 2020-01-31 | 2020-01-31 | 2020-05-08 | 59 | 9400 |  | 689355.43 |  |  | 2020-06-17 | 2020-12-08 |  |  |  |  | N | Y
NIMO | SOLARCITY CORP. (Solar City) | 00102968 | 017 - Utica | ORISKANY | 13424 | 36_17_33152 | WALESVILLE 331 | N |  | 1476 |  |  | RNM | N | 2014-03-25 | 2014-03-25 | 0 | 2014-03-25 | 2014-03-25 | 2014-05-02 | 1 | 2014-05-23 | 2014-05-23 | 2014-08-20 | 63 | 15000 |  | 46355 |  |  | 2014-10-10 |  |  | 2017-10-30 | 2017-10-30 | 2017-10-30 | Y | N
NIMO | Raj Soi (SSC Oswego II LLC) | 00253373 | 014 - Fulton/Volney | OSWEGO | 13126 | 36_14_25456 | PALOMA 254 | Y |  | 2500 | 5000 |  | CDG | Y | 2019-10-10 | 2019-10-21 | 7 | 2019-10-21 | 2019-10-21 | 2019-11-06 | 11 | 2020-01-06 | 2020-01-06 | 2020-03-30 | 57 | 10600 |  | 309447 |  |  | 2020-04-23 | 2020-10-23 |  |  |  |  | N | Y
NIMO | Raj Soi (SSC Scriba LLC) | 00256774 | 014 - Fulton/Volney | OSWEGO | 13126 | 36_14_28354 | WINE CREEK 283 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-11-20 | 2019-11-21 | 1 | 2019-11-21 | 2019-11-21 | 2019-11-21 | 0 | 2019-12-06 | 2019-12-06 | 2020-04-17 | 59 | 10300 |  | 765102 |  |  | 2020-06-01 | 2020-11-19 |  |  |  |  | N | Y
NIMO | Solar City | 00100897 | 015 - Oswego | OSWEGO | 13126 | South Oswego to Geres Lock 9 |  | N |  | 1960 |  |  | NM | N | 2015-05-27 | 2015-06-10 | 5 | 2015-06-10 | 2015-06-10 | 2015-07-01 | 0 | 2015-10-28 | 2015-10-28 | 2016-05-09 | 138 | 30000 |  | 24000 | [5 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | Y | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282693 |  | OSWEGO | 13126 | 36_14_25653 | NEW HAVEN 256 | N |  | 2250 |  |  | CDG | N | 2020-03-09 | 2020-03-18 | 7 | 2020-03-18 | 2020-03-18 | 2020-03-18 | 0 | 2020-07-14 | 2020-07-14 | 2020-11-10 | 59 | 9800 |  | 567862.5 |  |  | 2021-01-29 | [5 empty] | N | N
NIMO | Ryan McCune (Nexamp) | 00336828 | 015 - Oswego | OSWEGO | 13126 | 36_14_25456 | PALOMA 254 | N |  | 4000 |  |  | CDG | N | 2021-01-22 | 2021-01-28 | 4 | 2021-01-28 | 2021-01-28 | 2021-01-28 | 0 | 2021-03-22 | 2021-03-22 |  |  | 7800 | [10 empty] | N | N
NIMO | Christopher Stroud (Cipriani Energy Group Corp) | 00261056 | 014 - Fulton/Volney | OSWEGO | 13126 | 36_14_25455 | PALOMA 254 | N |  | 4750 |  |  | CDG | Y | 2019-12-19 | 2019-12-24 | 3 | 2019-12-24 | 2019-12-24 | 2019-12-24 | 0 | 2020-01-06 | 2020-01-06 | 2020-04-14 | 58 | 9400 |  | 851101.1 |  |  | 2020-08-24 | [5 empty] | N | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00270612 | 015 - Oswego | OSWEGO | 13126 | 36_14_25653 | NEW HAVEN 256 | N |  | 5000 |  |  | CDG | Y | 2019-12-24 | 2020-01-06 | 7 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 0 | 2020-02-18 | 2020-02-18 | 2020-05-27 | 56 | 9400 |  | 759703.86 |  |  | 2020-10-21 | 2021-04-12 |  |  |  |  | N | Y
NIMO | David Spotts (SSC Oswego II LLC) | 00301231 | 015 - Oswego | OSWEGO | 13126 | 36_14_28354 | WINE CREEK 283 | N |  | 5000 |  |  | CDG | N | 2020-07-17 | 2020-07-24 | 5 | 2020-07-24 | 2020-07-24 | 2020-07-24 | 0 | 2020-08-17 | 2020-08-17 | 2020-11-30 | 59 | 9400 |  | 581870 |  |  | 2021-03-10 | [5 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291574 |  | OTTO | 14719 | BAGDAD-DAKE HILL #815 |  | N |  | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-22 | 1 | 2020-07-24 | 2020-07-24 | 2020-11-03 | 57 | 11700 |  | 370383 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291577 | 010 - Olean | OTTO | 14719 | BAGDAD-DAKE HILL #815 |  | N |  | 5000 |  |  | CDG | N | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | 2020-06-23 | 2020-06-24 | 0 | 2020-09-04 | 2020-09-04 | 2020-11-03 | 29 | 11700 |  | 370383 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00291583 |  | OTTO | 14719 | BAGDAD-DAKE HILL #815 |  | N |  | 5000 |  |  | CDG | N | 2020-05-13 | 2020-05-20 | 5 | 2020-05-20 | 2020-05-20 | 2020-05-22 | 1 | 2020-07-24 | 2020-07-24 | 2020-11-03 | 57 | 11700 |  | 370383 | [8 empty] | N | N
NIMO | Nexamp Interconnections (Nexamp) | 00198681 | 035 - Gloversville | PALATINE BRIDGE | 13428 | 36_35_36652 | CLINTON 366 | Y |  | 5000 | 5000 |  | CDG | Y | 2018-11-07 | 2018-11-14 | 4 | 2018-11-14 | 2018-11-14 | 2018-11-26 | 5 | 2019-01-03 | 2019-01-03 | 2019-04-16 | 59 | 13300 |  | 2130947 |  |  | 2019-09-24 | 2020-03-18 |  |  |  |  | N | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316701 | 035 - Gloversville | PALATINE BRIDGE | 13428 | 36_35_36652 | CLINTON 366 | N |  | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-22 | 4 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 0 | 2020-12-02 | 2020-12-02 |  |  | 10400 | [10 empty] | N | N
NIMO | RIC Development, LLC | 00328128 | 009 - Lakewood/Stow | PANAMA | 14767 | SHERMAN-ASHVILLE #863 |  | N |  | 5005 |  |  | CDG | N | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 0 |  |  |  |  | 8700 | [10 empty] | N | N
NIMO | Ivaylo Tomchev (RIC Development) | 00292924 | 014 - Fulton/Volney | PARISH | 13131 | MALLORY-LIGHTHOUSE HILL #22 | LIGHTHOUSE HILL 61 | N |  | 5000 |  |  | CDG | N | 2020-05-29 | 2020-06-05 | 5 | 2020-06-05 | 2020-06-05 | 2020-06-09 | 1 | 2020-07-02 | 2020-07-02 | 2020-11-05 | 57 | 10900 |  | 1253945.94 | [8 empty] | N | N
NIMO | Theresa Baker (Distributed Solar Development, LLC) | 00186117 | 032 - Schenectady | PATTERSONVILLE | 12137 | 36_32_13853 | ROTTERDAM 138 | Y |  | 2500 | 2500 |  | CDG | Y | 2018-06-07 | 2018-06-07 | 0 | 2018-06-29 | 2018-06-29 | 2018-07-17 | 11 | 2018-09-26 | 2018-09-26 | 2019-04-18 | 35 | 17900 |  | 550765 |  |  | 2019-05-16 |  |  | 2020-12-31 | 2020-12-31 | 2020-12-31 | Y | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00301193 | 032 - Schenectady | PATTERSONVILLE | 12137 | 36_32_13853 | ROTTERDAM 138 | N |  | 5000 |  |  | CDG | N | 2020-09-04 | 2020-09-14 | 5 | 2020-09-14 | 2020-09-14 | 2020-09-22 | 5 | 2020-11-02 | 2020-11-02 | 2021-04-09 | 59 | 11700 |  | 1450569 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00315540 | 004 - Batavia | PAVILION | 14525 | 36_04_2951 | SHEPPARD RD 29 | N |  | 5000 |  |  | CDG | N | 2020-09-29 | 2020-10-06 | 5 | 2020-10-06 | 2020-10-06 | 2020-10-06 | 0 | 2020-11-19 | 2020-11-19 | 2021-04-01 | 59 | 9400 |  | 1055884 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315950 | 004 - Batavia | PAVILION | 14525 | N LEROY-ATTICA #208 |  | N |  | 5000 |  |  | CDG | N | 2020-10-05 | 2020-10-11 | 5 | 2020-10-11 | 2020-10-11 | 2020-10-11 | 0 | 2020-12-16 | 2020-12-16 | 2021-03-30 | 58 | 10900 |  | 977044 | [8 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00315954 | 004 - Batavia | PAVILION | 14525 | N LEROY-ATTICA #208 |  | N |  | 5000 |  |  | CDG | N | 2020-10-13 | 2020-10-19 | 4 | 2020-10-19 | 2020-10-19 | 2020-10-21 | 1 | 2020-12-22 | 2020-12-22 | 2021-03-31 | 56 | 10900 | [10 empty] | N | N
NIMO | Haley Orvedal (Galehead DG Solutions, LLC) | 00301143 | 014 - Fulton/Volney | PENNELLVILLE | 13132 | 36_11_24753 | GILBERT MILLS 247 | N |  | 5000 |  |  | CDG | N | 2020-07-20 | 2020-07-27 | 5 | 2020-07-27 | 2020-07-27 | 2020-07-27 | 0 | 2020-09-18 | 2020-09-18 | 2021-01-13 | 59 | 9900 |  | 573917.18 |  |  | 2021-04-06 | [5 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00304370 | 007 - Angola | PERRYSBURG | 14129 | 36_07_18151 | W. PERRYSBURG 181 | N |  | 5000 |  |  | CDG | N | 2020-08-03 | 2020-08-14 | 9 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 0 | 2020-10-28 | 2020-10-28 | 2021-03-10 | 55 | 11300 |  | 3430769 | [8 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00206375 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | N |  | 2000 |  |  | RNM | N | 2019-01-31 | 2019-02-08 | 6 | 2019-02-08 | 2019-02-08 | 2019-02-15 | 4 | 2019-06-05 | 2019-06-05 | 2019-09-17 | 59 | 9600 |  | 312484 |  |  | 2019-12-02 | 2020-09-08 |  |  |  |  | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00206376 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | N |  | 2000 |  |  | RNM | N | 2019-01-31 | 2019-02-11 | 7 | 2019-02-11 | 2019-02-11 | 2019-02-15 | 3 | 2019-04-02 | 2019-04-02 | 2019-09-17 | 72 | 10100 |  | 382481 |  |  | 2019-12-02 | 2020-09-08 |  |  |  |  | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00213825 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | N |  | 2000 |  |  | RNM | N | 2019-05-01 | 2019-05-01 | 0 | 2019-05-01 | 2019-05-01 | 2019-05-10 | 6 | 2019-07-02 | 2019-07-02 | 2019-10-01 | 59 | 10100 |  | 229907.35 |  |  | 2019-12-02 | 2020-09-08 |  |  |  |  | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00213829 | 013 - Watertown | PHILADELPHIA | 13673 | SOUTH PHILADELPHIA-INDIAN RIVER #25 | SUBT 13 | N |  | 2000 |  |  | RNM | N | 2019-05-01 | 2019-05-01 | 0 | 2019-05-01 | 2019-05-01 | 2019-05-10 | 6 | 2019-07-02 | 2019-07-02 | 2019-10-01 | 59 | 10100 |  | 341869 |  |  | 2019-12-18 | 2020-09-08 |  |  |  |  | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00320938 | 013 - Watertown | PHILADELPHIA | 13673 | SOUTH PHILADELPHIA-ANTWERP #24 |  | N |  | 2375 |  |  | CDG | N | 2020-10-30 | 2020-11-10 | 7 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 0 | 2021-02-16 | 2021-02-16 |  |  | 11300 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00318877 | 013 - Watertown | PHILADELPHIA | 13673 | SOUTH PHILADELPHIA-ANTWERP #24 |  | N |  | 4500 |  |  | CDG | N | 2020-10-14 | 2020-10-22 | 6 | 2020-10-22 | 2020-10-22 | 2020-11-03 | 7 | 2020-12-14 | 2020-12-14 |  |  | 11300 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00343940 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | N |  | 5000 |  |  | CDG | N | 2021-03-23 | 2021-03-28 | 4 | 2021-03-28 | 2021-03-28 | 2021-03-28 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00344239 | 013 - Watertown | PHILADELPHIA | 13673 | 36_13_32355 | INDIAN RIVER 323 | N |  | 5000 |  |  | CDG | N | 2021-03-23 | 2021-03-28 | 4 | 2021-03-28 | 2021-03-28 | 2021-03-28 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00344238 | 013 - Watertown | PHILADELPHIA | 13673 |  |  | N |  | 5000 |  |  | CDG | N | 2021-03-23 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00291077 | 011 - Syracuse | PHOENIX | 13135 | 36_11_5164 | PHOENIX 51 | Y |  | 2500 | 0 |  | CDG | N | 2020-06-18 | 2020-06-23 | 3 | 2020-06-23 | 2020-06-23 | 2020-06-24 | 0 | 2020-09-09 | 2020-09-09 | 2021-01-07 | 58 | 11400 |  | 1145233 | [8 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00347670 | 011 - Syracuse | PHOENIX | 13135 | BRISTOL HILL-PHOENIX #23 |  | N |  | 3000 |  |  | CDG | N | 2021-03-22 | 2021-03-26 | 4 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 0 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00337535 | 011 - Syracuse | PHOENIX | 13135 | BRISTOL HILL-PHOENIX #23 |  | N |  | 5000 |  |  | CDG | N | 2021-01-20 | 2021-01-27 | 5 | 2021-01-27 | 2021-01-27 | 2021-02-10 | 9 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00321525 | 011 - Syracuse | PHOENIX | 13135 | WOODARD #29 |  | N |  | 5000 |  |  | CDG | N | 2020-10-27 | 2020-11-03 | 5 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 | 2020-12-23 | 2020-12-23 | 2021-04-14 | 58 | 10900 |  | 4344033 | [8 empty] | N | N
NIMO | Greg Hering (NB Development LLC) | 00261672 | 017 - Utica | POLAND | 13431 | 36_17_62257 | POLAND 622 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-10-25 | 2019-11-06 | 8 | 2019-11-06 | 2019-11-06 | 2019-11-13 | 3 | 2019-11-21 | 2019-11-21 | 2020-03-18 | 58 | 11400 |  | 818727.5 |  |  | 2020-08-25 | 2021-03-01 |  |  |  |  | N | Y
NIMO | Joris Hay (Abundant Solar Power Inc.) | 00251479 |  | PORTLAND | 14716 | 36_08_15353 | BERRY RD 153 | N |  | 2500 |  |  | CDG | Y | 2019-08-30 | 2019-09-11 | 7 | 2019-09-11 | 2019-09-11 | 2019-09-17 | 3 | 2019-10-29 | 2019-10-29 | 2020-03-11 | 59 | 9800 |  | 579197.01 |  |  | 2020-07-20 | 2021-01-27 |  |  |  |  | N | Y
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00236961 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15353 | BERRY RD 153 | N |  | 3875 |  |  | CDG | N | 2019-06-17 | 2019-06-25 | 6 | 2019-06-25 | 2019-06-25 | 2019-07-03 | 5 | 2021-02-17 | 2021-02-17 |  |  | 9800 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00236876 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  | 5000 |  |  | CDG | N | 2019-06-17 | 2019-06-25 | 6 | 2019-06-25 | 2019-06-25 | 2019-07-09 | 8 | 2021-02-17 | 2021-02-17 | 2021-03-22 | 58 | 10100 |  | 807578 | [8 empty] | N | N
NIMO | Mario Rice (NY DIRECTWIND Portland, LLC) | 00106008 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  |  | 1000 | CDG | N | 2017-07-10 | 2017-08-10 | 8 | 2017-08-10 | 2017-08-10 | 2017-09-26 | 5 | 2018-05-23 | 2018-05-23 | 2018-10-22 | 59 | 14000 |  | 1675624.12 |  |  | 2019-03-13 | [5 empty] | N | N
NIMO | Mario Rice (NY DIRECTWIND Portland, LLC) | 00106013 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  |  | 1000 | CDG | N | 2017-08-09 | 2017-09-07 | 5 | 2017-09-07 | 2017-09-07 | 2017-09-14 | 4 | 2018-05-25 | 2018-05-25 | 2018-10-22 | 56 | 17800 |  | 1080544 |  |  | 2019-03-13 | [5 empty] | N | N
NIMO | Mario Rice (NY DIRECTWIND Portland, LLC) | 00109592 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  |  | 1000 | CDG | N | 2017-10-06 | 2017-10-17 | 2 | 2017-10-17 | 2017-10-17 | 2017-11-01 | 10 | 2018-05-23 | 2018-05-23 | 2018-10-22 | 59 | 18700 |  | 841189 |  |  | 2019-03-13 | [5 empty] | N | N
NIMO | Mario Rice (EWT Americas, Inc.) | 00186138 | 008 - Dunkirk/Fredoni | PORTLAND | 14769 | 36_08_15351 | BERRY RD 153 | N |  |  |  | 2000 | CDG | N | 2018-10-31 | 2018-11-09 | 7 | 2018-11-09 | 2018-11-09 | 2018-11-19 | 3 | 2019-01-14 | 2019-01-14 | 2019-05-01 | 59 | 12000 |  | 633322.53 |  |  | 2019-09-24 | [5 empty] | N | N
NIMO | Nexamp Interconnections (Nexamp) | 00239580 | 010 - Olean | PORTVILLE | 14760 | 36_10_2253 | DUGAN RD 22 | N |  | 4550 |  |  | CDG | Y | 2019-07-12 | 2019-07-19 | 5 | 2019-07-19 | 2019-07-19 | 2019-07-31 | 7 | 2019-08-02 | 2019-08-02 | 2020-02-04 | 54 | 11300 |  | 547419 |  |  | 2020-02-19 | 2020-09-10 |  |  |  |  | N | Y
NIMO | Elie Schecter (Potsdam Community Solar, LLC) | 00230901 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97653 | LAWRENCE AVE 976 | Y |  | 5000 | 2000 |  | CDG | Y | 2019-06-19 | 2019-06-28 | 7 | 2019-06-28 | 2019-06-28 | 2019-07-11 | 7 | 2019-08-14 | 2019-08-14 | 2020-01-07 | 59 | 9900 |  | 151280.8 |  |  | 2020-01-28 | 2020-10-19 |  |  |  |  | N | Y
NIMO | Community Energy Solar | 00093447 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97653 | LAWRENCE AVE 976 | N |  | 2000 |  |  | RNM | N | 2013-04-30 | 2013-04-30 | 0 | 2013-04-30 | [15 empty] | 2014-11-21 | 2014-11-21 | 2014-11-21 | Y | N
NIMO | Barton Pitts (Nexamp) | 00255150 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97654 | LAWRENCE AVE 976 | N |  | 3350 |  |  | CDG | Y | 2019-09-27 | 2019-10-10 | 9 | 2019-10-10 | 2019-10-10 | 2019-10-28 | 11 | 2019-12-02 | 2019-12-02 | 2020-03-11 | 59 | 9900 |  | 386058 |  |  | 2020-07-17 | 2021-01-07 |  |  |  |  | N | Y
NIMO | Dan Leary (OurGeneration, LLC) | 00287874 | 025 - Potsdam | POTSDAM | 13676 | 36_25_97654 | LAWRENCE AVE 976 | N |  | 4400 |  |  | CDG | N | 2020-04-27 | 2020-05-05 | 6 | 2020-05-05 | 2020-05-05 | 2020-05-05 | 0 | 2020-07-16 | 2020-07-16 | 2020-12-03 | 59 | 9400 |  | 191275 | [8 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00214650 | 016 - Pulaski | PULASKI | 13142 | 36_16_32451 | E. PULASKI 324 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-04-11 | 2019-04-23 | 8 | 2019-04-23 | 2019-04-23 | 2019-05-01 | 5 | 2019-07-12 | 2019-07-12 | 2019-11-26 | 59 | 10600 |  | 243562 |  |  | 2020-03-30 | 2020-10-28 |  |  |  |  | N | Y
NIMO | Jamal Batar (DSD Renewables) | 00108583 | 016 - Pulaski | PULASKI | 13142 | 36_16_32451 | E. PULASKI 324 | Y |  | 2000 |  |  | CDG | Y | 2017-09-07 | 2017-10-31 | 1 | 2017-10-31 | 2017-10-31 | 2017-11-16 | 10 | 2019-04-16 | 2019-04-16 | 2019-04-30 | 10 | 16800 |  | 347451.36 |  |  | 2019-02-07 | [5 empty] | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00284063 |  | PULASKI | 13142 | LIGHTHOUSE HILL-MALLORY 22 |  | N |  | 5000 |  |  | CDG | N | 2020-03-18 | 2020-03-26 | 6 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-17 | 58 | 10900 |  | 1191873 |  |  | 2021-03-15 | [5 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00284084 |  | PULASKI | 13142 | LIGHTHOUSE HILL-MALLORY 22 |  | N |  | 5000 |  |  | CDG | N | 2020-03-18 | 2020-03-26 | 6 | 2020-03-26 | 2020-03-26 | 2020-03-26 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-17 | 58 | 10900 |  | 1191873 |  |  | 2021-03-15 | [5 empty] | N | N
NIMO | Chris Matthews (AES Distributed Energy, Inc.) | 00293457 | 016 - Pulaski | PULASKI | 13142 | LIGHTHOUSE HILL-MALLORY 22 |  | N |  | 5000 |  |  | CDG | N | 2020-06-03 | 2020-06-10 | 5 | 2020-06-10 | 2020-06-10 | 2020-06-10 | 0 | 2020-08-07 | 2020-08-07 | 2021-03-29 | 60 | 10400 |  | 1358128 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00332764 | 016 - Pulaski | PULASKI | 13142 | LIGHTHOUSE HILL-MALLORY 22 |  | N |  | 5000 |  |  | CDG | N | 2020-12-18 | 2020-12-23 | 3 | 2020-12-23 | 2020-12-23 | 2020-12-23 | 0 | 2021-03-22 | 2021-03-22 |  |  | 11300 | [10 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00310886 | 038 - Glens Falls | QUEENSBURY | 12804 | 36_38_45352 | CEDAR 453 | Y |  | 5000 | 5000 |  | CDG | N | 2020-09-15 | 2020-09-24 | 7 | 2020-09-24 | 2020-09-24 | 2020-09-29 | 2 | 2020-11-02 | 2020-11-02 | 2021-03-26 | 56 | 9400 |  | 522548 | [8 empty] | N | N
NIMO | Stephen Mockler (Brookfield Renewable) | 00307399 | 038 - Glens Falls | QUEENSBURY | 12804 | 36_38_42356 | OGDEN BROOK 423 | N |  | 3600 |  |  | CDG | N | 2020-10-05 | 2020-10-05 | 0 | 2020-10-05 | 2020-10-05 | 2020-10-05 | 0 | 2020-11-13 | 2020-11-13 |  |  | 9400 | [10 empty] | N | N
NIMO | Kevin Bailey (High Peaks Solar, LLC) | 00242647 | 038 - Glens Falls | QUEENSBURY | 12804 | 36_38_45351 | CEDAR 453 | N |  | 4650 |  |  | CDG | Y | 2019-09-12 | 2019-09-23 | 7 | 2019-09-23 | 2019-09-23 | 2019-09-25 | 1 | 2019-10-22 | 2019-10-22 | 2020-03-30 | 59 | 8800 |  | 307050.08 |  |  | 2020-09-17 | [5 empty] | N | Y
NIMO | Timothy Ahrens (CleanChoice Energy) | 00303321 | 010 - Olean | RANDOLPH | 14772 | COLD SPRING-W SALAMANCA #804 |  | N |  | 3000 |  |  | CDG | N | 2020-07-28 | 2020-08-04 | 5 | 2020-08-04 | 2020-08-04 | 2020-08-04 | 0 | 2020-08-13 | 2020-08-13 | 2021-04-01 | 55 | 11300 |  | 5673511 | [8 empty] | N | N
NIMO | Mithun Vyas (DG New York CS, LLC) | 00221261 | 003 - Niagara Falls | RANSOMVILLE | 14131 | YOUNGSTOWN-SANBORN #403 | YOUNGSTOWN 88 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-05-01 | 2019-05-10 | 7 | 2019-05-10 | 2019-05-10 | 2019-05-24 | 9 | 2019-06-25 | 2019-06-25 | 2019-11-01 | 58 | 11400 |  | 265793 |  |  | 2019-11-13 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00197574 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_10557 | SWANN RD 105 | N |  | 4000 |  |  | CDG | Y | 2018-11-06 | 2018-11-14 | 5 | 2018-11-14 | 2018-11-14 | 2018-11-16 | 1 | 2019-05-16 | 2019-05-16 | 2019-08-13 | 59 | 14300 |  | 526185 |  |  | 2019-09-20 | 2020-06-30 |  |  |  |  | N | Y
NIMO | Mithun Vyas (Nextera Energy Resources, LLC) | 00172172 | 003 - Niagara Falls | RANSOMVILLE | 14131 | YOUNGSTOWN-SANBORN #403 |  | N |  | 5000 |  |  | CDG | Y | 2018-03-23 | 2018-03-23 | 0 | 2018-03-28 | 2018-03-28 | 2018-04-10 | 9 | 2018-06-11 | 2018-06-11 | 2018-11-14 | 56 | 12200 |  | 210903.87 |  |  | 2018-12-20 |  |  | 2020-06-16 | 2020-06-16 | 2020-06-16 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00173381 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_10557 | SWANN RD 105 | N |  | 5000 |  |  | CDG | Y | 2018-04-16 | 2018-04-16 | 0 | 2018-04-26 | 2018-04-26 | 2018-05-11 | 11 | 2018-06-20 | 2018-06-20 | 2018-09-11 | 57 | 15300 |  | 1321277 |  |  | 2018-10-04 |  |  | 2019-12-31 | 2019-12-31 | 2019-12-31 | Y | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00252179 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_7652 | SHAWNEE 76 | N |  | 5000 |  |  | CDG | Y | 2019-09-19 | 2019-10-01 | 8 | 2019-10-01 | 2019-10-01 | 2019-10-20 | 13 | 2019-11-07 | 2019-11-07 | 2020-10-07 | 59 | 9100 |  | 713893 |  |  | 2021-02-22 | [5 empty] | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00342783 | 003 - Niagara Falls | RANSOMVILLE | 14131 | 36_03_8964 | RANSOMVILLE 89 | N |  | 5000 |  |  | CDG | N | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 0 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00327615 | 003 - Niagara Falls | RANSOMVILLE | 14131 | YOUNGSTOWN-SANBORN #403 |  | N |  | 5000 |  |  | CDG | N | 2020-12-01 | 2020-12-08 | 5 | 2020-12-08 | 2020-12-08 | 2020-12-09 | 0 | 2021-03-23 | 2021-03-23 |  |  | 10700 | [10 empty] | N | N
NIMO | John Vigants (Bright Solar LLC) | 00333409 | 003 - Niagara Falls | RANSOMVILLE | 14131 | RANSOMVILLE-PHILLIPS RD #402 |  | N |  | 5000 |  |  | CDG | N | 2020-12-23 | 2021-01-04 | 6 | 2021-01-04 | 2021-01-04 | 2021-01-04 | 0 |  |  |  |  | 8100 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00290750 | 024 - Saranac Lake | RAYBROOK | 12977 | 36_24_83952 | RAYBROOK 839 | N |  | 5000 |  |  | CDG | N | 2020-05-20 | 2020-05-28 | 5 | 2020-05-28 | 2020-05-28 | 2020-05-28 | 0 | 2020-07-01 | 2020-07-01 | 2020-11-16 | 59 | 9400 |  | 689151.03 | [8 empty] | N | N
NIMO | Michael Frateschi (TJA Clean Energy) | 00282042 | 017 - Utica | REMSEN | 13438 | 36_17_33352 | SHERMAN 333 | N |  | 3500 |  |  | CDG | Y | 2020-03-04 | 2020-03-16 | 8 | 2020-03-16 | 2020-03-16 | 2020-03-17 | 0 | 2020-04-21 | 2020-04-21 | 2020-07-22 | 59 | 10800 |  | 832854.63 |  |  | 2020-11-23 | [5 empty] | N | Y
NIMO | Lluis Torrent (CAERO) | 00343922 | 030 - Albany | RENSSELAER | 12144 | 36_30_07858 | GREENBUSH 78 | N |  | 3060 |  |  | CDG | N | 2021-03-10 | 2021-03-17 | 5 | 2021-03-17 | 2021-03-17 | 2021-03-17 | 0 |  |  |  |  | 6600 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00343919 | 030 - Albany | RENSSELAER | 12144 | 36_30_07858 | GREENBUSH 78 | N |  | 5000 |  |  | CDG | N | 2021-03-10 | 2021-03-17 | 5 | 2021-03-17 | 2021-03-17 | 2021-03-17 | 0 |  |  |  |  | 6600 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171993 | 032 - Schenectady | REXFORD | 12148 | 36_32_34556 | GROOMS RD 345 | N |  | 2000 |  |  | CDG | Y | 2018-03-29 | 2018-03-29 | 0 | 2018-04-10 | 2018-04-10 | 2018-04-20 | 8 | 2018-07-23 | 2018-07-23 | 2018-10-10 | 56 | 12200 |  | 127366 |  |  | 2018-12-19 |  |  | 2020-12-10 | 2020-12-10 | 2020-12-10 | Y | Y
NIMO | Mark Richardson (Solitude Solar LLC) | 00183842 | 032 - Schenectady | REXFORD | 12065 | 36_32_34558 | GROOMS RD 345 | N |  | 4750 |  |  | CDG | Y | 2018-06-08 | 2018-06-08 | 0 | 2018-06-22 | 2018-06-22 | 2018-07-11 | 12 | 2018-08-22 | 2018-08-22 | 2018-12-03 | 33 | 12200 |  | 197550 |  |  | 2019-01-22 |  |  | 2019-09-26 | 2019-09-26 | 2019-09-26 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171992 | 032 - Schenectady | REXFORD | 12148 | 36_32_34556 | GROOMS RD 345 | N |  | 5000 |  |  | CDG | Y | 2018-03-29 | 2018-03-29 | 0 | 2018-04-12 | 2018-04-12 | 2018-04-20 | 6 | 2018-07-23 | 2018-07-23 | 2018-10-10 | 56 | 12200 |  | 212762 |  |  | 2018-12-19 | 2019-06-07 | 2019-06-07 | 2020-12-10 | 2020-12-10 | 2020-12-10 | Y | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00198332 | 032 - Schenectady | REXFORD | 12148 | 36_32_34557 | GROOMS RD 345 | N |  | 5000 |  |  | CDG | Y | 2018-10-19 | 2018-10-30 | 10.9549 | 2018-10-31 | 2018-10-31 | 2018-11-06 | 4 | 2019-02-25 | 2019-02-25 | 2019-06-05 | 59 | 13300 |  | 128866 |  |  | 2019-06-24 | 2019-12-20 | 2019-12-20 | 2020-12-22 | 2020-12-22 | 2020-12-22 | Y | Y
NIMO | Nexamp Interconnections (Nexamp) | 00250117 | 032 - Schenectady | REXFORD | 12148 | 36_32_34557 | GROOMS RD 345 | N |  | 5000 |  |  | CDG | Y | 2019-09-24 | 2019-10-04 | 8 | 2019-10-04 | 2019-10-04 | 2019-10-21 | 10 | 2019-12-24 | 2019-12-24 | 2020-04-06 | 57 | 8800 |  | 251223 |  |  | 2020-04-20 | 2020-10-07 |  |  |  |  | N | Y
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00196805 | 029 - Gouvernur | RICHVILLE | 13681 | 36_29_98353 | N. GOVERNEUR 983 | N |  | 1484 |  |  | CDG | Y | 2018-10-18 | 2018-10-25 | 5 | 2018-10-25 | 2018-10-25 | 2018-10-26 | 0 | 2018-12-13 | 2018-12-13 | 2019-05-29 | 58 | 13300 |  | 696561.53 |  |  | 2019-09-23 | 2020-03-17 |  |  |  |  | N | Y
NIMO | Nicole Leblanc (AMP Solar Developement Inc.) | 00196764 | 029 - Gouvernur | RICHVILLE | 13681 | 36_28_91453 | MCADOO 914 | N |  | 3300 |  |  | CDG | Y | 2018-10-11 | 2018-10-24 | 9 | 2018-10-24 | 2018-10-24 | 2018-11-02 | 6 | 2018-12-06 | 2018-12-06 | 2019-04-19 | 58 | 14300 |  | 678447.52 |  |  | 2019-09-13 | 2020-02-21 |  |  |  |  | N | Y
NIMO | Timothy Ahrens (CleanChoice Energy) | 00297280 | 009 - Lakewood/Stow | RIPLEY | 14775 | W PORTLAND-SHERMAN #867 |  | N |  | 5000 |  |  | CDG | N | 2020-07-17 | 2020-07-23 | 4 | 2020-07-23 | 2020-07-23 | 2020-07-28 | 2 | 2020-08-13 | 2020-08-13 | 2021-03-01 | 58 | 11700 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00325765 | 039 - Saratoga | ROCK CITY FALLS | 12863 | 36_39_130151 | SODEMAN ROAD | N |  | 5000 |  |  | CDG | N | 2020-11-17 | 2020-11-30 | 7 | 2020-11-30 | 2020-11-30 | 2020-12-17 | 12 | 2021-02-12 | 2021-02-12 |  |  | 11300 | [10 empty] | N | N
NIMO | Robert Garrity (Finlo, LLC) | 00287428 |  | ROME | 13440 | 36_17_33153 | WALESVILLE 331 | Y |  | 3500 | 0 |  | NA | Y | 2020-05-14 | 2020-05-20 | 4 | 2020-05-20 | 2020-05-20 | 2020-05-20 | 0 | 2020-07-24 | 2020-07-24 | 2020-11-18 | 58 | 12200 |  | 947692.87 |  |  | 2021-02-11 | [5 empty] | N | Y
NIMO | Robert Garrity (Finlo, LLC) | 00287422 |  | ROME | 13440 | 36_17_33153 | WALESVILLE 331 | Y |  | 5000 | 0 |  | NA | Y | 2020-05-08 | 2020-05-14 | 4 | 2020-05-14 | 2020-05-14 | 2020-05-15 | 0 | 2020-06-25 | 2020-06-25 | 2020-10-07 | 59 | 10600 |  | 944184.34 |  |  | 2021-01-25 | [5 empty] | N | Y
NIMO | David Bagley (Finlo, LLC) | 00340136 | 017 - Utica | ROME | 13440 | 36_18_76251 | ROME 762 | Y |  | 5000 | 0 |  | CDG | N | 2021-02-22 | 2021-02-26 | 4 | 2021-02-26 | 2021-02-26 | 2021-02-26 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00103305 | 017 - Utica | ROME | 13440 | 36_18_76258 | ROME 762 | N |  | 1899 |  |  | RNM | N | 2014-06-20 | 2014-06-20 | 0 | 2014-06-20 | 2014-06-20 | 2014-07-14 | 0 | 2014-09-16 | 2014-09-16 | 2014-12-05 | 58 | 25000 |  | 185970 | [5 empty] | 2015-12-21 | 2015-12-21 | 2015-12-21 | Y | N
NIMO | Borrego Solar Systems, Inc | 00103304 | 017 - Utica | ROME | 13440 | 36_18_76258 | ROME 762 | N |  | 1910 |  |  | RNM | N | 2014-06-20 | 2014-06-20 | 0 | 2014-06-20 | 2014-06-20 | 2014-07-18 | 0 | 2014-09-16 | 2014-09-16 | 2014-12-05 | 58 | 25000 |  | 198560 | [5 empty] | 2015-12-21 | 2015-12-21 | 2015-12-21 | Y | N
NIMO | groSolar | 00104500 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N |  | 1978 |  |  | RNM | N | 2014-08-21 | 2014-08-21 | 0 | 2014-08-21 |  |  |  | 2015-04-29 | 2015-04-29 | 2015-07-30 | 66 | 15100 |  | 97945 | [5 empty] | 2016-10-24 | 2016-10-24 | 2016-10-24 | Y | N
NIMO | ERNEST PORTNER (Dynamic Energy) | 00102339 | 018 - Rome | ROME | 13440 | 36_18_65355 | TURIN RD 653 | N |  | 1980 |  |  | CDG | N | 2016-07-18 | 2016-08-10 | 3 | 2016-08-10 | 2016-08-10 | 2016-08-16 | 0 | 2016-11-21 | 2016-11-21 | 2016-12-22 | 23 | 20300 |  | 697800 |  |  | 2017-05-22 |  |  | 2018-12-04 | 2018-12-04 | 2018-12-04 | Y | N
NIMO | Jordana Jusidman (groSolar) | 00100936 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N |  | 1997.6 |  |  | RNM | N | 2014-12-19 | 2015-01-15 | 6 | 2015-01-15 | 2015-01-15 | 2015-02-10 | 0 | 2015-08-05 | 2015-08-05 | 2015-10-26 | 58 | 20000 |  | 167126 |  |  | 2016-04-01 |  |  | 2017-09-04 | 2017-09-04 | 2017-09-04 | Y | N
NIMO | groSolar | 00104406 | 018 - Rome | ROME | 13440 | 36_18_65355 | TURIN RD 653 | N |  | 2000 |  |  | RNM | N | 2014-03-24 | 2014-03-24 | 0 | 2014-03-24 |  |  |  | 2014-06-25 | 2014-06-25 | 2014-12-15 | 123 | 15000 |  | 561330 | [5 empty] | 2016-08-04 | 2016-08-04 | 2016-08-04 | Y | N
NIMO | AES Distributed Energy, Inc. | 00100872 | 018 - Rome | ROME | 13440 | 36_18_76258 | ROME 762 | N |  | 2000 |  |  | RNM | N | 2015-05-18 | 2015-06-01 | 8 | 2015-06-01 | 2015-06-01 | 2015-06-30 | 0 | 2015-10-23 | 2015-10-23 | 2016-05-10 | 142 | 25000 |  | 179250 |  |  | 2017-01-31 |  |  | 2018-06-29 | 2018-06-29 | 2018-06-29 | Y | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00279596 | 018 - Rome | ROME | 13440 | 36_18_76258 | ROME 762 | N |  | 3500 |  |  | CDG | Y | 2020-02-18 | 2020-03-02 | 9 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 0 | 2020-04-07 | 2020-04-07 | 2020-08-12 | 59 | 8600 |  | 315942.67 |  |  | 2021-01-13 | [5 empty] | N | Y
NIMO | Bradley Davis (RENESOLA) | 00302519 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N |  | 4200 |  |  | CDG | N | 2020-07-30 | 2020-08-05 | 4 | 2020-08-05 | 2020-08-05 | 2020-08-05 | 0 | 2020-10-12 | 2020-10-12 | 2021-03-31 | 59 | 9000 |  | 235197 | [8 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00244500 | 018 - Rome | ROME | 13340 | 36_18_76257 | ROME 762 | N |  | 4825 |  |  | CDG | Y | 2019-07-30 | 2019-08-09 | 8 | 2019-08-09 | 2019-08-09 | 2019-08-13 | 1 | 2019-08-20 | 2019-08-20 | 2019-11-14 | 59 | 9000 |  | 292449.65 |  |  | 2019-12-02 | 2020-05-29 | 2020-05-29 | 2021-04-01 | 2021-04-01 | 2021-04-01 | Y | Y
NIMO | Kevin O'Neill (Seaboard Solar Holdings NY, LLC) | 00300534 |  | ROME | 13440 | 36_18_65358 | TURIN RD 653 | N |  | 4975 |  |  | CDG | N | 2020-10-02 | 2020-10-08 | 4 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 | 2020-12-03 | 2020-12-03 | 2021-04-14 | 59 | 8500 |  | 244672 | [8 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00282310 | 018 - Rome | ROME | 13440 | 36_18_65357 | TURIN RD 653 | N |  | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-16 | 7 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-05-14 | 2020-05-14 | 2020-10-30 | 58 | 9400 |  | 165841 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00315524 | 018 - Rome | ROME | 13440 | 36_18_76258 | ROME 762 | N |  | 5000 |  |  | CDG | N | 2020-09-29 | 2020-10-05 | 4 | 2020-10-05 | 2020-10-05 | 2020-10-26 | 5 | 2020-12-23 | 2020-12-23 |  |  | 10100 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc) | 00344650 | 018 - Rome | ROME | 13440 | 36_18_76251 | ROME 762 | N |  | 5000 |  |  | CDG | N | 2021-03-03 | 2021-03-10 | 5 | 2021-03-10 | 2021-03-10 | 2021-03-10 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Chandra Yarlagadda (Helios Energy New York LLC) | 00171907 | 005 - Avon | RUSH | 14543 | 36_05_5157 | E. GOLAH 51 | N |  | 3000 |  |  | CDG | Y | 2018-03-26 | 2018-03-26 | 0 | 2018-03-26 | 2018-03-26 | 2018-04-03 | 5 | 2018-04-10 | 2018-04-10 | 2018-06-21 | 51 | 9700 |  | 353922 |  |  | 2018-11-08 | 2019-06-25 |  |  |  |  | N | Y
NIMO | Chandra Yarlagadda (Helios Energy New York LLC) | 00171687 | 005 - Avon | RUSH | 14543 | 36_05_5157 | E. GOLAH 51 | N |  | 4500 |  |  | CDG | Y | 2018-03-26 | 2018-03-26 | 0 | 2018-03-26 | 2018-03-26 | 2018-04-03 | 5 | 2018-04-10 | 2018-04-10 | 2018-06-21 | 51 | 9700 |  | 452839.68 |  |  | 2018-11-08 | 2019-06-14 |  |  |  |  | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00172238 | 005 - Avon | RUSH | 14543 | 36_05_5155 | E. GOLAH 51 | N |  | 5000 |  |  | CDG | Y | 2018-04-06 | 2018-04-17 | 7 | 2018-04-17 | 2018-04-17 | 2018-05-01 | 9 | 2018-07-24 | 2018-07-24 | 2018-12-17 | 60 | 9700 |  | 370266.41 |  |  | 2019-04-16 | 2020-01-19 |  |  |  |  | N | Y
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100829 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N |  | 1400 |  |  | RNM | N | 2015-05-29 | 2015-06-28 | 8 | 2015-06-28 | 2015-06-28 | 2015-07-02 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-31 | 58 | 25000 |  | 273750 | [5 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | Y | N
NIMO | Michael McNeley (Kearsarge Solar LLC) | 00101325 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N |  | 1400 |  |  | CDG | N | 2015-05-29 | 2015-06-28 | 8 | 2015-06-28 | 2015-06-28 | 2015-07-02 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-31 | 58 | 25000 | [7 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | Y | N
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00102371 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_33554 | ST JOHNSVILLE 335 | N |  | 2000 |  |  | CDG | N | 2016-04-04 | 2016-04-04 | 1 | 2016-04-04 | 2016-04-04 | 2016-05-06 | 7 | 2016-10-17 | 2016-10-17 | 2017-01-12 | 60 | 17500 |  | 851650 |  |  | 2017-05-26 | [5 empty] | N | N
NIMO | Alex Curlin (Nexamp Solar LLC) | 00254035 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N |  | 2300 |  |  | CDG | Y | 2019-09-16 | 2019-09-26 | 8 | 2019-09-26 | 2019-09-26 | 2019-10-15 | 12 | 2019-11-13 | 2019-11-13 | 2020-04-20 | 55 | 10500 |  | 196067 |  |  | 2020-08-26 | 2021-02-19 |  |  |  |  | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables) | 00169955 | 035 - Gloversville | SAINT JOHNSVILLE | 13452 | 36_35_02051 | INGHAMS 20 | N |  | 5000 |  |  | CDG | Y | 2018-02-05 | 2018-03-07 | 1 | 2018-03-07 | 2018-03-07 | 2018-03-19 | 7 | 2018-09-17 | 2018-09-17 | 2018-11-27 | 48 | 12200 |  | 512299.95 |  |  | 2019-04-09 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS, LLC) | 00252698 | 001 - Buffalo | SANBORN | 14120 | 36_03_7655 | SHAWNEE 76 | Y |  | 5000 | 5000 |  | CDG | Y | 2019-09-16 | 2019-09-26 | 8 | 2019-09-26 | 2019-09-26 | 2019-10-15 | 12 | 2019-10-22 | 2019-10-22 | 2020-02-12 | 57 | 10100 |  | 1165465 |  |  | 2020-06-18 | 2020-12-28 |  |  |  |  | N | Y
NIMO | Thibaut Delespaul (CVE North America) | 00296735 | 001 - Buffalo | SANBORN | 14132 | 36_03_7656 | SHAWNEE 76 | N |  | 4000 |  |  | CDG | N | 2020-06-18 | 2020-06-25 | 5 | 2020-06-25 | 2020-06-25 | 2020-06-29 | 1 | 2020-08-25 | 2020-08-25 | 2021-01-13 | 58 | 10300 |  | 1042772 | [8 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171574 | 003 - Niagara Falls | SANBORN | 14132 | 36_03_21751 | WALMORE 217 | N |  | 5000 |  |  | CDG | Y | 2018-03-12 | 2018-03-12 | 0 | 2018-03-22 | 2018-03-22 | 2018-03-31 | 7 | 2018-05-15 | 2018-05-15 | 2018-07-26 | 50 | 13300 |  | 753581 |  |  | 2018-09-17 | 2019-04-24 | 2019-04-24 | 2020-10-23 | 2020-10-23 | 2020-10-23 | Y | Y
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316692 | 003 - Niagara Falls | SANBORN | 14132 | 36_03_7652 | SHAWNEE 76 | N |  | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-24 | 2020-10-24 | 2020-11-03 | 6 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00316695 | 003 - Niagara Falls | SANBORN | 14132 | 36_03_7652 | SHAWNEE 76 | N |  | 5000 |  |  | CDG | N | 2020-10-16 | 2020-10-24 | 6 | 2020-10-24 | 2020-10-24 | 2020-11-03 | 6 |  |  |  |  | 11300 | [10 empty] | N | N
NIMO | High Peaks Solar/Sycaway Solar and Wind | 00102989 | 016 - Pulaski | SANDY CREEK | 13145 | 36_16_6651 | SANDY CREEK 66 | N |  | 1980 |  |  | CDG | Y | 2017-01-29 | 2017-02-01 | 2 | 2017-02-01 | 2017-02-01 | 2017-02-15 | 10 | 2017-03-29 | 2017-03-29 | 2017-06-01 | 34 | 18700 |  | 593032 |  |  | 2018-02-27 |  |  | 2020-05-08 | 2020-05-08 | 2020-05-08 | Y | Y
NIMO | Kayti Curtis (Cypress Creek Renewables LLC) | 00101847 | 016 - Pulaski | SANDY CREEK | 13145 | 36_16_6651 | SANDY CREEK 66 | N |  | 2000 |  |  | CDG | N | 2016-08-30 | 2016-09-08 | 6 | 2016-09-08 | 2016-09-08 | 2016-09-12 | 2 | 2017-01-10 | 2017-01-10 | 2017-04-06 | 60 | 20000 |  | 593032 |  |  | 2017-06-30 |  |  | 2018-12-28 | 2018-12-28 | 2018-12-28 | Y | N
NIMO | Alexander McMenemy (Solar Generation Projects LLC) | 00242504 |  | SANDY CREEK | 13145 | 36_16_6652 | SANDY CREEK 66 | N |  | 2150 |  |  | CDG | Y | 2019-08-07 | 2019-08-15 | 6 | 2019-08-15 | 2019-08-15 | 2019-08-28 | 8 | 2019-11-01 | 2019-11-01 | 2020-04-03 | 56 | 10000 |  | 400229.4 |  |  | 2020-07-13 | 2021-02-02 |  |  |  |  | N | Y
NIMO | Andrew Biederman (RER Energy Group LLC) | 00106164 | 024 - Saranac Lake | SARANAC LAKE | 12983 | 36_24_92758 | LAKE COLBY 927 | N |  | 1500 |  |  | CDG | Y | 2017-08-15 | 2017-08-15 | 0 | 2017-09-08 | 2017-09-08 | 2017-09-15 | 5 | 2018-01-31 | 2018-01-31 | 2018-05-08 | 59 | 16800 |  | 320711.71 |  |  | 2019-02-05 |  |  | 2020-12-30 | 2020-12-30 | 2020-12-30 | Y | Y
NIMO | Dynamic Energy | 00102515 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_36951 | BROOK RD 369 | N |  | 2000 |  |  | RNM | N | 2013-03-22 | 2013-03-22 | 0 | 2013-03-22 | [15 empty] | 2014-07-30 | 2014-07-30 | 2014-07-30 | Y | N
NIMO | Brian DeMaio` (Onyx) | 00100935 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_41551 |  | N |  | 2000 |  |  | RNM | N | 2014-12-19 | 2015-01-12 | 5 | 2015-01-12 | 2015-01-12 | 2015-01-26 | 0 | 2015-05-21 | 2015-05-21 | 2015-05-27 | 4 | 35600 |  | 427338 |  |  | 2015-07-24 |  |  | 2017-08-28 | 2017-08-28 | 2017-08-28 | Y | N
NIMO | Lluis Torrent (CAERO) | 00314693 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_36952 | BROOK RD 369 | N |  | 3060 |  |  | CDG | N | 2020-10-23 | 2020-11-02 | 6 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 0 | 2020-11-10 | 2020-11-10 | 2021-02-10 | 51 | 8800 |  | 660644 | [8 empty] | N | N
NIMO | John McDonough (Omni Industria NY LLC) | 00192254 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_41556 | WEIBEL AVE 415 | N |  | 5000 |  |  | CDG | Y | 2018-10-12 | 2018-10-24 | 8 | 2018-10-24 | 2018-10-24 | 2018-11-02 | 6 | 2018-12-20 | 2018-12-20 | 2019-04-11 | 52 | 14300 |  | 389816 |  |  | 2019-09-25 | 2020-09-08 |  |  |  |  | N | Y
NIMO | Frank Ruffolo (Sky Solar Inc.) | 00309500 | 039 - Saratoga | SARATOGA SPRINGS | 12866 | 36_39_41551 | WEIBEL AVE 415 | N |  | 5000 |  |  | CDG | N | 2020-09-28 | 2020-10-03 | 5 | 2020-10-03 | 2020-10-03 | 2020-10-03 | 0 | 2021-03-15 | 2021-03-15 |  |  | 12500 | [10 empty] | N | N
NIMO | William Jordan (Jordan Energy & Food Enterprises, | 00314444 | 017 - Utica | SAUQUOIT | 13456 | 36_17_66852 | CHADWICKS 668 | N |  | 5000 |  |  | CDG | N | 2020-10-08 | 2020-10-14 | 4 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 0 | 2020-11-20 | 2020-11-20 | 2021-03-09 | 58 | 10100 |  | 945804 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00318911 | 017 - Utica | SAUQUOIT | 13456 | 36_17_66851 | CHADWICKS 668 | N |  | 5000 |  |  | CDG | N | 2020-10-23 | 2020-11-03 | 7 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 0 | 2021-03-05 | 2021-03-05 |  |  | 9400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00325164 | 017 - Utica | SAUQUOIT | 13456 | WHITESBORO-SCHUYLER #29 |  | N |  | 5000 |  |  | CDG | N | 2020-11-12 | 2020-11-19 | 5 | 2020-11-19 | 2020-11-19 | 2020-11-19 | 0 | 2021-03-05 | 2021-03-05 |  |  | 10900 | [10 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00205940 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32852 | HEMSTREET 328 | Y |  | 4980 | 4980 |  | CDG | Y | 2019-01-16 | 2019-01-28 | 7 | 2019-01-28 | 2019-01-28 | 2019-02-04 | 4 | 2019-06-06 | 2019-06-06 | 2019-08-28 | 57 | 10100 |  | 750589 |  |  | 2020-01-22 | 2020-09-04 |  |  |  |  | N | Y
NIMO | Kelsey Crane (ForeFront Power) | 00100795 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32851 | HEMSTREET 328 | N |  | 2000 |  |  | CDG | N | 2015-04-22 | 2015-05-03 | 3 | 2015-05-03 | 2015-05-03 | 2015-05-29 | 0 | 2015-07-22 | 2015-07-22 | 2016-05-09 | 208 | 35000 |  | 730737 |  |  | 2017-02-14 |  |  | 2018-12-20 | 2018-12-20 | 2018-12-20 | Y | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00284812 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32851 | HEMSTREET 328 | N |  | 2850 |  |  | CDG | Y | 2020-04-16 | 2020-04-24 | 6 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 0 | 2020-04-28 | 2020-04-28 | 2020-08-17 | 59 | 9400 |  | 324545.93 |  |  | 2020-12-11 | [5 empty] | N | Y
NIMO | Dallas Manson (Nexamp) | 00229123 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32851 | HEMSTREET 328 | N |  | 3500 |  |  | CDG | Y | 2019-05-28 | 2019-06-06 | 7 | 2019-06-06 | 2019-06-06 | 2019-06-26 | 13 | 2019-08-01 | 2019-08-01 | 2019-10-25 | 57 | 9900 |  | 128866 |  |  | 2020-03-25 | 2020-09-22 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00343339 | 031 - Troy | SCHAGHTICOKE | 12154 | 36_31_32851 | HEMSTREET 328 | N |  | 5000 |  |  | CDG | N | 2021-03-16 | 2021-03-24 | 6 | 2021-03-24 | 2021-03-24 | 2021-03-24 | 0 |  |  |  |  | 7600 | [10 empty] | N | N
NIMO | Giovanni Maruca (Lisha Solar 2, LLC) | 00252627 | 032 - Schenectady | SCHENECTADY | 12303 | 36_32_38154 | RUTH RD 381 | Y |  | 5000 | 4500 |  | CDG | Y | 2019-09-10 | 2019-09-20 | 8 | 2019-09-20 | 2019-09-20 | 2019-10-07 | 10 | 2020-01-28 | 2020-01-28 | 2020-04-21 | 59 | 9400 |  | 244984.81 |  |  | 2020-08-28 | 2021-02-22 |  |  |  |  | N | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00235255 | 032 - Schenectady | SCHENECTADY | 12303 | 36_32_38154 | RUTH RD 381 | Y |  | 4980 | 5000 |  | CDG | Y | 2019-06-11 | 2019-06-18 | 5 | 2019-06-18 | 2019-06-18 | 2019-07-02 | 9 | 2019-09-09 | 2019-09-09 | 2019-12-18 | 40 | 9400 |  | 973744 |  |  | 2020-02-05 | 2020-09-04 |  |  |  |  | N | Y
NIMO | Theresa Baker (General Electric International Inc) | 00186064 | 032 - Schenectady | SCHENECTADY | 12308 | 36_32_13755 | ROSA RD 137 | N |  | 1000 |  |  | CDG | Y | 2018-06-05 | 2018-06-05 | 0 | 2018-07-02 | 2018-07-02 | 2018-07-13 | 8 | 2018-08-01 | 2018-08-01 | 2019-01-04 | 55 | 12200 |  | 96649.49 |  |  | 2019-01-30 |  |  | 2020-03-27 | 2020-03-27 | 2020-03-27 | Y | Y
NIMO | Solar City | 00101509 | 032 - Schenectady | SCHENECTADY | 12303 | 36_32_36556 | CURRY RD 365 | N |  | 1536 |  |  | RNM | N | 2016-01-22 | 2016-03-22 | 9 | 2016-03-22 | 2016-03-22 | 2016-04-11 | 0 | 2016-05-20 | 2016-05-20 | 2016-08-16 | 60 | 17500 |  | 219830 |  |  | 2017-05-17 |  |  | 2019-09-20 | 2019-09-20 | 2019-09-20 | Y | N
NIMO | GENERAL ELECTRIC | 00101582 | 032 - Schenectady | SCHENECTADY | 12345 | Rotterdam to General Electric 14 |  | N |  | 1728 |  |  | RNM | N | 2015-11-13 | 2015-12-14 | 4 | 2015-12-14 | 2015-12-14 | 2016-01-06 | 0 | 2016-03-15 | 2016-03-15 | 2016-06-21 | 70 | 15000 |  | 24000 |  |  | 2016-05-31 |  |  | 2017-09-27 | 2017-09-27 | 2017-09-27 | Y | N
NIMO | Dynamic Energy | 00102057 | 032 - Schenectady | SCHENECTADY | 12306 | 36_30_28355 | ALTAMONT 283 | N |  | 1980 |  |  | CDG | N | 2016-03-15 | 2016-03-15 | 0 | 2016-09-29 | 2016-09-29 | 2016-10-12 | 0 | 2017-01-27 | 2017-01-27 | 2017-04-20 | 59 | 19700 |  | 144550 |  |  | 2017-06-16 |  |  | 2018-12-20 | 2018-12-20 | 2018-12-20 | Y | N
NIMO | Kelsey Crane (ForeFront Power) | 00101267 | 032 - Schenectady | SCHENECTADY | 12305 | 36_32_26553 | BURDECK ST 265 | N |  | 2000 |  |  | CDG | N | 2015-09-15 | 2015-09-15 | 0 | 2015-09-15 |  |  |  | 2016-02-09 | 2016-02-09 | 2016-05-17 | 70 | 10000 |  | 328650 |  |  | 2017-02-14 |  |  | 2018-12-27 | 2018-12-27 | 2018-12-27 | Y | N
NIMO | Theresa Baker (General Electric International Inc) | 00186134 | 032 - Schenectady | SCHENECTADY | 12306 | 36_32_24551 | WEAVER ST 245 | N |  | 2750 |  |  | CDG | Y | 2018-06-07 | 2018-06-07 | 0 | 2018-06-29 | 2018-06-29 | 2018-07-17 | 11 | 2018-08-16 | 2018-08-16 | 2019-01-08 | 54 | 13300 |  | 634510.85 |  |  | 2019-01-30 |  |  | 2020-07-10 | 2020-07-10 | 2020-07-10 | Y | Y
NIMO | Theresa Baker (General Electric International Inc) | 00190778 | 032 - Schenectady | SCHENECTADY | 12309 | 36_32_13757 | ROSA RD 137 | N |  | 3500 |  |  | CDG | Y | 2018-07-16 | 2018-07-23 | 6.6958 | 2018-07-24 | 2018-07-24 | 2018-08-03 | 8 | 2019-02-05 | 2019-02-05 | 2019-04-18 | 55 | 13300 |  | 375969.44 |  |  | 2019-05-16 |  |  | 2020-10-26 | 2020-10-26 | 2020-10-26 | Y | Y
NIMO | Dallas Manson (Nexamp) | 00278801 | 032 - Schenectady | SCHENECTADY | 12306 | 36_32_26553 | BURDECK ST 265 | N |  | 5000 |  |  | CDG | N | 2020-03-10 | 2020-03-17 | 5 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 2020-04-24 | 2020-04-24 | 2020-08-31 | 57 | 9900 |  | 1426159.35 |  |  | 2021-01-27 | [5 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00328095 | 032 - Schenectady | SCHENECTADY | 12306 | 36_32_26553 | BURDECK ST 265 | N |  | 5000 |  |  | CDG | N | 2020-11-25 | 2020-12-03 | 4 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 0 | 2021-03-12 | 2021-03-12 |  |  | 9400 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00338931 | 032 - Schenectady | SCHENECTADY | 12306 | 36_32_26553 | BURDECK ST 265 | N |  | 5000 |  |  | CDG | N | 2021-02-22 | 2021-03-02 | 6 | 2021-03-02 | 2021-03-02 | 2021-03-19 | 12 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00339090 | 032 - Schenectady | SCHENECTADY | 12303 | 36_32_36551 | CURRY RD 365 | N |  | 5000 |  |  | CDG | N | 2021-02-23 | 2021-03-02 | 5 | 2021-03-02 | 2021-03-02 | 2021-03-02 | 0 |  |  |  |  | 8000 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00330344 | 032 - Schenectady | SCHENECTADY | 12302 | ROTTERDAM - WEAVER ST #36 |  | N |  | 5000 |  |  | CDG | N | 2021-02-02 | 2021-02-08 | 4 | 2021-02-08 | 2021-02-08 | 2021-02-08 | 0 |  |  |  |  | 6600 | [10 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00330365 | 032 - Schenectady | SCHENECTADY | 12302 | ROTTERDAM - WEAVER ST #36 |  | N |  | 5000 |  |  | CDG | N | 2021-01-27 | 2021-02-05 | 7 | 2021-02-05 | 2021-02-05 | 2021-02-05 | 0 |  |  |  |  | 6600 | [10 empty] | N | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00171646 | 037 - Cobleskill | SCHOHARIE | 12157 | 36_37_23451 | SCHOHARIE 234 | N |  | 5000 |  |  | CDG | Y | 2018-03-16 | 2018-03-23 | 5 | 2018-03-23 | 2018-03-23 | 2018-04-06 | 9 | 2018-06-06 | 2018-06-06 | 2018-08-17 | 51 | 12200 |  | 695061 |  |  | 2019-04-03 | [5 empty] | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00278766 | 037 - Cobleskill | SCHOHARIE | 12157 | 36_37_39051 | MIDDLEBURG 390 | N |  | 5000 |  |  | CDG | N | 2020-03-05 | 2020-03-16 | 7 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 0 | 2020-03-24 | 2020-03-24 | 2020-08-03 | 57 | 9800 |  | 759071.57 |  |  | 2021-01-05 | [5 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00299765 | 039 - Saratoga | SCHUYLERVILLE | 12871 | 36_39_34256 | BATTENKILL 342 | N |  | 5000 |  |  | CDG | N | 2020-07-07 | 2020-07-17 | 8 | 2020-07-17 | 2020-07-17 | 2020-07-22 | 2 | 2020-09-08 | 2020-09-08 | 2020-12-22 | 54 | 10500 |  | 460138 | [8 empty] | N | N
NIMO | Todd Friedman (RESunance, LLC) | 00323200 | 010 - Olean | SCIO | 14880 | 36_10_0661 | KNIGHTS CREEK 6 | N |  | 3625 |  |  | CDG | N | 2020-11-04 | 2020-11-12 | 5 | 2020-11-12 | 2020-11-12 | 2020-12-01 | 10 | 2021-02-19 | 2021-02-19 |  |  | 10900 | [10 empty] | N | N
NIMO | Theresa Baker (Distributed Solar Development, LLC) | 00186075 | 032 - Schenectady | SCOTIA | 12302 | 36_32_13853 | ROTTERDAM 138 | Y |  | 4975 | 2500 |  | CDG | Y | 2018-06-08 | 2018-06-18 | 4 | 2018-06-18 | 2018-06-18 | 2018-07-03 | 10 | 2018-07-30 | 2018-07-30 | 2019-01-14 | 58 | 14000 |  | 820712 |  |  | 2019-02-01 | [5 empty] | N | Y
NIMO | Theresa Baker (General Electric International Inc) | 00188378 | 032 - Schenectady | SCOTIA | 12302 | 36_32_34556 | GROOMS RD 345 | N |  | 1350 |  |  | CDG | Y | 2018-06-18 | 2018-06-18 | 0 | 2018-06-21 | 2018-06-21 | 2018-07-11 | 13 | 2018-09-19 | 2018-09-19 | 2018-12-07 | 37 | 16600 |  | 212968.46 |  |  | 2019-01-29 |  |  | 2020-11-23 | 2020-11-23 | 2020-11-23 | Y | Y
NIMO |  | 00212139 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36053 | FRONT ST 360 | N |  | 4125 |  |  | CDG | Y | 2019-03-04 | 2019-03-12 | 6 | 2019-03-12 | 2019-03-12 | 2019-03-19 | 4 | 2019-05-08 | 2019-05-08 | 2019-10-08 | 53 | 9200 |  | 128866 |  |  | 2020-03-09 | 2020-09-03 |  |  |  |  | N | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00255894 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36051 | FRONT ST 360 | N |  | 4625 |  |  | CDG | Y | 2019-10-08 | 2019-10-18 | 9.9812 | 2019-10-21 | 2019-10-21 | 2019-11-06 | 12 | 2019-11-12 | 2019-11-12 | 2020-01-28 | 198 | 8500 |  | 227155 |  |  | 2020-02-25 | 2020-09-10 | 2020-09-10 | 2020-12-19 | 2020-12-19 | 2020-12-19 | Y | Y
NIMO | Sean McCleneghen (Active Solar Development) | 00315742 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36051 | FRONT ST 360 | N |  | 5000 |  |  | CDG | N | 2020-10-08 | 2020-10-12 | 2 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-10-22 | 2020-10-22 | 2021-02-23 | 60 | 9800 |  | 842886 | [8 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00315759 | 032 - Schenectady | SCOTIA | 12010 | 36_32_36051 | FRONT ST 360 | N |  | 5000 |  |  | CDG | N | 2020-10-08 | 2020-10-12 | 2 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 0 | 2020-10-22 | 2020-10-22 | 2021-02-22 | 57 | 9800 |  | 150428 | [8 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00315771 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36453 | SWAGGERTOWN 364 | N |  | 5000 |  |  | CDG | N | 2020-10-12 | 2020-10-16 | 4 | 2020-10-16 | 2020-10-16 | 2020-11-03 | 10 | 2020-11-09 | 2020-11-09 | 2021-03-11 | 59 | 8800 |  | 854302 | [8 empty] | N | N
NIMO | Sean McCleneghen (Active Solar Development) | 00315821 | 032 - Schenectady | SCOTIA | 12302 | 36_32_36453 | SWAGGERTOWN 364 | N |  | 5000 |  |  | CDG | N | 2020-10-21 | 2020-10-28 | 5 | 2020-10-28 | 2020-10-28 | 2020-11-04 | 4 | 2020-11-17 | 2020-11-17 | 2021-03-11 | 59 | 9400 |  | 704302 | [8 empty] | N | N
NIMO |  | 00187481 | 005 - Avon | SCOTTSVILLE | 14546 | 36_05_5051 | MUMFORD 50 | N |  | 4500 |  |  | CDG | Y | 2018-06-13 | 2018-06-19 | 4 | 2018-06-19 | 2018-06-19 | 2018-07-25 | 14 | 2018-11-09 | 2018-11-09 | 2019-02-27 | 59 | 15300 |  | 839729.84 |  |  | 2019-07-08 | 2020-01-13 |  |  |  |  | N | Y
NIMO |  | 00187483 | 005 - Avon | SCOTTSVILLE | 14546 | 36_05_5051 | MUMFORD 50 | N |  | 4500 |  |  | CDG | Y | 2018-06-13 | 2018-06-20 | 5 | 2018-06-20 | 2018-06-20 | 2018-07-25 | 14 | 2018-11-09 | 2018-11-09 | 2019-02-27 | 59 | 16400 |  | 478635.71 |  |  | 2019-07-08 | 2020-01-08 |  |  |  |  | N | Y
NIMO | NEXTera Energy Resources | 00103259 | 030 - Albany | SELKIRK | 12158 | 36_30_14951 | SELKIRK 149 | N |  | 957 |  |  | RNM | N | 2014-06-24 | 2014-06-24 | 0 | 2014-06-24 | 2014-06-24 | 2014-07-29 | 2 | 2014-09-08 | 2014-09-08 | 2014-09-08 | 0 | 10000 | [7 empty] | 2016-03-08 | 2016-03-08 | 2016-03-08 | Y | N
NIMO | NEXTera Energy Resources | 00103260 | 030 - Albany | SELKIRK | 12158 | 36_30_14951 | SELKIRK 149 | N |  | 1791 |  |  | RNM | N | 2014-06-24 | 2014-06-24 | 0 | 2014-06-24 | 2014-06-24 | 2014-07-29 | 2 | 2014-09-08 | 2014-09-08 | 2015-01-28 | 102 | 25000 |  | 185470 | [5 empty] | 2016-03-08 | 2016-03-08 | 2016-03-08 | Y | N
NIMO | NEXTera Energy Resources | 00101028 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N |  | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | NEXTera Energy Resources | 00101033 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N |  | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | NEXTera Energy Resources | 00101034 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N |  | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | NEXTera Energy Resources | 00101027 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 |  | N |  | 2000 |  |  | RNM | N | 2015-02-24 | 2015-04-30 | 2 | 2015-04-30 | 2015-04-30 | 2015-04-30 | 0 | 2015-11-02 | 2015-11-02 | 2016-05-06 | 134 | 12500 |  | 853778 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Chris Stroud (Cipriani Energy Group Corp.) | 00284528 | 030 - Albany | SELKIRK | 12158 | 36_30_02158 | BETHLEHEM 21 | N |  | 2000 |  |  | CDG | Y | 2020-03-23 | 2020-04-01 | 7 | 2020-04-01 | 2020-04-01 | 2020-04-03 | 1 | 2020-04-20 | 2020-04-20 | 2020-07-29 | 58 | 8100 |  | 155384 |  |  | 2020-12-09 | [5 empty] | N | Y
NIMO | Nexamp Interconnections (Nexamp) | 00197571 | 030 - Albany | SELKIRK | 12158 | 36_30_14952 | SELKIRK 149 | N |  | 5000 |  |  | CDG | Y | 2018-11-30 | 2018-12-12 | 8 | 2018-12-12 | 2018-12-12 | 2018-12-21 | 6 | 2019-06-17 | 2019-06-17 | 2019-10-29 | 57 | 9800 |  | 173220.91 |  |  | 2020-02-28 | 2020-09-03 |  |  |  |  | N | Y
NIMO | Elie Schecter (Selkirk Solar) | 00255702 | 030 - Albany | SELKIRK | 12158 | BETHLEHEM - SELKIRK #5 | SUBT 30 | N |  | 5000 |  |  | CDG | Y | 2019-09-24 | 2019-10-04 | 8 | 2019-10-04 | 2019-10-04 | 2019-10-21 | 10 | 2019-11-14 | 2019-11-14 | 2020-03-05 | 58 | 11300 |  | 262756 |  |  | 2020-07-02 | 2020-12-28 |  |  |  |  | N | Y
NIMO | Josh katz (Onyx Development Grou) | 00101079 | 037 - Cobleskill | SHARON SPRINGS | 13459 | 36_37_36351 | SHARON 363 | N |  | 1980 |  |  | RNM | N | 2015-03-17 | 2015-03-17 | 0 | 2015-05-13 | 2015-05-13 | 2015-06-29 | 0 | 2015-09-28 | 2015-09-28 | 2016-01-22 | 84 | 35000 |  | 755094 |  |  | 2017-01-27 |  |  | 2018-03-29 | 2018-03-29 | 2018-03-29 | Y | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00284814 | 037 - Cobleskill | SHARON SPRINGS | 13459 | 36_37_36352 | SHARON 363 | N |  | 3590 |  |  | CDG | N | 2020-05-06 | 2020-05-12 | 4 | 2020-05-12 | 2020-05-12 | 2020-05-12 | 0 | 2020-05-14 | 2020-05-14 | 2020-09-28 | 59 | 9000 |  | 1405370.45 | [8 empty] | N | N
NIMO | Dallas Manson (Nexamp) | 00253007 | 037 - Cobleskill | SHARON SPRINGS | 13459 | 36_37_36352 | SHARON 363 | N |  | 4750 |  |  | CDG | N | 2019-10-30 | 2019-11-07 | 6 | 2019-11-07 | 2019-11-07 | 2019-11-12 | 1 | 2019-12-20 | 2019-12-20 | 2020-11-18 | 58 | 9000 |  | 1862887 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00293437 | 009 - Lakewood/Stow | SHERMAN | 14781 | W PORTLAND-SHERMAN #867 |  | N |  | 4650 |  |  | CDG | N | 2020-05-27 | 2020-06-03 | 5 | 2020-06-03 | 2020-06-03 | 2020-06-04 | 0 | 2020-07-28 | 2020-07-28 | 2021-02-02 | 58 | 10900 |  | 381912 | [8 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00347615 | 009 - Lakewood/Stow | SHERMAN | 14781 | 36_09_5461 | SHERMAN 54 | N |  | 5000 |  |  | CDG | N | 2021-03-19 | 2021-03-25 | 4 | 2021-03-25 | 2021-03-25 | 2021-04-12 | 11 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00347626 | 009 - Lakewood/Stow | SHERMAN | 14781 | 36_09_5461 | SHERMAN 54 | N |  | 5000 |  |  | CDG | N | 2021-03-19 | 2021-03-25 | 4 | 2021-03-25 | 2021-03-25 | 2021-04-12 | 11 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00347637 | 009 - Lakewood/Stow | SHERMAN | 14781 | 36_09_5461 | SHERMAN 54 | N |  | 5000 |  |  | CDG | N | 2021-03-19 | 2021-03-25 | 4 | 2021-03-25 | 2021-03-25 | 2021-04-12 | 11 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Carrie Cosentino (Solar Liberty Energy Systems, In | 00305546 | 009 - Lakewood/Stow | SHERMAN | 14781 | W PORTLAND-SHERMAN #867 |  | N |  | 5000 |  |  | CDG | N | 2020-08-11 | 2020-08-24 | 9 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 0 | 2020-11-05 | 2020-11-05 | 2021-03-03 | 55 | 10900 |  | 751060 | [8 empty] | N | N
NIMO | Jamal Batar (DSD Renewables) | 00108584 | 008 - Dunkirk/Fredoni | SILVER CREEK | 14136 | 36_08_9954 | BENNETT RD 99 | N |  | 5000 |  |  | CDG | Y | 2017-09-15 | 2017-09-19 | 2 | 2017-09-19 | 2017-09-19 | 2017-09-28 | 6 | 2019-04-17 | 2019-04-17 | 2019-07-09 | 57 | 20600 |  | 563300.34 |  |  | 2019-11-12 | 2020-09-10 |  |  |  |  | N | Y
NIMO | Kelsey Crane (Forefront Power LLC) | 00330644 | 008 - Dunkirk/Fredoni | SINCLAIRVILLE | 14782 | 36_08_7261 | SINCLAIRVILLE 72 | N |  | 3375 |  |  | CDG | N | 2020-12-14 | 2020-12-21 | 5 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 0 | 2021-01-15 | 2021-01-15 |  |  | 10900 | [10 empty] | N | N
NIMO | Noah Siegel (Abundant Solar Power [SK1] LLC) | 00199552 | 011 - Syracuse | SKANEATELES | 13152 | 36_11_29156 | JEWETT RD 291 | N |  | 1000 |  |  | CDG | Y | 2018-11-29 | 2018-12-05 | 4 | 2018-12-05 | 2018-12-05 | 2018-12-07 | 1 | 2018-12-28 | 2018-12-28 | 2019-04-05 | 51 | 9800 |  | 227956.05 |  |  | 2019-07-08 | [5 empty] | N | Y
NIMO | Mike Borkowski (Community Power Group) | 00283959 | 011 - Syracuse | SKANEATELES | 13152 | 36_11_29156 | JEWETT RD 291 | N |  | 5000 |  |  | CDG | N | 2020-04-23 | 2020-04-30 | 5 | 2020-04-30 | 2020-04-30 | 2020-05-04 | 1 | 2020-10-02 | 2020-10-02 | 2020-12-23 | 55 | 11300 |  | 1032367 | [8 empty] | N | N
NIMO | Will Jurith (Standard Solar) | 00101899 | 030 - Albany | SLINGERLANDS | 12159 | 36_30_17852 | VOORHEESVILLE 178 | N |  | 1875 |  |  | CDG | Y | 2016-05-19 | 2016-06-02 | 8 | 2016-06-02 | 2016-06-02 | 2016-06-13 | 0 | 2017-05-19 | 2017-05-19 | 2017-08-14 | 58 | 19300 |  | 204368.53 |  |  | 2018-06-29 | 2019-01-09 | 2019-01-09 | 2020-12-23 | 2020-12-23 | 2020-12-23 | Y | Y
NIMO | Kevin O'Neill (Seaboard Solar Holding NY, LLC) | 00299913 |  | SLINGERLANDS | 12159 | BETHLEHEM - VOORHEESVILLE #1 |  | N |  | 4975 |  |  | CDG | N | 2020-10-02 | 2020-10-08 | 4 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 0 | 2020-12-03 | 2020-12-03 |  |  | 10900 | [10 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00294530 | 038 - Glens Falls | SOUTH GLENS FALLS | 12803 | 36_38_47651 | FARNAN RD 476 | N |  | 2500 |  |  | CDG | N | 2020-07-01 | 2020-07-09 | 5 | 2020-07-09 | 2020-07-09 | 2020-07-09 | 0 | 2020-08-12 | 2020-08-12 | 2020-12-22 | 59 | 8800 |  | 208096.67 |  |  | 2021-02-10 | [5 empty] | N | N
NIMO | Michael Cucchiara (Nexamp) | 00304035 | 038 - Glens Falls | SOUTH GLENS FALLS | 12803 | 36_38_47651 | FARNAN RD 476 | N |  | 2500 |  |  | CDG | N | 2020-08-27 | 2020-09-03 | 5 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 0 | 2020-10-30 | 2020-10-30 | 2021-03-15 | 59 | 9400 |  | 208037 | [8 empty] | N | N
NIMO | Kelsey Crane (Forefront Power LLC) | 00172236 | 038 - Glens Falls | SOUTH HARTFORD | 12838 | 36_38_33752 | BURGOYNE 337 | N |  | 2500 |  |  | CDG | Y | 2018-04-06 | 2018-04-19 | 7 | 2018-04-19 | 2018-04-19 | 2018-05-07 | 11 | 2018-12-07 | 2018-12-07 | 2019-06-18 | 59 | 16400 |  | 826877 |  |  | 2019-09-13 | 2020-03-25 |  |  |  |  | N | Y
NIMO | Grant Johns (BW Solar Holding Inc.) | 00308463 | 004 - Batavia | STAFFORD | 14143 | 36_04_2855 | E. BATAVIA 28 | N |  | 5000 |  |  | CDG | N | 2020-09-01 | 2020-09-05 | 4 | 2020-09-05 | 2020-09-05 | 2020-09-05 | 0 | 2020-12-09 | 2020-12-09 | 2021-03-08 | 59 | 10000 |  | 691341 | [8 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00310125 | 004 - Batavia | STAFFORD | 14143 | 36_04_2855 | E. BATAVIA 28 | N |  | 5000 |  |  | CDG | N | 2020-09-02 | 2020-09-14 | 7 | 2020-09-14 | 2020-09-14 | 2020-09-14 | 0 | 2020-12-09 | 2020-12-09 | 2021-03-08 | 59 | 11300 |  | 637353 | [8 empty] | N | N
NIMO | SunCommon | 00102393 | 010 - Olean | STEAMBURG | 14783 | COLD SPRING-W SALAMANCA #804 |  | N |  | 1440 |  |  | RNM | Y | 2016-07-26 | 2016-08-02 | 4 | 2016-08-02 | 2016-08-02 | 2016-08-05 | 0 | 2016-09-30 | 2016-09-30 | 2016-12-28 | 60 | 26200 |  | 211050 | [5 empty] | 2017-10-13 | 2017-10-13 | 2017-10-13 | Y | Y
NIMO | Kevin O'Neill (Seaboard Solar Holdings, LLC) | 00321660 | 008 - Dunkirk/Fredoni | STOCKTON | 14784 | DUNKIRK-HARTFIELD #852 |  | N |  | 4975 |  |  | CDG | N | 2020-11-17 | 2020-11-30 | 7 | 2020-11-30 | 2020-11-30 | 2020-11-30 | 0 | 2020-12-24 | 2020-12-24 |  |  | 11700 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00324703 | 008 - Dunkirk/Fredoni | STOCKTON | 14784 | DUNKIRK-HARTFIELD #852 |  | N |  | 4975 |  |  | CDG | N | 2020-12-03 | 2020-12-03 | 0 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 0 | 2020-12-29 | 2020-12-29 |  |  | 11700 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00336395 | 008 - Dunkirk/Fredoni | STOCKTON | 14784 | DUNKIRK-HARTFIELD #852 |  | N |  | 4975 |  |  | CDG | N | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-03 | 2021-02-11 | 5 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Kevin O'Neill (Seaboard Solar) | 00336399 | 008 - Dunkirk/Fredoni | STOCKTON | 14784 | DUNKIRK-HARTFIELD #852 |  | N |  | 4975 |  |  | CDG | N | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-03 | 2021-02-11 | 5 |  |  |  |  | 9000 | [10 empty] | N | N
NIMO | Matthew Fuller (Syracuse University) | 00282428 | 011 - Syracuse | SYRACUSE | 13210 | 36_11_22372 | ASH ST 223 | N |  |  | 0 |  | NA | N | 2020-03-06 | 2020-03-16 | 4 | 2020-03-16 | [18 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00293795 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23554 | HARRIS RD 235 | Y |  | 5000 | 5000 |  | CDG | N | 2020-06-08 | 2020-06-15 | 5 | 2020-06-15 | 2020-06-15 | 2020-06-15 | 0 | 2020-08-05 | 2020-08-05 | 2021-01-07 | 58 | 9300 |  | 642539 | [8 empty] | N | N
NIMO | Andrew Day (SOURCE RENEWABLES LLC) | 00323777 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23554 | HARRIS RD 235 | N |  | 2500 |  |  | CDG | N | 2020-12-30 | 2021-04-09 | 73 | 2021-04-09 | 2021-04-09 | 2021-04-09 | 0 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318806 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23550 | HARRIS RD 235 | N |  | 4400 |  |  | CDG | N | 2020-12-11 | 2020-12-11 | 0 | 2020-12-11 | 2020-12-11 | 2020-12-15 | 1 | 2021-01-11 | 2021-01-11 |  |  | 9400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00312212 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23551 | HARRIS RD 235 | N |  | 5000 |  |  | CDG | N | 2020-09-14 | 2020-09-20 | 5 | 2020-09-20 | 2020-09-20 | 2020-09-29 | 6 | 2020-11-19 | 2020-11-19 | 2021-04-15 | 59 | 10100 |  | 1041069 | [8 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00318493 | 011 - Syracuse | SYRACUSE | 13215 | 36_11_23550 | HARRIS RD 235 | N |  | 5000 |  |  | CDG | N | 2020-11-03 | 2020-11-08 | 4 | 2020-11-08 | 2020-11-08 | 2020-11-08 | 0 | 2020-12-08 | 2020-12-08 |  |  | 8800 | [10 empty] | N | N
NIMO | Samantha Lennon (GSPP 4575 State Route 69, LLC) | 00227418 | 018 - Rome | TABERG | 13471 | 36_18_65355 | TURIN RD 653 | N |  | 5000 |  |  | CDG | Y | 2019-06-11 | 2019-06-18 | 5 | 2019-06-18 | 2019-06-18 | 2019-06-21 | 2 | 2019-10-17 | 2019-10-17 | 2020-01-27 | 59 | 10100 |  | 191195 |  |  | 2020-04-27 | 2020-10-26 |  |  |  |  | N | Y
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00300053 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41851 | HAGUE RD 418 | N |  | 2500 |  |  | CDG | N | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | 2020-08-18 | 2020-08-18 | 0 | 2020-09-17 | 2020-09-17 | 2021-02-10 | 59 | 10100 |  | 1221491.88 | [8 empty] | N | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00305256 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41853 | HAGUE RD 418 | N |  | 5000 |  |  | CDG | N | 2020-09-23 | 2020-09-23 | 0 | 2020-09-23 | 2020-09-23 | 2020-09-29 | 3 | 2020-10-26 | 2020-10-26 | 2021-03-24 | 60 | 8800 |  | 689151 | [8 empty] | N | N
NIMO | Gordon Woodcock (Pivot Energy) | 00260469 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41852 | HAGUE RD 418 | N |  | 5000 |  |  | CDG | Y | 2019-12-02 | 2019-12-10 | 6 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 0 | 2019-12-12 | 2019-12-12 | 2020-07-16 | 57 | 10800 |  | 748741.76 |  |  | 2020-11-23 | [5 empty] | N | Y
NIMO | Johnson (Junction Solar, LLC) | 00264683 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41852 | HAGUE RD 418 | N |  | 5000 |  |  | CDG | N | 2020-01-21 | 2020-02-02 | 9 | 2020-02-02 | 2020-02-02 | 2020-02-02 | 0 | 2020-04-06 | 2020-04-06 | 2021-01-04 | 59 | 9400 |  | 1379264.67 | [8 empty] | N | N
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00305249 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41851 | HAGUE RD 418 | N |  | 5000 |  |  | CDG | N | 2020-08-17 | 2020-08-24 | 5 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 0 | 2020-11-12 | 2020-11-12 | 2021-02-24 | 59 | 9800 |  | 758846 | [8 empty] | N | N
NIMO | Standard Solar (Standard Solar Inc.) | 00340968 | 041 - Ticonderoga | TICONDEROGA | 12883 | 36_41_41851 | HAGUE RD 418 | N |  | 5000 |  |  | CDG | N | 2021-02-09 | 2021-02-17 | 5 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 0 |  |  |  |  | 7500 | [10 empty] | N | N
NIMO | Michael Prinzi (Solar Liberty) | 00101466 | 001 - Buffalo | TONAWANDA | 14150 | CA 34H #34 |  | N |  | 2000 |  |  | RNM | N | 2015-12-28 | 2016-02-26 | 3 | 2016-02-26 | 2016-02-26 | 2016-03-24 | 0 | 2016-05-17 | 2016-05-17 | 2016-08-11 | 60 | 19000 |  | 329550 |  |  | 2017-05-26 |  |  | 2020-01-31 | 2020-01-31 | 2020-01-31 | Y | N
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00172846 |  | TONAWANDA | 14150 | CA 34H #34 |  | N |  | 5000 |  |  | RNM | Y | 2018-04-03 | 2018-04-03 | 0 | 2018-04-19 | 2018-04-19 | 2018-06-21 | 10 | 2018-09-17 | 2018-09-17 | 2019-01-18 | 57 | 12200 |  | 320807.59 |  |  | 2019-06-07 | 2019-12-04 | 2019-12-04 | 2020-12-29 | 2020-12-29 | 2020-12-29 | Y | Y
NIMO | Giovanni Maruca (Eden DevCo LP) | 00276844 | 031 - Troy | TROY | 12180 | 36_31_26453 | BRUNSWICK 264 | Y |  | 5000 | 5000 |  | CDG | N | 2020-01-31 | 2020-02-13 | 9 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 0 | 2020-04-30 | 2020-04-30 | 2020-09-21 | 58 | 9100 |  | 362838.65 |  |  | 2021-02-02 | [5 empty] | N | N
NIMO | High Peaks Solar/Sycaway Solar and Wind | 00102169 | 031 - Troy | TROY | 12180 | 36_31_37256 | SYCAWAY 372 | N |  | 1980 |  |  | CDG | N | 2016-06-27 | 2016-07-02 | 5 | 2016-07-02 | 2016-07-02 | 2016-07-13 | 6 | 2016-10-21 | 2016-10-21 | 2017-01-17 | 60 | 27500 |  | 883650 |  |  | 2018-03-07 |  |  | 2019-12-31 | 2019-12-31 | 2019-12-31 | Y | N
NIMO | Jennifer hoeffner (Monolith Solar Assoc. LLC) | 00170011 | 031 - Troy | TROY | 12180 | 36_31_33457 | REYNOLDS RD 334 | N |  | 2000 |  |  | RNM | N | 2018-02-05 | 2018-02-05 | 0 | 2018-03-21 | 2018-03-21 | 2018-04-04 | 9 | 2018-06-07 | 2018-06-07 | 2018-08-24 | 55 | 14300 |  | 317954.38 |  |  | 2019-03-25 | 2019-09-20 | 2019-09-20 | 2020-12-10 | 2020-12-10 | 2020-12-10 | Y | N
NIMO | Lluis Torrent (CAERO) | 00337194 | 031 - Troy | TROY | 12180 | 36_31_37256 | SYCAWAY 372 | N |  | 2660 |  |  | CDG | N | 2021-01-19 | 2021-01-27 | 6 | 2021-01-27 | 2021-01-27 | 2021-02-12 | 11 |  |  |  |  | 6600 | [10 empty] | N | N
NIMO | Caitlin Majewski (xxx) | 00101073 | 031 - Troy | TROY | 12180 | 36_31_26453 | BRUNSWICK 264 | N |  | 3960 |  |  | CDG | N | 2015-03-18 | 2016-01-11 | 214 | 2016-01-11 | 2016-01-11 | 2016-03-14 | 0 | 2017-01-10 | 2017-01-10 | 2017-03-27 | 54 | 25000 |  |  |  |  | 2017-06-22 |  |  | 2019-09-19 | 2019-09-19 | 2019-09-19 | Y | N
NIMO | Lluis Torrent (CAERO) | 00311053 | 031 - Troy | TROY | 12180 | 36_31_37253 | SYCAWAY 372 | N |  | 4000 |  |  | CDG | N | 2020-10-05 | 2020-10-05 | 0 | 2020-10-05 | 2020-10-05 | 2020-10-05 | 0 | 2020-10-27 | 2020-10-27 | 2021-04-14 | 59 | 9400 |  | 124920 | [8 empty] | N | N
NIMO | Thibaut Delespaul (CVE North America, Inc.) | 00308358 | 031 - Troy | TROY | 12180 | 36_31_37252 | SYCAWAY 372 | N |  | 4000 |  |  | CDG | N | 2020-09-09 | 2020-09-09 | 0 | 2020-09-09 | 2020-09-09 | 2020-09-23 | 9 | 2020-10-28 | 2020-10-28 |  |  | 10400 | [10 empty] | N | N
NIMO | John J. Watson (CAERO) | 00290192 | 031 - Troy | TROY | 12182 | 36_31_12354 | N. TROY 123 | N |  | 5000 |  |  | CDG | Y | 2020-05-08 | 2020-05-15 | 5 | 2020-05-15 | 2020-05-15 | 2020-05-15 | 0 | 2020-07-09 | 2020-07-09 | 2020-11-18 | 59 | 9300 |  | 154427.24 |  |  | 2020-12-22 | [5 empty] | N | Y
NIMO | Borrego Solar Systems, Inc | 00213284 | 031 - Troy | TROY | 12180 | 36_31_12353 | N. TROY 123 | N |  | 5000 |  |  | CDG | Y | 2019-03-14 | 2019-03-26 | 8 | 2019-03-26 | 2019-03-26 | 2019-04-05 | 6 | 2019-06-18 | 2019-06-18 | 2019-09-04 | 54 | 9200 |  | 352330 |  |  | 2019-09-25 | 2020-03-16 |  |  |  |  | N | Y
NIMO | Lluis Torrent (CAERO) | 00321431 | 031 - Troy | TROY | 12180 | 36_31_37256 | SYCAWAY 372 | N |  | 5000 |  |  | CDG | N | 2020-11-12 | 2020-11-18 | 4 | 2020-11-18 | 2020-11-18 | 2020-11-30 | 5 | 2021-02-19 | 2021-02-19 |  |  | 9400 | [10 empty] | N | N
NIMO | Grant Johns (BW Solar Holding Inc.) | 00315532 | 012 - Cortland | TRUXTON | 13158 | 36_12_23051 | LABRADOR 230 | N |  | 5000 |  |  | CDG | N | 2020-09-29 | 2020-10-07 | 6 | 2020-10-07 | 2020-10-07 | 2020-10-07 | 0 | 2020-11-19 | 2020-11-19 | 2021-04-06 | 58 | 8800 |  | 9300004 | [8 empty] | N | N
NIMO | Greg Hering (ClearPath Energy) | 00240225 | 011 - Syracuse | TULLY | 13159 | 36_12_27851 | TULLY CENTER 278 | Y |  | 5000 | 0 |  | CDG | Y | 2019-07-15 | 2019-07-19 | 4 | 2019-07-19 | 2019-07-19 | 2019-08-01 | 8 | 2019-09-13 | 2019-09-13 | 2019-12-23 | 59 | 9900 |  | 224195 |  |  | 2020-06-08 | 2020-12-11 |  |  |  |  | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00243968 | 011 - Syracuse | TULLY | 13159 | 36_12_27852 | TULLY CENTER 278 | Y |  | 5000 | 0 |  | CDG | Y | 2019-08-05 | 2019-08-13 | 6 | 2019-08-13 | 2019-08-13 | 2019-08-21 | 5 | 2019-12-19 | 2019-12-19 | 2020-03-17 | 59 | 9900 |  | 252315.73 |  |  | 2020-06-08 | 2020-12-16 |  |  |  |  | N | Y
NIMO | Greg Hering (ClearPath Energy) | 00240219 | 011 - Syracuse | TULLY | 13159 | 36_12_27852 | TULLY CENTER 278 | Y |  | 5000 | 0 |  | CDG | Y | 2019-07-15 | 2019-07-19 | 4 | 2019-07-19 | 2019-07-19 | 2019-07-31 | 7 | 2019-08-19 | 2019-08-19 | 2019-12-10 | 58 | 9900 |  | 698473.53 |  |  | 2020-06-18 | 2020-12-11 |  |  |  |  | N | Y
NIMO | Borrego Solar Systems, Inc | 00343112 | 011 - Syracuse | TULLY | 13159 | 36_11_15067 | LORDS HILL 150 | N |  | 5000 |  |  | CDG | N | 2021-03-23 | 2021-03-28 | 4 | 2021-03-28 | 2021-03-28 | 2021-03-28 | 0 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00183955 | 023 - Lowville | TURIN | 13473 | 36_23_77352 | LOWVILLE 773 | N |  | 2500 |  |  | CDG | Y | 2018-06-11 | 2018-06-25 | 4 | 2018-06-25 | 2018-06-25 | 2018-07-17 | 14 | 2018-08-22 | 2018-08-22 | 2019-01-26 | 58 | 14300 |  | 815168 |  |  | 2019-05-28 | 2019-09-12 |  |  |  |  | N | Y
NIMO | Pat Goodale (Saturn Power Corp.) | 00330555 | 023 - Lowville | TURIN | 13309 | 36_23_71663 | COLLINSVILLE 716 | N |  | 5000 |  |  | CDG | N | 2020-12-17 | 2020-12-21 | 2 | 2020-12-21 | 2020-12-21 | 2021-01-04 | 7 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Andrew Day (Source Renewables, LLC) | 00210245 | 017 - Utica | UTICA | 13502 | 36_17_60656 | DEERFIELD 606 | Y |  | 3200 | 5000 |  | CDG | Y | 2019-04-10 | 2019-04-20 | 8 | 2019-04-20 | 2019-04-20 | 2019-04-29 | 5 | 2019-06-26 | 2019-06-26 | 2020-06-08 | 59 | 10300 |  | 830876.75 |  |  | 2020-10-14 | [5 empty] | N | Y
NIMO | Adam Ellis (Nexamp) | 00317740 | 017 - Utica | UTICA | 13502 | 36_17_65150 | TERMINAL 651 | N |  | 1625 |  |  | CDG | N | 2020-10-29 | 2020-10-29 | 0 | 2020-10-29 | 2020-10-29 | 2020-10-29 | 0 | 2021-03-03 | 2021-03-03 |  |  | 8800 | [10 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00304928 | 017 - Utica | UTICA | 13502 | 36_17_65150 | TERMINAL 651 | N |  | 2850 |  |  | CDG | N | 2020-08-20 | 2020-08-26 | 4 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 0 | 2020-09-14 | 2020-09-14 | 2020-12-11 | 59 | 8800 |  | 396093 |  |  | 2021-02-10 | [5 empty] | N | N
NIMO | Lluis Torrent (CAERO) | 00304033 | 017 - Utica | UTICA | 13502 | 36_17_60658 | DEERFIELD 606 | N |  | 4000 |  |  | CDG | N | 2020-08-04 | 2020-08-14 | 8 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 0 | 2020-09-09 | 2020-09-09 | 2020-12-28 | 59 | 8800 |  | 832557.83 | [8 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00293901 | 017 - Utica | UTICA | 13502 | 36_17_60656 | DEERFIELD 606 | N |  | 4000 |  |  | CDG | N | 2020-06-25 | 2020-07-01 | 4 | 2020-07-01 | 2020-07-01 | 2020-07-01 | 0 | 2020-08-18 | 2020-08-18 | 2020-11-24 | 59 | 9400 |  | 2042470 | [8 empty] | N | N
NIMO | Sam Youneszadeh (Dimension NY 1 LLC) | 00273422 | 017 - Utica | UTICA | 13502 | 36_17_66356 | SCHUYLER 663 | N |  | 4500 |  |  | CDG | Y | 2020-01-16 | 2020-01-30 | 9 | 2020-01-30 | 2020-01-30 | 2020-01-30 | 0 | 2020-02-27 | 2020-02-27 | 2020-06-25 | 59 | 8600 |  | 328500 |  |  | 2020-12-03 | [5 empty] | N | Y
NIMO | Wendy DeWolf (East Light Partners) | 00197190 | 033 - Hudson | VALATIE | 12184 | 36_33_42754 | VALKIN 427 | Y | 00207295 | 5000 | 0 |  | CDG | Y | 2018-11-26 | 2018-11-30 | 3.85 | 2018-12-03 | 2018-12-03 | 2018-12-10 | 5 | 2018-12-18 | 2018-12-18 | 2019-04-12 | 58 | 11700 |  | 801563.38 |  |  | 2019-07-25 | 2020-02-29 | 2020-02-29 | 2020-11-18 | 2020-11-18 | 2020-11-18 | Y | Y
NIMO | Stephanie Loucas (Wildcat Renewables, LLC) | 00344954 | 033 - Hudson | VALATIE | 12184 | 36_33_42752 | VALKIN 427 | N |  | 2750 |  |  | CDG | N | 2021-03-04 | 2021-03-11 | 5 | 2021-03-11 | 2021-03-11 | 2021-03-19 | 5 |  |  |  |  | 6900 | [10 empty] | N | N
NIMO | Khilan Munshi (Seaboard Solar) | 00344830 | 033 - Hudson | VALATIE | 12184 | 36_33_42754 | VALKIN 427 | N |  | 4975 |  |  | CDG | N | 2021-03-18 | 2021-03-25 | 5 | 2021-03-25 | 2021-03-25 | 2021-03-30 | 2 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Khilan Munshi (Seaboard solar) | 00344959 | 033 - Hudson | VALATIE | 12184 | 36_33_42754 | VALKIN 427 | N |  | 4975 |  |  | CDG | N | 2021-03-18 | 2021-03-25 | 5 | 2021-03-25 | 2021-03-25 | 2021-03-30 | 2 |  |  |  |  | 7200 | [10 empty] | N | N
NIMO | Tory Hanna (Davis Hill Development) | 00331687 | 031 - Troy | VALLEY FALLS | 12185 | MECHANICVILLE-CLAY HILL #2 |  | N |  | 5000 |  |  | CDG | N | 2021-01-06 | 2021-01-13 | 5 | 2021-01-13 | 2021-01-13 | 2021-01-22 | 5 |  |  |  |  | 9600 | [10 empty] | N | N
NIMO | Chris Matthews (AES Distributed Energy, Inc.) | 00293453 | 020 - Oneida | VERNON | 13476 | 36_20_50155 | ONEIDA 501 | N |  | 3750 |  |  | CDG | N | 2020-06-22 | 2020-06-27 | 5 | 2020-06-27 | 2020-06-27 | 2020-06-27 | 0 | 2020-07-14 | 2020-07-14 | 2021-02-10 | 58 | 10900 |  | 1015358 | [8 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00241074 | 020 - Oneida | VERNON | 13476 | 36_20_50153 | ONEIDA 501 | N |  | 5000 |  |  | CDG | Y | 2019-06-28 | 2019-07-10 | 7 | 2019-07-10 | 2019-07-10 | 2019-07-22 | 7 | 2019-09-05 | 2019-09-05 | 2020-04-10 | 52 | 9900 |  | 331346.25 |  |  | 2020-07-28 | 2021-02-03 |  |  |  |  | N | Y
NIMO | Joshua Gillebaard (TM MONTANTE SOLAR DEVELOPMENT L | 00207957 | 020 - Oneida | VERONA | 13478 | 36_20_50155 | ONEIDA 501 | N |  | 2500 |  |  | CDG | Y | 2019-02-04 | 2019-02-12 | 6 | 2019-02-12 | 2019-02-12 | 2019-02-19 | 3 | 2019-03-15 | 2019-03-15 | 2019-07-16 | 58 | 8600 |  | 181750 |  |  | 2019-11-01 | 2020-09-16 |  |  |  |  | N | Y
NIMO | Gordon Woodcock (TCA Microgrid Energy LLC) | 00287857 | 020 - Oneida | VERONA | 13478 | 36_20_50156 | ONEIDA 501 | N |  | 3000 |  |  | CDG | N | 2020-04-23 | 2020-05-04 | 7 | 2020-05-04 | 2020-05-04 | 2020-05-04 | 0 | 2020-06-10 | 2020-06-10 | 2020-09-21 | 58 | 10900 |  | 604511.63 |  |  | 2021-02-09 | [5 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00257886 | 030 - Albany | VOORHEESVILLE | 12186 | 36_30_17853 | VOORHEESVILLE 178 | N |  | 5000 |  |  | CDG | Y | 2019-10-16 | 2019-10-24 | 6 | 2019-10-24 | 2019-10-24 | 2019-11-05 | 7 | 2020-01-14 | 2020-01-14 | 2020-04-20 | 56 | 10800 |  | 1087482 |  |  | 2020-06-30 | 2020-12-23 |  |  |  |  | N | Y
NIMO | Michael Frateschi (TJA Clean Energy) | 00318875 | 025 - Potsdam | WADDINGTON | 13694 | 36_25_95756 | BRADY 957 | N |  | 5000 |  |  | CDG | N | 2020-10-14 | 2020-10-20 | 4 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 0 | 2020-12-08 | 2020-12-08 |  |  | 9800 | [10 empty] | N | N
NIMO | Standard Solar | 00254732 |  | WADSWORTH | 14533 | 36_05_5351 | YORK CENTER 53 | N |  | 5000 |  |  | CDG | Y | 2019-09-18 | 2019-09-30 | 8 | 2019-09-30 | 2019-09-30 | 2019-11-04 | 11 | 2019-12-09 | 2019-12-09 | 2020-04-24 | 26 | 10500 |  | 844269.77 |  |  | 2020-09-08 | 2021-02-08 |  |  |  |  | N | Y
NIMO | Mithun Vyas (DG New York CS LLC) | 00232001 | 011 - Syracuse | WARNERS | 13164 | 36_11_26658 | MILTON AVE 266 | Y |  | 3000 | 3000 |  | CDG | Y | 2019-06-03 | 2019-06-12 | 7 | 2019-06-12 | 2019-06-12 | 2019-06-28 | 11 | 2019-08-08 | 2019-08-08 | 2019-12-13 | 59 | 10300 |  | 835748 |  |  | 2020-01-06 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Christopher Stroud (Cipriani Energy Group Corp.) | 00297629 | 040 - Warrensburg | WARRENSBURG | 12885 | 36_40_32151 | WARRENSBURG 321 | N |  | 3200 |  |  | CDG | N | 2020-08-09 | 2020-08-09 | 0 | 2020-08-09 | 2020-08-09 | 2020-08-09 | 0 | 2020-08-28 | 2020-08-28 | 2020-12-16 | 58 | 10800 |  | 28507.5 | [8 empty] | N | N
NIMO | Tory Hanna (Davis Hill Development) | 00325790 | 040 - Warrensburg | WARRENSBURG | 12885 | 36_40_32152 | WARRENSBURG 321 | N |  | 5000 |  |  | CDG | N | 2020-11-18 | 2020-11-30 | 6 | 2020-11-30 | 2020-11-30 | 2020-11-30 | 0 | 2020-12-21 | 2020-12-21 | 2021-04-01 | 59 | 9200 |  | 220122.23 | [8 empty] | N | N
NIMO | Giovanni Maruca (Eden DevCo LP) | 00334283 | 031 - Troy | WATERFORD | 12188 | 36_31_41352 | PROSPECT HILL 413 | Y |  | 5000 | 5000 |  | CDG | N | 2020-12-30 | 2021-01-07 | 5 | 2021-01-07 | 2021-01-07 | 2021-01-07 | 0 |  |  |  |  | 7700 | [10 empty] | N | N
NIMO | Pat Goodale (Saturn Power Corp.) | 00340257 | 006 - Albion/Medina | WATERPORT | 14571 | 36_06_7363 | WATERPORT 73 | N |  | 5000 |  |  | CDG | N | 2021-02-11 | 2021-02-18 | 4 | 2021-02-18 | 2021-02-18 | 2021-03-10 | 13 | 2021-04-08 | 2021-04-08 |  |  | 8400 | [10 empty] | N | N
NIMO | Dallas Manson (Nexamp) | 00338559 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76054 | COFFEEN 760 | Y |  | 3500 | 0 |  | CDG | Y | 2021-01-25 |  |  | 1899-12-31 | [18 empty] | N | Y
NIMO | Tiffany Robicheau (Borrego Solar Systems, Inc) | 00300527 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  |  | 0 | 5000 | CDG | N | 2020-09-08 | 2020-09-15 | 5 | 2020-09-15 | 2020-09-15 | 2020-09-15 | 0 | 2020-10-26 | 2020-10-26 |  |  | 10900 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315558 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 12200 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315563 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 11800 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315565 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81757 | E. WATERTOWN 817 | Y |  |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 11800 | [10 empty] | N | N
NIMO | Edward Shambeau (Borrego Solar Systems, Inc) | 00315556 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81756 | E. WATERTOWN 817 | Y |  |  | 0 | 5000 | CDG | N | 2020-10-09 | 2020-10-15 | 4 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 2020-12-02 | 2020-12-02 |  |  | 13000 | [10 empty] | N | N
NIMO | Dallas Manson (Nexamp Solar LLC) | 00247815 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76054 | COFFEEN 760 | Y |  | 3500 | 1500 |  | CDG | Y | 2019-09-18 | 2019-09-30 | 8 | 2019-09-30 | 2019-09-30 | 2019-10-18 | 13 | 2019-12-02 | 2019-12-02 |  |  | 8300 | [10 empty] | N | Y
NIMO | Dallas Manson (Nexamp) | 00280409 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76054 | COFFEEN 760 | Y |  | 3500 | 1500 |  | CDG | Y | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-02-23 | 2021-02-23 | 0 | 2021-04-01 | 2021-04-01 |  |  | 8300 | [10 empty] | N | Y
NIMO | Yogesh kumar (OYA Solar L.P.) | 00268269 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76055 | COFFEEN 760 | Y |  | 5000 | 5000 |  | CDG | N | 2020-01-08 | 2020-01-14 | 4 | 2020-01-14 | 2020-01-14 | 2020-01-21 | 3 | 2020-03-25 | 2020-03-25 |  |  | 11400 | [10 empty] | N | N
NIMO | Christopher Matthews (AES Distributed Energy, Inc. | 00280311 | 013 - Watertown | WATERTOWN | 13601 | 36_13_87552 | W. ADAMS 875 | Y |  | 5000 | 5000 |  | CDG | N | 2020-03-19 | 2020-03-31 | 8 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 0 | 2020-04-09 | 2020-04-09 | 2020-12-04 | 58 | 11800 | [10 empty] | N | N
NIMO | David Wagner (Cypress Creek) | 00100819 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76056 | COFFEEN 760 | N |  | 1988 |  |  | RNM | N | 2015-05-27 | 2015-05-27 | 0 | 2015-11-19 | 2015-11-19 | 2015-11-24 | 3 | 2016-02-26 | 2016-02-26 | 2016-07-05 | 92 | 20000 |  | 145767 | [5 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | Y | N
NIMO | Kelsey Crane (ForeFront Power) | 00100863 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76056 | COFFEEN 760 | N |  | 2000 |  |  | CDG | N | 2015-05-13 | 2015-06-01 | 3 | 2015-06-01 | 2015-06-01 | 2015-06-17 | 0 | 2015-10-21 | 2015-10-21 | 2016-05-06 | 142 | 25000 |  | 213350 |  |  | 2017-01-31 |  |  | 2018-12-21 | 2018-12-21 | 2018-12-21 | Y | N
NIMO | Ben Sufrin (AES Distributed Energy, Inc.) | 00100873 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81755 | E. WATERTOWN 817 | N |  | 2000 |  |  | RNM | N | 2016-01-11 | 2016-01-11 | 0 | 2016-01-11 |  |  |  | 2016-03-03 | 2016-03-03 | 2016-07-20 | 99 | 20000 |  | 727350 |  |  | 2017-01-31 |  |  | 2018-06-26 | 2018-06-26 | 2018-06-26 | Y | N
NIMO | Michael Cucchiara (Nexamp) | 00170289 | 013 - Watertown | WATERTOWN | 13601 | 36_13_81756 | E. WATERTOWN 817 | N |  | 4180 |  |  | CDG | Y | 2018-02-12 | 2018-03-02 | 3 | 2018-03-02 | 2018-03-02 | 2018-03-14 | 7 | 2018-12-19 | 2018-12-19 | 2019-04-01 | 55 | 15300 |  | 496572.86 |  |  | 2019-08-07 | 2020-01-24 |  |  |  |  | N | Y
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00327867 | 013 - Watertown | WATERTOWN | 13601 | 36_13_74865 | MILL ST 748 | N |  | 5000 |  |  | CDG | N | 2021-01-12 | 2021-01-19 | 4 | 2021-01-19 | 2021-01-19 | 2021-01-25 | 3 | 2021-03-22 | 2021-03-22 |  |  | 8700 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00342646 | 013 - Watertown | WATERTOWN | 13601 | 36_13_74865 | MILL ST 748 | N |  | 5000 |  |  | CDG | N | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 0 |  |  |  |  | 7900 | [10 empty] | N | N
NIMO | Mark Richardson (Solitude Solar LLC) | 00342649 | 013 - Watertown | WATERTOWN | 13601 | 36_13_74865 | MILL ST 748 | N |  | 5000 |  |  | CDG | N | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 0 |  |  |  |  | 7900 | [10 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00244403 | 013 - Watertown | WATERTOWN | 13601 | 36_13_76055 | COFFEEN 760 | N |  | 5000 |  |  | CDG | Y | 2019-08-12 | 2019-08-21 | 8 | 2019-08-21 | 2019-08-21 | 2019-08-28 | 4 | 2019-09-04 | 2019-09-04 | 2020-01-09 | 59 | 9900 |  | 1325818.85 |  |  | 2020-03-30 | 2020-10-27 |  |  |  |  | N | Y
NIMO | Yogesh Kumar (OYA Solar CDG LLC) | 00343465 | 013 - Watertown | WATERTOWN | 13601 |  |  | N |  | 5000 |  |  | CDG | N | 2021-03-16 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar CDG LLC) | 00343504 | 013 - Watertown | WATERTOWN | 13601 |  |  | N |  | 5000 |  |  | CDG | N | 2021-03-16 |  |  | 1899-12-31 | [18 empty] | N | N
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00345257 | 010 - Olean | WELLSVILLE | 14028 | 36_10_2362 | S. WELLSVILLE 23 | N |  | 5000 |  |  | CDG | N | 2021-03-25 | 2021-04-01 | 5 | 2021-04-01 | 2021-04-01 | [17 empty] | N | N
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00241095 | 010 - Olean | WELLSVILLE | 14895 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | Y | 2019-07-12 | 2019-07-22 | 6 | 2019-07-22 | 2019-07-22 | 2019-08-01 | 7 | 2019-09-03 | 2019-09-03 | 2020-01-14 | 56 | 12200 |  | 286322 |  |  | 2020-01-29 | 2020-09-13 |  |  |  |  | N | Y
NIMO | Green Street Power Partners | 00270158 | 010 - Olean | WELLSVILLE | 14895 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | Y | 2019-12-19 | 2020-01-02 | 8 | 2020-01-02 | 2020-01-02 | 2020-01-24 | 14 | 2020-03-25 | 2020-03-25 | 2020-07-17 | 58 | 11700 |  | 258907.6 |  |  | 2020-09-18 | 2021-03-24 |  |  |  |  | N | Y
NIMO | Rich Gulden (Omni-Navitas Holdings, LLC) | 00292039 | 010 - Olean | WELLSVILLE | 14806 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | N | 2020-05-18 | 2020-05-25 | 5 | 2020-05-25 | 2020-05-25 | 2020-05-25 | 0 | 2020-07-29 | 2020-07-29 |  |  | 11200 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00307487 | 010 - Olean | WELLSVILLE | 14895 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | N | 2020-09-24 | 2020-09-30 | 4 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 0 | 2021-02-18 | 2021-02-18 |  |  | 11700 | [10 empty] | N | N
NIMO | Timothy Ahrens (CleanChoice Energy) | 00307519 | 010 - Olean | WELLSVILLE | 14895 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | N | 2020-09-24 | 2020-09-30 | 4 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 0 | 2021-02-17 | 2021-02-17 |  |  | 11700 | [10 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00310146 | 010 - Olean | WELLSVILLE | 14806 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | N | 2020-09-14 | 2020-09-16 | 2 | 2020-09-16 | 2020-09-16 | 2020-09-29 | 8 | 2020-10-01 | 2020-10-01 | 2021-03-03 | 56 | 9900 |  | 1975758 | [8 empty] | N | N
NIMO | Conner Witsken (Next Era Energy) | 00194050 |  | WEST VALLEY | 14171 | 36_10_2561 | W. VALLEY 25 | Y |  | 5000 | 3300 |  | CDG | Y | 2018-10-19 | 2018-10-26 | 5 | 2018-10-26 | 2018-10-26 | 2018-11-07 | 7 | 2019-01-10 | 2019-01-10 | 2019-03-22 | 49 | 13300 |  | 275059 |  |  | 2019-08-27 | 2020-02-24 |  |  |  |  | N | Y
NIMO | Conner Witsken (Next Era Energy) | 00194084 | 010 - Olean | WEST VALLEY | 14171 |  |  | Y |  | 5000 | 3300 |  | CDG | Y | 2018-10-19 | 2018-10-26 | 5 | 2018-10-26 | 2018-10-26 | 2018-11-07 | 7 | 2019-01-10 | 2019-01-10 | 2019-03-22 | 49 | 13300 |  | 275059 |  |  | 2019-08-27 | 2020-02-24 |  |  |  |  | N | Y
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00268873 | 010 - Olean | WEST VALLEY | 14042 | DAKE HILL-MACHIAS #803 |  | N |  | 5000 |  |  | CDG | N | 2019-12-10 | 2019-12-20 | 8 | 2019-12-20 | 2019-12-20 | 2020-01-14 | 14 | 2020-03-25 | 2020-03-25 | 2020-07-17 | 58 | 11300 |  | 241232.4 |  |  | 2021-02-01 | [5 empty] | N | N
NIMO | John McDonough (Omni Navitas Holdings LLC) | 00270585 | 010 - Olean | WEST VALLEY | 14042 | DAKE HILL-MACHIAS #803 |  | N |  | 5000 |  |  | CDG | N | 2019-12-23 | 2020-01-06 | 8 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 0 | 2020-06-08 | 2020-06-08 | 2020-09-24 | 59 | 11300 |  | 10000 |  |  | 2021-01-29 | [5 empty] | N | N
NIMO | Richard Gulden (Omni Navitas Holdings LLC) | 00294430 | 008 - Dunkirk/Fredoni | WESTFIELD | 14787 | W PORTLAND-HARTFIELD #866 |  | N |  | 5000 |  |  | CDG | N | 2020-06-03 | 2020-06-10 | 5 | 2020-06-10 | 2020-06-10 | 2020-06-10 | 0 | 2020-09-04 | 2020-09-04 | 2020-12-21 | 57 | 11200 |  | 316295 | [8 empty] | N | N
NIMO | Michael Kennedy (Citizens Energy Corporation) | 00280888 | 017 - Utica | WESTMORELAND | 13490 | 36_17_33153 | WALESVILLE 331 | N |  | 4800 |  |  | RNM | Y | 2020-03-17 | 2020-03-24 | 5 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 0 | 2020-04-16 | 2020-04-16 | 2020-09-30 | 58 | 9600 |  | 498099.19 |  |  | 2021-02-09 | [5 empty] | N | Y
NIMO | William Jordan (Jordan Energy & Food Enterprises, | 00300676 | 017 - Utica | WESTMORELAND | 13490 | 36_17_33153 | WALESVILLE 331 | N |  | 5000 |  |  | CDG | N | 2020-07-28 | 2020-08-03 | 4 | 2020-08-03 | 2020-08-03 | 2020-08-06 | 2 | 2020-09-25 | 2020-09-25 | 2021-02-08 | 59 | 10100 |  | 1590545 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00096556 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N |  | 2000 |  |  | RNM | N | 2014-10-29 | 2014-11-10 | 9 | 2014-11-10 | 2014-11-10 | 2014-11-17 | 0 | 2015-04-24 | 2015-04-24 | 2015-06-15 | 36 | 32600 | [7 empty] | 2016-09-02 | 2016-09-02 | 2016-09-02 | Y | N
NIMO | Borrego Solar Systems, Inc | 00096559 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N |  | 2000 |  |  | RNM | N | 2014-10-29 | 2014-10-29 | 0 | 2014-10-29 | 2014-10-29 | 2014-11-17 | 7 | 2015-04-24 | 2015-04-24 | 2015-06-15 | 36 | 32600 | [7 empty] | 2016-09-02 | 2016-09-02 | 2016-09-02 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00101082 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N |  | 2000 |  |  | RNM | N | 2015-03-17 | 2015-07-17 | 5 | 2015-07-17 | 2015-07-17 | 2015-07-30 | 0 | 2016-04-11 | 2016-04-11 | 2016-07-06 | 60 | 25000 |  | 271800 | [5 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100826 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18752 | WHITEHALL 187 | N |  | 2000 |  |  | RNM | N | 2015-05-28 | 2015-05-28 | 0 | 2015-07-20 | 2015-07-20 | 2015-07-29 | 0 | 2016-03-17 | 2016-03-17 | 2016-07-14 | 60 | 25000 | [7 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | Y | N
NIMO | Robert Tompkins (Borrego Solar Systems, Inc) | 00100827 | 038 - Glens Falls | WHITEHALL | 12887 | 36_38_18751 | WHITEHALL 187 | N |  | 2000 |  |  | RNM | N | 2015-06-01 | 2015-06-28 | 7 | 2015-06-28 | 2015-06-28 | 2015-07-02 | 0 | 2016-04-13 | 2016-04-13 | 2016-07-06 | 60 | 25000 |  | 225100 | [5 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | Y | N
NIMO | Adam Ellis (Nexamp) | 00305797 | 017 - Utica | WHITESBORO | 13492 | 36_17_64656 | YAHNUNDASIS 646 | N |  | 3120 |  |  | CDG | N | 2020-08-28 | 2020-09-05 | 6 | 2020-09-05 | 2020-09-05 | 2020-09-05 | 0 | 2020-10-02 | 2020-10-02 | 2021-02-18 | 59 | 8600 |  | 237185 | [8 empty] | N | N
NIMO | Borrego Solar Systems, Inc | 00296047 | 017 - Utica | WHITESBORO | 13492 | 36_17_64655 | YAHNUNDASIS 646 | N |  | 5000 |  |  | CDG | N | 2020-07-09 | 2020-07-22 | 9 | 2020-07-22 | 2020-07-22 | 2020-07-22 | 0 | 2020-09-11 | 2020-09-11 | 2021-01-14 | 59 | 9100 |  | 1815200 | [8 empty] | N | N
NIMO | Adam Ellis (Nexamp) | 00305789 | 017 - Utica | WHITESBORO | 13492 | 36_17_64655 | YAHNUNDASIS 646 | N |  | 5000 |  |  | CDG | Y | 2020-08-28 | 2020-09-05 | 6 | 2020-09-05 | 2020-09-05 | 2020-09-05 | 0 | 2020-10-02 | 2020-10-02 | 2021-01-12 | 59 | 8600 |  | 150427.38 |  |  | 2021-02-10 | [5 empty] | N | Y
NIMO | ReneSola Power Holdings LLC | 00167026 | 010 - Olean | WHITESVILLE | 14895 | 36_10_10161 | WHITESVILLE 101 | N |  | 1498.5 |  |  | CDG | Y | 2018-10-31 | 2018-11-13 | 8 | 2018-11-13 | 2018-11-13 | 2018-11-26 | 6 | 2019-04-11 | 2019-04-11 | 2019-07-01 | 56 | 12200 |  | 691710 |  |  | 2019-11-07 | 2020-05-06 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY LP) | 00281629 | 010 - Olean | WHITESVILLE | 14897 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | Y | 2020-04-09 | 2020-04-21 | 8 | 2020-04-21 | 2020-04-21 | 2020-04-22 | 0 | 2020-04-27 | 2020-04-27 | 2020-09-03 | 58 | 10900 |  | 285725.16 |  |  | 2020-10-29 | 2021-04-07 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY LP.) | 00282137 | 010 - Olean | WHITESVILLE | 14897 | S WELLSVILLE-ANDOVER #541 |  | N |  | 5000 |  |  | CDG | Y | 2020-04-29 | 2020-04-29 | 0 | 2020-04-29 | 2020-04-29 | 2020-05-13 | 9 | 2020-05-15 | 2020-05-15 | 2020-09-23 | 56 | 10900 |  | 1608913.8 |  |  | 2020-12-01 | [5 empty] | N | Y
NIMO | RIC Development, LLC | 00341182 | 018 - Rome | WILLIAMSTOWN | 13493 | 36_18_66954 | LEHIGH 669 | N |  | 5000 |  |  | CDG | N | 2021-02-10 | 2021-02-17 | 4 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 0 |  |  |  |  | 7800 | [10 empty] | N | N
NIMO | Teddy Epstein (Novis Renewables) | 00273164 | 003 - Niagara Falls | WILSON | 14172 | 36_03_9363 | WILSON 93 | N |  | 4250 |  |  | CDG | Y | 2020-01-30 | 2020-02-12 | 9 | 2020-02-12 | 2020-02-12 | 2020-02-14 | 1 | 2020-02-25 | 2020-02-25 | 2020-06-04 | 56 | 10900 |  | 689356 |  |  | 2020-10-20 | [5 empty] | N | Y
NIMO | Geoff Johnson (Cypress Creek Renewables LLC) | 00342787 | 003 - Niagara Falls | WILSON | 14172 | 36_03_9362 | WILSON 93 | N |  | 5000 |  |  | CDG | N | 2021-03-17 | 2021-03-23 | 4 | 2021-03-23 | 2021-03-23 | 2021-03-23 | 0 |  |  |  |  | 8400 | [10 empty] | N | N
NIMO | Yogesh Kumar (OYA Solar NY, L.P.) | 00242193 | 005 - Avon | YORK | 14592 | 36_05_5352 | YORK CENTER 53 | N |  | 5000 |  |  | CDG | Y | 2019-08-12 | 2019-08-21 | 8 | 2019-08-21 | 2019-08-21 | 2019-08-28 | 4 | 2019-09-04 | 2019-09-04 | 2020-01-13 | 58 | 9900 |  | 692356 |  |  | 2020-03-30 | 2020-10-27 |  |  |  |  | N | Y
NIMO | Yogesh kumar (OYA Solar NY, L.P.) | 00237538 | 003 - Niagara Falls | YOUNGSTOWN | 14174 | 36_03_10558 | SWANN RD 105 | N |  | 5000 |  |  | CDG | Y | 2019-07-12 | 2019-07-17 | 3 | 2019-07-17 | 2019-07-17 | 2019-07-19 | 1 | 2019-09-05 | 2019-09-05 | 2019-12-16 | 58 | 10600 |  | 1259207.01 |  |  | 2020-03-30 | [5 empty] | N | Y